## Sheet1
Project: Water And Sewerage Support Program_- New Providence Water Supply And Sanitation Systems Up-grade
Project Number BH-L1028 and Loan Contract Number No. 2624/OC-BH
Period comprised in this Procurement Plan: From Jan 2012 to Dec 2016
Ref. No. 1 | Description of and category of procurement contract | Estimated cost in (US$ thousand) | Procure-ment method 2 | Review (ex-ante or ex-post) | Source of financing and percentage |  | Prequali-fication 3 (Yes/No) | Estimated Dates |  | Status 4 (pending, in process, awarded, cancelled) | Comments
[5 empty] | IDB % | Local / Other % |  | Publication of specific procurement notice | Completion of contract
1 | WORKS
1.1 | Rehab of Lift Stations - Civil/mechanical/electrical & security up-grades at 50 lift stations | 950000 | NCB | Ex-post | IDB |  | No | 2012-08-31 | 2016-12-31
1.2 | Rehab of Collection Systems - Rehabilitation of inefficient/ineffective sewer systems | 3850000 | ICB | Ex-ante | IDB |  | Yes | 2012-08-31 | 2016-12-31
1.3 | Rehabilitation of Wastewater Treatment Plants & Disposal Wells - Rehabilitation of three (3) WWTPs and six (6) disposal wells. | 10000000 | ICB | Ex-ante | IDB |  | Yes | 2012-08-31 | 2016-12-31
2 | NON-CONSULTING SERVICES
2.1 | Automatic Meter Reading/Intelligence AMR/AMI - IT software programming & integration of management information system for targeted customer accounts | 500000 | NCB | Ex-post | IDB |  | No | 2012-05-31 | 2014-05-31
2.2 | Public Relations Campaign - Project PR and customer win-back campaign | 1200000 | NCB | Ex-post | IDB |  | No | 2012-08-31 | 2015-08-31
2.3 | Establishment of Economic/Environmental Regulator - Hiring qualified staff, training, Laboratory up-grades, office rent & reorganise MOTE. | 2750000 | NCB | Ex-post | IDB |  | No | 2013-07-01 | 2014-12-31 |  | Comprises a number of small contracts, which will be awarded for Lab-Upgrades, staff training, office rent & outfitting (to be disclosed in 2013).
3 | CONSULTING SERVICES
Component 1
3.1, 3.2 | NRW Reduction Contract - Baseline survey & development of a NRW reduction strategy, leak detection & repairs, civil construction works, pressure management, Asset management & integration of GIS & WOM and NRW training for WSC's staff. SCADA- Introduction & integration of SCADA to improve system monitoring & design operating improvement actions. Public Relations Campaign - A portion of Project PR and customer win-back campaign. | 50500000 | QBS | Ex-ante | IDB |  | No | 2009-08-31 | 2020-03-31 |  | Contract is 5-years for reduction and 5-years maintenance of reduction; only reduction phase financed by IDB
3.3 | Technical Assistance - Supervision consulting services for the execution of the NRW program. | 1000000 | QCBS | Ex-ante | IDB |  | No | 2012-05-31 | 2016-12-31
Component 2
Institutional Strengthening
3.4 | HR Reorganisation Strategy- Develop & implement new organization structure, including an operational strategy design, a HR strategy and define benchmark KPIs in preparation for regulation by URCA. | 1063000 | SSS | Ex-post | IDB |  | No | 2010-08-31 | 2015-08-31 | In Progress | Org restructuring review is in progress, Bench mark etc to commence in II Qtr 2012. In accordance with para. 3.9-3.13 of the Consultant policies, Castalia Strategic Advisors approved to be consultant @$0.7M. An additional $0.363M allocated for retroactive fees for Castalia.
3.5 | Tariff Study - Undertake a tariff study & development of a scheme proposal consistent with the new economic regulated sector. | 500000 | QCBS | Ex-post | IDB |  | No | 2013-08-31 | 2014-08-31
Component 3
3.6 | Master Plan & Designs - Development of a WWT Master Plan to address wastewater collection, treatment & disposal for New Providence, inclusive of technical, social, environmental & financial analysis. | 1580000 | QCBS | Ex-ante | IDB |  | No | 2012-05-31 | 2013-05-31
3.7 | Construction Supervision - Supervision of rehabilitation of collection systems, WWTPs & disposal wells. | 1240000 | LCS | Ex-ante | IDB |  | No | 2013-02-28 | 2016-12-31
Component 4
3.8 | Consulting Assistance - Hiring of a consultant to draft By-laws and Guidelines for establishment of the Economic & Environmental regulators | 250000 | QCII | Ex-ante | IDB |  | No | 2012-12-31 | 2013-12-31
1 If there are a number of similar individual contracts to be executed in different places or at different times, these can be grouped together under a single heading, with an explanation in the comments column, indicating the average individual amount and the period during which the contracts would be executed. For example: an education project that includes school construction might include an item labeled “School Construction” for an estimated cost of US$20 million and an explanation under the Comments column such as this: “This item encompasses some 200 contracts for school construction averaging US$100,000 each, to be awarded individually by the participating municipal governments over a three-year period between January 2006 and December 2008.”
2 Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; Consulting Firms: QCBS: Quality- and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection; Individual Consultants: QCNI: Selection based on comparison of qualifications of national individual consultants; QCII: Selection based on comparison of qualifications of international individual consultants.
3 Applicable only to Goods and Works in case the new Policies apply. In the case of previous Policies, it is applicable to Goods, Works and Consulting Services.
4 Column “Status” will be used for retroactive procurement and when updating the procurement plan.
| Allocated Sub-total | 75383000
| Sub-total prior to Unallocated | 74900000
| Check | -483000