# TRADE AND POVERTY (T&P) TRUST FUND # TC PROJECT COMPLETION NOTE

# Basic Information

# Project number, title, country/region: TC N°: RG-T1332: Mobilizing Aid for Trade in Latin America # Relation to Bank strategies and operation(s): This project contributed to mainstream trade into the beneficiary countries’ development agendas, as stated in relevant Country Strategies. - Project team members: Paolo Giordano (INT/INT), team Leader; Anneke Jessen; Jessica Luna; Jaime Miranda (INT/INT); Kevin McTigue (LEG/SGO) - T&P Fund contribution, (in USD), and % of total project financing: US$ 150,000, 42% of total project financing. # TC project approval date: 8/2/2007 - Execution period: 5 months

## Restatement of Objectives and Key Activities

Objectives The general objective of the TC was to help Latin America policymakers and private sector actors to identify and address trade-related challenges arising from global market integration through the provision of on the job training on the Aid for Trade Initiative (AFT) launched by the WTO. Specific objectives included: (i) raise awareness on the Aid for Trade Initiative (ii) present lessons learned and challenges related to mobilizing AFT from the national government and private sector perspectives; and (ii) support governments, donors and the private sector to identify mechanisms to better address specific trade-related challenges in the region, and moving towards shared solutions under the AFT initiative. Key Activities The main activities entailed the preparation of background papers that served as basis for the regional overview on AFT and the on-the-job training for policymakers - Trade and Finance Ministers, private sector representatives and donor agency representatives, on mobilizing AFT in Latin America and the Caribbean.

## Outputs and Outcomes

Outputs - 2 papers that served as background papers for the report: Mobilizing Aid for Trade in Latin America which was the basis for the discussions at the regional review on AFT. This report was widely distributed at the Regional Review meeting, presented at the Global Review Meeting at the WTO in November 2007 and posted at the website www.iadb.org/aidfortradelac; - A document with the proceedings of the Regional Review meeting was prepared and presented at the Global Review Meeting on AFT in Geneva. - The Regional Review meeting on AFT for Latin America and the Caribbean with the participation of Trade and Finances Ministers, private sector and senior donor agency representatives. - The Regional Review had a wide coverage of national and international press. Mr. Luis Alberto Moreno, President of the IDB and Mr. Pascal Lamy, Director General of the WTO gave a joint press conference. Outcomes - The Regional Review on AFT brought for the first time together trade and finance ministers, bilateral donors, regional and multilateral agencies and private sector representatives to discuss how to build the capacity and infrastructure that countries in the region need to take advantage of – and connect to – today's dynamic global economy. More generally, the meeting helped fostering the dialogue among governments, donors and the private sector to address specific trade-related challenges in the region, prioritize needs, and move towards shared solutions under the AFT initiative. - The activity helped the Bank to identify together with high-level policy makers in the region key trade-challenges of their countries and sub-regions; prioritize needs and set our priorities for future action. In concrete terms, the meeting contributed shifting the focus of the AFT initiative from policy debate to implementation, and promoting more effective policies. - The on-the job training to policymakers of the LAC region allowed them to share information about best practices and discuss the importance of mainstreaming trade into the development agendas that will contribute to strengthen both the national and the Bank’s trade agendas. - Participants, in particular government officials, brought back their experience of information of trade strategies and best practices to their countries. This in turn will have a multiplicative impact in the diffusion of the effects of the project. - Participants have a better understanding of the Aid for Trade Initiative. This in turn will have an effect of strengthening their participation in the Initiative contributing with concrete recommendations on how to operationalize the Initiative. - Participants actively participated in the discussions demonstrating a common understanding of the needs of the region and the importance of the AFT Initiative. They highlighted the need for increased and effective financing including better leveraging of development assistance and multilateral lending. There was a recognition that trade, investment, and domestic reform, not aid alone, were the main drivers of economic development, but that financial assistance, strategically invested, could provide an important catalyst for export growth and competitiveness. - Participants engaged in fruitful discussions and share experiences at the parallel break-out sessions on to South America, Central America and the Caribbean where they identify key issues and priorities in each sub region. They achieved a common understanding of cross-cutting issues: country ownership, regional approaches, key priorities ( trade-related infrastructure and regional public goods, trade finance and SME export development, trade facilitation and standards and export promotion and export diversification); public-private partnerships, and additional and effective financing, that were presented at the Global Review of AFT. This exercise of identification of priorities and challenges will in turn contribute to enhance trade debate in the region.

## Contribution to Bank Strategies and Operations

- The TC contributed to mainstreaming trade into the beneficiary countries’ development agendas, which is an objective stated in most recent Country and Regional Strategies of the Bank. - More specifically, the TC contributed to raise awareness on the AFT Initiative in the region which in turn will strengthen Latin America and the Caribbean countries participation in the Initiative. It also contributed to identify trade-related challenges in the region and prioritize needs. This contributed to enhance both national and Bank’s trade agendas.

## Lessons Learned ### (substantive/operational as well as managerial: i.e trust fund, procurement, execution, etc.)

- Overall, the project was crucial to achieve the objectives of raising awareness of the AFT Initiative and the identification of trade-related challenges of the region. Policymakers, private sector representatives and donors had a unique opportunity to address trade challenges, share experiences and start moving from debate to implementation of AFT projects. In addition, the project was crucial to enhance participation of smaller countries of the region in the AFT debate. - This project was an excellent example of donor coordination to implement trade projects in the region.

## Recommendations to the Trust Fund and to the Bank

- Explore mechanisms to improve donor coordination and extend it to the regional level.