- Inter-American Development Bank

- Technical Cooperation Proposal (Trust Funds)

- TC Brief

### TC N: BR-T-1019

- General information

Name of the T.C. Project:	Urban Renewal and Development Program of Santos.

Name of the Fund:		French Technical Cooperation Fund for Consultancy Services and Training Activities – Regular Fund.

Beneficiary Country: 		Brazil- City of Santos.

Beneficiary Agencies: 	Companhia de Desenvolvimento Habitacional e Urbano (CDHU), Prefeitura Municipal de Santos (PMS), and the Port Authority of Santos.

Estimated Total Amount:							US$146,700

Amount to be financed by the Trust Fund: 	US$146,700

Execution: 				09 months

Disbursement: 			18 months

- Objectives And Justification

  - The objective of the TC is to assist the Federal Port Authority, the State of Sao Paulo government (CDHU) and the municipality of Santos, in defining a joint proposal for the urban renewal and development of the port city of Santos.  The historic quarters of Santos have been subject to an intense process of renewal during the past years.  The specific objectives of this TC are to assist the authorities in: (i) defining long term objectives for the current process of urban renewal; (ii) defining the specific project components of an eventual municipal program; (iii) defining the legal agreements necessary for the execution and administration of a complex project involving various public organisms and the private sector.

  - The Port Authority, CDHU and the city of Santos have agree that French experience would be critical to help the Brazilian preparation team for the design of the core housing and other urban redevelopment projects (historic Center) using intervention instruments and ad hoc institutions based on French experience in the area (such as The Euro-Med in Marseille).

- Description

  - The program being developed by the Federal, State and Municipal authorities, tentatively would have three principle components:

    - Urban renewal, opening the city to the sea, and conservation of historic and cultural heritage.  Seeks to preserve the cultural heritage of Santos and stimulate new economic, social and cultural activity in that port city, particularly in those areas selected as strategic for the revitalization of the city. Investments will be undertaken to restore common areas and public buildings, private building such as “cortiços” (tenements) in such a way as to stimulate private real estate investment.  Specific individual civil works will be undertaken as well as more simple replicable works.  In addition, complementary mechanisms for coordinating with and stimulating private real estate investment will be defined.

    - Local development promotion. This component will consist of activities to stimulate local economic activity and employment, based on the comparative advantages of the city.

    - Institutional strengthening for execution of urban renewal. This component will seek to consolidate an intervention and management instrument appropriate for the design, execution and administration of programs in which different national, state and local governments participate, particularly in the areas of: (i) development planning, (ii) execution management and (iii) public resource management.

- Consulting Services

  - For the design of the Program, in conjunction with the Brazilian authorities, the following areas were identified as in need of external consulting services:

      - Definition of the long term objectives: One high-level French economist with at least 20 years of experience in urban development and transport. One high-level French consultant with at least 10 years of experience in with planning and implementing working arrangements between port authorities and local and regional authorities for urban and transportation development (2F).

      - Program definition: Local consultants to include an economist, an architect-urban planner, an engineer and an environmental expert, each with at least 10 years experience in the formulation and analysis of urban development projects (2L).

      - Institutional and legal framework: One high-level French consultant with ample knowledge and experience with the administration of Contracts Plan and the design of institutional frameworks. One local consultant with at least 10 years of experience in the analysis and design of institutional strengthening (1F).

      - Strategy for the promotion of the renovation of private historical buildings:  One high-level French consultant with at least 10 years of experience in urban development and knowledge of urban incentives systems for private investment. One local consultant with at least 10 years of experience and knowledge of the Brazilian housing subsidies system and of local finance of public services (1F, 1L).

      - Definition of the intervention in the area of the port:  One high-level French consultant, architect, with recognized experience with the recycling of public buildings and public spaces (1F).

- Activities

  - Definition of the long term objectives: This activity will be executed with an estimated 50 work days (35 of French consulting) and will have as products the following reports:

      - Diagnostic summary of the economic, social, physical situation of the city, with particular attention to the historic tendencies and current opportunities for economic and social development;

      - Possible scenarios and identification of the principle economic, social and environmental impacts; and

      - Recommended long term objectives for the city with corresponding justification.

  - Program definition: This activity will be carried out with approximately 75 consulting days and will have as products the following reports:

      - Description of socio economic outputs of the “without program” scenario

      - Feasible options for Program investment configurations; and

      - Justification of selected alternative, based on institutional, economic, social and environmental criteria.

  - Institutional and legal framework:  This activity requires approximately 50 consulting days (30 of French consultants) and will have as its products: (i) a diagnostic report of the Brazilian legal and institutional context and the principle issues to be solved for project execution coordination; (ii) the design of the recommended inter-institutional instrument; and (iii) identification of the institutional strengthening subcomponents for the CDHU, the executive branch of the Regional Government and the Municipal Government.

  - Strategy for the renovation and of private historic buildings: This activity requires an estimated 45 consulting days (30 of French consultants) and will have as products the following reports: (i) a diagnostic of the private urban property of Santos, and (ii) the design of the proposal for a policy for the renovation of this property.

  - Definition of the intervention in the port: This activity requires an estimated 30 French consulting days sand will have as products the following reports: (i) a diagnostic summary of the area’s physical, cultural and social characteristics; and identification of its development potential; and (ii) the development of an appropriate concept project for the area.

- Cost (in US$)

  - The French consulting firm that will be selected to execute the TC will be evaluated based on the quality level of its proposal for the Plan of Operations and the supporting CV.  The consulting expertise and respective costs are presented in the following table.

|  | Units | Number | Unit Cost | Cost in US$ |
| --- | --- | --- | --- | --- |
| 1. French Consulting Firm |  |  |  |  |
| Administration and overhead |  |  |  | 13,500 |
| French Consultant Firm Honoraria |  | Up to 125 | 615 | 76,825 |
| Urban Economist | Days | Up to 20 |  |  |
| Port Administrator | Days | Up to 15 |  |  |
| Institutional Specialist | Days | Up to 30 |  |  |
| Urban Development Specialist | Days | Up to 30 |  |  |
| Architect | Days | Up to 30 |  |  |
| Travel |  |  |  |  |
| Tickets Paris-Santos–Paris | Tickets | 5 | 1,600 | 8,000 |
| Per Diems | Days | 65 | 180 | 11,700 |
| Total 1 |  |  |  | 110,025 |
| 2. Local Consultants (Up to 25%) |  |  |  |  |
| Honoraria |  |  |  |  |
| Economist | Days | Up to 45 |  |  |
| Urban Development Specialist | Days | Up to 45 |  |  |
| Environmentalist | Days | Up to 30 |  |  |
| Total 2 |  |  |  | 36,675 |
| Total |  |  |  | 146,700 |

- Technical Responsibility: Tracy Betts (COF/CBR), email: Tracyb@iadb.org,            Tel.: (+5561) 317-4200, Fax: (+5561) 321-3112.

- Environmental aspects:  Arcindo Santos (RE1/SO1), email: Arcindos@iadb.org,            Tel.: (202) 623-2950.

- Responsibility for Disbursements:  Patrick Saint Pol Maydieu (RE1/SO1), e-mail: PATRICKS@iadb.org, Tel.: (202) 623-1992.

- Recommendation

  - Patrick Saint Pol Maydieu, recommends the approval of this operation and the use of resources from the French Technical Cooperation Fund for Consultancy Services and Training Activities – Regular Fund totaling up to US$146,700 in order to finance the corresponding technical cooperation.

- Certification

7.1 	I certify that this operation was approved for financing by the donor of the French Technical Cooperation Fund for Consultancy Services and Training Activities – Regular Fund through a fax dated February 21, 2005 and signed by the General Director. In addition, I certify that resources from the French Technical Cooperation Fund for Consultancy Services and Training Activities – Regular Fund are available for up to US$146,700 in order to finance the activities described and budgeted in this document.  The commitment and disbursement of these resources shall be made only by the Bank in US Dollars. The same currency shall be used to stipulate the remuneration and payments to consultants, except that local consultants working in their own borrowing member country shall have their remuneration defined and paid in the currency of that country. No resources of the Fund shall be made available to cover amounts greater than the amount certified herein above for the implementation of this TC Brief. Amounts greater than the certified amount may arise from commitments on contracts denominated in a currency other than the Fund currency, resulting in currency exchange rate differences, for which the Fund is not at risk.

(ORIGINAL SIGNED)

___________________________				Date: March 1, 2005

- Arnoldo M. da Fonseca, RE2/TEC/CHF

- Approval

(ORIGINAL SIGNED)

___________________________				Date: March 4, 2005

Alicia S. Ritchie, RE1/SO1/CHF