Technical cooperation profile

- Basic project data

| Country/Region: | Latin America and the Caribbean |  |  |
| --- | --- | --- | --- |
| Program Name/Number: | Conference: Youth as Agents of Change (RG-T1467) |  |  |
| Team Leader/Members: | Leader: Rosario Londoño (SCL/SPH); other members: Isabel M. Alvarez-R. (EXR/PRL); Kai Hertz (VPC/GCM); Fabian Koss (EXR/PRL); Elena Suarez (EXR/PRL); Rosina de Souza (LEG); and Ethel Muhlstein (SCL/SPH). |  |  |
| Date of Request: | Bank initiative. |  |  |
| Beneficiary: | Young people from borrowing IDB member countries |  |  |
| Executing Agency: | The Bank, through the Social Protection and Health Division (SCL/SPH) and the IDB YOUTH Program in the Office of External Relations (EXR/PRL). |  |  |
| Financing plan: | IDB (FSO, net income): IDB Youth: Total: | US$ US$ | 100,000 5,000 105,000 |
| Tentative dates: | Profile MGR | February 2008 |  |
|  | Plan of Operations QRR | February 2008 |  |
|  | President | March 2008 |  |

- Background and problem statement

- A.	Young People and the IDB

  - More than 40 percent of the population of Latin America and the Caribbean (LAC) is under the age of 30.  How today’s youth generation grows and develops has important implications for the region’s economies, societies, environment, and governments. Recognizing the critical role young people play in building stable democracies, sustainable economies, and social equality, the Inter-American Development Bank launched IDB YOUTH in 1995.  IDB YOUTH promotes the active participation of Latin American and Caribbean youth in the development process, and values them as true agents of change. It facilitates the direct communication of young people with governments, the private sector, and nongovernmental organizations so youth can express their opinion, take a stand, and actively contribute to the development process.

  - The Bank has contributed to the development of young people with programs and projects that benefit them in the areas of education, capacity building, employment generation, access to technology, and health services, among others. Research shows that when youth have access to basic services and can offer meaningful contributions at the local level, school dropout rates, crime incidence, drug use, and violence are notably reduced. Moreover, young people that are involved through volunteerism and participation in their early years are more likely to continue to be engaged, responsible citizens as adults.

  - It is within this context, that the Bank financed a technical cooperation (ATN/FT-9881-RG; “Youth Participation Communications Campaign”) in collaboration with MTV Latin America to showcase and further incite youth actions and programs that had and continue to have significant effects on local communities. The campaign was named “Youth As Agents of Change”. Through this initiative, 6000 youth in the region submitted projects they are executing to support the social and economic development of their communities. MTV-LA filmed the 25 projects with the highest impact in seven different countries, and aired them throughout Latin America and posted them on their webpage. Building on the experiences of this program, such as the level of engagement and participation, the impact of youth-driven projects in their communities, and the sustainability and participation of local partners, this project seeks to provide a platform for youth during the Bank’s Annual Meeting in Miami, 2008.

  - This event will present a unique opportunity for young people from the region to exchange information, share experiences and notable practices, finding common ground and potentially creating new and catalytic partnerships promising to contribute to the development of their communities. The event will also serve as a venue for youth practitioners from the region, high-level officials from the public and private sector, to see the benefits of investing in young people in systematic, integrative approaches that facilitate their access to local economic and social opportunities and promote their participation at the community level.

- B.	Youth as Agents of Change

  - The Bank’s experience in youth development and participation confirms the success of the MTV-LA/IDB Campaign: Many young people are contributing daily to their development and that of their communities.  Currently, the LAC region – due to its demographics - has a window of opportunity to significantly alter extreme poverty by making strategic investments in young people to have a new generation that is healthy, educated, and has the right skills to be a part of the real needs of the local economies, and thus, serve as Agents of Change.

  - A project on training for youth on life skills and other cognitive elements, which has been recognized by the GE Foundation’s “Life Skills for Employability Program”, ILO’S Report on youth employment and a report prepared for the World Bank’s Human Development Network all give evidence about how young people are making a difference in their communities. These targeted interventions either seek better employment opportunities for youth and/or foster their entrepreneurial spirit.  It is within this context, that this project seeks to increase the knowledge and awareness of these interventions, thus enriching ongoing initiatives or providing input and incentives for youth, NGOs, and public entities in the region to scale up and multiply these investments.

- Program objective and description

- A.	Objectives

  - The purpose of this project is to have a discussion forum with youth leaders (Agents of Change) who have made a significant contribution to their community, renowned youth practitioners, and representatives of public, private and non-profit sectors to present key components of notable practices that have facilitated the participation of youth in their local development programs and promoted positive youth development. This Forum is to take place as part of the Bank’s Annual meeting in Miami, Florida in April 2008.

  - The specific objectives of the project are: (i) to provide a platform where young people can share their experiences as youth leaders engaged in advancing the development of their communities; (ii) to disseminate notable practices and effective methodologies for expanding programs that foster youth participation in the development process; (iii) to encourage inter-sectorial dialogue to better coordinate holistic youth programs; and (iv) to highlight the current demographic window of opportunity by investing strategically in youth development.

- B.	Description

  - This program will include five components: (i) volunteer event; (ii) youth project’s exhibit area; (iii) youth forum; (iv) production and distribution of materials; and (v) identification of the baseline and evaluation of the Learning kit and How-to-Manual.

  - Volunteer event

  - In order to highlight the contributions of youth through voluntary service and to highlight the Bank’s interest in corporate social responsibility, the volunteer event would engage youth and other participants during the annual meeting, in a hands-on community service project that would benefit a Latino community in the Miami area. The event will focus on a school makeover with activities for reforestation, lighting, cleanup, and beautification. This event would offer participants the opportunity to interact and work with the youth and residents of Miami, as well as with many other volunteers. The event will take place in the context of National & Global Youth Service Day, an annual celebration commemorating the contributions young people have made throughout the year in their communities through volunteer work.

  - Youth project exhibits

  - An exhibit area will be organized where young leaders, entrepreneurs and participating organizations can display information on their respective programs. The exhibit will be inaugurated with a reception at the end of the Youth forum (see below) and will remain open throughout the Annual Meeting.  Space will be reserved for sponsors.

  - Youth forum

  - This component will finance a forum for half a day comprising three plenary sessions. The first plenary will premiere the “Youth As Agents of Change” campaign in the US for the first time and bring together the youth leaders that were featured in the campaign. This plenary would highlight the 25 youth projects that MTV filmed in 7 different countries of Latin America that were selected from more than 6000 submissions from youth throughout the region, as stated above.

  - The second plenary will be dedicated to bridge young people from the Latin American and the Caribbean region with Hispanic/Latino youth from the US. This interaction will allow for LAC youth and USA youth to have an open dialogue and exchange ideas on the broader role that youth can play as partners in the development process.

  - The final plenary will highlight the importance of having a holistic and integrated approach to investing in young people, and creating policy environments that support youth development. Selected youth leaders, international development specialists, youth practitioners, representatives from the public, private and non-for-profit sectors will have an opportunity to exchange ideas and experiences on what works in youth development and participation. The half-day program will offer participants many opportunities to network and explore future collaborations.

  - Production of materials and dissemination of findings

  - This component will finance a Learning Kit and How-to-Manual will be produced to highlight key factors that facilitate a young person’s ability to become a social entrepreneur and an agent of change. This hands-on capacity building manual will be developed for community leaders, youth educators, and young leaders to serve as a guide on how to engage young people in community projects at the local level. It will also highlight the 25 Agents of Change, the diversity of their projects, and will include a DVD of the one-hour documentary produced by MTV Latin America.

  - A final document will also be produced to summarize the notable practices presented and recommendations resulting from the Youth Forum.  All these materials will be made available on-line.

- 5.	Identification of the baseline and evaluation of the Learning kit and How-to-Manual

  - Under this component, a consultant will be hired to identify the baseline and evaluation methodology of the effectiveness and practical use of the Learning kit and the How-to-Manual. The consultant will prepare a survey to be randomly distributed amongst a group of beneficiaries and will design the evaluation methodology to be implemented 6 and 12 months after the event. Beneficiaries who have been randomly excluded from obtaining the kit and manual in the first round will receive the manual six months after the event.

- Cost and financing

  - It is estimated that the total cost of the project is US$105,000. The Bank will contribute US$100,000 from the Fund for Special Operations (FSO, net income, non reimbursable) and another US$5,000 will be funded by the IDB YOUTH program to cover the costs of the evaluation of the effectiveness of the Learning Kit and How-to-Manual.  Through the proper dissemination of the Learning Kit and How-to-Manual this TC will continue to benefit Bank clients, beneficiaries and operations long after the youth forum even is over.

| - Component | - IDB (FSO) | - IDB Youth | - Total |
| --- | --- | --- | --- |
| - 1. Youth forum | - 50,000 |  | - 50,000 |
| - 2. Youth project’s exhibit | - 9,000 |  | - 9,000 |
| - 3. Production of materials - and dissemination of results | - 19,000 |  | - 19,000 |
| - 4. Logistical support | - 20,000 |  | - 20,000 |
| - 5. Baseline and evaluation methodology |  | - 5,000 | - 5,000 |
| - 6. Contingencies | - 2,000 |  | - 2,000 |
| - Total | - 100,000 | - 5,000 | - 105,000 |

- Executing agency

- A.	Executing Agency

  - The Bank will be the executing agency for this operation through the Social Protection and Health Division (SCL/SPH) and the IDB YOUTH Program in the Office of External Relations (EXR/PRL). The work of the Bank on youth development, its direct relationship with the more than 9,000 youth organizations that are members of the IDB YOUTH Program Network, and the high profile events that have been organized in the past seven regional annual meetings have placed the Bank at the forefront of youth development and participation.

  - The Bank will hire a local consulting firm in Miami for the overall production of the Youth Forum and the Youth Exhibit. Services to be provided are staging, audio and video equipment rentals, sound and lighting. Additionally, and as mentioned before, a youth development specialist will be hired to produce the How-to-Manual; printing and design services of the manual will also be required. Another consultant will be hired to support the identification of the baseline and evaluation methodology.

  - The project will be executed within a period of 8 months, and the disbursement period will be of 12 months, as of project approval.

  - The procurement of goods and services, selection and hiring of consulting services for this TC will follow the procedures established by the bank Policy on Procurement of Goods and Services (GN-2349-7) and the bank Policy for the Selection and Hiring of Consultants (GN-2350-7).

  - Contracts for the procurement of goods and services at or below the equivalent of US$10,000 will be made using the price comparison method. For the hiring of consulting services below US$15,000, the short list method can be applied.

- monitoring and evaluation

- Monitoring, technical and basic responsibility

  - The technical and basic responsibility of this TC will be shared by SCL/SPH and IDB YOUTH in EXR/PRL.

  - IDB Youth and SCL/SPH will closely monitor the execution of all of the components by working closely with the consultants and actively participating in the design and execution of all of the activities. IDB YOUTH has extensive experience with the organization and execution of these types of seminars, having lead 7 events in for the past 9 Bank Annual Meetings. IDB YOUTH will also be present 5 days prior to the event and will be responsible for overseeing the Youth Forum and the Volunteer Event.

  - Moreover, SPH and IDB Youth will monitor the identification of the baseline and evaluation methodology, as well as the content of the Learning Kit and How-to- Manual.

  - Progress and final reports. Standard Bank procedures for auditing, financial management of the resources and reporting will be followed. A midterm report on the proceedings of the first three components will be shared on-line after the event. A final report, including the evaluation of the Learning Kit and How-to-Manual will be made available after the evaluation is completed.

  - Evaluation. Evaluations sheets of the Volunteer Event, the Youth Forum and the Youth Exhibit will be distributed to the participants and processed by IDB YOUTH to determine ways in which future similar events can be improved. A more thorough impact evaluation of the effectiveness of the Learning Kit and How-to-Manual will be undertaken by SPH a year after the event.

- Major issues

  - No major issues have been identified for execution of this Conference.

- Action Plan

  - It is expected that the project will be ready for distribution to the QRR during the month of February, with final approval expected during the month of March 2008.

- environmental and Social Strategy

  - No negative environmental impact is anticipated from this regional technical cooperation. Several of the Agents of Change projects that will be highlighted during the exhibit and conference are about environmental protection and preservation.

  - Based on the Safeguard Policy Filter Report (#2008-01163616-2 ), the project does not require a classification and / or further environmental or social actions. Based on the SSF (#2008-01163906-2), this technical cooperation is a category “C” project.

- Certification

  - The Grants and Cofinancing Management Unit (VPC/GCM) certifies that US$100,000 from the net income of the Fund for Special Operations are available for the financing of the project activities proposed in this Plan of Operations.

- (original signed)

- ________________________________

- Marguerite S. Berger, Chief VPC/GCM

- Approval

- (original signed)

- Vo. Bo.:	_______________________________________

- Michael D. Jacobs, Chief, SCL/SPH

- (original signed)

Approved:	________________________________________

Kei Kawabata, Manager SCL

ILO (2006). Global Employment Trends for Youth.

See James C. Knowles and Jere R. Behrman, The World Bank (2005). HNP Discussion Paper: The Economic Returns to Investing in Youth in Developing Countries. A Review of the Literature.

The volunteer event will be co-financed by Direct TV and other local partners.

The project proposal is included in the revised technical cooperation program for 2007 (GN-2408-10), approved by the Board of Executive Directors on December 19, 2007.