GUYANA

Social Amelioration Program (SIMAP II)

(Loan 985/SF-GY)

PROJECT COMPLETION REPORT (PCR)

Minutes of the Management Review Committee (MRC)

July 23, 2003

# I.   PARTICIPANTS

1.1	The MRC was presided by Mr. Juan Manuel Fariña (SO3).  Participants included:  Messrs. Marco Nicola (CGY); Carlos Antola (COF/CGY); Frank Nieder, (FI3); Arne Paulson (RE3); Ashu Handa (SO3); Gabriel Castillo (OD6); Adrienne Pratt (OD6); and Jorge Lamas (SO3), who acted as secretary.

II.   RECOMMENDATIONS

  - The MRC agreed that the table on lessons learned presented in section V was well done and presented many of the relevant issues.  However, it should be revised to include whether a high community contribution was an adequate indicator in targeting program resources based on the communities needs.  Also, to review the document in order to make sure that other lessons learned are fully reflected in the discussion of the implementation of the project.  Specifically, include a description of the problems encountered in the implementation of nutrition subprojects.

III.   OBSERVATIONS

  - In addition to the above recommendations, the revised PCR should take into consideration oral and written comments received from the MRC, and:

- include a discussion of the third development objective related to the demonstration to other agencies and communities and how it was reached;

- specify that the problem of retaining appropriate staff in the project execution unit affected the implementation of the program in its later stages;

- review the factual accuracy of whether all infrastructure projects followed the minimum cost alternative criteria in section II E;

- include a brief discussion of the project selection process;

- provide more details regarding the difficulties experienced in implementing technical-vocational training activities;

- include evidence available that allows to support the statement that projects financed would be sustainable over time;

- add a table describing the composition, according to project types, of activities financed .

_________________________	_________________________

Juan Manuel Fariña	             Jorge Lamas

Chief, RE3/SO3	    MRC Secretary, RE3/SO3

Project Completion Report (PCR)

Part One

PROJECT NAME: Social Amelioration Program II (SIMAPII)

PROJECT NUMBER: GY0025

LOAN AND TC NUMBERS: 985/SF-GY

COUNTRY: Guyana

EXECUTING AGENCY:  SIMAP

SECTOR: Social

MODALITY: Investment Loan

DATE APPROVED: May 16th, 1997

DATE COMPLETED:  May 16th, 2002

LOAN AND TC AMOUNTS:  Loan US$ 17 millions

FINAL PROJECT IMPLEMENTATION CLASSIFICATION: Satisfactory

FINAL PROJECT ASSUMPTION CLASSIFICATION: High

FINAL DEVELOPMENT OBJECTIVE CLASSIFICATION: Probable

Prepared By

COF/CGY

BACKGROUND

The Social Impact Amelioration Programme (SIMAP) was established as an autonomous agency in 1990, with the assistance of two IDB non-reimbursable technical co-operations, with the objective to alleviate and reduce poverty. In 1992 SIMAP was financed through a US$11.7 million World Bank loan and a US$ 13.5 million IDB loan SIMAP I.  Following the completion of these programs, the national authorities requested a new loan operation for SIMAP. In May 1997, the Bank approved another loan of US$17,000,000 - SIMAP II operation which was completed in 2002.

I. 	PROJECT OBJECTIVES AND COMPONENTS.

- The objectives of the program were to: (i) Improve the standard of living and income-earning potential of low-income households via the financing of small-scale community generated project; (ii) increase the capability of low-income communities to identify, articulate and address their priority needs.

- The program had two components:

I 	Projects Component (US$15,478,000), with four sub-components:

  - Social and economic infrastructure rehabilitation projects, which financed social and economic infrastructure, rehabilitation or upgrading.

  - Emergency Response Mechanism Projects: designed to rapidly process and finance small (less than US$5,000) self-help projects that address local emergency infrastructure repair needs.

  - Amerindian Projects: which financed community-managed and designed projects, with significant levels of self-help.

  - Nutrition and technical/vocational training Projects: which was designed upon the completion of evaluations, to assess their effectiveness.

The Implementation of the component was guided by the following project cycle:

| Phase of Project | Accumulated Time per Type of Project |  |  |
| --- | --- | --- | --- |
|  | Regular | Amerindian | EMRP |
| Application |  | 1 week | 3 days |
| Registration | 1 week | 2 weeks | 5 days |
| Selection and Ranking | 3 weeks | 3 weeks | 6 days |
| Project Preparation | 11 weeks | 4 weeks | 8 days |
| Project Appraisal | 13 weeks | 6 weeks | 9 days |
| Management Review Committee | 14 weeks | 7 weeks | 9 days |
| Board Approval | 16 weeks | 9 weeks | 9 days |
| Review by Funding Agency | 17 weeks | 10 weeks | 9 days |
| Contracting | 21 weeks | 10 weeks | 14 days |
| Board Review (when applicable) | 23 weeks | 10 weeks | 14 days |
| Review by the Bank | 24 weeks | 10 weeks | 14 days |
| Monitoring (execution) | 48 weeks | 34 weeks | 59 days |

II 	Institutional Support Component (US$1,100,000): Under this component the operation financed the administrative and operational cost of the program executing unit, and the technical assistance for training and to conduct independent evaluations, as follows:

- Training for SIMAP staff on project eligibility criteria and procedures.

- Training for community development.

- Training to improve the environmental management of SIMAP.

- Evaluation of the emergency response mechanism projects.

- Evaluation of the technical vocational training projects.

- Assumptions

The main assumptions for the achievement of the overall objectives of the program were:

- Projects financed by SIMAP will increase the capacity of communities to improve their situation.

- Experience with SIMAP projects will enable communities to organize themselves for other purposes.

- The SIMAP experience is useful and can be replicated.

The main assumptions for the implementation of the component I was:

- Communities are capable of identifying their needs and organizing themselves to request assistance and contribute to the execution and operation of projects.

The main assumptions for the implementation of the component II, were:

- SIMAP’s past experiences will continue to achieve efficient project execution.

- SIMAP and community coordination with related ministries and agencies is effective.

### II. 	PROJECT RESULTS AND DEVELOPMENT OBJECTIVES

- Based on Section I (A, B, C), above:

1. 	Achievement of the Components

Component I. It was originally planned that the program could finance a total of 632 projects. This would comprise of 164 Social and Economic Infrastructure Rehabilitation projects, 288 Emergency response mechanisim projects and 180 Amerindian projects.

The project’s component was substantially achieved. SIMAP completed a total of 610 projects which were distributed as follows:

| ##### Type of Project | Estimated Number of Project to be Financed | Actual Number of Projects Financed |
| --- | --- | --- |
| Rehabilitation Project (Regular) | 164 | 111 |
| Emergengy response Mechanisim | 288 | 389 |
| Amerindian | 180 | 110 |
| Nutrition and Technical Training | 0 | 2 |
| Total | 632 | 610 |

| Type of Project | % Of the Total |
| --- | --- |
| Schools and Related Infrastructure | 50 % |
| Transport | 25% |
| Potable Water | 11% |
| Community Centers | 7% |
| Residential Drainage/ D&I | 5% |
| Others | 2% |

Component II. All the activities and consultancies considered in the project were carried out as stated in the loan contract. Training for SIMAP staff on project eligibility criteria, procedures and environmental management was done. The training for community development and the consultancies for the evaluation of the emergency response mechanism, and the technical vocational training projects was also implemented.

- Number of Beneficiaries.

No register was designed ex-ante nor formally put in place to monitor the number of beneficiaries during the execution process. However the impact of the project in terms of beneficiaries was substantial.  For instance, SIMAP education projects helped to rehabilitate 12.5% of the school’s infrastructure system, which benefited approximately 15,000 students, or 10% of the total enrollment figures for the educational system .

In the case of the vocational training program SIMAP executed the subcomponent in-house.  This decision was the result of not been able to attract institutions interest to provide the services.  SIMAP did implement the activities agreed on the subcomponent.  Nevertheless, SIMAP did not have the capacity or the expertise to monitor a technical vocational program.

The technical vocational subcomponent provided in-plant training for 887 out-of-school youths between the ages of 16 and 25 in different skills and in different places in 198 vocational training agencies.  By the end of the project a total of 60 youths were employed by the agencies which provided the training, with 19 others being admitted to tertiary institutions to continue studies. There is no available data or tracers on the current employment status of the other trainees.

For the nutrition program, executed by the Ministry of Health (MOH) and based on MOH figures, SIMAP estimated 2,500 as the total number of beneficiaries, including mothers and children.

3. 	Achievement of the Project Development Objectives

The objective of improving the standard of living and income-earning potential of lower-income households via the financing of small-scale community generated project was substantially achieved.

Poverty Targeting

In terms of Income Generation and Distribution, an independent evaluation of SIMAP II, undertaken in 2001 () presented some valuable conclusions in order to assess the achievement of one of the aspects – low-income, targeting of the main project objective ().

An analysis of the income level of the project beneficiaries was undertaken in order to examine the targeting groups. The average income of the project beneficiaries was divided into four groups, according to their monthly family income. The threshold between the third and fourth category corresponded to an average family income of G$25,000, which is less than US$1 a day per person (), and thus all projects in the first three income categories, comprised 94% of the beneficiaries. Considering that World Bank established internationally the poverty line under US$2 per person per day, the projects can be considered very well targeted by international standards.

To verify the conclusion, three ways were used to estimate the average income of the project beneficiaries: the poverty map of Guyana (MAP), SIMAP owns estimation based in the community profile (SIMAP), and the consultants own estimate based on site interviews and surveys (Cons).  There is a close correlation between the consultant’s estimate and the SIMAP estimate. The poverty map serves as a reference and confirmation, even though there is a slight difference in the distribution.

The independent assessment also arrived at another important conclusion shown by the Average Income by type of project, considered three SIMAP types of projects:

It can be observed that practically all beneficiaries are under the G$21,000 income per household per month. Also, it can be seen that the Amerindian program had resulted in the best-targeted projects relative to national norms, probably due to its exclusive operation in regions where Amerindians live, which tend to be amongst the poorest in the country.

It can also be seen that the “Emergency Response Mechanism Projects” (ERMP) achieved better targeting than the other types of projects - including those operated in the same areas, considering that ERMP required a high community contribution (25%) and did not appear to deter poorer communities from participating. In fact, this feature may assist in targeting by filtering out projects that are not very high priority for the community. This shows also that the selection process for ERMP projects by SIMAP had better prioritization/targeting than regular projects that tended to be financed on a first-come first-served basis, as long as they met the eligibility criteria.

The regular program had a few beneficiaries of projects in the over US$1/person/day income category, but this was mainly for projects - analyzed by the Consultant- farm to market roads benefiting better to do rice farmers.

An independent evaluation of the Amerindian Program has also confirmed that the main objective of the project is being met. It found that while the program is not intended as a comprehensive solution to structural poverty in the Amerindian communities of Guyana, it has led to significant improvements in the provision of basic services and standards of living. This component as well as the integration of Amerindians in the regular projects have positively impacted in the regional distribution of per capita spending in remote areas.

Improving Income Earning Potential and Standard of Living

The income generation effect of a social investment fund is difficult to measure and probably does not happen in the very short term ().

Nevertheless, considering for instance the substantial number of projects financed by SIMAP in primary education, benefiting around 15,000 children of very low- income families is having a significant impact. It is well accepted that primary education is a key factor in social mobility and increasing productivity/income. The income earning potential for the beneficiaries of these projects must improve in the future, but it is not possible to be measured now.

The Standard of Living on the well-targeted low-income beneficiaries is also improved by many the projects.  For instance, the savings of people-time of the low- income population benefiting of drinking water; the savings and increase of income for low-income population, made possible by road to markets projects; the case of ERMP projects, having the willingness of the beneficiaries to co-finance 25% of the investment, cannot happen without significant benefits to the population.

(ii) Increase the capability of lower income communities to identify, articulate and address their priority needs.

The objective of increasing the capability of low-income communities to identify, articulate and address their priority need, was insufficiently met.

A consultant conducted an independent evaluation doing surveys among the beneficiary population.  Surveyed communities considered that 7 out of 41 projects assessed, were not of the “highest priority” to them and only one was considered high priority.  In other words, in the sample, around 18% of the projects were not identified, articulated to address the priority needs of the population and the majority of the projects were adequate but not a high priority.  This cannot be considered an improvement when compared to a similar evaluation conducted in 1996 on SIMAP I, and in this sense there was no progress in this aspect.

This situation shows that the degree of participation of the beneficiaries in the project cycle, especially the identification of projects, did not work as well as desired.  An improved project cycle giving priority to wider community participation and maybe a co-financing of the projects, could have improved the program results.

The independent report showed also that the type of project had a significant impact on the declared priority of the project by the beneficiaries.  Water projects, Residential Drainage, Drainage and Irrigation, Schools and Roads, received the highest rankings. On the other hand community centers, teachers houses and river clearing projects were considered worse in terms of community priority.

(iii)To provide a demonstration effect for other public agencies on procedures to more effectively and efficiently respond to local demand and implement investment programs.

MOE has addressed the effective intervention of SIMAP to assist the communities with the school related issues.  In the case of specific demands SIMAP has proved to be able to satisfy then within a reasonable timeframe.

- There is no difference between the current assessment of objectives of SIMAP and the latest formal statement of objectives agreed upon with the Borrower.

- The project did not achieve any unexpected results. Nevertheless, according to government authorities – see part 2 of the PCR - SIMAPII  consolidated the principle and benefits among state agencies, of addressing low-income population needs, by small interventions financed by the state and implemented privately.

- As showed previously in this report the main objective to improve the living standards of lower income household was probably achieved. However this is a long-term objective, and the evaluation analysis cannot be limited to the period of execution of the operation.

The likelihood of increasing the capability of lower income communities to self-identify their priority as showed in A II 2, is still an issue. The results were not satisfactory, nevertheless a large number of projects implemented, responded to real needs.

In terms of sustainability projects on the whole are reasonably sustainable, and the ex-post project operation and maintenance should be undertaken by the state or the communities. This aspect of the regular Program is clearly improved from SIMAP I. The community contribution requirement and the strengthened finances of the National Democratic Councils, have contributed to an improvement in the operation and maintenance capabilities of the projects. Community co-financing contribution filtered-out projects, which operation and maintenance was not affordable to the sponsor.

The ERMP projects were not as successful as the regular program in terms of operation and maintenance.  To a degree this is an expected result as the “emergency’ nature of ERMP, which finances very small projects (under US$5,000 each) tend to have less institutional support for the operation and maintenance as opposed to the larger regular projects.  Nevertheless, there is considerable scope for improvement in the ERMP projects, considering that the NDC was frequently the sponsor, and  the strengthening of NDC may improve the results.

Projects in the education sector were more sustainable. Operation and maintenance was split between the Ministry of Education (through the Regions) and the Parents and Teachers Associations (PTA).  The PTA is responsible for cleaning and doing small repairs and the Ministry of Education for the larger repairs. This division of functions appeared to work, although greater clarity is needed to define exactly who is responsible for what, and better MOE supervision for some PTAs is convenient. In spite of some complaints about the MOE, the operation and maintenance results were very positive, due to two major factors: rehabilitation of existing schools with students, reduces the risk building infrastructure that will sit unused; PTA’s and teachers maintained close supervision of the projects, providing an intimate knowledge, with strong incentives to act effectively on any maintenance problem.

Problems are most apparent in the Amerindian projects. This is partly due to the financial weakness of the Village Councils in comparison with NDCs who receive property tax income and direct funds from the central Government. Village Councils that had some income, such as mining royalties, were much more capable of complying with operation and maintenance responsibilities.

Overall, local authorities and line ministries are including their budgets maintenance allowances.  MOE is developing a maintenance program to track the used of the resources allocated  for this propose.

Coordination with responsible agencies was adequate. SIMAP formally asks for a letter of concurrence from the agency responsible for maintenance and did not proceed to execute a project without it.  However, communities and the public in general is not well informed or involved in the process. It seems recommendable to have a more public “hand over of letter of concurrence” to define or establish responsibilities and accountability, in the public’s eye, and determine clearly the contact officer in the appropriate institution, to highlight problems once SIMAP’s responsibility ends.

E.	The ex-ante analysis of SIMAP did not include any calculation of the project’s rate of return or cost-efficiency analysis. Most of infrastructure projects followed the minimum cost alternative criteria.

#### III. 	CHANGES IN ORIGINAL OBJECTIVES, COMPONENTS AND ASSUMPTIONS

- There were no changes in SIMAP’s original objectives, components or assumptions during the program execution.

- Not Applicable – The operation was an investment loan

- The end-of-year performance classification for each year of SIMAP’s execution was as follow:

| End of Year PPMR Performance Classification | Years in Execution |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1997 | 1998 |  | 1999 |  | 2000 |  | 2001 |  | 2002 |  |
| Development Objectives (DO) [HP, P, LP, I] | P | P |  | P |  | P |  | P |  | P |  |
| Implementation Process (IP) [VS, S, U, VU] | U |  | S |  | S |  | S |  | S |  | S |
| Probability of Assumptions holding true [H, L] | H | H |  | H |  | H |  | H |  | H |  |

#### IV. 	LESSONS LEARNED FROM THE PROJECT

- Project Design

- The Development Objectives of SIMAP were realistically formulated.  However no clear benchmarks were identified during the design stage. The main means of verification identified in the logical framework was the Household Income and Expenditure Surveys (LSMS/HIES). This indicator has not been updated since 1999 and could not be used, and alternative proxy was used.  It is important to establish clear benchmarks in order to assess the project’s result and make sure that the means of verification will be available when come the time of assessing the program.

- The original components of SIMAP were appropriate for achieving SIMAP’s stated objectives. The mostly successful implementation of the projects’ components is explained by the significant resources allocated to the institutional strengthening of SIMAP’s. This increased its capability to perform efficiently and to deliver the required community development training to implement the program.

- The project assumptions related to project components were realistically assessed. However the assumptions related to the project objectives were not correctly defined in the logical framework. The assumptions seems to describe factors under project control and not external factor exogenous to the project:

- Projects financed by SIMAP will increase the capacity of communities to improve their situation

- Experience with SIMAP projects will enable communities to organize themselves for other purposes.

- The SIMAP Experience is useful and can be replicated.

Assumptions are a very important aspect of the project design stage and need to be clearly expressed.

- The planned sequencing of the components was correct and reflected the normal standards used for social investment funds. The time assigned to complete the execution of the program was underestimated and the project required a 24 months extension. This was mainly due to institutional capacity (See 5. below). To execute the nutrition component, within the extended timeframe, the execution was delegated to the Ministry of Health. Realistic timetable for execution and disbursement should be taken into account during project design.

- The institutional capacity of the Executing Agency was overestimated. More than one thousand applications were submitted to SIMAP. It is unquestionable that the great number of applications submitted, overwhelmed the institutional capability of SIMAP, which was unable to process them in a timely fashion. This adversely affected the prioritization process and resulted in some disillusionment on the part of the beneficiary organizations and sponsors.

- What contributed most to the complete implementation of the Project was the simplicity of most of the components. The possibility of rapid action under the Emergency Projects subcomponent gave SIMAP more flexibility and made it possible to implement a significant number of projects in a relatively short time.  Hence SIMAP was able to accomplish a significant number of projects in all of the regions of the country.

- Project Execution

- The aspect of project execution that most contributed to the project implementation was the possibility of rapid actions under the ERMP subcomponent.

Also the good organization and response of the Parent Teachers Associations (PTA) in the educational projects (See 2 D) can be considered the main reason for their high sustainability, within all the projects implemented by SIMAP.

- The most significant problem that arose during project execution was the difficulties that SIMAP faced in implementing the nutrition subcomponent.  Despite the fact  SIMAP developed a National Plan of Action, the staff did not have the technical knowledge and expertise  to implement and monitor the nutrition subcomponent. The execution responsibility was transferred to the Ministry of Health to carry out the activities to completion. The Ministry of Health was able to articulate an aggressive and successful breast-feeding campaign, which according to preliminary reports produced a considerable reduction of diarrhea in infants 0 to 6 months old ().

- In terms of quality of the outputs. Overall quality of the infrastructure projects delivered under “Component I” was adequate for most projects; SIMAP projects were finished to a quality sometimes above the Regional norms. Sponsor groups participation contributed to a better construction supervision. Also SIMAP financed inspectors to monitor daily the larger projects; community became familiar with these inspectors, and transmitted concerns to be investigated, if not always resolved.  Regarding “Component 2”, the quantity of training courses were less than originally planned. Environmental and maintenance training courses were largely theoretical and lacked some practical application for the communities.

- All components were completed satisfactorily as agreed in the loan contract.

- Borrower/Executor Performance

- In general the Executing Agency’s performance was acceptable considering that before the Bank approved the program, a change in the senior management of SIMAP occurred.  This change had several implications in the execution because the new management primarily focused on the delivery of infrastructure reducing the community participation aspect, affecting the potential build-up of long-term capacity of the local communities to address their needs.  The Management Information System (MIS) did not include a monitoring and evaluation module as required by the project document under component II. This aspect created serious difficulties in the day-to-day monitoring of the project as well as in its periodical and final evaluations.

- Also toward the end of the program, staff salaries stagnated vis a vis other project executing units.  The result was a higher attrition rate than expected originally and retention of personnel became a problem.

- Coordination with other agencies in the Government was satisfactory.  Good coordination was shown with the Ministry of Education which was the agency with the most vested interests considering that more than 50% of SIMAPII were invested in the education sector (see Section D). Also good coordination existed with the 10 Regional Democratic Councils and the Guyana Water Authority (GUYWA) () which contributed positively to the program.

- The improvement of the institutional capacity of SIMAP is an on-going process. SIMAP operated effectively to address to some of the immediate low-costs needs of the communities. However during the execution of the project SIMAP was unable to make the transition to become a better development agency. Despite the effort done through the activities that comprised SIMAPII, the entity is still weak to respond to its mandate. The main reasons that contribute to this situation: the lack of an adequate managerial vision of SIMAP’s own role; the high turnover of personnel, due mainly to a low salaries failing to attract and keep qualified professionals, and; the low key attitude of SIMAP Board, failing to add value to decisions and to exercise its supervisory role

- Project Performance Monitoring by the Executor

- SIMAP’s performance monitoring was clearly established at the initial stages of its execution. However the required monitoring system was not fully implemented making it difficult to assess the project’s results.

- The Executing Agency monitored mainly the delivery of the civil work infrastructure. Less effort was made to establish a follow-up system to monitor community participation, ownership, number and income data from beneficiaries, project maintenance outputs and outcomes.

- Bank Supervision

- The Bank maintained supervision of SIMAP. This included regular communications between the sector specialist assigned by the COF, and the Executing Agency/ Project Unit.  Inspection visits were performed as established in the Bank’s procedures, as well as periodical Bank’s Administration Missions. Bank approved two extensions of the period of project execution (for a total of 24 months cumulative), mainly to allow the completion of the execution of the nutrition subcomponent by the Ministry of Health.

- The Bank maintained through the execution of the project, a good relationship with SIMAP and other institutions involved.  Beneficial impact was produced by these close relationships and specifically due to the coordination between the Bank, SIMAP and the Ministry of Education in terms of sustainability of the educational projects that represent 50% of the program resources. Also, the involvement of the Ministry of Health during the last six months of the program was a significant contribution for the implementation of the nutrition component.  Without the flexible approach of the Bank and the rapid and responsive intervention of the Ministry of Health, SIMAPII would have cancelled the balance on these un-disbursed funds.

### V. 	MAIN LESSONS AND RECOMMENDATIONS FOR FUTURE PROJECTS

Notwithstanding the success of SIMAP in financing community-based infrastructure, there is a great scope for improvement in several areas.  A number of lessons were learned from SIMAPII that indeed were taken into account in the design of the SIMAP III operation, as they can be seen in the table:

| Problems | Lessons Learned |
| --- | --- |
| Targeting | Poverty Maps are too macro and can become obsolete, or not updated, making difficult to assure adequate targeting of low-income groups. Agile poverty assessment instrument should be conceived and used to complement existing poverty maps, applied to isolated or substantially altered communities. |
| Community Needs assessment and project contribution. | It is important to analyze whether community contribution is an adequate indicator in targeting program resources based on the communities needs. |
| Promotion. | Social Investments Funds (SIF) tend to be “first-come first-served”, and the poorest never-reached communities tend to be kept outside. SIF should identify proactively isolated “never served” communities through a targeted promotion effort to provide equality. |
| Community Participation | The sustainability of the small-scale, community based projects envisioned under SIF hinges on the capacity of the communities to operate and maintain project activities. To help communities learn and commit to the long-term success of the community's poverty alleviation, community training components must be mandatory for each project (). |
| Projects Ranking | A scoring formula is required to ensure the best projects are selected, incorporating incentives to channel resources towards the poorest communities and higher impact projects. Poor “never served” and “good track record” communities should be promoted. |
| SIF institutional mandate and its organizational structure | - Once requests or participatory plans are ready, community members expect a "rapid response" of the SIF. SIF must decline early on the non-feasible requests (closing the case) or move on and keep the community, municipality and sponsors informed on the project status. - SIF should concentrate and make emphasis on community development, targeting and efficient management, while outsourcing infrastructure design and engineering, supervision. - The SIF planning/design process should not be a "fix one-shot deal" for a program. There should be opportunities for revision of plans procedures, criteria, and time for participants to come to a full understanding of their own problems /needs. - SIF have a limited capacity to address health and education programs. Execution of specific activities for health and education related programs, e.g. nutrition, technical and vocational education shall be delegated to the line ministries. |
| Monitoring and Evaluation | SIF should put greater emphasis on project monitoring through simple reliable data collection combined with an upgraded MIS system, able to generate reports on performance indicators and operational audits. The collection of baseline data should be incorporated into community applications/requests forms in order to facilitate the process. |

Part Two

Prepared by SIMAP

PROJECT NAME: Social Impact  Amelioration Program

IDB LOAN AND TC NUMBER(S): Loan 985/SF – GY TC:

BORROWER AGENCY RESPONSIBLE FOR THIS REPORT:  SIMAP

I. 	PROJECT OBJECTIVES

A. 	Although it may be difficult to fully assess all of the results of the project at this stage, please indicate which objectives* you feel have been achieved under the project, and to what extent.

The objectives of the project were in general achieved. The main objective, to raise the living standards and income-earning potential of lower-income households via the financing of small-scale community generated projects has been achieved. The schools, roads, water systems and community centers that were built have contributed to the communities.

Education and some other public works projects are sustainable and some of the others more vulnerable initiatives can become so with some additional help to the communities. The process, although limited by human and other resources availability has contributed to increase the capability of lower-income communities to identify, articulate and address their priority needs.

Some of the communities, although not all, have been able to provide a demonstration effect for other public agencies on procedures to more effectively and efficiently respond to local demand and implement investment programs.

B. 	In your judgment, are there any project objectives that are unlikely ever to be achieved? If so, why?

No, all the objectives of the project are achievable. The most difficult area would be for the communities to be able to fully develop their own capabilities to grow. There is lack of sufficient personnel in the region to be able to achieve this level in a systematic way. There is a need for additional help.

The improvement of the Project Cycle and Project Management is necessary to make the Agency more effective and to avoid the backlog of request for help from the communities. SIMAP needs to be able to improve in this areas too.

II. 	PROJECT DESIGN AND EXECUTION

A. 	What aspects of the project’s overall design most contributed to the project’s successes and/or failures? Why?

Flexibility is an important issue when a great number of requests needed to be handled. The idea of the Emergency Projects as a fast track to be able to approve and implement without having to exhaust all the steps of a long and complicated process helped SIMAP to obtain good results.

B. 	What aspects of project execution most contributed to the project’s successes and/or failures? Why?

The group working in SIMAP is a committed one, especially those in the regions. Sometimes the turnover ratio becomes somewhat high making things more difficult.

C. 	Did significant problems arise during project execution? If so, what were these problems and what measures were taken in an attempt to solve them? Were these measures successful?

One significant problem is the remuneration package felt low by many. Some efforts were made to gain some improvement but nothing came out of them. The Government did not take any action and SIMAP did not get an answer to the request of the improvement of salaries.

Another problem is the small amount of personnel in the regions dealing directly with the communities.

D. 	Has the institutional capacity of the institutions and agencies involved in the project been strengthened as a result of the project? If so, how?

Yes. There is a lot of experience gained, especially with the involvement of the communities.

Another issue is the deeper consciousness about the importance of the project cycle as a management tool and its implications for the way in which the projects are treated and selected.

E. 	Did any unforeseen events, beyond the control of those directly involved in project execution, adversely affect the project and the likelihood that it will achieve its development objectives? If so, please explain.

No

III. 	BANK PERFORMANCE

A. 	How well did the Bank perform during the preparation and execution phase of the project? (Was the Bank an able and efficient administrator? Did the Bank provide good and timely advice? Did the Bank maintain an effective dialog with the executing agency and between the institutions or agencies that were involved with the project?)

The Bank during the preparation and the implementation of the process was always present and helpful. During SIMAP II both institutions had very good relations leading to a more flexible and effective environment. With some changes of personnel that took place late in the project implementation some adjustments needed to be made. The learning process has been hard but good results are to be expected.

B. 	What significant impact, if any, did the Bank’s performance have on the outcome of this project?

The supportive stand of the Bank at the beginning of the project and for most of its implementation was very helpful and contributed to the good functioning in SIMAP. The changes in approach at the end were demanding and slowed things significantly. Nevertheless the introduction of a more demanding project cycle could benefit at the end.

IV. 	LESSONS LEARNED

A. 	Are there any lessons from the Bank’s performance in this project that could be used to improve future projects? If so, what are they?

To have enough and well prepared human resources is of prime importance for SIMAP. The persons functioning in the regions and those in charge of the different units in the main office need to perform at a very high level. At the present it is very difficult to keep the good ones and even to attract new recruits is difficult. Training should be always present and a compensation package should be in place in order to provide an effective mechanism to recruit capable personnel and retain it.

Part Three

Basic Data

- BASIC PROJECT DATA

| Project dates (months/year) |  |  | Original | Actual |  |
| --- | --- | --- | --- | --- | --- |
| Date of inclusion in the pipeline |  |  | Not Available |  |  |
| Date of Profile II or Loan Request |  |  | Not Available | 18 July 1996 |  |
| Date of Analysis Mission |  |  | Not Available | 26-30 August 1996 |  |
| Date of Loan Committee Approval |  |  | Not Available | 20 November 1996 |  |
| Date of Contract Effectiveness |  |  | Not Available | 16 May 1997 |  |
| Date of Compliance with prior conditions |  |  | 16 November 1997 | 18 February 1998 |  |
| Calendar of investments |  |  |  |  |  |
| Starting date | Not Available |  |  | December 1997 |  |
| End date | Not available |  |  | May 2002 |  |
| Disbursement calendar |  |  |  |  |  |
| First disbursement | 18 February 1998 |  |  | 17 March 1998 |  |
| Last disbursement | 16 May 2000 |  |  | 16 May 2002 |  |
| For sector loans |  |  |  |  |  |
| First tranche | N/A |  |  | N/A |  |
| Second tranche | N/A |  |  | N/A |  |
| Third tranche | N/A |  |  | N/A |  |
| Date of physical initiation of works | N/A |  |  | N/A |  |
| Date of loan commitment | N/A |  |  | N/A |  |
| Date(s) of Cancellation(s) | N/A |  |  | May 2002 Partial |  |
| Mid-term review and evaluation |  |  |  |  |  |
| Date of mid-term review (if required) |  | N/A |  |  | 20 February 2001 |
| Due date of borrower ex-post evaluation (if required) |  | N/A |  |  | N/A |
| Due date of Bank ex-post evaluation (if required) |  | N/A |  |  | N/A |
| Summary cost data |  |  |  |  |  |
| Total amount of IDB financing |  | 17,000,000 |  |  | 16,745,578 |
| IDB financing as % of total cost |  | 90% |  |  | 83% |
| Total cost of project |  | 18,900,000 |  |  | 20,215,000 |
| Cumulative investment as of (month/year) |  | May 2002 |  |  | 16,745,578 |
| Reminder required for completion |  | N/A |  |  | N/A |

B. 	PROJECT COST AND FINANCING

1. 	Project cost and source of financing (all amounts in millions of US$)

| Investment category | IDB | Borrower | Other | IDB | Borrower | Other |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Administration | 1,100 | 650 | 1,750 | 1,149 | 2,016 | 6,665 |
| 2. Project Financing | 15,478 | 709 | 16,187 | 15,328 | 982 | 48,684 |
| 3. Technical Assistance | 100 | 100 | 200 | 98 | 15 | 513 |
| 4. Unallocated | 152 | 75 | 227 | 0 | 0 | 0 |
| 87.1 Financial Cost | 170 | 366 | 536 | 170 | 457 | 1699 |
| TOTAL | 17,000 | 1900 | 18,900 | 16,745 | 3,470 | 57,561 |

2. 	Schedule of Investments

Original				 Actual

| Years | IDB | Borrower | IDB | Borrower |
| --- | --- | --- | --- | --- |
| Year 1998 | 4,960 | Not Available | 1,622 | 611 |
| Year 1999 | 5,760 |  | 4,818 | 703 |
| Year 2000 | 6,280 |  | 5,068 | 770 |
| Year 2001 | 0 |  | 3,900 | 1,149 |
| Year 2002 | 0 |  | 1,337 | 237 |
| # TOTAL | 17,000 | 1,900 | 16,745 | 3,470 |

C. 	LOAN/TC DATA

| Original Loan/TC amount | $17,000,000 |
| --- | --- |
| Amount disbursed | $16,745,578 |
| Amount cancelled | $254,422 |
| First disbursement |  |
| Original date (month/year) | 18 February 1998 |
| Actual date (month/year) | 17 March 1998 |
| Last disbursement |  |
| Original date (month/year) | 16-May-2000 |
| Actual date (month/year) | 16-May-2002 |

Assessment conducted for the Basic Education Access Management Program (BEAMS) LO-1107/SF-GY

Guyana: An Evaluation of the SIMAP II Program (September 2000). C. MacDonald and S. Joseph.(nutrition, vocational and technical training programs were not included in this evaluation)

The Household Income and Expenditure Surveys (LSMS/HIES) identified as the main mean of verification for this aspect at the national level has not been updated since 1999.

Assuming an exchange rate of G$182.75=US$1.00 and assuming an average family size of 4.8.

J. Renshaw, SIMAP Amerindian Program.

Only a good baseline ex-ante and an ex-post long term study, could asses this aspect of the program

The Minister of Health referred publicly to a reduction in gastrointestinal cases reported in health care post and centers where SIMAP financed Breastfeeding campaign was operating.

Project Report GY-0061 SIMAP III.

For example, infrastructure projects should include training of community associations in activities related to the operation, oversight and maintenance of the facilities.