GUYANA

SOCIAL  IMPACT AMELIORATION PROGRAM (SIMAP I)

(LO-912/SF-GY)

MANAGEMENT REVIEW COMMITTEE (MRC) MINUTES

FOR THE PROJECT COMPLETION REPORT (PCR)

#### October 2, 2001

I.	PARTICIPANTS

1.1	A Management Review Committee (MRC) meeting was held to review the Project Completion Report of the above project.  Juan M. Fariña (SO3/CHF) chaired the meeting; other participants included Iwan Sewberath-Misser (RE3/OD6) and Silvia Raw (RE3/SO3), who acted as secretary.  Comments were also received from Pablo Adam (RE3/SC3) and Ashu Handa (RE2/SO3).  The Representation did not participate in the MRC.

# II.	RECOMENDATION

  - The MRC reviewed the PCR and agreed that once the following changes are incorporated, it should be resubmitted to RE3 for its final approval.

III.	OBSERVATIONS

The main issues discussed for inclusion in the PCR are as follows:

  - Sources of information: The PCR should identify the sources used.  Most of the report appears to be based on the midterm review of the program, which should be referenced.  However, the document also makes reference to an ex-post evaluation (para. 2.4).  This probably refers to the yearly evaluation of SIMAP projects completed in the previous year, rather than a formal ex-post evaluation of the whole program.  This should be clarified; if an ex-post evaluation of the entire project indeed exists, its findings should be presented.

  - Description of achievements: The PCR should provide a more detailed description of the social and economic infrastructure projects carried out under the investment component (paragraph 2.2, section a) and of the technical assistance component (para. 2.4)

  - Nutrition: The discussion of the nutrition component argues that it was well targeted and that the contents of the supplements “were felt to have met the major deficiencies detected in the target population.”  No evidence is provided for either claim. Since an ex-post evaluation of the parallel World Bank nutrition program exists (M. Immink, 1997), the MRC suggested that this report’s findings be incorporated in the PCR.

  - Technical-vocational component: Little is said about this component.  The PCR argues that it was well targeted, since it was concentrated in the two regions with the largest populations, which is a non-sequitur. It also hints at procurement problems; in para. 2.1 the repeated extensions in the loan are attributed to this component.  Since the experience was repeated in SIMAP II and the IDB is once again considering support for technical-vocational training, it is important to include further information on the problems encountered, especially institutional ones.

  - Targeting: The discussion of whether the project succeeded in reaching the most vulnerable groups in Guyana (section 2.7) is contradictory.  For example, para. 2.7 states that the programme successfully targeted the most vulnerable groups; para. 2.7.1 states that “it does necessarily follow” that projects were well targeted, while para. 2.7.5 states that “at the project level SIMAP did not always succeed in targeting the most vulnerable groups.”  The entire section should be clarified. A good starting point would be to explain what mechanisms were used to target the projects, since a poverty map was not available under SIMAP I.

  - Main lessons and recommendations:

- According to the PCR, the Bank and the Borrower need to define programme objectives more clearly (para. 5.2).  However, there is nothing in the PCR to suggest there was lack of clarity of objectives.

- The PCR also recommends that the Bank and the Borrower “provide more of a mandate to the executing agency to help with targeting.”  This is a misunderstanding; SIMAP had a mandate to target; what it may have lacked is an instrument to do so (see point 3.5 above).

/signed/		/signed/

__________________	___________________

## Silvia Raw	Juan M. Fariña

## MRC Secretary	MRC Chairman

Project Completion Report (PCR)

#### Part One

PROJECT NAME : Social Impact Amelioration Programme (SIMAP I) PROJECT NUMBER: GY-0047 LOAN AND TC NUMBER(S): L0-912/ SF–GY COUNTRY: Guyana EXECUTING AGENCY (IES): Social Impact Amelioration Programme SECTOR: Social MODALITY: Investment DATE APPROVED: 23 /10 /93 DATE COMPLETED: 31/08/99 LOAN/TC AMOUNT(S): US$ 13.5 mn FINAL PROJECT IMPLEMENTATION CLASSIFICATION (HS, S, U, VU): S FINAL PROJECT ASSUMPTIONS CLASSIFICATIONS (H, L): H FINAL DEVELOPMENT OBJECTIVES CLASSIFICATION (HP, P, LP, I): P

1. PROJECT OBJECTIVES AND COMPONENTS

1.1 The general objective of the programme was to support the Government of Guyana’s (GOG) efforts to limit the negative impact of the Economic Recovery Programme.

The specific objective of the programme was to support the Social Impact Amelioration Programme’s (SIMAP) mission of financing small scale, locally sponsored projects that served the priority needs of Guyana’s most vulnerable population. The operation was designed to contribute to the empowerment of community based organisations (CBOs).

1.2 The programme comprised two components: investment and institutional support.

Investment

    - Within this component the Loan financed projects in four areas: a) social and productive infrastructure, b) nutrition, c) Amerindian development and Technical/vocational programs.

a) 	Social and Productive Infrastructure. This sub-component was designed to provide financing for projects sponsored by local groups, CBOs and local & regional government. Social infrastructure projects were to include the rehabilitation or expansion of the following facilities: schools, community centres, old age homes, welfare institutions etc. Productive infrastructure projects were to cover the rehabilitation or reconstruction of local roads, drainage and irrigation (D&I) systems, bridges and local markets.

Social infrastructure projects were expected to cost an average of approximately US$25,000 and productive infrastructure projects an average of approximately US$50,000. Although there was no pre-fixed limit on the division of resources between project types it was estimated that social infrastructure projects would account for about 70 % of infrastructure projects. According to the initial report prepared by SIMAP in 1994 it was estimated that US$7.3 mn would be spent on this sub-component. With some US$5.11 mn being spent on social infrastructure projects and US$2.19 mn on productive infrastructure projects. 300 small-scale infrastructure projects were to be financed over the four-year period 1994 – 1997, with 75 projects being executed each year.

b)	Nutrition. This sub-component was designed to provide food supplements, basic nutrition surveillance, and nutrition education to pregnant and lactating women, infants under the age of two years, and malnourished children from two to five years. The  project was to begin by operating for 12 months in a given clinic. Bank financing was initially not to exceed US$1 mn to support 10 health clinics. The average cost for each clinic was estimated at US$90,000 for a one-year programme, serving approximately 900 beneficiaries. Medical supplies, drugs and furniture for each clinic were estimated at US$11,500, whilst the food supplement was budgeted at US$7 per beneficiary per month. An additional amount of US$3 mn could also be committed. For this financing to be disbursed a National Nutrition Plan for the reporting and treatment of nutritional deficiencies had to be drawn up, an Action Plan to implement it developed and a Proposal to finance it approved, within 18 months of Loan signature.

c) 	Amerindian Development. This was a pilot programme to promote the welfare and/or economic development of Amerindian communities. Twenty projects limited to US$200,000 total costs were to be financed and completed within 18 months of the first disbursement. These projects could include components that were eligible as infrastructure projects. However, they could also include  technical assistance to improve crop cultivation techniques or handicraft technology and design, the construction of a house for a teacher, purchasing of a boat and outboard motor for transporting local produce to market, and basic tools and equipment for productive activities. Other eligible activities included those to provide health and sanitary or nutritional services, primary or vocational education, or to improve the economic condition of Amerindian communities. After evaluating the results of this programme and after specific eligibility and selection criteria were agreed with the Bank, further projects could be financed under this sub-component up to a total value of US$500,000.

d) 	Vocational Training.  For this sub-component to be incorporated, the Bank required i) a satisfactory evaluation report of the results of the vocational training programme executed in the start-up phase of SIMAP and ii) eligibility and selection criteria to be agreed with SIMAP. It was anticipated that 20% of students to be trained would be guaranteed employment.

Institutional Support

1.2.2	Total costs of the Institutional Support category were estimated in the Loan Proposal at US$2.8 mn with a GOG contribution of US$ 1.39 mn to SIMAP’s operating expenses. Bank financing was to be divided into two sub-components:

- General support (US$1.22 mn). Under this sub-component 17 staff positions deemed  critical to the execution of the programme were to be financed at a cost of US$650,000.  Budgetary provision was made to cover the cost of  professional services for project preparation and project evaluation at a value of US$570,000.

- Technical assistance (US$190,000). This sub-component was included to provide 23 person-months of technical assistance and consultancy services to improve SIMAP’s capacity in project preparation and appraisal, administration support, Management Information Systems (MIS), ex-post Project Evaluation, environmental issues and nutrition policy.

Contingencies

1.2.3	No contingencies for the investment projects were provided for in the Budget and any increases in the average project costs were to be reflected in a decrease in the number of projects financed. However, the sum of US$255,000 was budgeted for equipment, purchase and increments in general support required.

Total cost of the programme was estimated at US$15 mn with the Bank contributing US$13.5 mn from the Fund for Special Operations, and the difference of US$1.5 mn coming from local counterpart resources. Table B1 – Project Cost and Source of Financing in Part Three provides the projected and actual project costs and source of financing.

Executing agency for the Loan was SIMAP. The Government was to transfer funds on a grant basis from the loan and the local counterpart to SIMAP. SIMAP was not to execute the projects directly but would act as a source of funding, channelling resources to projects with community sponsors. SIMAP was to be responsible for the appraisal of these projects and would monitor their execution.

Disbursements were scheduled over a four-year period, with the funds being committed over a three and a half-year period. The commitment period was defined to allow for the execution of sub-projects and ensure adequate monitoring of the activities. Table B2 in Part Three provides the schedule of investments.

1.2.4	Annex 1 provides the Logical Framework which was retrospectively fitted. From this matrix it can be seen that the main assumptions on which the successful implementation of the project components was based were:  a)  that the GOG co-operated in the preparation and implementation of a National Nutrition Plan; and b)  SIMAP and community co-ordination with related Ministries and agencies was effective.

Assumptions on which the overall achievement of project objectives was based were: a)  the experience with SIMAP projects would enable communities to organise for other purposes; b) facilities and amenities restored through projects would be effectively operated and properly maintained by sponsors/communities/ public agencies post project;  c)  the socio-economic conditions in Guyana would not decline further over the project period.

From the Loan Proposal one can also determine the following assumptions on which the achievement of project objectives was based:- i)  sponsors would come forward, with viable projects, which would meet the targets; ii) SIMAP would be able to appraise and evaluate projects and move them through the project cycle efficiently; iii) SIMAP would retain sufficient staff; iv) the GOG would release funds, and v) finally that SIMAP’s operational/ institutional  capacity would not worsen.

##### 2. PROJECT RESULTS AND DEVELOPMENT OBJECTIVES

Achievement of Project Components

2.1	Although the loan disbursement period was established for four years four extensions were  approved were given, with the project  ending in August 1999, or one year over term.  Cumulative extensions were largely due to a major supplier defaulting on the equipment to be procured for the technical/vocational component.

A total of 150 projects were completed at a cost of US$12 mn, according to the data provided by SIMAP. It should be noted that disbursements from the IDB for Project financing totalled US$ 12.226 mn. SIMAP explains this discrepancy as being due to the fact that an average exchange rate was used to calculate US$ disbursements up to 1995, and that prior to 1996 the system was not fully computerised. Furthermore, they stated that in addition to differing exchange rates after 1995 used in their General Ledger and claims modified by the Bank, some General Ledger rates were not adjusted to reflect the exchange rate changes on claims by the Bank. This report uses the figures given by SIMAP since they were able to provide data on disbursements by type within Project financing, with the caveat that their figures may need some adjustment for exchange rate adjustment/conversion.

Investment

2.2    A total of 103 infrastructure projects were completed compared to the 300 anticipated in the Loan Proposal. This discrepancy can be attributed to the increased cost of completing the projects (see below) and problems experienced within the project cycle.

a)	Social and Productive Infrastructure. Under this sub-component a total of US$7.85 mn was spent or 7% more than originally budgeted. Some 80% of these projects were social infrastructure projects (82), and this was slightly above the 70% anticipated in the loan proposal. The average cost of these was US$95,700 or some 283% more than had been anticipated. This was due to the fact that the works undertaken were repairs and rehabilitation, and during execution, unanticipated structural problems, often hidden behind finished surfaces, became apparent, causing delays and variations in cost estimates. However, whilst the number of communities which benefited may have been fewer than expected it does not necessarily follow that fewer beneficiaries were able to take advantage of this sub-component.

Productive infrastructure projects averaged US$115,276 or 130% more than had been expected. This was partly a result of the sponsors’ and SIMAP’s engineers desire to extend the life of the structure through elevated technical specifications, and the fact that the original Programme costs for this category were under-estimated.

Under the infrastructure sub-component there were 147,745 beneficiaries of which 100,104 were direct beneficiaries of social infrastructure projects and 47,641 were direct beneficiaries of productive infrastructure projects.  Within the social infrastructure projects a total of 3,084 nursery school pupils, 13,935 primary school pupils, and 9,703 secondary school pupils benefited from having their deteriorated learning environments rehabilitated.

Tables 4a, 4b, and 4c in Annex 2 provide a regional breakdown of the number of projects completed and total costs by type.

b) 	Nutrition. There was a delay in starting the nutrition sub-component due to a lack of information from the Ministry of Health regarding malnutrition levels at clinics across the country. Eventually, some 25 health clinics were selected according to their location and levels of malnutrition. The programme began by financing 10 of these, with the understanding that the rest would be financed once the National Nutrition Plan had been implemented. The programme was estimated to run for 12 months initially, but due to problems with awarding contracts it eventually operated over an 18 month period. A total of 1,779 pregnant women, 1,481 children aged 6 to 23 months and 1,031 children aged 2 to 5 years benefited under this sub-component. The average cost of the nutrition programmes was US$39,000 or some  61 % less than the budgeted figure of US$ 100,000. This discrepancy can be explained by the fact that the programme actually benefited significantly fewer persons than had been expected, e.g. the figure budgeted was some 9,000 beneficiaries at a cost of US$ 7 each or US$ 63,000 total, whilst the programme eventually only covered some 4,291 beneficiaries, less than 50% of the target group.

The contents of the nutrition supplements were felt to have met the major deficiencies detected in the target population. However, the Ministry of Health had difficulty in providing the educational inputs into this component.

The Government failed to implement the National Nutrition Policy and therefore this part of the programme did not utilise any of the additional funding budgeted for it’s execution.

c)	Amerindian Development. A total of 20 pilot Amerindian projects were completed and evaluated by the end of 1996. Based on this evaluation the Bank increased funding for this sub-component for an additional 27 projects in Regions 1,2,7,8 and 9 (some of which have been regarded as infrastructure projects by SIMAP in their calculations). The ceiling for Amerindian projects was also raised from US$ 10,000 to US$ 20,000 per project due to the high costs associated with undertaking work in these remote communities. Some 15,017 Amerindians benefited from the investments under this sub-component. Tables 4a, 4b,and 4c in Annex 2 provide information on the regional distribution and value of Amerindian projects.

d)	Technical/Vocational. Based on the recommendations of the evaluation of the previous In-Plant Technical/Vocational Programme, a technical/vocational training assistance programme was proposed and approved in September 1995. Training was co-ordinated by the Board of Industrial Training in two batches, Feb. 1996-Jan. 1997, and April 1997–Dec. 1997. A total of 854 unemployed school leavers received in-plant technical/vocational training in 9 out of the 10 regions at 200 public and private agencies. Of these approximately 50% were employed at the end of the programme. A total of 828 youths received six months formal training in Regions 2, 4 and 6, at eight Technical/Vocational Education Training institutions. This institutional training concluded in March 1999 after considerable problems with procurement of equipment.

2.3	Institutional Support

a)	General Support. US$801,000 or 34 % less than budgeted in the Loan Proposal was spent on this aspect of the programme. The funds were utilised to support the 17 key positions as planned, and obtain professional services for project preparation and evaluation. The sum spent was lower than envisaged since the salaries paid to the supported staff were lower than expected. Although a semi-autonomous agency, SIMAP’s salaries were still determined by the Ministry of Finance and thus could not be raised to the levels budgeted. A total of US$418,696 was transferred from this category to project financing in January 1999, since all commitments under this category had been met.

b)	Technical Assistance. An amount of US$137,630 was spent under this category from Bank finances. This was 28 % lower than the US$190,000 budgeted. The six consultancies scheduled under this component were carried out in the last quarter of 1995 and the first quarter of 1996. Most of the agreed recommendations were implemented by SIMAP. The funds remaining under this component, once these consultancies had been executed, were transferred to the category of project financing in January 1999.

Contingencies

2.4	The funds budgeted under this sub-component were also transferred to project financing in January 1999 for the execution of additional infrastructure projects.

A final transfer between categories occurred in August 1999 when the funds which had been budgeted for the 1998 ex-post evaluation of the Loan, were transferred to Project financing from the technical assistance component, since the ex-post evaluation was jointly done in 1998 for Loans 912/SF-GY and 985/SF-GY and was financed under the latter.

Achievement of Project Objectives

2.5	Project Objective to finance small-scale locally sponsored projects.  Whilst the average cost of infrastructure projects exceeded that budgeted for in the Loan Proposal, one can still argue that at an average of US$99,840 they can still be viewed as small scale when compared to traditional infrastructure projects. From Table 1 in Annex 2, it can be seen that the projects financed by SIMAP had a wide variety of sponsors. Looking at all the project types as a whole it can be seen that the majority of sponsors were NGOs or Local Authorities and Village Councils. Thus it would be fair to say that the project achieved its objective of financing small-scale locally sponsored projects and contributed to the empowerment of CBOs.  Data provided by SIMAP on the size range of projects by type are given in Table 2 in Annex 2. Again this would support the view that the objective of financing small scale projects was met.  A Mid Term Evaluation conducted in 1996 also concluded that SIMAP had successfully encouraged the participation of CBOs in the development of projects.

2.6	Project Objective – to serve the priority needs of Guyana’s population. Since the projects were community based, with the sponsors rooted in the community, it would be fair to assume that the projects represented the priority needs of Guyana’s population and thus fulfilled this part of the objective. However, it should be noted that since SIMAP had no method of assessing how representative the sponsor groups were, it is possible that the projects did not necessarily always represent the highest priority needs of the community or district as a whole. Furthermore, the mid-term review noted that SIMAP did not pursue sufficient pre-application publicity. This meant that there was a tendency for those communities which had previously benefited to access funds once more, whilst more remote communities, which might be vulnerable or have projects of higher priority, would be disadvantaged. Not all communities, especially remote communities, would have had equal access to SIMAP to articulate demands, implying that whilst the objective was met at a general level, this might not have been the case at a specific level.

2.7	Project Objective – to serve the priority needs of Guyana’s most vulnerable population.  Table 3 in Annex 2 presents information on the average income of project communities by type of project, and the 1996 poverty line. This poverty line is used for comparison since most of the social and productive, Amerindian and Health projects had been started by 1996 and thus would have been judged against the criteria of income levels in 1995 and 1996. From this Table it can be seen that for all projects the average income of the beneficiary communities was below the poverty line. Thus the programme can be said to have successfully targeted the more vulnerable population groups.

2.7.1	A regional analysis of the projects implemented in this programme (Tables 4a, 4b & 4c, Annex 2) shows that social infrastructure projects were undertaken in all the regions of Guyana in a manner fairly proportionate with population levels. The Tables also provide information on Bank funded investment on infrastructure per capita. From these Tables it can be seen that investment was concentrated in Regions 4 and 6, whilst Regions 1,7,8, & 9 which are more remote, received considerably less investment. It could be argued that given the high concentration of population within Regions 4 and 6 there would necessarily be a greater number of vulnerable groups in these regions, and hence the projects were well targeted. However, communities found in the more isolated regions tend to be more vulnerable due to their remoteness. These communities include the highest concentrations of Amerindians who are usually homogenous in income level. Thus any project which has a wide number of beneficiaries and community support in these areas can almost certainly be counted as well targeted. On the other hand, in Regions 2 – 6, economic activity is much less homogenous, with a consequential wider spread in income levels. Whilst the data on regional distribution show that projects were spread throughout the regions, it does not therefore follow that SIMAP’s projects were necessarily well targeted at Guyana’s most vulnerable population.

2.7.2	The high proportion of administration costs associated with projects in remote areas tended to act as a disincentive to their development by SIMAP. Also the limited pre-application publicity undertaken by SIMAP tended to reduce demand for projects and further restrict the access of vulnerable groups.

2.7.3	The mid-term evaluation looked at a sample of 29 projects. An analysis was conducted of the income level of the project beneficiaries. The dividing point between the income quartiles was based on the World Bank Strategies for Reducing Poverty, March 1994, with adjustment made for inflation. The mid-point within the quartiles below which households could be considered very poor was G$26,000, whilst a household with an income above G$34,050 could be considered poor but perhaps not the most vulnerable. This methodology fitted in with the Bank’s own low-income threshold of US$251 per month/household or G$35,100.

2.7.4	The evaluation found that, whilst the number of projects by income level was fairly proportionate, the total cost of projects by income level, was not so evenly distributed. Indeed, the upper two quartiles, received two-thirds of the investment in the 29 projects, whilst those households which were clearly more vulnerable in income terms, i.e. with incomes below G$26,000, received just one-third of the investment.

2.7.5	Although SIMAP functioned under Operating Regulations agreed with the Bank it had no clear methodology for prioritising incoming projects. When this was combined with its large inventory (735 projects by the end of this Loan), and poor project cycle management it was almost impossible to ensure that projects were targeted at the most vulnerable groups. Thus whilst at a general level it can be said that the programme met this objective, it should be noted that at the project level SIMAP did not always succeed in targeting the most vulnerable groups.

2.7.6	Looking at the rest of the programme, it can be seen that Technical/Vocational projects were concentrated in Regions 4 and 6. Since these regions have higher population levels, it would be fair to assume they also had higher levels of unemployment. The objective of serving the priority needs of Guyana’s most vulnerable population would have been met by this part of the programme.

2.7.7	The Health and Nutrition projects were well targeted since clinics were chosen from a list compiled by the Ministry of Health indicating those with the highest levels of malnutrition. Thus any project which targeted these clinics through food supplements and education would have directly benefited the most vulnerable groups in Guyana.

2.8	There were no differences between the current assessment of components or objectives and the latest formal statement of components and objectives agreed with the Borrower.

2.9	Unexpectedly, the Project assisted in revamping the country’s contracting industry.  SIMAP was conceived at a time when Guyana’s economic situation had been deteriorating for some years. This had adversely affected the contracting sector. Since the projects undertaken by SIMAP were small, they provided a base for the local private contracting sector to grow and learn, and get back on its feet again. Thus, partly through SIMAP, Guyana’s contracting industry has been revitalised, providing a strong base for future infrastructure investment works.

2.10	The programme as a whole should be sustainable. The infrastructure projects, which represent the majority of investments were mainly rehabilitation projects. Thus, maintenance costs for these structures should be relatively low for the short to medium term. The rehabilitated schools in particular should be sustainable since the policy was to rehabilitate buildings which were already in use, so limiting the possibility that they would not be used after the project. Furthermore, the project sponsors for schools were usually Parent Teacher Associations. Thus parents have an incentive to protect their children’s environment whilst the teachers, in daily occupation of the premises, should have a vested interest in their maintenance.

2.11	Other projects completed under the social infrastructure sub-component e.g.: community centres and shelters should also have lower maintenance costs due to the extent of the rehabilitation conducted under the programme.  Furthermore sponsor groups for these projects have indicated a willingness to contribute to maintenance costs themselves and raise funds which should improve their sustainability.

2.12    The process of obtaining funds from SIMAP has meant that communities have had to come together and organise themselves. They should therefore be in a better position to work together to collect funds and undertake maintenance. The fact that local communities sponsored projects has also tended to give them a feeling of ownership of completed projects and thus a greater incentive to maintain them.

2.13	However, problems may be experienced with sustainability since, whilst projects were identified by sponsor groups generally, it is the line Ministry or local authority which has overall responsibility for long term and systematic maintenance. The Loan proposal noted the possibility that if the line Ministries’ capacity to plan and execute systematic maintenance did not improve, problems with the sustainability of the programme as a whole would be experienced. Unfortunately, over the life of the programme, it would be fair to say that the line Ministries were not adequately strengthened and in many cases suffered further, due to sustained staff losses and lack of finance.

2.14	The productive infrastructure projects may be the least sustainable. Whilst the D&I projects included a requirement for farmers to organise themselves and undertake regular maintenance of the canals and drains, this has not happened, resulting in resilting and problems with the sustainability of these works. One problem experienced with D&I was confusion over the division of responsibility for maintenance. In some areas these structures fell under the local authority and in others under the D&I Board. There needs therefore to be a prerequisite for farmers/sponsors in these sub-projects to have developed and implemented a Water Users Association before projects are undertaken, which would ensure that fees are collected and maintenance undertaken regularly.

2.15	The road projects may also prove to be unsustainable since most users have not been prepared to pay adequate maintenance costs. In addition, road sponsors are not politically strong enough to ensure that the regional authority or the communities contribute to maintenance.

2.16	The Amerindian projects are generally felt to be more sustainable in the long term given that most of the projects incorporated a large element of self-help serving to demonstrate that the projects undertaken were high priorities within the communities, and therefore showing the level of commitment to the projects.

2.17	The mid-term evaluation, which examined the sustainability of 29 projects, found that generally those projects, that had a high level of community involvement in their development and execution, tended to be more sustainable. Furthermore, it was noted that using the Amerindian projects as a guide the incorporation of a self help element into projects tended to motivate the beneficiaries to identify more with the project, actively take care of it and maintain it over the long term.

2.18	The nutrition projects were undertaken in areas with high malnutrition levels and whilst                  successful at reaching these targeted persons, they may not be sustainable in the long term.  Indeed the benefits of these projects will be short-lived unless the Government articulates a National Nutrition Policy, implements it and provides adequate nutritional education and monitoring to the vulnerable groups.

2.19	There are no project objectives that are unlikely ever to be achieved.

2.20	There was no calculation of the project’s rate of return or cost efficiency analysis in the ex-ante analysis of the project.

  - The mid-term evaluation calculated the economic rates of return for economic Infrastructure projects to exceed 12%. The evaluation also found that greater community participation and stronger CBOs tended to be associated with greater project effectiveness.

3. CHANGES IN ORIGINAL OBJECTIVES, COMPONENTS AND ASSUMPTIONS

3.1	No significant changes occurred in the project’s objectives, components or assumptions during execution  (after project approval).

3.2	This programme was not a sector or hybrid operation.

3.3	The following Table is based on the PPMRs presented to Headquarters:

YEARS IN EXECUTION

| End of Year PPMR Classification | 0 | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- | --- |
| Development Objectives (DO) [HP, P, LP I] |  |  | HP | P | P | P |
| Implementation Progress (IP) [ VS, S,U, VU] |  |  | S | S | S | S |
| Probability of Assumptions holding true [H,L] |  |  |  | H | H | H |

4. LESSONS LEARNED FROM THE PROJECT

Project design

4.1	The original objectives of the project seem to have been realistically formulated. However, they were rather general in nature and perhaps could have benefited from being more specific. SIMAP was given little guidance as to how to prioritise projects to ensure that they were better targeted at the most vulnerable groups, or to promote the sustainability of the completed projects.

4.2	The original components of the project were necessary and sufficient for achieving the project’s stated objectives. The investment component enabled SIMAP to finance bottom-up community driven projects, which reflected the needs and priorities of the various groups, whilst the requirement that projects be sponsored by CBOs helped to empower locally communities. The guidelines established in SIMAP’s operating manual further ensured that SIMAP could target, at a general level, low-income groups, thus fulfilling its mandate.

4.3	The institutional support component of the Loan helped SIMAP to develop a strong base for the execution of the investment component. The financing of key positions within SIMAP e.g.: the finance and accounts section and the MIS, and the re-organisation of SIMAP prior to first disbursement contributed considerably to SIMAP’s ability to accomplish its objectives. Technical assistance also ensured that SIMAP was able to access support in areas that required development.

4.4	The programme was developed without the benefit of the logical framework approach, since it was developed in 1993. However, during Loan management, the PPMR was introduced as a means of classifying end of year performance, and a Log Frame was retrospectively fitted. This identified the assumptions on which the programme’s successful completion depended, and can be seen at Annex 1.  During Loan preparation a number of risks to project completion were identified. These can be taken as assumptions on which the project is based – see section 1.2.4 above.  At a general level these risks were correctly identified and realistically assessed.  The following pre-conditions were incorporated in the Loan, as a means of minimising risks:

i)  GOG agreed to transfer resources for execution;  ii) an account was established at the Bank of Guyana with resources from ARSA  with sufficient funds to cover the counterpart requirement; iii)  SIMAP implemented a new organisational structure as agreed with the Bank;  iv)  an internal audit unit was been created within SIMAP and adequately staffed;  iv)  SIMAP put into effect the Programme operating regulations as agreed.  These conditions were designed to ensure that SIMAP should have access to the funds required, have the necessary staff complement and regulations to allow it to function adequately and meet its objectives.

4.5	The programme was deliberately designed to be conservative in size, to allow for the fact that SIMAP’s operational capacity might not improve and could even worsen during project execution. This proved to be a realistically assessed scenario, since during execution, despite the financing of staff positions provided by the project, SIMAP found it difficult to attract and retain the full staff complement. Whilst it was able to execute the programme as specified it might have found it difficult to execute a larger programme due to this staffing issue.  It had been assumed that SIMAP staff would be paid a salary in excess of that of Government line Ministries and in keeping with the private sector. In fact, salary levels were never to reach the levels anticipated by the Bank, causing some loss of staff and limiting SIMAP’s ability to fulfil its mandate.

4.6	The new organisational structure was not sufficient to allow SIMAP to execute its functions effectively. It became apparent during execution that there was a need for greater representation within the Regions by SIMAP, to ensure that it could better undertake pre-application publicity and so target vulnerable groups and isolated communities more effectively. Furthermore, projects in the Regions could have benefited from a greater input from SIMAP officers right through the project process, and often after project completion. This would have helped to strengthen the sponsor groups further and better empower the CBOs. Additional regional offices would also have meant that more SIMAP officers were in the field to oversee the supervision and contraction of projects, and so avoid some of the problems experienced through poor supervision.

4.7	Under the technical assistance sub-component the Loan incorporated support to develop a  National Nutrition Plan and a Plan of Action to finance and implement it. Thus, steps were adequately incorporated to mitigate the risk that the nutrition component would not be fully executed. Despite these steps the Government still did  not implement the Plan.

4.8	The planned sequencing of components appears to have been adequate, in that it allowed SIMAP to respond to community requests as they were articulated.

4.9	The institutional capacity of the executing agency seems to have been adequately assessed in the project’s design. As noted above the programme was deliberately conservative in size, as SIMAP’s operational capacity might not improve over the life of the project. Also, considerable institutional support was provided to SIMAP. Additional support was given in the form of financing to subcontract project preparation; the centralisation of SIMAP’s management of procurement of works contracts; and the streamlining of the process of obtaining Bank concurrence for project financing.

4.10	The aspect of project design which most contributed to the project’s success was the fact that communities were able to identify their priorities and work together to obtain finance for the rehabilitation of infrastructure. The programme can be said to have been successful at empowering local groups. Demands articulated by CBOs were encouraged, and projects executed in response to people’s perceptions of their priorities rather than Government determined priorities. This meant that they would have been better targeted, reflecting the priorities of low income communities to a greater extent.

4.11	The outsourcing out of project profile preparation and project execution can also be seen as a positive aspect of project design. SIMAP was able to sub-contract substantial volumes of construction works to small private firms in a transparent fashion, which had a positive impact on private commercial firms. SIMAP’s success has helped to demonstrate the concept that public agencies can sometimes achieve their goals more effectively by increasing the participation of private sector firms.

4.12	The small size of projects enabled SIMAP to deliver projects of satisfactory quality at a reasonable cost to the targeted low income groups. It also proved beneficial in that their impact was immediate, and encouraged other communities to apply.

4.13	The aspect of project design which most contributed to its failures was the fact that there was no transparent system laid out for the prioritisation of projects within SIMAP. Projects were dealt with as they were submitted, mainly, but not always, in a chronological order. No attempt was made to prioritise projects, and determine which ones would best meet the criteria of benefiting the most vulnerable sections of society. Similarly, projects were evaluated on a national basis rather than a regional basis. There was no way to judge which project would better meet SIMAP’S objectives, and no way to compare projects by region. Perhaps SIMAP could have better achieved its objectives by selecting projects on the basis of the highest priority for a Region. SIMAP could also have better achieved its mandate if it had been given clear guidance as to the levels of income/attributes of a community that would distinguish one community from another in poverty terms, that is, if there had been clear divisions/categories into which projects could be placed for evaluation depending on their relative levels of poverty.

4.14	An additional design failing was the lack of pre-application publicity incorporated into SIMAP’s functions. In addition, the organisational restructuring of SIMAP, undertaken as a precondition, had not taken into account the need for the decentralisation of SIMAP.

4.15	Finally, SIMAP had no effective procedures to evaluate how representative a CBO might be and no procedures to remove an unrepresentative group from a project. This could have led to conflict and extra costs as project designs were changed etc. However, there were few problems with CBOs and the SIMAP strategy of using CBOs as sponsoring agencies can be considered a success.

Project Execution

4.16	The aspect of project execution that most contributed to the project’s success was the tendering out of projects. SIMAP’s tender process was transparent and effective. It operated outside of the regular Government tendering process and was thus able to process tenders faster and at a rate more consistent with SIMAP’s requirements. SIMAP maintained a list of prequalified contractors through semi-annual invitations in the press. These contractors were categorised by Region, Project type and the scale of work they were able to undertake. In addition, SIMAP would only allow a maximum of three contracts per contractor. This system helped to minimise the time taken to let tenders since there was no need to advertise each contract. The system also ensured that it was mainly contractors from the Region who won contracts, provided they could undertake the work, and this had a multiplier effect within the Region through employment etc.

4.17	The time taken from the awarding of contracts to completion of works, was also good in SIMAP. Using the average of a sample of projects for 1995-1998 and comparing length of time to execute the works to time taken for the whole project cycle, it appears that project execution was relatively quick and efficient (Table 5, Annex 2). Thus for 1998, whilst it took 1,564 days from the acknowledgement of a project request right through the project cycle, project execution accounted for just 319 days or 20% of the project cycle.

4.18	Finally, the system of contracting out the development of project profiles was also a useful tool to aid project execution. This meant that SIMAP officers could be free to undertake other activities necessary to the functioning of SIMAP.

4.19	Poor Management of the project cycle as a whole is the aspect which most contributed to the project’s failures. From the samples used to obtain the averages for the years 1995-1998 it was found that it took from 1.7 to 5.5 months for sponsor groups to receive an acknowledgement of their application from SIMAP. In some cases it could take up to 23.6 months (Ithaca D&I project 1996). Similarly the process of project preparation and appraisal was lengthy and drawn out. The average time taken to develop a project for the Board in 1995 accounted for some 57% of the project process, whilst in 1998 it accounted for 68%, demonstrating that this aspect of SIMAP’s operations showed no improvement over the life of the programme. The Table also demonstrates that it was not unusual for it to take up to 56.9 months on average (1997) to respond to the demands of a community. Sponsors naturally could get frustrated during this time and even disband as a group, before any action was taken by SIMAP.

4.20	Problems were experienced with the technical capacity of supervisors and some contractors. This led to some difficulties with interpreting specifications and forecasting financing, and contributed to some of the cost-over runs experienced.

4.21	Cost over-runs could also be attributed to the fact that during the early part of the programme SIMAP did not have enough skilled and experienced engineers, and thus problems were not always adequately identified. To overcome this, SIMAP actively sought to employ more engineers. It also tried through its regional offices in Berbice and Essequibo to ensure that SIMAP officers visited sites more frequently to oversee the work of supervisors and contractors.

4.22	Following the mid term evaluation, SIMAP incorporated an element of self-help into all its projects, rather than just Amerindian ones. This tended to increase sponsor participation in project design and execution, and so limit some variations. However, the 1998 ex-post evaluation noted that there was still a need to facilitate and encourage greater participation by communities in the project cycle to aid project execution.

4.23	Whilst fewer projects were completed than envisaged, they were generally technically sound and effective in meeting the sponsors’ requirements. The investment component of the programme was executed in a timely manner, though problems with procurement in the nutrition and technical/vocational areas affected their execution.

  - Since the final disbursement under the project has been given there are no components that can be regarded as incomplete.

##### Borrower/Executor performance

4.25	SIMAP performed well throughout the execution phase of the project. It maintained good relations with all the line Ministries under which projects were executed and communicated reasonably well with the sponsor groups. 	Financial and procurement arrangements were generally carried out effectively through the tender process described in section 4.20 above.

4.27	SIMAP used the technical assistance available under the Loan to develop an efficient Management Information System, which served as a useful management tool.

4.28	As noted in section 4.20, SIMAP’s decision-making capacity was not as effective as it could have been. The management of the project cycle led to serious difficulties in responding speedily to the demands of beneficiary communities. In particular the time taken to prepare projects for submission to the Board delayed execution of the programme. However, it should be noted that SIMAP did take action to solve problems as they arose and was willing and able to introduce changes recommended in the mid-term review and accepted by the Bank.

4.29	SIMAP used staff and consultants well during this project, adopting consultants’ recommendations that were appropriate and effective. SIMAP did experience staffing problems, but was still able generally to develop and maintain a professional core of staff.

4.30	SIMAP maintained excellent relationships with the Government departments under whose mandates the sponsored projects fell. It was required to sign an institutional agreement with the relevant line Ministry/Local Authority for the post-project Operation and Maintenance of the upgraded/rehabilitated facility. This process was followed and should have ensured the sustainability of the projects. SIMAP also maintained excellent communications with sponsors and with the Bank, which meant that any problems could be discussed quickly and solutions found.

4.31	The institutional capacity of SIMAP was not significantly improved over the programme. As was noted in Section 4 above SIMAP found it hard to attract and retain sufficient staff, and it’s management of the project cycle was poor through out the project.

4.32	SIMAP did try to follow up on critical assumptions and take steps to make adjustments. It tried to ensure that co-ordination with Ministries and agencies was effective, and that facilities restored would be effectively operated and maintained. However, some of the assumptions were outside their capacity to influence e.g.: the implementation of the National Nutrition Plan, and the assumption that the socio-economic conditions in Guyana did not decline further.

Project performance monitoring by the Borrower/Executor.

4.33	The Loan proposal clearly laid out the requirement for SIMAP to produce Annual Reports. The items to be covered in the Annual Reports were detailed within the annexes to the Loan. These reports were to be discussed with the Country Office, following which a memorandum setting out principal conclusions and agreements was to be developed. In addition some 10 – 20 ex-post evaluations of projects were to be undertaken each year. Finally, a mid term evaluation was to be conducted.

4.34	These arrangements were followed, in that SIMAP did present Annual Reports  to the Bank, ex-post evaluations of projects were carried out for each year, and a mid term review was undertaken. However, it should be noted that the Bank commented a number of times on the paucity of the data presented in the Annual Reports, particularly with regard to income levels and number of project beneficiaries.

4.35	The indicators and benchmarks to measure the achievements of the programme’s objectives were adequate and useful. However, the lack of compliance by SIMAP on the issues mentioned in IV.D.2 meant that it was not as easy to evaluate SIMAP’s performance annually as it should have been. However, the presentation of ex-post evaluation reports and the mid-term review did assist in the measurement of objectives.

Bank Supervision

4.36	The Bank performed well throughout the execution phase of the project. It maintained  a close working relationship with the executing agency and Government as a whole. This meant that problems could be discussed and solutions found, before they affected the programme in any significant manner. The Bank was an able and efficient administrator,  always willing to listen to the executing agency and provide assistance.

4.37	The Bank’s relationship with the executing agency had a positive impact on the outcome of the project, since SIMAP felt able to ask for help and discuss problems.

5.	MAIN LESSONS AND RECOMMENDATIONS FOR FUTURE PROJECTS

5.1.	The main lessons learned from the project are:

- SIMAP’s system of waiting for a sponsor was not the most effective method of meeting the project’s objectives. Rather there is a distinct need to educate actively target communities to ensure good prioritisation of projects and equal access to funds.

- There is a need for a transparent method of prioritising projects within SIMAP, thereby better targeting assistance to the most vulnerable communities.

- There is a need to incorporate a contribution from beneficiaries into projects. Beneficiaries are better able to define their priorities since they experience the problems first hand, and their participation in the design and execution phases can help to limit cost over-runs. The self help approach to social infrastructure projects helps to encourage a sense of ownership by the community, so enhancing durability and the quality of the finished product.

- The system of sponsorship helps to empower communities who benefit from seeing the projects they consider priorities executed in a relatively short period

- There is a need for SIMAP to provide technical and administrative support to sponsoring agencies to assist in their development. The stronger the sponsoring agency the more able it is to identify problems with supervision and work with SIMAP and the contractor to ensure that quality projects are executed on time.

- There is a need to reform SIMAP’s organisational structure to develop systems that would allow for better management of the project cycle, and thus a speedier response to the execution of priority projects.

5.2	Based on the lessons learned from this project perhaps the Bank and Borrower need to define programme objectives more clearly, and provide more of a mandate to the executing agency to help with targeting.

Part Three – Basic Data

Table A1

# BASIC PROJECT DATA

Project Dates (month/year) Original Actual Date of inclusion in pipeline Date of Profile II or Loan Request 04/93 Date of Analysis Mission 07/93 Date of Loan Committee Approval 09/93 Date of Board Approval 10/93 Date of Contract Effectiveness 14/2/94 Date of Compliance with Prior Conditions 12/8/94 22/8/94 Calendar of Investments: - Starting Date - End Date Disbursement Calendar - First Disbursement 08/94 25/11/94 - Last Disbursement 14/02/98 03/09/99 Date of Physical Initiation of Works Date of Loan Commitment Date(s) of Cancellation(s)

OPERATIONAL REQUIREMENTS

REPORTS

Original Actual ### Mid-Term Review and Evaluation Date of mid-term review (if required) 02/95 07/96 Due date of borrower ex-post evaluation (if required) Due date of Bank ex-post evaluation (if required) Summary Cost Data Total Amount of IDB Financing $ 13.5mn $13.5mn IDB Financing as % of Total Cost 90% 89% Total Cost of Project $ 15mn $ 15.2 mn Cumulative Investment as of ___/___ (month/year) Remainder Required for Completion

Table B1

PROJECT COST AND FINANCING (all amounts in US$ mn)

| Original | Actual |
| --- | --- |

| ###### Investment Category | IDB | Borrower | Total | IDB | Borrower | TOTAL |
| --- | --- | --- | --- | --- | --- | --- |
| 1.Project financing | 11,500 |  | 11,500 | 12,226 | 385.2 | 12,611.36 |
| - Institutional Development - General Support - Technical assistance | 1,410 1,220 190 | 1,390 1,390 | 2,800 2,610 190 | 938.93 801.3 137.6 | 1,018.88 1,018.88 | 1,957.81 1820.18 137.63 |
| 3. Contingencies | 255 |  | 255 | 0 |  | 0 |
| - Financial charges - Interest - Credit Commission 4.3 FIV | 335 200 135 | 110 110 | 445 200 110 135 | 335 200 135 | 297 167.83 129.17 | 632 367.83 129.17 135 |
| TOTAL | 13,500 | 1,500 | 15,000 | 13,500 | 1,701.17 | 15,201.17 |

Table B2

## OPERATIONAL REQUIREMENTS AND REPORTS

Schedule of Investments

Original Actual Years IDB Borrower Other IDB Borrower Other Year 1 1,140 130 144.4 22.4 Year 2 1,790 200 2,923.86 92.82 Year 3 5,870 650 4,105.9 882.19 Year 4 4,700 520 3,861.7 201.1 Year 5 2,210.5 292.4 Year 6 253.5 210.25 Year 7 TOTAL 13,500 1,500 13,500 1,702

##### Table B3

- LOAN/TC DATA

Original Loan/TC Amount $ 13.5 mn Amount Disbursed $ 13.5 mn Amount cancelled First disbursement - Original date (m/y) 08/94 -- Actual date (m/y) 11/94 Last Disbursement - Original Date (m/y) 02/98 - Actual Date (m/y) 09/99

Annex One – Logical Framework

| PPMR | OBJECTIVES | INDICATORS | MEANS OF VERIFICATION | ASSUMPTIONS |
| --- | --- | --- | --- | --- |
|  | GOAL To improve the living standards of the poorest strata of the population Empower low-income communities to identify, articulate and address their priority needs | - Indicators of poverty in communities receiving SIMAP assistance are significantly reduced. - Number of applications presented to SIMAP and other organisations Increased annually by 20% average. - 10% average annual increase in number of communities with active community-based organisations. Community participation in SIMAP projects. | - Comparison of HIES survey for different years. - SIMAP’s records and survey of local SIF’s. 3. SIMAP annual report evaluation. | Projects financed by SIMAP will increase capability of communities to improve their situation. |
| OBJECTIVES | PURPOSE The development and financing of sustainable small-scale projects that respond to the priority needs of low income communities | - 250 projects have been sponsored by local organisations and financed by SIMAP agency. - 75% of the beneficiaries are from low-income households. - 75% of the projects are executed on schedule and within budget. - 75% of the completed projects are operating effectively and adequately maintained. | - SIMAP’s MIS Community Profiles (SIMAP project files) and annual evaluations of completed projects. - Completion Certificates and Disbursement records. - Annual evaluation of completed Projects. | The experience with SIMAP projects will enable communities to organise for other purposes. Facilities and amenities restored through projects are effectively operated and properly maintained by sponsors/communities/public agencies post project. The socio-economic conditions in Guyana do not decline further over the project period. |
| COMPONENTS | OUTPUTS - Social and productive infrastructure projects are financed and executed in an efficient manner. - Nutritional projects are financed and assistance is provided towards the development of a national nutrition plan. - Amerindian pilot projects are executed and evaluated. - Subject to favourable evaluation of Tec-Voc training pilot project, further tec-voc projects are implemented. - Institutional Strengthening of SIMAP Agency’s management. | - 150 social and productive infrastructure projects are completed. - 40 nutritional projects completed and assistance given in the drafting and implementation of the National Nutrition Plan of Action - 20 pilot projects completed in Amerindian communities and a further 40 projects completed upon favourable evaluation of the pilot phase. - Further tec-voc projects completed in each of the ten regions. - Institutional strengthening Consultancies successfully implemented. | - Site inspections, SIMAP’s MIS and Completion Reports. - Site inspections, SIMAP’s MIS And MOH records - Site inspections, SIMAP’s MIS and Completion reports. - Consultant’s evaluation report, Project visits and Board of Industrial Training records. SIMAP’s records and consultants’ final reports | - GOG co-operates in the preparation and implementation of the National Nutrition Plan. - SIMAP and community coordination with related Ministries and Agencies is effective. |
|  | ACTIVITIES - Promote, select, prepare, appraise, execute and evaluate Amerindian, Nutrition, Tec-Voc training and social and productive infrastructure projects identified by sponsors for low-income communities - Hire consultants and facilitate their diagnosis, training of staff and implementations agreed upon. - Administer SIMAP Project cycle management | US$ 11,500,000 US$ 190,000 US$2,610,000 | SIMAP agency accounting records and the audited financial statements of the program and SIMAP agency | - The local construction industry is not overloaded. - Competent, motivated professional are attracted and appointed to staff SIMAP agency. - Low-income communities and public agencies are willing to co- Operate and participate in projects. - SIMAP staff and management are receptive to training and Procedures. - Favourable evaluation of Amerindian and Tec-Voc pilot Programmes. |

Annex 2

Table One - Types of Sponsors

| Sponsor type | Regular | Amerindian | Health | Tech.Voc | Totals |
| --- | --- | --- | --- | --- | --- |
| Local Authority/Village Council Municipality Non-Governmental Organisation (NGO) Regional Democratic Council (RDC) Other Government Agency Other | 2 2 74 11 1 2 | 13 25 | 1 8 1 | 1 7 2 | 17 2 114 11 6 2 |
| Totals | 92 | 38 | 10 | 10 | 150 |

Table 2 - Size range of projects financed

| Project type | Least Expensive | Most Expensive |
| --- | --- | --- |
| Social | US$ 5,597 | US$ 250,058 |
| Productive | US$ 10,026 | US$ 223,128 |
| Amerindian | US$ 676 | US$ 12,008 |

Table 3 - Average income of project communities (all figures in Guyana $)

| Project Type | Average income of Project Community |
| --- | --- |
| Schools | 14,700 |
| Roads | 12,000 |
| Drainage and Irrigation | 9,700 |
| Community Development – including Health Centres, Multi-purpose Halls | 10,200 |
| Amerindian | 5,200 |
| 1996 Poverty Line | 26,700 |
| IDB low-income threshold | 35,000 |

Source: SIMAP

Table  Four a) -  Regional Breakdown by Project Type and Number

| Region | Social | Productive | Amerindian | Health | Technical/Vocational | Total |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 6 |  | 12 | 1 |  | 19 |
| 2 | 6 | 1 | 2 | 2 | 2 | 13 |
| 3 | 10 | 4 | 1 | 1 |  | 16 |
| 4 | 23 | 6 | 3 | 4 | 7 | 43 |
| 5 | 9 | 3 |  | 1 |  | 13 |
| 6 | 15 | 7 | 2 | 1 | 1 | 26 |
| 7 | 4 |  |  |  |  | 4 |
| 8 | 2 |  | 2 |  |  | 4 |
| 9 | 1 |  | 5 |  |  | 6 |
| 10 | 6 |  |  |  |  | 6 |
| Total | 82 | 21 | 27 | 10 | 10 | 150 |

Table 4 b) -  Regional Breakdown by Amount US$

| Region | Social | Productive | Amerindian | Health | Technical/Vocational | Total |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 102,984 |  | 95,489 | 71,992 |  | 270,465 |
| 2 | 446,910 | 216,519 | 16,999 | 51,040 | 166,817 | 898,285 |
| 3 | 939,316 | 658,318 | 6,199 | 39,373 |  | 1,643,205 |
| 4 | 2,339,080 | 442,816 | 12,454 | 176,933 | 866,361 | 3,837,644 |
| 5 | 862,218 | 431,470 |  | 22,715 |  | 1,316,403 |
| 6 | 1,888,116 | 671,667 | 6,588 | 24,623 |  | 2,683,296 |
| 7 | 99,378 |  |  |  | 92,302 | 99,377 |
| 8 | 36,552 |  | 14,944 |  |  | 51,496 |
| 9 | 18,623 |  | 21,273 |  |  | 39,896 |
| 10 | 1,114,286 |  |  |  |  | 1,114,286 |
| Total | 7,847,428 | 2,420,790 | 173,946 | 386,676 | 1,125,480 | 11,954,321 |

Table 4c) -  Number and Amount of Infrastructure projects as a percentage of population

| Region Number | Population | % | Number of Projects | % of Number | Amount spent US$ | % of amount spent |
| --- | --- | --- | --- | --- | --- | --- |
| 1 2 3 4 5 6 7 8 9 10 | 18,516 41,966 102,760 310,758 55,556 148,967 17,941 5,672 15,338 38,598 | 2.4 5.6 13.6 41.1 7.3 19.7 2.4 0.8 2.0 5.1 | 6 7 14 29 12 22 4 2 1 6 | 6 7 13.6 28 12 21 4 2 1 6 | 102,984 663,429 1,597,634 2,781,896 1,293,688 2,559,783 99,378 36,552 18,623 1,114,286 | 1 6 15.5 27 12.6 25 1 0.5 0.2 11 |
| Total | 756,072 | 100.0 | 103 |  | 10,268,218 |  |

Table 5 - Time taken between the various stages of the project cycle, and the total time taken for the project cycle in days and  cumulative percentage.

| Project Cycle Activities | 1995 | % | 1996 | % | 1997 | % | 1998 | % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Registration/Acknowledgement | 56.6 | 5.5 | 165.2 | 10.9 | 52.4 | 3 | 133.6 | 8.5 |
| Preparation of Profile |  |  | 324.8 | 32.5 | 611 | 39 | 872.1 | 64 |
| Appraisal | 435.9 | 47.9 | 234 | 48 | 126.8 | 46.3 | 39.6 | 66.8 |
| Prioritise for Board | 98 | 57 | 149 | 58 | 202 | 58 | 26.5 | 68.5 |
| Board Approval | 5.1 | 57.9 | 1.7 | 58 | 1.3 | 58.2 | 0 | 68.5 |
| Bank Approval | 84.1 | 66 | 70.2 | 62.8 | 179.5 | 68.8 | 71.1 | 73 |
| Contract signature | 64.9 | 72.3 | 192.2 | 75.6 | 287 | 85.5 | 78 | 78 |
| Start of work | 30.5 | 75.3 | 37 | 78 | 35.8 | 87.7 | 24.8 | 79.6 |
| End of work | 254 | 100 | 330.5 | 100 | 211 | 100 | 319 | 100 |
| Project Cycle | 1029 |  | 1504.7 |  | 1707 |  | 1564.9 |  |

Part Two

PROJECT NAME: SIMAP Agency IDB PROJECT NUMBER: 912/SF-GY IDB LOAN AND TC NUMBER(S)" – Loan 912/SF-GY BORROWER AGENCY(IES): SIMAP AGENCY

1.	PROJECT OBJECTIVES

A.	Although it may be difficult to fully assess all of the results of the project at this stage, please indicate which objectives* you feel have been achieved under the project, and to what extent.

The objective: Financing small scale, locally sponsored projects that serve priority needs of Guyana's low income population (Annexe A) has been achieved to a large extent. This has been possible as a result of SIMAP's mandate and modus operandi. The achievement of the objective has been facilitated as a result of SIMAP's interaction with community groups, the training programmes for Community Development Officers (CDOs), and the poverty classification of the country through the poverty maps.

B.	In your judgement, are there any project objectives* that are unlikely ever to be achieved? If so, why?

No.

*	Please refer to both physical and non-physical objectives.

II	PROJECT DESIGN AND EXECUTION

A. 		What aspects of the project's overall design most contributed to the project's successes and/or failures? Why?

The need for SIMAP to undertake projects which have been deemed priority in the applicants estimation, has been responsible to a large extent to SIMAP's success. The source of involvement and ownership especially during the stages of preparation and execution has contributed to such success.

B.	What aspects of the project's execution most contributed to the project's successes and/or failures? Why?

The method of pre-qualification of Contractors/Supervisors; The tendering process, SIMAP's management of the various stages of the project (including execution), the imposition of penalties as per contract for defective and delayed works, as well as the sponsors' involvement and regular meetings, consultations with all stakeholders all contributed to the success of the project. The semi autonomous status of SIMAP, with a Board that was pre-active and prepared to deal with "emergencies" as they arose, also helped to contribute to the achievements. Also decentralization of the Agency's operations to Essequibo and Berbice. Close coordination of all the stages of the project cycle with the Agency's Management, Staff, Non-Governmental Organisations, Sponsors, Ministries and Communities.

- Did significant problems arise during project execution? If so, what were

- these problems and what measures were taken in an attempt to solve

- them? Were these measures successful?

Delays in achieving execution schedules (completion dates) due to attempted

solutions.

a)	adverse weather conditions - extension of contractual periods.

b)	severe shortages of building materials- extension of contractual periods.

- inadequate supervision and - penalties and close monitoring

- inexperienced and incompetent (to some extent) dishonest contractor

penalties and close monitoring.

A large number of applications on SIMAP's database which had to be addressed on a yearly approach.

- Has the institutional capacity of the institutions and agencies involved in

- the project been strengthened as a result of the project? If so, how?

Yes; e.g. GUYWA  (Guyana Water Authority), Schools, Tech Voc Institutions;

by improved and enhanced facilities, improved environment, modernized

equipment, etc.

E.	Did any unforeseen events, beyond the control of those directly involved in project execution, adversely affect the project and the likelihood that it will achieve its development objectives? If so, please explain.

EL NINO; Shortages of materials, number of contractors and supervisors (especially for the remote hinterland areas). The Agency did achieve development objectives, but in a delayed way.

III.	BANK PERFORMANCE

- How well did the Bank perform during the preparation and execution phase of the project? (Was the Bank an able and efficient administrator? Did the Bank provide good and timely advise? Did the Bank maintain an effective dialog with the executing agency and between the institutions or agencies that were involved with the project?)

Very well.

1) Yes.

2) Yes

3) Yes

- What significant impact, if any, did the Bank's performance have on the outcome

of this project?

Review of Project profiles and submission of "No Objections" in a timely manner resulted in the Agency achieving the planned activities and the objective of the programme. Regular Project Performance Review initiated by the Bank to discuss progress and impediments also contributed to the Agency's performance. Site visits to projects by personnel from the Bank and SIMAP assisted in understanding the difficulties and problems associated with social projects and resulted in mutually agreed solutions.

IV.                    LESSONS LEARNED

- Are there any lessons from the Bank's performance in this project that could be

used to improve future project? If so, what are they?

Continuing constant dialogue and regular review of project problems and

Achievements  could be a mechanism to improve future project. Also, visiting of

projects while in preparation and execution.

- Are there any additional comments or recommendations regarding the project

and/or the Bank that need to be mentioned and/or that should be taken into account

in future projects?

Full discussions with administrators and beneficiaries of the projects to

ensure clear  understanding of the project are essential to the success of

any future projects.

SIMAP was formally created in 1990 as a semi-autonomous public corporation. The Bank approved a technical co-operation facility, ATN/TF – 3663-GY to finance SIMAP’s start-up phase in December 1990.

Technical assistance for the drafting of this plan was included under this Loan.

Agricultural Rehabilitation Special Account established under LO 839/SF-GY.

This sample was based on a random, but representative choice of projects completed each year for which all the necessary information was available.

This table is based mainly on the income of the beneficiary community, since it would have been difficult to determine the average income of the beneficiary household in some of the project types e.g.: schools, multi purpose halls. The direct beneficiaries in these cases only form part of the project community.