# TRADE AND POVERTY (T&P) TRUST FUND # TC PROJECT COMPLETION NOTE

# Basic Information

# Project number, title, country/region: TC N°: RS-T1331: Promoting Trade Knowledge among Parliamentarians of the Americas # Relation to Bank strategies and operation(s): This project contributes to mainstreaming trade into the beneficiary countries’ development agendas, as stated in relevant Country Strategies. - Project team members: Paolo Giordano (INT/ITD), team Leader; Carlos Cordovez (SDS/SGC); Ignacio Corlazzoli (RE2/SC2); Jaime Miranda (INT/RTC); Diego Buchara (LEG) - T&P Fund contribution, (in USD), and % of total project financing: US$ 20.000, 29% of total project financing. # TC project approval date: 2/16/2007 - Execution period: 6 months

## Restatement of Objectives and Key Activities

Objectives: Promote knowledge of the economic, social and legal prerequisites of an inclusive pro-poor trade agenda. Specific objectives include contributing to: (i) strengthening the capacity of Latin American and Caribbean parliamentarians to understand the nature of a rules-based international trading system; (ii) improve their capacity to work with constituents, business and civil society in the formulation of international trade policy agendas and in the implementation of domestic complementary reforms that contribute to poverty reduction; and (iii) to foster the sharing of experiences and lessons learned and encourage dialogue and cooperation among parliamentarians of the hemisphere on issues relating to trade policy. Key Activities: The main activity entailed holding a two-and-a-half day training workshop bringing together 20 to 25 participants from legislatures of North, Central, South America and the Caribbean.

## Outputs and Outcomes

Outputs: -1 trade capacity-building workshop was coordinated, with 16 participants from South, Central, North American and Caribbean legislatures. - 6 course modules were prepared and delivered to participants on the issues of: trade rules and politics (modules 1 and 2), the role of Parliament in trade and development (module 3), public consultations (module 4), trade, poverty and development (module 5) and gender and trade (module 6). - A briefing book was distributed to each participant, containing training materials and presentations prepared by the Centre for Trade Policy and Law, the Parliamentary Centre, the Inter-American Development Bank and the North-South Institute - A workshop evaluation was conducted and feedback forms were filled out by participants, eliciting very positive comments. - A report of proceedings was prepared and distributed to participants, parliaments and other FIPA stakeholders. - Two press releases were issued by the FIPA Secretariat, and a section has been developed on the FIPA website including materials, presentations, press releases, a report and a photo gallery of the event - Photographs of the event were published in the Ottawa Embassy newspaper, featuring workshop participants; an article will also be published in the next issue of the FIPA newsletter ParlAmericas Outcomes: - Legislators have a better understanding of the rules-based international trading system and of their role in promoting a more efficient and equitable economic global governance - Participants are better equipped to contribute, through their parliamentary functions, to the effective oversight of trade policies implemented by governments - Participants contributed to an informed dialogue on trade and pro-poor trade policies at the country level / have a better understanding in working with constituents, business and civil society of the formulation of international trade policy agendas and the implementation of domestic complementary reforms that contribute to poverty reduction - Legislators of the hemisphere contributed to a regional dialogue on pro-poor trade and integration, by sharing their views and recommendations in the context of hemispheric institutions and coordination mechanisms - The activity lead to enhanced collaborative efforts with a view at developing a permanent capacity-building process for the parliamentarians of the region - Participants will bring back the experience to their respective Parliaments to expand the effect of the activity

## Contribution to Bank Strategies and Operations

- The outputs of the TC contribute to mainstreaming trade into the beneficiary countries’ development agendas, as stated in relevant Country Strategies.

## Lessons Learned ### (substantive/operational as well as managerial: i.e trust fund, procurement, execution, etc.)

- Overall, the balance of content provided in the pilot project was appropriate. Parliamentarians, however, suggested several possible future subject areas that could be included in a future workshop, including interests of small economies, policy reform case strategies, and methods of channeling positive elements of globalization for local benefit. -There were some challenges because of the disparate levels of participants’ background knowledge. - Future workshops should give parliamentarians a greater role in both directing sessions and sharing lessons learned from their own country’s experiences.

## Recommendations to the Trust Fund and to the Bank

- Finance similar capacity building events to strengthen the role of legislatures in the design of a pro-poor hemispheric trade agenda, at both the national and regional levels.