GUYANA

Remedial Maintenance Project for Georgetown
Sewerage and Water Supply Systems
(GY-0006) (LO-909/SF-GY)

Project Completion Report (PCR)

Minutes of the Management Review Meeting (CRG)

August 28, 2003

- Participants

  - Alvaro Llosa (EN3/CHF), CRG Chairman; Adrienne Pratt (RE3/OD6); Diego Buchara (LEG/OPR); Jacques Roumani (ROS/PMP); Alejandro Taddia (RE3/FI3); Gabriel Castillo (FE3/OD6); Marco Nicola (COF/GY); Stuart Hughes (COF/GY) and L. Víctor Traverso (RE3/EN3), CRG Secretary.

  - Written comments were received from: (i) David Rogers (RE3/OD5); (ii) Adrienne Pratt (RE3/OD6); (iii) Alejandro Taddia (RE3/FI3); and (iv) Jacques Roumani and Luis René Cáceres (ROS/PMP).

- Recommendations

  - The CRG found the PCR to be overall an accurate and fair representation of the achievements and issues that occurred during project implementation. However, to strengthen the report, the CRG recommends the following issues be addressed:

    - Objectives. The CRG recommended that the achievement of objective should be clarify in terms of fully or partially achieved and relate them to the emergency nature of the project.

    - Frame of reference. Introduce an explanation of the circumstances under which the project was appraised and the loan approved, indicating the emergency nature of the operation. The CRG team indicated that this was included in section B of the report on page 2 and in section IV A 1 on page 8.

    - Rating. Provide an explanation of why the project despite its emergency nature and 10 years of execution is rated as satisfactory.

    - Execution of the Project. Clarify the execution of the infrastructure and institutional component and how they support each other.

    - First Phase Operation. Explain how this project was actually a first phase operation and a second one was planned to complement the activities initiated with the project.

    - Baseline. Even though the PCR indicates the absence of a logical framework and a baseline, it should specifically indicate that no physical targets were identify originally in the project document.

    - Policy Changes. To look for a more specific explanation of why the policy changes did not take place as expected and what lessons can be learned.

    - Lessons Learn. Review sections IV and V to clarify the lessons learned.

    - Technical Issues. Explain why the billing system took eight months to be operational and why the meters were not compatible with the system.

- Conclusions

  - The CRG recommends approving the PCR once the modifications discussed above are incorporated into the document.

| Alvaro Llosa, EN3/CHF CRG Chairman |  | L. Víctor Traverso, RE3/EN3 CRG Secretary |
| --- | --- | --- |

PROJECT COMPLETION REPORT (PCR)

# PART ONE

Project Name:	Remedial Maintenance Project for Georgetown Sewerage and Water Supply Systems

Project Name:	GY-0006

Loan Number:	909/SF – GY

Country:	Guyana

Executing Agency:	Georgetown Sewerage and Water Commissioners (GS&WC)

Sector:	OS-AGU

Modality:	Investment

Date Approved:	September 29, 1993.

Date Completed:	May 31, 2002.

Loan Amounts:	US$13,500,000

Final Project Implementation Classification: Satisfactory

Final Project Assumptions Classification: High

Final Development Objectives Classification: Probable

#### PROJECT OBJECTIVES AND COMPONENTS

  - Project Objectives

The overall Project objective was to restore a safe and reliable water supply to the resident of Georgetown and to avert serious risks posed to public health.

The specific objectives of the Project were:

- To effect a rapid and observable improvement in water availability and quality.

- To promote the establishment of an efficient and autonomous water and sewerage company for Georgetown.

- To establish the financial viability of GS&WC by implementing a new tariff system based on measured consumption and the cost of the service provided.

- To train key personnel in GS&WC to adequately perform all the managerial, operational, maintenance, commercial, financial, and accounting functions.

- To establish and regularly update a Costumer Registry as a basis for better billing and collection.

- To encourage water conservation.

##### Project Components

During the design phase specific problems were identified which indicated a trend towards the complete breakdown of the system including equipment failures, lack of maintenance, chemical shortages and inadequate disinfections of the water supplied. Most major components of the water distribution system such as wells, pumps, pipes, values and treatment systems needed rehabilitation, replacement or repair. Wells were continually failing because of corrosion, equipment breakdown and the lack of operable stand-by capability in a time of frequent power outages. This resulted in variable flows and insufficient pressures throughout the system. Leakage and wastage of water was reported to be 70%. A socioeconomic survey showed that only 36% of households received water in their dwellings.

Threats to public health resulted from contaminated surface water due to raw sewage from blocked or broken sewers entering nearby ditches and the effluent from septic tanks and pit latrines which discharged to storm channels, entering water mains at times of low or negative pressures.

The Georgetown Sewerage and Water Commissioners, the semi-autonomous entity responsible for providing water and sewerage services to Georgetown lacked the financial, human and material resources to carry out adequate maintenance and replace obsolete or damaged parts and equipment. Water tariffs did not cover costs. The organizational structure of GS&WC was perceived to be cumbersome and it was dependent on the government for financial resources and management.

Against the backdrop of those serious challenges and potential threats the project was designed and appraised. The Loan subsequently provided the needed resources for the Government to begin to address the problems plaguing the water sector in the capital city.

Based on the above assessment the project was designed with four basic components:

  - Remedial Maintenance. (US$ 8.7 Million). This first component had three major lines of action: The rehabilitation of the water distribution system; the improvement of the water treatment and disinfections systems at the Shelter Belt Treatment Plant; and the performance of critical maintenance activities on the sewerage and sewer pumping system.

  - Water meter installation and storage tanks. (US$ 1.7 Million). This component had four lines of action: The installation of meters for residential customers in rehabilitated areas; complete installation of meters for commercial and industrial customers and for municipal and government structures; installation of bulk meters as required; and the installation of elevated storage tanks in critical areas.

  - Reform of the legal framework. (US$ included in component 4). This component was directed toward the development of the necessary regulatory and legal changes to be able to establish the operational autonomy of GS&WC and to develop the legal basis of a tariff system that could assure financial viability.

  - Institutional and financial strengthening of GS&WC. (US$ 4.1 Million including component 3). In this component there were 10 different lines of action to:

      - Develop the managerial and operational skills within GS&WC;

      - Identify professional personnel to serve as counterparts and/or hire the personnel needed if non-existent in GS&WC;

      - Install a management information system (MIS) able to provide dependable information for fiscal and management purposes;

      - Develop a salary incentive system that promotes efficiency and retain and attract talented personnel;

      - Strengthen the maintenance capacity of the institution;

      - Maintain a dependable customer registry linked to the billing and collection systems;

      - Develop a good billing system and a scheme to facilitate payments by customers;

      - Develop an education and public awareness program to inform consumers of the project and demonstrate the incentives for paying in time and conserve de water;

      - Make a marginal cost study;

      - Select and hire, following acceptable procedures, an independent firm to audit GS&WC.

- The main assumptions of the project were:

  - The willingness of the Government of Guyana (GOG) to implement a tariff strategy that would have enabled GS&WC to recover the costs of services provided.

- The support from GOG to the institution in order to cover the shortfalls in revenue during the project execution.

- Ensuring competitive salaries in order for GS&WC to maintain and attract good personnel.

- The willingness of the GOG to approve the metering program and to move to consumption based charging.

- A stable industrial climate.

#### PROJECT RESULTS AND DEVELOPMENT OBJECTIVES

  - 1.	The actual level of achievement of projects components

Component 1- Remedial Maintenance.

      - 8 miles of new trunk mains installed.

      - 6 new wells drilled and commissioned.

      - 24 sewerage-pumping stations rehabilitated.

      - Critical maintenance at main treatment plant completed.

      - Chlorinating equipment installed at all 7 production sites.

## Component 2 - Water meter installation and storage tanks

    - 10,000 meters installed citywide.

    - Two 500,000-gallon tanks and associated pump station installed and

Commissioned.

## Component 3 - Reform of the legal framework

- The Georgetown Sewerage and Water Amendment Bill was enacted in 1994.This act allowed for the creation of a new Board of Management, which was installed and gave the tariff setting authority to GS&WC.

## Component 4 - Institutional and financial strengthening of GS&WC

      - The managerial and operational skills within GS&WC were improved by means of training technology and Know-how transfer from the consulting firm. A new organizational structure was implemented;

      - Professional personnel to serve as counterparts was selected or hired if non-existent in GS&WC. Key management positions were identified and filled.

      - A management information system (MIS) able to provide information for fiscal and management purposes was installed and made operational. Some delays occurred because of some technical problems, and the input data was not always of adequate quality, generating different problems including collection losses;

      - A salary structure and system was established that promoted efficiency, retaining and attracting talented personnel;

- The maintenance capacity of the institution was improved. A Preventative Programmed Maintenance System” was implemented and some remedial work was done by means of GS&WC capacity;

      - The maintenance of a dependable customer registry linked to the billing and collection systems;

      - Develop a good billing system and a scheme to facilitate payments by customers;

      - A public and customer relations programs was implemented, including an education and public awareness program to inform consumers of the project and demonstrate the incentives for paying in time and conserve de water;

2.	The current expected level of achievement of project objectives is as follows:

The general objective of a “remedial” project for the Guyana’s Georgetown sewage and potable water system was attained, saving the city from a probable collapse, assuring a basic service for the population, providing the groundwork and allowing a step forward for a better service and a more efficient utility.

The six specific objectives were achieved partially, to a reasonably satisfactory degree as follows:

- An observable improvement in water availability and quality was probably obtained with the remedial works done to the water and sewage system. Nevertheless there were neither baseline data nor a final technical evaluation at the end of the program to assess improvements ().  It is generally accepted that water by the end of the project was more readily available in dwellings and of a somewhat better quality than before.  However water supply and quality were not at established international standards.

- A more efficient and autonomous water and sewerage company for Georgetown was attained by the project. The establishment of GS&WC as an autonomous entity within a new and more operational legal framework, was successfully completed in 1994 with the installation of a new board with tariff setting powers, although the Minister of Housing and Water still was required to concur with any tariff increases.  GS&WC was transformed into an better-organized and managed agency.  Staff levels were reduced from 450 in 1995 to 237 in 2001. An attractive salary structure was implemented which was competitive with the private sector. This resulted in GS&WC attracting and maintaining key managers who were supported and trained by the Project Management Firm.

- Progress in the financial viability of GS&WC was obtained by implementing a new tariff system based on measured consumption and the cost of the service provided. Nevertheless the tariff and collection coverage improvements were not sufficient to achieve 100% sustainability. This aspect was out of the project control and further complicated by the merger of GS&WC with GUYWA, company that had only a 30% of financial sustainability. The financial viability of the institution was improved with the changes introduced in the tariff system, the new billing and collection systems, the financial and accounting systems and the installation of meters, introducing the trend towards charging for measured consumption. GS&WC failed to achieve the collection levels established in the contract. Audited financial statements for the year 2001 showed coverage for O, M &D at 67% up from 62% in 1996. Government fiscal transfers reduced from G$244.1M in 1996 to $30.1M in 2001. However, those changes failed to achieve the anticipated 100% coverage of operations, maintenance and depreciation (O, M & D) costs with tariff revenues by the end of the program.

- Key personnel in GS&WC were trained to adequately perform all the managerial, operational, maintenance, commercial, financial, and accounting functions, but part of the effort was lost by staff rotation or other factors This helped to transform GS&WC into a better-organized and managed agency.  Staff levels were reduced from 450 in 1995 to 237 in 2001. An attractive salary structure was implemented which was competitive with the private sector. This resulted in GS&WC attracting and maintaining key managers who were supported and trained by the Project Management Firm.

- A more reliable Costumer Registry was established and regularly updated to serve as a basis for better billing and collection. Improvements were made through a new management information system to be used by the institution, specifically in the Costumer Registry. Problems were found and the installation of the new system took more time and effort than expected. This was also true for the billing and collection system. Nevertheless both systems were by end of project operational and in use.

- Water conservation campaigns were organized. Results would normally manifest themselves either in reduced total production or reduced wastage however there is no hard evidence of the results of these campaigns.

  - Differences of component or objectives

The current assessment of the components and objectives is similar to the latest formal statement produced in agreement with the borrower.

  - Unexpected achievements

It should be mentioned that based on the positive tangible changes that the project achieved within the public company GS&WC, in 2002 the GOG decided to create a single Water Authority covering the entire country (GWI) and modernize the sector by inviting private sector participation (See D below).  This was due in fact to the positive experience and progress observed –but with limited in scope- achievements of the project.

It should be mentioned however that this also generated a certain level of uncertainty within GS&WC and may have contributed to delays in implementation progress towards the end of the project.

D.	Achievement and Sustainability of Project Objectives

As mentioned in Section II 2 all six of the project objectives were partially achieved. For some significant improvements were made. The GOG was slow to take some measures that were linked to the financial feasibility of the institution. Nevertheless it was still committed to furnish more and better quality water to the citizens of Georgetown and the entire country. This led it in October 1999 to embark on a program to modernize the entire water sector.

With support from the United Kingdom Department for International Development (DFID) three related diagnostic studies were conducted for the Ministry of Housing and Water. One of these studies looked at the potential benefits of a merger of GS&WC and the Guyana Water Authority (GUYWA), the other water utility providing service in the country.

The recommendation of the study was in favor of creating a single new water and sanitation utility to provide service to the entire country. This was done in June 2002 when GS&WC and GUYWA were merged to form Guyana Water Incorporated (GWI).

It should be noted that prior to the merger GS&WC had a coverage ratio (coverage of O, M & D costs from revenues) of approximately 67% whereas GUYWA was only approximately 30-33%.

Also recommended was the need for international private sector involvement in the management of the new utility. The GOG accepted these recommendations and a consulting firm was hired to identify an appropriate management contract option, prepare pre-qualification and bidding documents and assist with the selection of a private operator for the water utility.

As a result of this exercise a “Performance Based Management Contract” (PBMC) with clearly established performance indicators and benchmarks was signed in December 2002 between the GOG and a large UK based management contractor with extensive experience in the water sector.

The sector has therefore changed dramatically and the creation of the new national agency made impossible to maintain the project sustainability objective. However, once the GWI by means of the PBMC contract achieves the performances targets contained in its contract the objectives of the project are attainable and should be sustainable.

E. 	Reasons for non-achievement of project objectives

The general objective of the program is substantially met as stated in Section 2. Also the specific objectives were partially but reasonably satisfactorily attained. All objectives are fully attainable and should be met –and expanded- within the framework of a modernized water sector currently being implemented by the GOG in partnership with the entire donor community.

F.	Economic analysis of the Project

Due to the nature of the investment made, it is difficult to quantify in a reliable manner the benefits produced by the project. An attempt was made, at the design stage to obtain crude estimates of the project economic viability using SIMOP models simulations. At that point it was considered that with the repair of 80% of the connections without service and the reduction in water losses reduced by 28% the rate of internal return would have been at 18%. That internal rate of return would become lower than 12% if the number of rehabilitated connections were only 69% with a reduction of water losses at 15%.   Since the design phase, it was considered that these results were unlikely and no specific benchmarks were set.

  - CHANGES IN ORIGINAL OBJECTIVES, COMPONENTS AND ASSUMPTIONS

    - No changes occurred in the project’s objectives and assumptions, they remained the same during the implementation of the project. With regard to project components no physical targets were identified in the original project document with the PMF being required to establish an execution work plan for the project once it was hired. During the course of the preparation of that work plan the PMF made a determination that it was not feasible to (i) install elevated storage tanks due to the severely deteriorated state of the distribution network and the likelihood of increased leakages as a result of the increased pressures and (ii) rehabilitate the entire distribution system as was anticipated based on the estimates prepared by a Bank consultant in 1992. Instead components 1 & 2 were modified and ground storage tanks and a trunk main system were installed in order to achieve the objective of effecting a rapid and observable improvement in water availability and quality.

    - The operation was an investment loan hence this section is not applicable.

  - Historical ratings of the project:

| Month Year | Dec 1997 | Jun 1998 | Dec 1998 | Jun 1999 | Dec. 1999 | Jun 2000 | Dec. 2000 | Jun 2001 | Dec 2001 | Jun 2002 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IP | S | S | S | U | U | U | S | S | S | S |
| AS | H | H | H | H | H | H | H | H | H | H |
| DO | P | P | P | P | P | P | P | P | P | P |

The absence of a logical framework and baseline data made monitoring the project difficult. In this context rating implementation progress in the PPMR became highly subjective depending entirely on the assigned specialist’s assessment. In addition, the lack of formal training in the use of the logical framework and the PPMR system by both Bank and Executing Agency staff compounded this problem and could partly explain the apparent inconsistency in the final implementation progress rating for an emergency project being rated as satisfactory nine years after it was approved by the Board.

  - LESSONS LEARNED FROM THE PROJECT

### Project Design

- Project Objectives

The objectives were in general well designed. They were realistically formulated and in tune with the needs and possibilities of the country at the time.  Nevertheless the design dated 1993 and no Logical Framework or benchmarks were established in order to measure the achievement of the objectives.

The project was designed to urgently address immediate problems of the water and sewerage system of Georgetown in preparation for a larger operation (see 4). These problems that could have led to a serious collapse of the system could not be properly assessed in the design phase of the operation.  The objective of rehabilitate the basic infrastructure and modernize the institutional setting were well identified

Also, a great amount of investment was required to rehabilitate the water and sewerage system in Georgetown. Consequently, from the technical point of view it would have been relatively easy to identify different alternatives for the allocation of the available funds. However, given the scarcity of those funds, in order to better achieve objectives 2 and 3 the decision should not be made only based on technical criteria. A business-like approach would have been much more suitable in order to allocate funds in areas that would have helped to generate new funds hence the financial viability of the institution. The quick generation of funds could have created the opportunity of additional investments in less profitable areas.

- Project Components

The components of the project were appropriate and flowed logically from the objectives established for the project.

The project was a first phase operation, which was designed on an emergency basis to arrest the trend towards the collapse of the water and sanitation systems in Georgetown. It intended to achieve this by rehabilitating the water distribution and sewerage system of the city and by strengthening GS&WC. Estimates of cost and quantities for this were based on the work of an individual consultant hired by the Bank in 1992. However the inaccuracy of the estimates and the time elapsed between the study and the actual implementation of the project made the US$8.7 millions allocated for remedial work significantly inadequate for the complete improvement needs.

Recognizing these limitations and the constraining environment in which the loan was prepared the Bank financed in 1994 a detailed diagnostic study of the water and sanitation system in Georgetown through ATN/SF (JF)-3640-GY Georgetown Water and Sewerage Master Plan. The Master Plan formed the basis for the preparation of the follow-up operation LO-1047/SF-GY “Georgetown Water Supply and Sewerage Program II”, which was approved in 1999 and intends to consolidate the achievements of LO-909/SF-GY.  This operation is the second stage of a long-term comprehensive plan for the rehabilitation of the Georgetown water supply and sewerage systems.

- Project Assumptions

The basic assumptions were correctly selected and stated, but some of them did not hold true, during implementation of the project:

  - The willingness of the Government of Guyana (GOG) to implement a tariff strategy that would have enabled GS&WC to recover the costs of services provided was not effective early on and meant a reduction in the sustainability of the company. The willingness and maybe possibilities of the GOG of raising tariffs was done in a timely manner ().

  - The support from GOG to the institution in order to cover the shortfalls in revenue during the project execution was correct.  GoG provided 25% more than the planned counterpart funds and supported some recurrent costs increases required for professional staff salaries in GS&WC.

  - The Borrower ensured competitive salaries in order for GS&WC to maintain and attract good personnel.

  - The GOG approved the metering program and moved to consumption based charging. Nevertheless collection was a problem.

  - During the project execution a stable industrial climate was available.

One assumption was neglected, the impact of the major changes promoted in the sector by other donors –merging companies- created a new reality that was not foreseen.   See also comments under 4 below.

- Sequencing

The sequencing of the components was well thought out and done on a rational basis. Emergency repairs at the major water production facility coincided with the institutional strengthening of GS&WC. This should have produced immediate results, which could be used to justify initial tariff increases. The next stage involving improvements in the water distribution system which should have led to the increased availability and quality of water to customers would have justified further tariff increases. Once a certain measure of public confidence developed the metering program could then be implemented. So there were tangible benefits to justify tariff increases as much as was possible.

In situation like this, projects have to include a strong incentive to ensure that decisions made during execution maintain the equilibrium between physical and institutional components. This is even more important when the institutional components imply actions that may represent a political cost in the short-term, like an increase in water tariffs.

5.	Institutional Capacity of Executing Agency

The institutional capacity was not well estimated at the design stage and this error was a significant source of problems faced during the implementation process. As a consequence, changes took more time than expected and the implementation process was severely delayed. Also some difficult political decisions were to be taken at a moment that was not very conducive to early appropriate actions.

The hiring of the project management firm was done and the team in charge of the project did a professional job at acceptable levels. Nevertheless the institution was in some aspects too weak to be the desirable counterpart. Following the re-engineering of the organization the majority of the managers of the former GS&WC were re-hired to fill the positions in the restructured entity. The result of this was that once the project management firm departed GS&WC reverted to its previous management style and organizational culture. In addition, the main managers of GS&WC were appointed only in an acting capacity and the leadership that they were capable of exercising at that point was not sufficient to take the institution through a fully successful project implementation.

- The Aspect of the project design that most contributed to the successes was the inclusion of a project management firm (PMF) to assist the executing agency implement the project. The firm was accountable for implementing the program despite resistance and slowness of the official counterparts. This helped significantly to the project to completion and the satisfactory implementation of all components included in the program. However as stated in 5 above this was not enough to introduce a cultural change in the management of the utility company (See also Section V A).

- Project Execution

  - Most important factors in project execution (Successes and Failures)

The PMF that was hired was committed to the work and was technically capable. Its presence contributed to the achievements that were recorded during the execution of the project.

In addition the planned sequencing of activities and investments proposed by the PMF in their work plan can also be cited as contributing to project execution success.

The lack of implementation capacity of the interim leadership of the institution and the fact that GOG did not take all the necessary measures to implement the expected changes the financial aspects of GS&WC in a timely manner were the main reason for the protracted execution of this operation.

  - Significant problems arose and action taken.

During the implementation of the project important technical factors were faced.

(i) The accounting and the billing and collection systems installed in GS&WC did not work as expected producing technical problems and delays. GS&WC was without system for approximately 8 months due to the complete collapse of the software supporting the previous billing system and data migration problems with the new system; customers could not be billed during this period. This had a detrimental impact on the company finances, late in 2001 and in 2002. Action was taken and the installation of the new system was later completed yielding better results, but still at the end of the project some difficulties remained.

(ii) Technical problems occurred with the introduction of the meters that were not compatible with the systems already in use in the institution. Initially it was found that due to the high level of particulate in the water the filters in the meters became blocked on a regular basis. This required technicians to go out to repair meters in order to correct the problem, producing a delay in the execution of the project.

(iii) Most of the managerial staff in GS&WC were not appointed but were “acting” in their positions during project execution, without being confirmed by the authorities. This created a problem weakening the leadership for change and the leverage capacity with other units of the Governments, was not as effective as would have been desirable.  After raising the issue to the authorities, managers were appointed formally providing stable professional and high level staff

  - Quality, Quantity and Time ()

In terms of quality each component delivered under the project was satisfactory in comparison with industry standards and original expectations.

In terms of time the project was slow to implement, having a planned execution period of 4 years it was required four additional years to implement (the project had 49 months of cumulative extensions, see Execution)

The quantity of project outputs was satisfactory, reasonable unit costs were observed in most of the project activities. Nevertheless, (as stated in Section IV A.2) the infrastructure and financing needs were underestimated and the remedial maintenance financing was below the required level, however the component was substantially completed.

  - Actions to be taken completing all components

All components were substantially completed.

To mention that the institutional strengthening process initiated by GS&WC was over ridden by the creation of a merged national water agency, GWI, which has taken charge of the national water sector including previous GS&WC responsibilities. See also Section II A.

- Borrower/Executor Performance

  - How well the Borrower executed the project

The borrower accomplished what was expected and provided the necessary counterpart funding, but was slow in the project implementation schedule and unduly late to take some policy measures. This made less effective the project development effects and reduced some results in the financial/sustainability area.  GS&WC was reluctant to apply the required tariffs nor reached the desired levels of collection.  The GS&WC and the PEU complied with the financial contractual requirements, although it was consistently late in submitting the audited financial statements.

  - Utilization of Staff

As explained -during part of the execution period- staff in GS&WC was not complete and/or was not formally appointed. As a result, thou most consultants recommendations were appropriate and effective, their effectiveness was less than expected due to difficulties to transfer technology and knowledge. Consequently the company did not assimilate part of the know-how.   After the consulting firm departure, GS&WC was not able to continue performing at the same level. Also, as stated, GS&WS did not have a well-established and stable leadership and principal managers were not fully empowered in their acting capacity, making them less effective than desirable.

  - Relationship with other institutions

GS&WC maintained a fairly good level of relationships with other institutions. The diminished acting capacity of their leadership hampered their leverage vis-à-vis the central Government.

  - Improvement of Institutional Capacity

GS&WC has been merged with GUYWA becoming Guyana Water Inc. GWI with a mandate now covering the entire territory of Guyana. GWI has incorporated most of the senior managers within its new structure and management should be in a position to make good use of the skills acquired during the project execution.

  - Critical Assumptions

GS&WC was not in a position to facilitate critical assumptions to take place. On most occasions there were high-level GOG decisions that were beyond GS&WC institutional capabilities.  For example: despite the commitment of the borrower to move toward a tariff system based on consumption, the authorities believed that this would cause undesirable social reactions and the decision was continuously postponed.  The decision came very late with consequent negative impact on the executor financial performance.  GS&WC could not reach by the end of the program the anticipated benchmark of 100% coverage of costs for operations.

- Project Performance Monitoring by the Borrower/Executor

  - System used to monitor the project

During the design, it was clearly established that the project performance would be monitored through semiannual progress reports and annual evaluations.  The Borrower agreed to this and has substantially complied with the contractual obligation. In addition, there were the usual inclusions of financial and institutional inspection visits to be conducted by the Country Office. The project document did not state any specific benchmark for the infrastructure component. For this reason the monitoring was mainly focused on activities rather than the achievement of the objectives of the overall program.

- Bank Supervision

  - Throughout the execution phase the Bank remained proactive and maintained a close working relationship directly with the executing agency.

  - The absence of a formal project logical framework made difficult the elaboration and follow up, by means of the Project Programming and Monitoring Report PPMR. In addition the lack of training in the use of Log Frame and the PPMR system by both Bank as well as executing agency staff reduced the effectiveness of this management and supervision tool.

  - Bank staff met regularly with the executing agency and the project management firm. Inspections visits were carried over on a regular basis. The relationship between the Bank and the borrower was good at all times and assisted the implementation of all project components.

    - MAIN LESSONS AND RECOMMENDATIONS FOR FUTURE PROJECTS

A.	Main lessons relevant to other projects

Indicators and Benchmarks: During the design phase, there must be clear definition of the indicators and benchmarks as well as the methodologies, sources and resources to gather the information to adequately measure the achievement of the project outputs, outcomes and objectives.

Management support: Weak executing agencies require a strong external project management support. The assistance of a project management firm is of significant importance for project implementation. In this project was a key factor to restructure GS&WC and to introduce new management principles.

Know How Transfer. The lack of a well-structured training program with appropriate monitoring and evaluation mechanisms for the transfer of technology and knowledge from the consulting firm, resulted in an insufficiently developed knowledge base in GS&WC. This manifested itself once the project management firm departed with GS&WC reverting to its old organizational culture. Clear mechanisms for sustainable knowledge transfer should be included in the design phase of each project.

Feasibility of Policy Changes: The project called for important sector policy changes involving major political and social implications. These changes such as water tariff levels and moving from a fix to metered charge to customers have direct economic impact on the average household. The capacity of timely implement the required changes and absorbing the political cost, as well as the willingness for customers to pay the real costs of providing water should have been more carefully assessed during project preparation. In this sense the following are lessons learned:

    - Project Design should consider longer execution time, to let the expected delay and processing of the difficult policy decision-making issues;

    - Improve Project Design creating early incentives for the policy change. For instance using time-slice design or triggers to allow access to part of the resources for infrastructure, once the policy decisions are implemented.

    - Allowing Differential Tariffs for different income groups.  Change from universal low tariff to universal cost recovery tariffs is politically difficult. Differential tariff could be applied to middle / high-income groups, with less political resistance, facilitating the policy change and improving faster utility sustainability.

Incentives for Institutional Change. A clear trend in project execution is to move early on with infrastructure and equipment components, and delay the institutional modernization/change. This can reduce the development effectiveness of projects. A late start of institutional changes is a risk for the sustainability of the project. The implementation of important changes may lose technical support because of the departing of the consulting firm. They became low priority by external events or simply cancelled by inertia.  Projects considering institutional change should include a strong incentive or mid term assessment, ensuring decisions early on during execution, to maintain equilibrium between physical and institutional components.

Financial Sustainability: In cases where rapid progress for sustainability is required, a business-like approach in the resources investment is more suitable. Allocating funds to provide service in areas/sectors that are willingly to pay –with the corresponding tariff and collection effort- would generate more easily revenue, providing better financial viability to the institution. The generation of these revenues can provide sustainability for investments in less profitable areas/sectors.

VI.	ADDITIONAL COMMENTS

Documents and records information on this project was not always available as desired. Some documents were not found in COF/CGY or HQ’s records and “partial” PCR’s were not prepared by the Specialists that handled the operation in COF/CGY, when they stop supervising the operation, (as established in CO-309).

This fact is worsened by the long time –eighth years- it took to implement the project that required several Specialists to accompany the project during execution.  Events and progress was not always duly documented, to provide a comprehensive and fully informed view of what was happening.

PART TWO

PROJECT NAME:	Georgetown Water/Sewerage Maintenance Programme

IDB PROJECT NUMBER: GY 0006

IDB LOAN AND TEC NUMBER(S):  909/SFGY

BORROWER AGENCY(IES)

RESPONSIBLE FOR THIS REPORT: Georgetown Sewerage and Water Commissioners (GS&WC)

1.	Project Objectives

- Objectives achieved and to what extent

The Programme had six objectives that were all, to a certain degree, obtained during the implementation period. They were:

  - To effect a rapid and observable improvement in water availability and quality.

  - To promote the establishment of an efficient and autonomous water and sewerage company for Georgetown.

  - To establish the financial viability of GS&WC by implementing a new tariff system based on measured consumption and the cost of the service provided.

  - To train key personnel in GS&WC to adequately perform all the managerial, operational, maintenance, commercial, financial, and accounting functions.

  - To establish and regularly update a Costumer Registry as a basis for better billing and collection.

  - To encourage water conservation.

The improvements were significant although in some instances the success was not complete. The availability and quality of the water has improved although is not at the desirable level. GS&WC has disappeared but there is a new agency in charge of the sector with national responsibilities. The costumer registry has served well and the system in which it was based is still operational.

- Are there any objectives that will not be achieved?

It is more a problem of level of achievement and the adaptation of a different environment. The answer should be no, all of them will be achieved but there are certain limitations. For example, there is a new agency now in charge of the management of water and sewer facilities. GS&WC will not be the implementing agency. It will be GWI. The strengthening effort will not be able to deliver the same kind of impact since certain personnel have been removed and others are in different positions. Nevertheless there is an overall gain in this respect.

Tariffs and costumer management will continue to change and there is always a challenge in trying to make these public service agencies sustainable in a country like Guyana where the population lacks the means to pay for what the services really are worth.

2.	Project Design and Execution

- Most significant design aspects

The design put together a number of very important and needed actions in order to improve the situation of the water service and the sewer in Georgetown at a relatively low-cost. It took into account issues of sustainability from the management and human resources perspective as well as from the financial point of view.

- Most significant execution aspects

The presence of the company that came in as a consultant was critical. The team that came to Guyana did a more than adequate job in pushing ahead the implementation of the project. In fact in some instances it took the place of the local leadership, which was weakened by the situation at the interior of the institution. The transference of know-how was not done systematically and it never reached the desired levels. As a consequence, once the consultants went away much was lost at the operational and management level.

- Significant problems

During the implementation process there were several significant problems:

  - The institutional weakness of GS&WC that lacked a solid leadership and the capacity to absorb all the know-how and experience brought in by the consultant company.

  - The inability of the GOG to take the decisions that were demanded by the necessity to make the agency financially sustainable, the introduction of the meters and some other seemingly unpopular demands.

  - The delays that distorted the implementation of the project.

  - The change of direction that the strategy of the sector took when the creation of GWI displaced the no longer needed GS&WC.

- Institutional Capacity

The leadership in GS&WC was weak. The persons in charge of the management of the agency were by the most part not confirmed in their positions and had a provisional appointment. The consultant company and the agency made significant efforts to train the personnel and enhance its capacity. A good process for the transference of knowledge and experience was never developed. Finally the agency disappeared and another institutional body was made responsible for the service.

- Unforeseen events

When the project was designed and for most of its implementation period the creation of GWI was not expected that changed the impact that could be expected from the project since GS&WC ceased to exist.

3. 	Bank Performance

- Performance of the Bank during design and execution

The Bank performed well during both moments of the Project Cycle. The persons in charge were accessible and did what was in their power to support the design and implementation.

B. 	Impact of the Bank

The Bank helped with the selection and contacts with the consulting agency, which proved to be a necessary ingredient. It also helped with the assumptions although not always the decisions came on time.

4.	Lessons Learned

- Lessons from the Bank’s performance

There are a number of lessons that can be learned:

The importance of the assumptions during the implementation of the project needs to be stressed. They must be seriously taken into account in order to develop a good risk management model and reduce their possible negative impact in the implementation.

In the design of the project there were no provisions for an end of the project evaluation and an impact evaluation some years down the line. These two are necessary elements in order to obtain the full benefit from the projects that are implemented, especially if they are going to be followed by other projects in the same sector.

The design of a Monitoring and Evaluation system is an issue to take into consideration since the first moment in which the project is starting to be considered.

B.  Additional comments or recommendations.

Even though in general the project can be considered a success there are significant needs in the sector and GWI needs support.

Part Three

- Basic Project Data

| Project dates (month/year) | Original | Actual |
| --- | --- | --- |
| Date of inclusion in pipeline Date of Profile II or Loan Request Date of Analysis Mission Date of Loan Committee Approval Date of Board Approval Date of Contract Effectiveness Date of Compliance with Prior Conditions Calendar of Investments Starting Date End Date Disbursement Calendar: First Disbursement Last Disbursement For Sector Loans: First Tranche Second Tranche Third Tranche Date of Physical Initiation of Works Date of Loan Commitment Date(s) of Cancellation(s) Due date for borrower ex-post evaluation (if required) Due date of the Bank ex-post evaluation (if required) Summary Cost Data (US$) | Not Available Not Available Not Available Not Available 29 September 1993 13 April 1994 25 July 1995 1994 13 April 1998 1994 13 April 1998 1994 N/A N/A Not required Not required | Available Find Available Find Available Find Available Find 29 September 1993 13 April 1994 25 July 1995 November 1995 May 2002 November 1995 May 2002 November 1995 N/A May 2002 (3% partial) Not required Not required |
| Total Amount of IDB Financing | $13,500,000 | $13,195,088 |
| IDB Financing as % of Total Cost | 90 % | 87% |
| Total Cost of Project | $15,000,000 | $15,279,000 |
| Cumulative investment as of May 2002 |  | $15,279,000 |
| Remainder Required for Completion |  | None |

- Project Cost and Financing

- Project cost and source of financing (in thousands US$)

| Original |  |  |  | Actual |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Investment Category | IDB | Borrower | Total | IDB | Borrower | Total |
| 1 Engineering & Admin. | 3,396 | 150 | 3546 | 3,463 | 564 | 4,027 |
| 2 Direct Cost | 7,855 | 1,100 | 8,955 | 9,236 | 1,151 | 10,387 |
| 3 Concurrent cost | 108 |  | 108 | 61 | 0 | 61 |
| 4 Unallocated | 1,705 | 188 | 1893 | 0 | 0 | 0 |
| 5. Financial cost | 436 | 62 | 498 | 435 | 369 | 804 |
| Total | 13,500 | 1,500 | 15,000 | 13,195.00 | 2,084.00 | 15,279.00 |

- Loan Data

| Original Loan amount | $13,500,000 |
| --- | --- |
| Amount disbursed | $13,195,088 |
| Amount canceled | $ 304,912 |
| First Disbursement Original date (m/y) Actual date (m/y) | N/A November 1995 |
| Last Disbursement Original date (m/y) Actual date (m/y) | April 1998 May 2002 |

PART FOUR – Minutes of the MRC

GUYANA

Remedial Maintenance Project for Georgetown
Sewerage and Water Supply Systems
(GY-0006) (LO-909/SF-GY)

Project Completion Report (PCR)

Minutes of the Management Review Meeting (CRG)

August 28, 2003

- Participants

  - Alvaro Llosa (EN3/CHF), CRG Chairman; Adrienne Pratt (RE3/OD6); Diego Buchara (LEG/OPR); Jacques Roumani (ROS/PMP); Alejandro Taddia (RE3/FI3); Gabriel Castillo (FE3/OD6); Marco Nicola (COF/GY); Stuart Hughes (COF/GY) and L. Víctor Traverso (RE3/EN3), CRG Secretary.

  - Written comments were received from: (i) David Rogers (RE3/OD5); (ii) Adrienne Pratt (RE3/OD6); (iii) Alejandro Taddia (RE3/FI3); and (iv) Jacques Roumani and Luis René Cáceres (ROS/PMP).

- Recommendations

  - The CRG found the PCR to be overall an accurate and fair representation of the achievements and issues that occurred during project implementation. However, to strengthen the report, the CRG recommends the following issues be addressed:

    - Objectives. The CRG recommended that the achievement of objective should be clarify in terms of fully or partially achieved and relate them to the emergency nature of the project.

    - Frame of reference. Introduce an explanation of the circumstances under which the project was appraised and the loan approved, indicating the emergency nature of the operation. The CRG team indicated that this was included in section B of the report on page 2 and in section IV A 1 on page 8.

    - Rating. Provide an explanation of why the project despite its emergency nature and 10 years of execution is rated as satisfactory.

    - Execution of the Project. Clarify the execution of the infrastructure and institutional component and how they support each other.

    - First Phase Operation. Explain how this project was actually a first phase operation and a second one was planned to complement the activities initiated with the project.

    - Baseline. Even though the PCR indicates the absence of a logical framework and a baseline, it should specifically indicate that no physical targets were identify originally in the project document.

    - Policy Changes. To look for a more specific explanation of why the policy changes did not take place as expected and what lessons can be learned.

    - Lessons Learn. Review sections IV and V to clarify the lessons learned.

    - Technical Issues. Explain why the billing system took eight months to be operational and why the meters were not compatible with the system.

- Conclusions

  - The CRG recommends approving the PCR once the modifications discussed above are incorporated into the document.

The budget allocated to each component is not available in the Country Office files, invested amounts per component -without financial charges- are reported in this document.

Being a 1993 approved Loan, no Logical Framework or specific benchmarks for components were set during project design.

Ex-post evaluation was not considered for this operation

The Bank approved the follow-up operation LO-1047/SF-GY “Georgetown Water Supply and Sewerage Program II” which intend to consolidate the achievements of LO-909/SF-GY.  This program is the second stage of a long-term comprehensive plan for the rehabilitation of the Georgetown water supply and sewerage systems, that began with a 1094 Master Plan ATN/SF(JF)-3640-GY.

This statement is in contradiction with the “High Probability” rating given in the Project Performance Monitoring Report (PPMR), all along the execution of the program.

See also comments under: 2. project’s components and 4. sequencing above.