| LO:1320/OC-BH: New Providence Transport Program. Procurement Plan June 2010 Update |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. No. | Description of the contract and estimated cost of procurement | Procurement method' | Review (prior or post) | Source of financing and percentage |  | Prequalification (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
|  |  |  |  | IDB % | Local/other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| A | Consulting Services |  |  |  |  |  |  |  |  |  |
| 1 | Consultant as Transport Specialist for 2 years to support the establishment of the TPPU in implementing transport policy and initiatives arising from the TDP. $375,000 | LIB | Prior | 100 | 0 | No | Invitation 2/2004 | May/07 | Completed |  |
| 2 | Consultant to conduct Congestion Study of New providence. $113,100 | NCB | Prior | 100 | 0 | No | Aug/05 | /06 | Completed |  |
| 3 | Consultant to develop road safety and driver education manuals and Develop and collection and analysis of road safety data. $101,922 | NCB | Prior | 100 | 0 | No | Mar/05 | /06 | Completed |  |
| 4 | Consultant to support development and provision of public bus system. $162,500 | NCB | Prior | 100 | 0 | No | Oct/05 | /07 | Completed |  |
| 5 | Consultant to develop a routine maintenance management system (RMMS) $300.000 | ICB | Prior | 100 | 0 | Yes | /09 | /10 | In Progress | Expected to be Awarded in July 2010 |

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC; price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build. own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality- and cost-based selection QBS: Quality-based selection FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants' qualifications; SSS: Single-source selection; 3CV's: Selection of Individual Consultant based on 3CV's

| LO:1320/OC-BH: New Providence Transport Program. Procurement Plan June 2010 Update |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref- No. | Description of the contract and estimated cost of procurement | Procurement method' | Review (prior or post) | Source of financing and percentage |  | Prequalification (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
|  |  |  |  | IDB % | Local/other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| A | Consulting Services |  |  |  |  |  |  |  |  |  |
| 6 | Engineering Consultancy Services for supervision of Road Corridor improvements. $6,022,000 | QCBS | Prior | 100 | 0 | Yes | /01 | Jun/08 | Awarded | In Progress |
| 7 | Completion of designs for CNPRIP. 52,275,000 | Continuation of services | Prior | 70 | 30 | No | N/a | 07 | Completed |  |
| 8 | Environmental consultants to provide oversight for road corridor improvements $706,000 | ICB | Prior | 100 | 0 | No | /01 | /05 | Completed |  |
| 9 | Consultant to develop Downtown Nassau Traffic Management Plan $260,000 | ICB | Prior | 100 | 0 | Yes | /06 | /2011 | Cancelled/Postponed by Cabinet |  |
| B | Civil Works |  |  |  |  |  |  |  |  |  |
| 10 | Rehabilitation of existing road corridors and construction of road corridors (19 corridors in total) in New Providence. Awarded at $52.0 million | ICB | Prior | 70 | 30 | Yes | 100 | Nov./02 | Contract terminated | Contractor went into receivership. 3 corridors were completed. |
| 11 | Relocation of walls and fences within right of way of road corridors to be constructed. Eleven small contracts totaling $831,000 | NCB | Prior | 70 | 30 | No | /06 | /08 | Completed |  |
| 12 | Rehabilitation of existing and construction of existing road corridors (12 total) in New Providence. Total contract *$113,200,000 | LIB/DC | Prior | 100 | 0 | Post-qual | May/07 | Sept/11 | On-going | Bids evaluated. Additional (3) corridors directly negotiated. *$22.8M to he funded with funds from this loan (LO-1320) |

| LO:1988/OC-BH: Supplementary Financing For New Providence Transport Program. Procurement Plan June 2010 Update |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. No. | Description of the contract and estimated cost of procurement | Procurement method' | Review {prior or post) | Source of financing and percentage |  | Prequalification ('teslNo) | Estimated dates |  | Status (pending, in process. awarded, cancelled) |
|  |  |  |  | IDB % | Local/other % |  | Publication of specific procurement notice | Completion of contract |  |
| A | Consulting Services |  |  |  |  |  |  |  |  |
| 1 | Consultant as Transport Specialist for 2 years to provide technical leadership of the TPPU in implementing the transport initiatives arising from the updated TDP and recommendations of previous consultancies. $360,000. | 3 CV's | Prior | 100 | 0 | Shortlist | Jul/08 | Dec/10 | Awarded |
| 2 | 1 local consultant for 2 years to support the TPPU/ORC in implementing public transport recommendations. $120,000 | 3 CV's | Prior | 100 | 0 | No | N/A | N/A | Funds to be used in TPPU's budget |
| 3 | Consultant to Develop and implement a Routine Maintenance management System for the roads in New Providence (supplemental) S290,000 | ICB | Prior | 100 | 0 | Shortlist | Feb/10 | Nov/10 | In Progress |
| 4 | Organizational capacity assessment of MOWT $30,000 | ICB | Prior | 100 | 0 | No | Apr/10 | Aug/10 | In Progress |

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting: FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOOTBOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer: PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality- and cost-based selection QBS: Quality-based selection FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultant;' qualifications; SSS: Single-source selection; 3CV's: Selection of Individual Consultant based on 3CV's

| LO:1988/OC-BH: Supplementary Financing For New Providence Transport Program. Procurement Plan June 2010 Update |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. No. | Description of the contract and estimated cost of procurement | Procurement method | Review (prior or post) | Source of financing and percentage |  | Prequalification (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) |
|  |  |  |  | IDB % | Local/other % |  | Publication of specific procurement notice | Completion of contract |  |
| 5 | Implementing of Organizational Strengthening of MOWT $320,000 | QCBS | Prior | 100 | 0 | Shortlist | April 10 | Jan/11 | In Progress |
| 6 | Engineering Consultancy Services for Supervision of Road Corridor improvements. $6,672,095 | DC | Prior | 100 | 0 | Shortlist | N/A | Dec/12 | In Progress |
| 7 | 2 full-time individual consultants as Project Engineers for the supervision of road corridor improvements $350,000 | 3CV's | Prior | 100 | 0 | No | Jun/10 | Dec/I1 | Awarded |
| 8 | Procure Road Safety equipment and train MOWT personnel $120,000 | NCB | Prior | 100 | 0 | No | Sept/10 | Sepll | In Progress |
| B | Civil Works |  |  |  |  |  |  |  |  |
| 8 | Rehabilitation of existing road corridors and construction of new road corridors in New Providence (12 corridors total) $113,200,000 | LIBIDC | Prior | 100 | 0 | Yes (post) | N/a (LIB) Bid docs issued May 2007 | Dec/11 | Awarded |
| 9 | Construct recreational facilities for the development of Big Pond Park $1,800,000 | NCB | Prior | 100 | 0 | No | July/09 | July/10 | In progress |
| C | Goods & Services |  |  |  |  |  |  |  |  |
| 10 | Appointment of Consultant for the update of the Big Pond Park $200,000. | ICB | Prior | 100 | 0 | No | Jan/09 | July/10 | Awarded |