## PEP-Budget par produit
|  |  |  | Physique | [5 empty] | Financier | [5 empty] | BID
|  | Unit | Unit Cost | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total | Year 1 | Year 2 | Year 3 | Year 4 | year 5 | TOTAL |  | Budget Notes
Component 1 | Strengthening the OMRH's transversal management of human resources | [8 empty] | 2698595 | 2751024.9643 | 2362340.2857 | 718685.4286 | 412343.1429 | 8942988.8214 | 8942988.8214
| Composition of 3 Task Forces to do this (1p from OMRH, 2p from the Tresor Inspection Directorate, 1p DSalaries, 1p DPC, 2p ONI, 1 DRH institution concerned, 3 police officers) with 2 drivers for data collection | [14 empty] | 0
Activity 1.1 | Development and implementation of an HR management policy | Policy |  | 1 |  |  |  |  | 1 | 71000 | 0 | 0 | 0 | 0 | 71000 | 71000
Product | HR management policy developed and validated | Policy |  | 1 |  |  |  |  | 1 | 71000 | 0 | 0 | 0 | 0 | 71000 | 71000
Activity 1.1.1 | Recruitment of specialists who: 1) Evaluate the human resources function (structures, standards, procedures, practices) 2) Provide recommendations 3) Develop HRM policy and implementation plan | Contract |  | 2 | 0 | 0 | 0 | 0 | 2 | 64800 |  |  |  |  | 64800 | 64800 | 90 days of work; 2 local consultants @$360/d
Activity 1.1.2 | Validation workshops | Workshops |  | 2 | 0 | 0 | 0 | 0 | 2 | 6200 |  |  |  |  | 6200 | 6200 | 2 validation worskhops of 100people each with meals @$25pp and conf. room rental
Activity 1.2 | Strengthening the legal and regulatory framework | Strengthening |  | 1 | 0 | 0 | 0 | 0 | 1 | 136440 | 0 | 0 | 0 | 0 | 136440 | 136440
Product | Human resources management standards, procedures and tools established and approved by the OMRH | Package |  | 1 |  |  |  |  | 1 | 136440 | 0 | 0 | 0 | 0 | 136440 | 136440
Activity 1.2.1 | Recruitment of specialists that: 1) Will evaluate the human ressources function (structures, normes, procedures, practices), 2) Provide recommendations, 3) Elaborate the policy and plan of implementation of the HRM | Contract |  | 3 |  |  |  |  | 3 | 130240 |  |  |  |  | 130240 | 130240 | 90d for 2 local consultants @$360/d and 60d for 1 int. consultant @$760/d with 2 travels to Haiti @$2.5Keach with 40days of perdiem and car rentar @$386/d
Activity 1.2.2 | Valdation workshops | Workshops |  | 2 |  |  |  |  | 2 | 6200 |  |  |  |  | 6200 | 6200 | 2 validation worskhops of 100people each with meals @$25pp and conf. room rental ($600/d)
Activity 1.3 | Strengthening the managerial and technical capacities of the OMRH | Strengthening |  | 1 |  |  |  |  | 1 | 408925 | 744285.7143 | 744285.7143 | 397142.8571 | 281428.5714 | 2576067.8571 | 2576067.8571
Product | Report on the HR Gap assessment o the OMRH | Report |  | 1 | 0 | 0 | 0 | 0 | 1 | 21600 | 0 | 0 | 0 | 0 | 21600 | 21600
Activity 1.3.1 | Recruitment of a specialist to perform: 1) Analysis of the human resources gap at the OMRH in order to provide the necessary staff for its new functional organization 2) Develop job profiles for the OMRH 3) Design a technical training program and motivation programs | Contract |  | 1 |  |  |  |  | 0 | 21600 |  |  |  |  | 21600 | 21600 | 60d of 1 int. consultant @$360/d
Product | Recruitment of new personnel at the OMRH | Contract |  | 10 | 15 | 15 | 15 | 15 | 70 | 128571.4286 | 385714.2857 | 385714.2857 | 192857.1429 | 128571.4286 | 1221429 | 1221429
Activity 1.3.2 | Recruitment of staff for the OMRH | Contract |  | 10 | 15 | 15 | 15 | 15 | 70 | 128571.4286 | 385714.2857 | 385714.2857 | 192857.1429 | 128571.4286 | 1221428.5714 | 1221428.5714 | Estimation for the recruitment of 15 new employees for the OMRH (10 hired in 2019 and 5 more in 2020), @HTG 150K/m each ($2K/m; average salary of technical, professional and direction personnel in IADB wage bill). Reduction in year 4 and 5 of amount to be paid (half of total in year 4 and 1/3 in year 5) for government absorption
Product | Funding of salary supplements at the OMRH | Complements |  | 15 | 15 | 15 | 15 | 15 | 15 | 231428.5714 | 308571.4286 | 308571.4286 | 154285.7143 | 102857.1429 | 1105714.2857 | 1105714.2857
Activity 1.3.3 | Funding of salary supplements at the OMRH | Complements |  | 15 | 15 | 15 | 15 | 15 | 15 | 231428.5714 | 308571.4286 | 308571.4286 | 154285.7143 | 102857.1429 | 1105714.2857 | 1105714.2857 | Salary complement estimated for 7 people from the category A and 8 from category B of direction personnel. Eliibibility criteria to be defined; those who meet the criteria will then be selected and will need to meet specific conditions before they receive a salary complement. Estimation of HTG100K/m ($1.4K/m) for category A personnel and HTG120K/m ($1.7K/m) for category B personnel (circa difference between max actual salary and max IADB salary for specific category).
Product | OMRH Trainers Forms on HR Management Standards, Procedures and Tools | Trainers |  | 15 | 0 | 0 | 0 | 0 | 15 | 2325 | 0 | 0 | 0 | 0 | 2325 | 2325
Activity 1.3.4 | Training of OMRH trainers by specialists recruited in component 1.2 activity 1, on HR management procedures and tools | Workshops |  | 1 |  |  |  |  | 1 | 2325 |  |  |  |  | 2325 | 2325 | Workshop for 15 OMRH personnel (food @$25pp) includes cost for document printing (@$30pp)
Product | Technical training workshops and incentive programs for retirement for current and new OMRH staff | Workshops |  | 2 | 2 | 2 | 2 | 2 | 10 | 25000 | 50000 | 50000 | 50000 | 50000 | 225000 | 225000
Activity 1.3.5 | Conduct of training sessions and incentive programmes for retirement based on the recruitment of specialists to develop human resources management standards, procedures and tools (component 1.2 activity 1) | Training |  | 2 | 2 | 2 | 2 | 2 | 10 | 25000 | 50000 | 50000 | 50000 | 50000 | 225000 | 225000 | Estimation for trainings and motivation programs for OMRH. Currently has 90 employees. See Annex of component budget notes
Activity 1.4 | Adaptation of offices, office supplies, computer and communication equipment to strengthen the OMRH | Equipped Office |  |  | 1 |  |  |  | 1 | 677500 | 542800 | 7500 | 7500 | 7500 | 1242800 | 1242800
Product | Equipped offices, operating IT equipment, energy security, communication service and operational internet | Equipped Office |  |  | 1 | 0 | 0 | 0 | 1 | 677500 | 542800 | 7500 | 7500 | 7500 | 1242800 | 1242800
Activity 1.4.1 | Acquisition of equipment, minor computer equipment, installation equipment, reliable internet service and office furniture | Materials |  | 7 | 2 |  |  |  | 9 | 677500 | 542800 | 7500 | 7500 | 7500 | 1242800 | 1242800 | See Annex of component budget notes
Activity 1.5 | Design of a new job structure and review of the salary scale | Position and salary structure |  |  |  |  | 1 |  | 1 | 501750 | 425250 | 592288.5714 | 195776.5714 | 51428.5714 | 1766493.7143 | 1766493.7143
Product | Job and Competency Repository with levels, classification and job profiles developed and valid | Frame of Reference |  |  |  | 1 |  |  | 1 | 501750 | 425250 | 408780 | 144348 | 0 | 1480128 | 1480128
Activity 1.5.1 | Recruitment of a firm for: 1) Make an inventory of what already exists 2) Establish the job and skills reference framework (REC) by institution 3) Develop job profiles and classify them 4) Evaluate, classify and categorize jobs 5) Identify and create job corps and their special status 6) Development of an electronic personnel evaluation module 7) Accompanying the OMRH and the PS institutions in the evaluation of public servants | Contract |  | 1 | 1 | 1 |  |  | 3 | 480000 | 360000 | 360000 |  |  | 1200000 | 1200000 | Based on experience from European Union
Activity 1.5.2 | Exchange and validation workshop (that includes the experiences of females at the Public Service) | Workshops |  | 5 | 15 | 5 |  |  | 25 | 21750 | 65250 | 21750 |  |  | 108750 | 108750 | 25 workshops in total estimated (18 ministries and 7 among the Autonomous Agencies) with 150 people, food @$25pp and room rental @$600/d
Activity 1.5.3 | Evaluation of the personnel of governmental entities by the institutions and the OMRH with the support of the firm of the activity 1 | Evaluations completed |  |  |  | 1 | 1 |  | 2 |  |  | 27030 | 82008 |  | 109038 | 109038 | Evaluation of all governmental personnel. Estimation for work to be done in PaP and outside PaP. Total of 102 governmental institutions (18 ministires and 84 Autonomous Agencies) 42 communes to be visited (10 year 3 then 32 year 4); Printing costs of $10/copy for 2 people per DRH and per institution Outisde PaP: 4 days travel of 3 people with average per diem of $208.25/d/p
Activity 1.5.4 | Recruitment of two experts for the development of a personnel reclassification plan (right-sizing) | Contract |  |  |  |  | 2 | 2 | 4 |  |  |  | 62340 |  | 62340 | 62340 | Estimation for salary of 1 international consultant for 30days @$760/d with 40 days of per diem @$386/d (car rental, M&I, hotel) and 60 days of nat. consultant at @$360/d
Product | Elaboration and implementation of the new salary scale | Scale |  |  |  |  | 1 |  | 1 | 0 | 0 | 183508.5714 | 51428.5714 | 51428.5714 | 286365.7143 | 286365.7143
Activity 1.5.6 | Recruitment of specialists to support the sub-committee in the establishment of the salary grid and the preparation of a plan for the implementation of the grid | Contract |  |  |  | 2 |  |  | 2 |  |  | 132080 |  |  | 132080 | 132080 | 60d of 2 int. consultants @$760/d/p with 2 travels pp to Haiti @$2.5Keach with 40days of perdiem and car rentar @$386/d/p
Activity 1.5.7 | Funding of gratuities to members of the sub-commission | Complements |  |  |  | 1 | 1 | 1 | 3 | - | - | 51428.5714 | 51428.5714 | 51428.5714 | 154285.7143 | 154285.7143 | 10 members in commission. Incentive of HTG30K ($429) per member per month. Elibigility criteria and conditions to receive amount to be defined
Activity 1.6 | Design a retirement incentive program for public servants | Incentive Program Design |  | 0 | 0 | 1 | 0 | 0 | 1 | 50000 | 50000 | 0 | 0 | 0 | 100000 | 100000
Product | Program conditions reviewed and approved | Approved Conditions |  | 0 | 0 | 1 | 0 | 0 | 1 | 50000 | 50000 | 0 | 0 | 0 | 100000 | 100000
Activity 1.6.1 | Revision of modalities of the program of voluntary retirement of public servants | Revised Conditions |  |  |  | 1 |  |  | 1 | 0 | 0 |  |  |  | 0 | 0 | No cost part of OMRH and MEF general activities
Activity 1.6.2 | Identification of personnel eligible for retirement in ministries and public institutions | Staff identified |  |  |  | 1 | 1 |  | 2 | 0 | 0 |  |  |  | 0 | 0 | No cost part of OMRH and MEF general activities
Activity 1.6.3 | Awareness and inTraining on the process | Awareness raising |  |  |  | 1 | 1 |  | 2 | 50000 | 50000 | 0 | 0 |  | 100000 | 100000 | Estimation for awareness raising
Activity 1.7 | Design of a payroll audit to identify officials to voluntary retirement and total employees | Payroll design |  |  | 1 | 1 |  |  | 2 | 700000 | 750000 | 800000 | 0 | 0 | 2250000 | 2250000
Product | Payroll audit to identify officials by voluntary retirement | Audit |  |  | 1 | 1 |  |  | 2 |  | 50000 | 100000 |  |  | 150000 | 150000
Activity 1.7.1 | Recruitment of the company for the design of the audit | Contract |  |  | 1 | 1 |  |  | 2 |  | 50000 | 100000 |  |  | 150000 | 150000
Product | Salary audit to Identify total officials | Audit |  | 1 | 1 | 1 |  |  | 3 | 700000 | 700000 | 700000 |  |  | 2100000 | 2100000
Activity 1.7.2 | Recruitment of the company for the design of the salary audit | Contrat |  | 1 | 1 | 1 |  |  | 3 | 700000 | 700000 | 700000 |  |  | 2100000 | 2100000
Activity 1.8 | Strengthening the gender dimension in the public service | Gender Reinforcement |  | 1 | 1 | 1 | 1 | 1 | 5 | 50000 | 18266 | 18266 | 18266 | 18266 | 123064 | 123064
Product | Activities to reinforce the gender aspect in the Public Service | Activities |  | 1 | 4 | 4 | 4 | 4 | 17 | 50000 | 18266 | 18266 | 18266 | 18266 | 123064 | 123064
Activity 1.8.1 | Forum of women civil service executives to gather their experiences, share in training and recommendations | Forum |  | 1 |  |  |  |  | 1 | 50000 |  |  |  |  | 50000 | 50000 | Estimation for forum
Activity 1.8.2 | Extension of existing programs and launch of awareness campaigns for women to participate in competitions (implementation of the MCFDF plan, Validation of Professional Knowledge and Experience) | Campaign |  |  | 2 | 2 | 2 | 2 | 8 |  | 7500 | 7500 | 7500 | 7500 | 30000 | 30000 | Estimation for awareness raising
Activity 1.8.3 | Accompanying and mentoring women for their professional development and supporting them in the submission of final dissertations | Mentorship |  |  | 2 | 2 | 2 | 2 | 8 |  | 10766 | 10766 | 10766 | 10766 | 43064 | 43064 | Estimation for support to women to finish their thesis
Activity 1.9 | Training and skills development and career development plan | Training Plan |  | 1 |  |  |  |  | 1 | 38580 | 120423.25 | 0 | 0 | 0 | 159003.25 | 159003.25
Product | HRD staff training on human resource management standards, procedures and tools established and approved by the OMRH (Component 1.1) | Trained Staff |  | 204 | 360 |  |  |  | 564 | 38580 | 58823.25 | 0 | 0 | 0 | 97403.25 | 97403.25
Activity 1.9.1 | Training offered to HR departments of government entities on HRM policy in PaP | Training |  | 3 |  |  |  |  | 3 | 38580 |  |  |  |  | 38580 | 38580 | Total of 3 trainings of 5 days that includes 2 DRH people from the 102 institutions
Activity 1.9.2 | Training offered to HR Departments of government entities on HRM policy at the SD level | Training |  |  | 1 |  |  |  | 1 |  | 58823.25 |  |  |  | 58823.25 | 58823.25 | 40 people training of 5 days for 9 other departments; 3 people travel (incl driver) for 7 day mission. Room rental at $450/d
Activity 1.9.3 | Coaching of HRDs by the OMRH | Coaching |  |  | 1 | 1 | 1 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No cost part of OMRH usual activities
Product | Development and validation of a training and development plan | plan |  | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 61600 | 0 | 0 | 0 | 61600 | 61600
Activity 1.9.4 | Recruitment of experts to develop a training and development plan | Training Plan |  |  | 1 |  |  |  | 1 |  | 43200 |  |  |  | 43200 | 43200 | Two national experts for 60 days @360/d
Activity 1.9.5 | Validation workshop | Validation Workshop |  |  | 2 |  |  |  | 2 |  | 18400 |  |  |  | 18400 | 18400 | 2 x 2day workshops for 100 people with $30 printing cost/person
Activity 1.10 | Design and Implementation of change management and communication strategy | campaigns |  | 2 | 3 | 4 | 2 | 3 | 14 | 64400 | 100000 | 200000 | 100000 | 53720 | 518120 | 1021840
Product | Elaboration of a change management strategy | strategy |  | 1 | 0 | 0 | 0 | 0 | 1 | 14400 | 0 | 0 | 0 | 0 | 14400 | 14400
Activity 1.10.1 | Recruitment to develop a change management strategy | Contract |  | 1 |  |  |  |  | 1 | 14400 |  |  |  |  | 14400 | 14400 | 1 national consultant working 40 days at $360/d
Product | Promotion and awareness campaigns | Campaigns |  | 2 | 3 | 4 | 2 | 3 | 14 | 50000 | 100000 | 200000 | 100000 | 53720 | 503720 | 503720
Activity 1.10.2 | Promotion and awareness campaigns | Campaigns |  | 2 | 3 | 4 | 2 | 2 | 14 | 50000 | 100000 | 200000 | 100000 | 53720 | 503720 | 503720 | Estimation
Activity 1.10.3 | Design and implementation of a communication strategy | Plan |  | 1 | 1 | 0 | 0 | 0 | 2 | 100000 | 0 | 0 | 0 | 0 | 100000 | 100000
Component 2 | Improvement of cross-cutting human resources management systems (HRMIS) | [8 empty] | 2459223.1614 | 4834171.2138 | 5355664.7662 | 994397.7273 | 570285.7127 | 14213742.5815 | 14213742.5815
Activity 2.1 | Public Administration Integrated Human Resources Management System (HRMIS/ SIGRH) including pay and pension management modules | SIGRH |  |  |  |  | 1 |  | 1 | 302720 | 2435534.6667 | 3340489 | 3125 | 0 | 6081868.6667 | 6081868.6667
Product | Post-Implementation Review Document - Implementation of the current HRMIS/ SIGRH | Report |  | 1 | 0 | 0 | 0 | 0 | 1 | 10800 | 0 | 0 | 0 | 0 | 10800 | 10800
Activity 2.1.1 | Review and validation of the Terms of Reference | Terms of ref |  | 1 |  |  |  |  | 1 | 0 |  |  |  |  | 0 | 0 | No cost
Activity 2.1.2 | Appraiser Recruitment | Contract |  | 1 |  |  |  |  | 1 | 10800 |  |  |  |  | 10800 | 10800 | 60 days of national consultant
Product | Recruitment of the AMOA | AMOA |  | 1 | 0 | 0 | 0 | 0 | 1 | 218480 | 0 | 0 | 0 | 0 | 218480 | 218480
Activity 2.1.3 | Preparation of the TOR which includes that the AMOA will have to prepare the DAO among others | Contract |  | 1 |  |  |  |  | - | 0 |  |  |  |  | 0 | 0 | No cost
Activity 2.1.4 | Recruitment of consultants | Contract |  | 2 |  |  |  |  | 2 | 218480 |  |  |  |  | 218480 | 218480 | 120 of international consultant and 240 days of national consultant
Product | Specifications drawn up and validated | Specifications |  | 1 | 0 | 0 | 0 | 0 | 1 | 69740 | 0 | 0 | 0 | 0 | 69740 | 69740
Activity 2.1.5 | Recruitment of a consultant to elaborate the specifications | CDCFT |  | 1 |  |  |  |  | 1 | 66040 |  |  |  |  | 66040 | 66040 | 60 days of international consultant with corresponding expenses (see component 1 for more inTraining on corresponding int. cons. expenses)
Activity 2.1.6 | Workshops to validate the specifications | Workshops |  | 1 |  |  |  |  | 1 | 3700 |  |  |  |  | 3700 | 3700 | 2 day workshop with 50 ppl
Product | Licitation for the HRMIS/ SIGRH elaborated and validated with specifications | Licitation validaded |  | 1 | 0 | 0 | 0 | 0 | 1 | 3700 | 0 | 0 | 0 | 0 | 3700 | 3700
Activity 2.1.7 | Licitation finalized for the MEF, OMRH, BID based on the AMOA | Licitation finalized |  | 1 |  |  |  |  | 1 | 0 |  |  |  |  | 0 | 0 | No cost
Activity 2.1.8 | Workshops of validation of the licitation | Workshops |  | 2 |  |  |  |  | 2 | 3700 |  |  |  |  | 3700 | 3700 | 2 day workshop with 50 ppl
Product | Integrator for the implementation of the solution, recruited | Self-powered integrator |  | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 2435534.6667 | 2730489.3333 | 0 | 0 | 5166024 | 5166024
Activity 2.1.9 | Launching of proposals based on the validated licitation | Call for proposals launched |  |  | 1 |  |  |  | 1 |  | 0 |  |  |  | 0 | 0 | No cost
Activity 2.1.10 | Specific assistance during the evaluation of tenders | Contract |  |  | 1 |  |  |  | 1 |  | 21620 |  |  |  | 21620 | 21620 | 15 days of international consultant with corresponding expenses
Activity 2.1.11 | Legal assistance to finalize the Contract model | Contract |  |  | 1 |  |  |  | 1 |  | 6000 |  |  |  | 6000 | 6000 | 15 days of national consultant at $400/d in case needed. For IFMIS, was added to WB budget
Activity 2.1.12 | Selection of the integrator for supply, installation, deployment and maintenance plan of the HRMIS (integrator will also have to provide the list of equipment to be purchased for the HRMIS) | Contract |  |  | 1 |  |  |  | 1 |  | 1365244.6667 | 2730489.3333 |  |  | 4095734 | 4095734 | Estimation for SIGRH as system expansion and training to be added to integrator's contract
Activity 2.1.13 | Acquisition of 400 licenses | Licences |  |  | 1 |  |  |  | 1 |  | 1000000 |  |  |  | 1000000 | 1000000 | Estimation
Activity 2.1.14 | Recruit 1 consultant to define the "Business Process Model" (macro-process) | Contract |  |  | 1 |  |  |  | 1 |  | 42670 |  |  |  | 42670 | 42670 | 30 days of international consultant with corresponding expenses
Product | Hardware and equipment and software infrastructure acquired | Materials |  | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 610000 | 0 | 0 | 610000 | 610000
Activity 2.1.15 | Acquisition of hardware, software and equipment based on the integrator's specifications and recommendations | Materials |  |  |  | 2 |  |  | 2 |  |  | 545000 |  |  | 545000 | 545000 | Estimation
Activity 2.1.16 | Installation and Deployment of Hardware, Equipment and Infrastructure Software | Installation |  |  |  | 2 |  |  | 2 |  |  | 65000 |  |  | 65000 | 65000 | Estimation
Product | Acquired and functional HRMIS | SIGRH acquis et fonctionnel |  | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 2.1.17 | Validation of the integration process proposed by the integrator | Validation |  |  | 1 |  |  |  | 1 |  | 0 |  |  |  | 0 | 0 | No cost here as included in integrator contract
Activity 2.1.18 | Parameterization of the solution | Setting |  |  |  | 1 |  |  | 1 |  |  | 0 |  |  | 0 | 0 | No cost here as included in integrator contract
Activity 2.1.19 | Implementation of test procedures | Test |  |  |  | 1 |  |  | 1 |  |  | 0 |  |  | 0 | 0 | No cost here as included in integrator contract
Activity 2.1.20 | Realizations of specific developments | Developments |  |  |  | 1 |  |  | 1 |  |  | 0 |  |  | 0 | 0 | No cost here as included in integrator contract
Product | System deployed within OMRH, DPC/MEF,Salaries/MEF | Deployment |  | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 2.1.21 | Deployment of hardware, equipment and infrastructure software | Deployment |  |  |  | 1 |  |  | 1 |  |  | 0 |  |  | 0 | 0 | No cost here as included in integrator contract
Product | System extended to the various ministries and other institutions concerned | Extension |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 2.1.22 | extension of hardware, equipment and infrastructure software to other institutions concerned | Extension |  |  |  |  | 1 |  | 1 |  |  | 0 |  |  | 0 | 0 | No cost here as included in integrator contract
Product | System maintenance over the life of the project and implementation of a maintenance plan beyond the project | Maintenance Plan |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 3125 | 0 | 3125 | 3125
Activity 2.1.23 | Development of a Maintenance Plan by the integrator beyond the project (preventive and curative) | Maintenance Plan developed |  |  |  |  | 1 |  | 1 | [5 empty] | 0 | 0 | No cost here as included in integrator contract
Activity 2.1.24 | Training of DSI/MEF and DSI/OMRH technicians in system maintenance (system support) | Training |  |  |  |  | 1 |  | 1 |  |  |  | 3125 |  | 3125 | 3125 | 5 day workshop for 25 people
Activity 2.2 | Mandatory Biometric Register of Public Servants that will identify them and purge the government compensation database | Registration |  | 1 | 1 | 1 |  |  | 3 | 988797.2857 | 955220.7143 | 774427.7143 | 20571.4286 | 0 | 2739017.1429 | 2739017.1429
Product | Biometric census action plan developed | Action Plan |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 2.2.1 | Discussions with ONI to develop an action plan and identify opportunities for collaboration | Action Plan developed |  | 1 |  |  |  |  | 1 | 0 | [6 empty] | No cost associated
Activity 2.2.2 | Preparation and departmental support of the methodology and action plan for identifying public servants | Action Plan granted |  | 1 |  |  |  |  | 1 | [5 empty] | 0 | 0 | No cost associated
Product | Data Collection and Salary Database Sanitization by Government Institution | Governmental Institution |  | 21 | 33 | 33 | 0 | 0 | 87 | 988797.2857 | 955220.7143 | 774427.7143 | 20571.4286 | 0 | 2739017.1429 | 2739017.1429
Activity 2.2.3 | Composition of 3 Task Forces to do this (1p from OMRH, 2p from the Tresor Inspection Directorate, 1p DSalaries, 1p DPC, 2p ONI, 1 DRH institution concerned, 3 police officers) with 2 drivers for data collection | Data collection |  | 21 | 33 | 33 |  |  | 87 | 162664.2857 | 254635.7143 | 254635.7143 | 20571.4286 |  | 692507.1429 | 692507.1429 | MEF confirmed in meeting of 17 AUG that they have completed the work for the MENFP (30K) but not yet its Autonomous Organism. Out of the 90K civil servants, 60K would be left to be verified. 1 TF can verify inTraining for 20K civil servants in 1 year. 3 Task Force in total are therefore needed due to possible risks, estimated that it will take 1yr 1/2 starting in May 2019 (Ministry of Health to take one year because of complexity). 3 verifications per month estimated during 11 months/year (December not counted). Out of 102 institutions, some civil servants do not get paid through National Treasury but own institution's funds. Therefore not counted One TF is composed of 13 people total given complexity of work. Collaboration to be made with ONI to use their biometric equipment purchased. The TF will have the support of the Direction Inspection Tresor (DIT)'s back office in PaP. Civil servants would be added to the DIT to complete the work and the IDB would finance salary complements. The DIT would have a total of 28 pp (2per Task Force, 4 people per Task Force to prepare the file of checks to be given before each missions and 8 people for the constant analysis and treatment of inTraining after missions). The 8 pp in back office would be compensated 12 months compared to the others who would work over 11 months and also need to be paid 1 year after completion of data collection so that they can continue to clean the database. 3 DIT coordinators also needed to coordinate work. Salary complement: - OMRH, DPC/MEF, DIT/MEF, DSolde/MEF and ONI personnel to receive 1/3 of technical personnel salary of HTG15K/m each ($214/m) - 3 coordinators at the DIT/MEF to coordinate the three task forces to receive max HTG20K/m each ($286/m). - 2 drivers and 3 police officers to receive each HTG7.5K/m ($107/m) - One time bonus for collaboration for 3 people/ DRH of HTG18K e ($257e)
Activity 2.2.4 | Acquisition d'equipements additionnels a ceux de l'ONI + entretien de ceux de l'ONI | Acquisition |  | 1 | 1 |  |  |  | 2 | 522921 | 224109 |  |  |  | 747030 | 747030
Activity 2.2.5 | Travel budget to regions | Deplacement |  | 1 | 1 | 1 |  |  | 3 | 303212 | 476476 | 519792 |  |  | 1299480 | 1299480 | 8 day missions; 2 missions outside of PaP expected for 2 out of the 3 TF. Average of 208.25/d per diem for 13 TF members *2
Product | Sanitization Biometric Census Repository | Repertoire assaini |  | 1 | 1 | 1 | 1 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 2.2.6 | Work within MEF to clean up the database | Sanitation |  | 1 | 1 | 1 | 1 | 1 | 5 | [5 empty] | 0 | 0 | No cost associated
Product | Maintenance of the database during the life of the project and launch of a maintenance plan beyond the project | Entretien |  | 1 | 1 | 1 | 1 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 2.2.7 | Collaboration between government entities, OMRH and MEF | Sanitation |  | 1 | 1 | 1 | 1 | 1 | 5 | [5 empty] | 0 | 0 | No cost associated
Activity 2.3 | Strengthening of the managerial and technical capacities of the MEF | Strengthening |  | 1 |  |  |  |  | 1 | 137314.2857 | 462857.1429 | 462857.1429 | 231428.5714 | 154285.7127 | 1448742.8556 | 1448742.8556
Product | Report about the gap evaluation of HR of the MEF | Report |  | 1 |  |  |  |  | 1 | 21600 |  |  |  |  | 21600 | 21600
Activity 2.3.1 | Recruitment of a specialist to perform: 1) Analysis of the gap in human resources of the MEF to provide the necessary staff for its new functional organization 2) Design of employment profiles for the MEF 3) Design of a technical training and motivational programs | Contract |  | 1 |  |  |  |  | 1 | 21600 |  |  |  |  | 21600 | 21600
Product | Recruitment of new people within the MEF | Contract |  | 5 | 10 | 10 | 10 | 10 | 10 | 64285.7143 | 257142.8571 | 257142.8571 | 128571.4286 | 85714.2849 | 792857.142 | 792857.142 | We are estimated a hiring of 10 more employees for the MEF (5to be hired in 2019 and another 5 in 2020). We will reduced the salary paid by the project in year 4 and 5 (50% for year 4 and 33% for year 5), to be absorbed by the government.
Activity 2.3.2 | Recruitment of new people within the MEF | Contract |  | 5 | 10 | 10 | 10 | 10 | 10 | 64285.7143 | 257142.8571 | 257142.8571 | 128571.4286 | 85714.2849 | 792857.142 | 792857.142 | Non cumulatif.
Product | Financing of salary complements | Complements |  | 5 | 10 | 10 | 10 | 10 | 10 | 51428.5714 | 205714.2857 | 205714.2857 | 102857.1429 | 68571.4279 | 634285.7136 | 634285.7136 | Salary complement. For MEF, salary complement estimated for 10 people. Estimation of HTG122K/m.
Activity 2.3.3 | Financing of the salary complements for the MEF | Complements |  | 5 | 10 | 10 | 10 | 10 | 10 | 51428.5714 | 205714.2857 | 205714.2857 | 102857.1429 | 68571.4279 | 634285.7136 | 634285.7136 | Salary complement
Activity 2.4 | Budget Process Re-engineering Project, Procedures Manuals for Treasury Payments | Document |  | 1 | 0 | 0 | 0 | 0 | 1 | 136980 | 0 | 0 | 0 | 0 | 136980 | 136980
Product | Payment Procedures Manuals | Manual |  | 1 | 0 | 0 | 0 | 0 | 1 | 136980 | 0 | 0 | 0 | 0 | 136980 | 136980
Activity 2.4.1 | Recruitment of an expert for: 1) The updating of the payment procedures manual taking into account the LEELF 2) Elaboration of the budget nomenclature of the state and the didactic guide 3) Elaboration of the charter and procedures for managing budgetary programmes 4) Drafting of methodological guides (CDMT, PAP, RAP, CHD...) | Contract |  | 1 |  |  |  |  | 1 | 129580 |  |  |  |  | 129580 | 129580 | 120 days of international consultant with corresponding expenses
Activity 2.4.2 | Validation Workshop | Validation Workshop |  | 1 |  |  |  |  | 1 | 7400 |  |  |  |  | 7400 | 7400 | 50people 4 day workshop
Activity 2.5 | Equipment for interdepartmental connection and computer data security (for Directorate of Information Systems (DSI) / MEF, DPC / MEF etc.) | Equipements |  | 4 | 4 | 4 | 0 | 0 | 12 | 396000 | 299000 | 360000 | 0 | 0 | 1055000 | 1055000
Product | Hardware and equipment acquired and installed | Materials |  | 4 | 4 | 4 | 0 | 0 | 12 | 396000 | 299000 | 360000 | 0 | 0 | 1055000 | 1055000
Activity 2.5.1 | Acquisition of materials and equipment | Acquisition |  | 4 | 4 | 4 |  |  | 12 | 396000 | 299000 | 360000 |  |  | 1055000 | 1055000 | Estimation
Activity 2.6 | Setting up Training Workshops to ensure the continuous development of skills (in IT, HRMIS, biometric identification, etc.) | Workshops |  | 0 | 0 | 1 | 1 | 1 | 3 | 100000 | 312000 | 221890.9091 | 519272.7273 | 196000 | 1349163.6364 | 1349163.6364
Product | SIGRH users trained (2.1) | Certifications |  | 0 | 0 | 100 | 200 | 100 | 400 | 0 | 0 | 21890.9091 | 419272.7273 | 196000 | 637163.6364 | 637163.6364
Activity 2.6.1 | Training plan and support documents, prepared by the SIGRH integrator | Plan de Training |  |  |  | 1 |  |  | 1 |  |  | 0 |  |  | 0 | 0 | Included in Integrator contract
Activity 2.6.2 | Printing Supporting Documents | Impression |  |  |  | 1 | 1 |  | 2 |  |  | 9090.9091 | 27272.7273 |  | 36363.6364 | 36363.6364 | Estimation for 400 people
Activity 2.6.3 | Training provided to OMRH, DPC/MEF and Pay/MEF by the integrator | Training |  |  |  | 1 |  |  | 1 |  |  | 12800 |  |  | 12800 | 12800 | 100 people workshop for 4 days
Activity 2.6.4 | Training provided to other government institutions | Training |  |  |  |  | 10 | 5 | 15 |  |  |  | 392000 | 196000 | 588000 | 588000 | Estimation for total of 15 workshops of 4 day each, with 20 people/workshop, with room rental and computer rental/p at $80/d as all might not have laptop to bring to workshop
Product | MEF team trained on budget processes, programming and macroeconomic framework (2.3) | Trained Staff |  | 0 | 200 | 0 | 0 | 0 | 200 | 0 | 112000 | 0 | 0 | 0 | 112000 | 112000
Activity 2.6.5 | Training on Component 2.3, Activity 1 | Training |  |  | 1 |  |  |  | 1 |  | 112000 |  |  |  | 112000 | 112000 | 5 workshops total 4 days for 200 people in total
Product | Teams trained on existing and acquired specialized equipment | Trained Staff |  | 150 | 300 | 300 | 150 | 0 | 900 | 100000 | 200000 | 200000 | 100000 | 0 | 600000 | 600000
Activity 2.6.6 | Staff training on existing and acquired specialized equipment | Training |  | 5 | 10 | 10 | 5 |  | 30 | 100000 | 200000 | 200000 | 100000 |  | 600000 | 600000 | Estimation (travel of trainers etc…)
Activity 2.7 | Strengthening the DSI/MEF team | Contract |  | 5 | 5 | 0 | 0 | 0 | 10 | 255411.59 | 191558.69 | 0 | 0 | 0 | 446970.28 | 446970.28
Product | DSI/MEF positions covered | Positions |  | 5 | 5 | 0 | 0 | 0 | 5 | 255411.59 | 191558.69 | 0 | 0 | 0 | 446970.28 | 446970.28
Activity 2.7.1 | Financing the salary of the DSI / MEF team | Contract |  | 5 | 5 | 0 | 0 | 0 | 5 | 255411.59 | 191558.69 |  |  |  | 446970.28 | 446970.28 | See Annex of component budget notes
Activity 2.8 | Strengthening of the team of the DSI / OMRH | Contract |  | 6 | 8 | 9 | 10 | 10 | 14 | 142000 | 178000 | 196000 | 220000 | 220000 | 956000 | 956000
Product | DSI/OMRH positions covered | Positions |  | 5 | 7 | 8 | 9 | 9 | 9 | 102000 | 138000 | 156000 | 180000 | 180000 | 756000 | 756000
Activity 2.8.1 | Funding the salary of the DSI/OMRH team | Contract |  | 5 | 7 | 8 | 9 | 9 | 9 | 102000 | 138000 | 156000 | 180000 | 180000 | 756000 | 756000 | See Annex of component budget notes
Product | Strengthening of the team of the DSI / OMRH | Contract |  | 1 | 1 | 1 | 1 | 1 | 5 | 40000 | 40000 | 40000 | 40000 | 40000 | 200000 | 200000
Activity 2.8.2 | Technical Assistance(s) | Contract |  | 1 | 1 | 1 | 1 | 1 | 5 | 40000 | 40000 | 40000 | 40000 | 40000 | 200000 | 200000 | See Annex of component budget notes
Component 3 | Strengthening the institutional capacity of selected entities for service improvement | [8 empty] | 2817800 | 6984935.5 | 11464290 | 3940190 | 2211591 | 27418806.5 | 27418806.5
Activity 3.1 | Preparation and/or updating of functional and operational analysis of selected departments and services (functional analysis, job descriptions, recruitment plan, gap analysis, organizational models | Functional Analysis |  | 0 | 2 | 0 | 0 | 0 | 4 | 500000 | 614250 | 0 | 0 | 0 | 1114250 | 1114250
Product | Functional analysis of MARNDR and MTPTC updated with proposals for : 1. Organizational Model 2. Gap analysis in technical and superior human resources 3. Required job profiles 4. Recruitment plans 5. Training Plans | Functional Analysis |  | 0 | 4 | 0 | 0 | 0 | 4 | 500000 | 614250 | 0 | 0 | 0 | 1114250 | 1114250
Activity 3.1.1 | Firm recruitment for the MARNDR who will perform: - Preparation of functional and operational reviews; - The review of the human resources composition | Contract |  | 1 |  |  |  |  | 1 | 200000 | 300000 |  |  |  | 500000 | 500000 | Estimation
Activity 3.1.2 | Validation workshop | Validation Workshop |  |  | 1 |  |  |  | 1 |  | 6200 |  |  |  | 6200 | 6200 | 2 day workshop with 100ppl
Activity 3.1.3 | Firm recruitment for MTPTC to perform: - Preparation of functional and operational reviews; - The review of the human resources composition | Contract |  | 1 |  |  |  |  | 1 | 300000 | 301850 | 0 |  |  | 601850 | 601850 | Estimation
Activity 3.1.4 | Validation Workshop | Validation Workshop |  |  | 1 |  |  |  | 1 |  | 6200 |  |  |  | 6200 | 6200 | 2 day workshop with 100ppl
Activity 3.2 | Implementation of the Training Program | Training |  | 0 | 1 | 1 | 1 | 1 | 4 | 0 | 200000 | 200000 | 200000 | 200000 | 800000 | 800000
Product | Training based on what has been proposed at Component 3.1 level | Training |  | 0 | 2 | 3 | 3 | 3 | 11 | 0 | 200000 | 200000 | 200000 | 200000 | 800000 | 800000
Activity 3.2.1 | Selection of experts to carry out the Trainings | Contract |  |  | 1 | 1 |  |  | 2 | 0 | 20000 | 20000 | 20000 | 20000 | 80000 | 80000 | Estimation
Activity .2.2 | Training Offered | Training |  |  | 1 | 1 | 1 | 1 | 4 | 0 | 180000 | 180000 | 180000 | 180000 | 720000 | 720000 | Estimation
Activity 3.3 | Implementation of the incentive for voluntary retirement program | Number of incentive packages |  | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 3000000 | 7000000 | 0 | 0 | 10000000 | 10000000
Product | Payment of incentives to ministry staff based on functional evaluations Payment of incentives to ministry staff based on functional evaluations | Payment |  |  | 1 | 1 | 0 | 0 | 2 |  | 3000000 | 7000000 | 0 | 0 | 10000000 | 10000000 | Estimation de fonctionnaires a la retraite pour année 2: 278 fonctionnaires et pour l'année 3: 647 fonctionnaires pour avoir un total de 925 fonctionnaires.
Activity 3.3.1 | Payment of incentives to departmental staff based on functional assessments MARNDR | Payment |  |  | 1 | 1 |  |  | 2 |  | 3000000 | 7000000 |  |  | 10000000 | 10000000 | Estimation
Product | Payment of incentives to staff of other ministries | Payment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Activity 3.3.2 | Payment of incentives to staff of other ministries | Payment | [6 empty] | 0 | [5 empty] | 0 | 0 | Estimation
Activity 3.4 | Recruitment Payment of salaries of new civil servants recruited and additional salaries for existing civil servants.* For year 2 with a salary of 100%, year 3 a salary of 75%, year 4 with a salary of 50% and year 5 with a salary of 25%. | Recruitment |  | 0 | 200 | 200 | 0 | 0 | 400 | 0 | 1800000 | 2700000 | 1800000 | 900000 | 7200000 | 7200000
Product | Prioritization of middle and senior managers to be recruited | Priorization |  | 0 | 2 | 2 | 1 | 0 | 1 | 0 | 1800000 | 2700000 | 1800000 | 900000 | 7200000 | 7200000
Activity 3.4.1 | Identification of priority positions to be covered (managerial and technical) | Priorization |  |  | 1 | 1 |  |  | 2 |  |  |  | 0 |  | 0 | 0 | No cost associated
Activity 3.4.2 | Competitive recruitment with and gender approach based on improving public service standards as a project product | Recruitment |  |  | 1 | 1 | 0 | 0 | 2 |  | 1800000 | 2700000 | 1800000 | 900000 | 7200000 | 7200000 | Estimation based on average monthly salary of USD 750. In Year 2 is paid for this project to 200 officials 100% of the salary. In Year 3 is paid to 400 officials 75% of the salary. In Year 4 to 400 officials 50% of the salary, and in Year 5, 25%. Assumption: Average monthly salary: US$750.
Activity 3.5 | UEP MARNDR : Acquisition and deployment of an IT solution for the development, implementation and evaluation of MARNDR's public investment programs. | Software (IT Solution) |  | 1 |  |  |  |  | 1 | 500000 | 0 | 0 | 0 | 0 | 500000 | 500000
Product | International licitation for the acquisition of an IT solution for the design, execution and evaluation of MARNDR's public investment programmes | IT Solution |  | 1 |  |  |  |  | 1 | 500000 | 0 | 0 | 0 | 0 | 500000 | 500000
Activity 3.5.1 | Elaboration of a complete licitation meeting the expectations of the MARNDR, the Government, the TFPs in terms of services rendered by the IT solution | Elaborated DAO |  | 1 |  |  |  |  | 1 | 0 |  |  | 0 |  | 0 | 0 | No cost associated
Activity 3.5.2 | Recruitment of the firm | Contract |  | 1 |  |  |  |  | 1 | 500000 |  |  |  |  | 500000 | 500000 | Estimation
Activity 3.6 | Rehabilitation and equipment of Municipal Agricultural Offices (BAC) and Training Schools | Rehabilitation and equipment of BAC and Training Schools |  |  |  | 10 | 10 |  | 20 | 100000 | 150000 | 150000 | 600000 | 0 | 1000000 | 1000000
Product | Structural evaluation of existing BACs and training schools | Structural Evaluation |  | 10 | 33 | 0 | 0 | 0 | 43 | 100000 | 150000 | 0 | 0 | 0 | 250000 | 250000
Activity 3.6.1 | Elaboration of a DAO for the selection of a company which will carry out the structural evaluation of the existing BAC and schools of Trainings and will transmit an estimate of the costs of rehabilitation and the necessary equipments | Elaborated DAO |  | 1 |  |  |  |  | 1 | 0 |  |  | 0 |  | 0 | 0 | No cost associated
Activity 3.6.2 | Launch of the call for tender | Launched DAO |  | 1 |  |  |  |  | 1 | 0 |  |  |  |  | 0 | 0 | No cost associated
Activity 3.6.3 | Recruitment of the firm | Contract |  | 1 | 1 |  |  |  | 2 | 100000 | 150000 |  |  |  | 250000 | 250000 | Estimation
Product | BACs and training schools selected, rehabilitated and equipped |  |  | 0 | 0 | 10 | 10 | 0 | 20 | 0 | 0 | 150000 | 600000 | 0 | 750000 | 750000
Activity 3.6.4 | Priorization by the MARNDR of the BAC to rehabilitate and equip on the base: - the Report of the firm that carried out the structural evaluation and made a cost proposal - services that have been selected by MARNDR | Priorization by the MARNDR |  |  | 1 |  |  |  | 1 | 0 |  |  |  |  | 0 | 0 | No cost associated
Activity 3.6.5 | Elaboration of a DAO for the selection of company(ies) that will carry out the rehabilitation of the centers and provide a PGES | Elaborated DAO |  |  | 1 |  |  |  | 1 |  | 0 |  |  |  | 0 | 0 | No cost associated
Activity 3.6.6 | Launch of the call for tender | Launched DAO |  |  | 1 |  |  |  | 1 |  | 0 |  |  |  | 0 | 0 | No cost associated
Activity 3.6.7 | Recruitment of the firm(s) | Contract |  |  |  | 1 |  |  | 1 |  |  | 150000 | 600000 |  | 750000 | 750000 | Estimation
Activity 3.7 | Support to farmers with services of extension and technical assistance | Assistance |  | 1 | 1 | 1 | 1 | 1 | 5 | 455400 | 534900 | 994290 | 1070190 | 842489 | 3897269 | 3897269 | 3897269
Product | Farmers that received services of extension or technical assistance | Farmers |  |  | 250 | 500 | 1500 | 1500 | 1250 | 455400 | 534900 | 994290 | 1070190 | 842489 | 3897269 | 3897269 | 3897269
Activity 3.8 | Design and implementation of Integrated Statistical Platform for the MARNDR | platform |  | 1 | 0 | 0 | 0 | 0 | 1 | 860000 | 0 | 0 | 0 | 0 | 860000 | 860000
Product | Integrated statistical platform for the MARNDR designed and implemented | platform |  | 1 | 0 | 0 | 0 | 0 | 1 | 860000 | 0 | 0 | 0 | 0 | 860000 | 860000
Activity 3.9 | Strengthening road network surveillance | Reinforcement of road surveillance |  | 4 | 13 | 1 | 0 | 0 | 18 | 152400 | 415785.5 | 150000 | 0 | 0 | 718185.5 | 718185.5
Product | Conceptual Model Document | Conceptual model |  | 2 | 0 | 0 | 0 | 0 | 2 | 10800 | 0 | 0 | 0 | 0 | 10800 | 10800
Activity 3.9.1 | Development of ToRs for the conceptual model of road network monitoring | Elaborated TOR |  | 1 |  |  |  |  | 1 | 0 |  |  | 0 |  | 0 | 0 | No cost associated
Activity 3.9.2 | Recruitment of an expert on the basis of ToRs | Contract |  | 1 |  |  |  |  | 1 | 10800 |  |  |  |  | 10800 | 10800 | 30 days of work of national consultant
Product | Process re-engineering document with updated rules and procedures | Re- engineering Documents |  | 1 | 0 | 0 | 0 | 0 | 1 | 21600 | 0 | 0 | 0 | 0 | 21600 | 21600
Activity 3.9.3 | Elaboration of TdRs for the Recruitment of an expert who will reengineer the processes, update the rules and procedures and propose the software to be acquired | Elaborated TOR |  | 1 |  |  |  |  | 1 | 0 |  |  |  |  | 0 | 0 | No cost associated
Activity 3.9.4 | Recruitment of an expert on the basis of ToRs | Contract |  | 1 |  |  |  |  | 1 | 21600 |  |  |  |  | 21600 | 21600 | 60 days of work of national consultant
Product | Software acquisition in connection with the database | Software |  | 1 | 0 | 0 | 0 | 0 | 1 | 120000 | 0 | 0 | 0 | 0 | 120000 | 120000
Activity 3.9.5 | On the basis of the expert's recommendations, acquire the software | purchased software |  | 1 |  |  |  |  | 1 | 120000 |  |  |  |  | 120000 | 120000 | Estimation
Product | Road network monitoring system developed | Systeme de surveillance routier |  | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 43200 | 0 | 0 | 0 | 43200 | 43200
Activity 3.9.6 | Development of ToRs for Recruitment of an expert who will develop a road network monitoring system and provide a Training Plan | Logiciel acquis |  |  | 1 |  |  |  | 1 | 0 |  |  |  |  | 0 | 0 | No cost associated
Activity 3.9.7 | Recruitment of an expert on the basis of ToRs | Contract |  |  | 1 |  |  |  | 1 |  | 43200 |  |  |  | 43200 | 43200 | Estimation
Product | Road network monitoring system implemented | Road surveillance system |  | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 200000 | 0 | 0 | 0 | 200000 | 200000
Activity 3.9.8 | Acquisition of the system on the basis of the expert's recommendations | purchased software |  |  | 1 |  |  |  | 1 |  | 180000 |  |  |  | 180000 | 180000 | Estimation
Activity 3.9.9 | Deployment at the DD level | Software deployed |  |  | 1 |  |  |  | 1 |  | 20000 |  |  |  | 20000 | 20000 | Estimation
Product | MTPTC Staff Training | Workshops |  | 0 | 10 | 0 | 0 | 0 | 10 | 0 | 22585.5 | 0 | 0 | 0 | 22585.5 | 22585.5 | 22585.5
Activity 3.9.10 | Staff training at PaP by the expert | Workshops |  |  | 1 |  |  |  | 1 |  | 1350 |  |  |  | 1350 | 1350 | Training for 7 people at UE during 2 day workshop
Activity 3.9.11 | Staff training in the DDs with the expert | Workshops |  |  | 9 |  |  |  | 9 |  | 21235.5 |  |  |  | 21235.5 | 21235.5
Product | Acquisition of EU equipment from the MTPTC | Equipments |  | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 150000 | 150000 | 0 | 0 | 300000 | 300000
Activity 3.9.12 | Acquisition of equipment for the EU from the MTPTC | Training |  |  | 1 | 1 |  |  | 2 |  | 150000 | 150000 |  |  | 300000 | 300000 | Estimation
Activity 3.10 | Equipment for selected MTPTC services | Equipments | [6 empty] | 0 | 50000 | 70000 | 70000 | 70000 | 69102 | 329102 | 329102
Product | Visits of drainage and construction works | Visits |  | 18 | 24 | 24 | 24 | 24 | 114 | 30000 | 50000 | 50000 | 50000 | 50000 | 230000 | 230000
Activity 3.10.1 | Regular field visits | Visits |  | 18 | 24 | 24 | 24 | 24 | 114 | 30000 | 50000 | 50000 | 50000 | 50000 | 230000 | 230000 | Estimation
Product | Raising the awareness of the population and engineers on the protection of works / constructions | Awareness raising |  | 2 | 2 | 2 | 2 | 2 | 10 | 20000 | 20000 | 20000 | 20000 | 19102 | 99102 | 99102
Activity 3.10.2 | Engineer and public awareness activities | Awareness raising |  | 2 | 2 | 2 | 2 | 2 | 10 | 20000 | 20000 | 20000 | 20000 | 19102 | 99102 | 99102 | Estimation
Activity 3.11 | Strengthening the CSC/CA | Strengthening |  | 1 | 1 | 1 | 1 | 1 | 5 | 200000 | 200000 | 200000 | 200000 | 200000 | 1000000 | 1000000
Product | Strengthening judicial review, simplification of control procedures, training of judges and support to CSC/CA employees for the issuance of annual accountability reports | Activities |  | 1 | 1 | 1 | 1 | 1 | 5 | 200000 | 200000 | 200000 | 200000 | 200000 | 1000000 | 1000000
Activity 3.11.1 | Financing of activities | Contract |  | 1 | 1 | 1 | 1 | 1 | 5 | 200000 | 200000 | 200000 | 200000 | 200000 | 1000000 | 1000000 | To finalize with CSCCA sequence of activities to be financed at $1M
4 | Project Management | [8 empty] | 911862.0183 | 842013.538 | 866862.0183 | 836862.018 | 966862.0183 | 4424461.611 | 4424461.611
| Strengthening of the fiduciary support of the Project (UCP/MEF)/Operation/audit | Strengthening |  | 1 | 1 | 1 | 1 | 1 | 5 | 425425.27 | 425425.27 | 425425.27 | 425425.27 | 425425.27 | 2127126.35 | 2127126.35
Product | Strengthening of the fiduciary support of the Project (UCP/MEF)/ Functioning/ audit | Strengthening |  | 1 | 1 | 1 | 1 | 1 | 5 | 425425.27 | 425425.27 | 425425.27 | 425425.27 | 425425.27 | 2127126.35 | 2127126.35
Activity 4.1.1 | Financing of salaries for the fiduciary management of the project | Salaries |  | 7 | 7 | 7 | 7 | 7 | 35 | 304104.35 | 304104.35 | 304104.35 | 304104.35 | 304104.35 | 1520521.75 | 1520521.75
Activity 4.1.2 | Operating expenses | Operating expenses |  | 1 | 1 | 1 | 1 | 1 | 5 | 76320.92 | 76320.92 | 76320.92 | 76320.92 | 76320.92 | 381604.6 | 381604.6
Activity 4.1.3 | Audit | Audit |  | 1 | 1 | 1 | 1 | 1 | 5 | 45000 | 45000 | 45000 | 45000 | 45000 | 225000 | 225000
| Strengthening Project Administration (OMRH)/Functioning | Strengthening |  | 1 | 1 | 1 | 1 | 1 | 35 | 356224.628 | 356224.628 | 356224.628 | 356224.628 | 356224.628 | 1781123.14 | 1781123.14
Product | Strengthening Project Administration (OMRH)/Functioning | Stengthening |  | 7 | 7 | 7 | 7 | 7 | 35 | 356224.628 | 356224.628 | 356224.628 | 356224.628 | 356224.628 | 1781123.14 | 1781123.14
Activity 4.2.1 | Salary funding for project management and monitoring and evaluation | Salaries |  | 5 | 5 | 5 | 5 | 5 | 25 | 151855.4 | 151855.4 | 151855.4 | 151855.4 | 151855.4 | 759277 | 759277
Activité 4.2.2 | Activités de planification et de suivi de l'OMRH | Monitoring activities |  | 1 | 1 | 1 | 1 | 1 | 5 | 43600 | 43600 | 43600 | 43600 | 43600 | 218000 | 218000
Activity 4.2.3 | Operating expenses | Operating expenses |  | 1 | 1 | 1 | 1 | 1 | 5 | 160769.228 | 160769.228 | 160769.228 | 160769.228 | 160769.228 | 803846.14 | 803846.14
| Design of a project baseline and implementation of a performance monitoring and evaluation system | Monitoring and evaluation of results |  | 1 | 1 | 1 | 1 | 1 | 5 | 10000 | 10000 | 50000 | 10000 | 150000 | 230000 | 230000
Product | Baseline available, Plan finalized, monitoring and evaluation activities for the project |  |  | 1 | 1 | 1 | 1 | 1 | 5 | 10000 | 10000 | 50000 | 10000 | 150000 | 230000 | 230000
Activity 4.3.1 | Salary funding for project management and monitoring and evaluation | Salaries |  | 1 | 1 | 1 | 1 | 1 | 5 | 10000 | 10000 | 10000 | 10000 | 10000 | 50000 | 50000
Activity 4.3.2 | Consultancies for different activities of evaluation | consultancy |  | 0 | 0 | 2 | 0 | 3 | 5 | 0 | 0 | 40000 | 0 | 140000 | 180000 | 180000
| Monitoring and Evaluation / CRFP | Monitoring and evaluation of the RFP |  | 1 | 1 | 1 | 1 | 1 | 5 | 106212.1203 | 36363.64 | 21212.1203 | 31212.12 | 21212.1203 | 216212.121 | 216212.121
Product | Monitoring and Evaluation of the Reform of the Public Finance | Monitoring and evaluation of the RFP |  | 1 | 1 | 1 | 1 | 1 | 5 | 106212.1203 | 36363.64 | 21212.1203 | 31212.12 | 21212.1203 | 216212.121 | 216212.121
Activity 4.4.1 | Financing of salaries of the personnel of the CRFP | Salaries |  | 7 | 7 | 7 | 7 | 7 | 35 | 106212.1203 | 36363.64 | 21212.1203 | 31212.12 | 21212.1203 | 216212.121 | 216212.121
| Development of a risk mitigation plan | Mitigation risk plan |  | 1 | 1 | 1 | 1 | 1 | 5 | 14000 | 14000 | 14000 | 14000 | 14000 | 70000 | 70000
Product | Risk probability matrix developed; Risk mitigation plan developed | Mitigation risk plan |  | 1 | 1 | 1 | 1 | 1 | 5 | 14000 | 14000 | 14000 | 14000 | 14000 | 70000 | 70000
Activity 4.5.1 | Financing of salaries to elaborate the risk matrix | Salaries |  | 1 | 1 | 1 | 1 | 1 | 5 | 14000 | 14000 | 14000 | 14000 | 14000 | 70000 | 70000
TOTAL | [9 empty] | 8887480.1798 | 15412145.2161 | 20049157.0703 | 6490135.1738 | 4161081.8739 | 54999999.514 | 54999999.514
Note on E71: Baron, Marie Edwige: Pas de cout associe
Note on C73: Baron, Marie Edwige: Cahier de charge fonctionnel et Techniques
Note on C74: Baron, Marie Edwige: Cahier de charge fonctionnel et Techniques
Note on B82: Baron, Marie Edwige: Eventuellenent recruter un consultant externe: Proposition 15 jrs a $ 400
Note on B86: Baron, Marie Edwige: Listes de Mat et D'equipements seront elaborees par le consultant qui aura a elaborer le cahier de charges 90 000 US
Note on N100: Catherine Alexis: 25 personnes au total sur 2 jours
Note on B106: Catherine Alexis: Les fonctionnaires sont consideres pas les contractuels car pas de base de donnees fiables. Suite a l'implementation du SIGRH, tout contractuel devra se faire enregistrer biometriquement/confirmer identite pour l'emission du contrat et recevoir un paiement
Note on J138: Catherine Alexis: not cumulative
Note on J139: Catherine Alexis: not cumulative
Note on J141: Catherine Alexis: not cumulative
Note on J142: Catherine Alexis: not cumulative
Note on J161: Catherine Alexis: non cumulatif