## Sheet1
PROCUREMENT PLAN FOR NON-REIMBURSABLE TECHNICAL COOPERATIONS
Country: Regional |  |  |  |  | Executing agency: Inter-American Development Bank |  |  |  |  | Public or private sector: Public & Private
Project number: RG-T3126 |  |  |  |  | Title of Project: Developing a Sustainable and Enabling Investment Climate in Guyana
Period covered by the plan: September 2017 - September 2020
Threshold for ex-post review of procurements:N/A |  |  |  | Goods and services (in US$):____________ |  | N/A |  | Consulting services(in US$):____________ | 270000
Item Nº | Ref. AWP | Description (1) | Estimated contract cost (US$) | Procurement Method (2) | Review of procurement (3) | Source of financing and percentage |  | Estimated date of the procurement notice or start of the contract | Technical review by the PTL (4) | Comments
[6 empty] | IDB/MIF % | Local/other % |  |  |  | Direct Contracting
1 |  | Component 1 | [8 empty] | International Competitive Bidding
Individual consultants
1.1 |  | Consultancies to developed Cluster Project Concept Notes | 50000 | IICQ | Ex-ante | 100 | 0 | 2017-10-15 | Yes
1.2 |  | Knowledge Product on Gender Equality | 40000 | IICQ | Ex-ante | 100 | 0 | 2017-10-15 | Yes
1.3 |  | Consultancy to develop Technology Extension Services Pilot | 25000 | IICQ | Ex-ante | 100 | 0 | 2018-01-15 | Yes
|  | Sub-total | 115000
2 |  | Component 2
Individual consultants
2.1 |  | Consultancies to develop Business Climate Reforms Projects | 120000 | IICQ | Ex-ante | 100 | 0 | 2017-10-15 | Yes | This sub-component will fund 10 consultancies at 12,000 each
2.2 |  | Knowledge Product | 35000 | IICQ | Ex-ante | 100 | 0 | 2017-10-15 | Yes |  | Ex Post
|  | Sub-total | 155000
National System
Total |  |  | 270000 | Prepared by: |  |  | Date: 10/3/2017
(1) Grouping together of similar procurement is recommended, such as computer hardware, publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Goods and works: CB: Competitive bidding; PC: Price comparison; DC: Direct contracting.
(2) Consulting firms: CQS: Selection Based on the Consultants' Qualifications; QCBS: Quality and cost-based selection; LCS: Least Cost Selection; FBS: Selection nder a Fixed Budget; SSS: Single Source Selection; QBS: Quality Based selection.
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection.
(2) Country system: include selection Method
(3) Ex-ante/ex-post review: In general, depending on the institutional capacity and level of risk associated with the procurement, ex-post review is the standard modality. Ex-ante review can be specified for critical or complex process.
(4) Technical review: The PTL will use this column to define those procurement he/she considers "critical"or "complex"that require ex ante review of the terms of reference, technical specifications, reports, outputs, or other items.