Support for the Implementation of the Ebs Investment Plan

SU-L1039

Procurement Plan

Duration: From 2015 to 2019:

| Code | Principal Project Procurement Activity | Estimated Cost (US$) | Funding Source |  |  |  | Procurement Method | Pre-Qual. (Yes/No) | Specific Procurement Notice | Review By Bank |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB | Local | IDB | Local |  |  | (Tentative Publication Date) | (Ex-ante/Ex-post) |
|  |  |  | US$ | US$ | % | % |  |  |  |  |
| Component I - Improvement of EBS’ Operations. |  |  |  |  |  |  |  |  |  |  |
| Goods |  |  |  |  |  |  |  |  |  |  |
|  | Purchase of the Distribution Management System and Outage Management System (DMS/OMS) | $1,273,000 | $1,273,000 |  | 100% |  | ICB | NO | Q3,2015 | Ex-Ante |
|  | Purchase of the Enterprise Resource Planning (ERP) system | $8,763,000 | $8,763,000 |  | 100% |  | ICB | NO | Q2,2016 | Ex-Ante |
| Consultancy Services |  |  |  |  |  |  |  |  |  |  |
|  | Design of the Distribution Management System / Outage Management System (DMS/OMS) | $67,000 | $67,000 |  | 100% |  | ICB | NO | Q1, 2015 | Ex-Ante |
|  | Design and implementation of the Energy Efficiency Framework plan | $2,000,000 | $2,000,000 |  | 100% |  | SSS | NO | Q1,2016 | Ex-Ante |
|  | Design of the Guidelines for the EBS transition to a new corporate structure | $750,000 | $750,000 |  | 100% |  | ICB | NO | Q1, 2016 | Ex-Ante |
| Component II - Critical Infrastructure. |  |  |  |  |  |  |  |  |  |  |
| Works |  |  |  |  |  |  |  |  |  |  |
|  | Engineering, procurement and construction of Substation J upgrade. | $4,000,000 | $4,000,000 |  | 100% |  | ICB | NO | Q2,2015 | Ex-Ante |
|  | Engineering, procurement and construction of Substation F upgrade. | $4,000,000 | $4,000,000 |  | 100% |  | ICB | NO | Q3, 2015 | Ex-Ante |
|  | Engineering, procurement and construction of Substation Boma. | $10,000,000 | $10,000,000 |  | 100% |  | ICB | NO | Q3, 2015 | Ex-Ante |
| Other costs |  |  |  |  |  |  |  |  |  |  |
|  | Administration | $400,000 | $400,000 |  | 100% |  |  |  |  |  |
|  | Technical auditing, monitoring and evaluation | $300,000 | $300,000 |  | 100% |  | QCNI | NO | Q4, 2017 | Ex-Ante |
|  | Contingencies | $1,447,000 | $1,447,000 |  | 100% |  |  | NO |  |  |
| Total |  | $33,000,000 | $33,000,000 |  | 100% |  |  |  |  |  |

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; QCNI: Comparison of Qualifications of the National Individual Consultant; QCII: Comparison of Qualifications of the International Individual Consultant; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality- and cost-based selection QBS: Quality-based selection FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection; SH: Shopping method.