Natural Hazard Management in Urban Coastal Area (JA-T1019)

Annex 11 – Procurement Plan

Period included in this procurement plan: from: 01/2009  - 05/2011

1. CONSULTANCY SERVICE

| Description of Contract | Estimated cost of Procurement (US) | Procurement Method | Source of financing and percentages |  | Estimated Dates |  | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB-DPF (%) | Local Counterpart (%) | Publication of specific Procurement Notice | Completion of contract |  |
| Perform Risk Assessment for Three Major Coastal Areas | 80.0000 | Limited International Competitive Bidding – Quality –and Cost Based selection (QCSB) | 100 | 0 | Q1 2009 | Q2 2010 | Pending |
| Formulation of Ten Parish Risk Management Plans (includes hosting of workshops and a participatory Methodology) | 155,000 | International Competitive Bidding- Selection based on Quality-and Cost Based Selection QCBS) | 100 | 0 | Q1 2009 | Q1 2011 | Pending |
| Support to Telecommunication Plan | 18,000 | International Individual Consultant Selection based on Qualification | 83 | 17 | Q1 2009 | Q1 2011 | Pending |
| Development of a model for coastal community risk plan | 6,500 | National individual Consultant Selection based on Qualifications | 100 | 0 | Q1 2009 | Q1 2010 | Pending |
| Detailed design and implementation of mitigation projects identified in community plans | 90,000 | Limited International Competitive Bidding – Quality – and Cost Based Selection | 100 | 0 | Q1 2010 | Q2 2011 | Pending |
| Review of National Disaster programme and ODPEM’s organizational structure | 18,000 | International Individual Consultant Selection based on Qualifications | 83 | 17 | Q1 2009 | Q1 2010 | Pending |
| Review and analysis of institutional and legal framework – development of subsidiary legislation | 15,000 | International Individual Consultant Selection based on Qualifications | 100 | 0 | Q1 2009 | Q1 2010 | Pending |
| Procure IT equipment ( hardware and software ) staff training for ODPEM to conduct disaster simulations | 10,000 | Local Shopping | 100 | 0 | Q4 2009 | Q1 2010 | Pending |
| Evaluation | 20,000 | National individual Consultant Selection based on Qualifications | 100 | 0 | Q2 2010 | Q2 2011 | Pending |
| Auditing ( according to AF200) | 15,000 | National individual Consultant Selection based on Qualifications | 100 | 0 | Q4 2010 | Q2 2011 | Pending |

Natural Hazard Management in Urban Coastal Area (JA-T1019)

Annex 11 – Procurement Plan

Period included in this procurement plan: from: 01/2009 - 05/2011

11. GOODS

| Description of Contract | Estimated cost of Procurement (US) | Procurement Method | Source of financing and percentages |  | Estimated Dates |  | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB-DPF (%) | Local Counterpart (%) | Publication of Specific Procurement Notice | Completion of contract |  |
| Procurement of telecommunication equipment (company must provide training) | 45,000 | National Competitive Bedding | 100 | 0 | Q1 2009 | Q1 2011 | Pending |
| IT hardware/software to conduct disaster analysis and simulations (including training) | 153,000 | International Competitive Bidding | 91 | 9 | Q1 2010 | Q4 2010 | Pending |
| Office supplies and consumables | 10,000 | Shopping (price comparisons) | 0 | 100 | Q1 2009 | Q2 2011 | Pending |