## Sheet1
Inter-American Development Bank
ORP/GCM
PROCUREMENT PLAN FOR BANK EXECUTED OPERATIONS
Country: Brazil | [5 empty] | Executing Agency: IDB | [7 empty] | UDR: CBR
Project number: BR-T1394 |  |  |  |  | Title of Project: Sustainable Transit-Oriented Development in Brazil
Period covered by the Plan: [24 months] December 1st, 2018 - December 1st, 2020 |  |  |  |  | Total Project Amount: |  | 2000000
Component | Procurement Type (1) (2) | Service type (1) (2) | Description | Estimated contract cost (US$) | Selection Method (2) | Type of Contract | Source of Financing and Percentage |  |  |  | Estimated date of the procurement notice | Estimated contract start date | Estimated contract length | Comments
[7 empty] | IDB/MIF |  | Other External Donor
[7 empty] | Amount | % | Amount | % |  |  |  |  | Direct Contracting
Select comp | Select Proc. Type | Goods Included in Firm Cons. RFP | Consultant 1: brief description |  | select method | Select Cont. Type |  |  |  |  | 2016-03-01 |  |  |  | International Competitive Bidding
Component 1 | A. Consulting services | Consulting Firm (GN-2765) | Local Consultant to carry out literature review and assessment of international case studies in the developing world to understand land markets, legal frameworks and institutional structures that enable or/and constrain TOD system developments and to undertake a country diagnosis for Brazil, including constraints and recommendations to develop TOD Systems in Brazilian municipalities | 300000 | FCS | Lump Sum | 300000 | 100% | 0 | 0% | Q4 2018 | Q1 2019 |  | The external consultant(s) will be hired
Component 2 | A. Consulting services | Consulting Firm (GN-2765) | Design of TOD guidelines and step-by-step manual to support Brazilian municipalities in developing their own TOD systems | 400000 | FCS | Lump Sum | 400000 | 100% | 0 | 0% | Q1 2019 | Q1 2019 |  | The external consulting firm will be hired
Component 3 | A. Consulting services | Consulting Firm (GN-2765) | Design of TOD pilot project and implementation of technical assistance and capacity building to deliver TOD systems in Brazilian municipalities | 1300000 | FCS | Lump Sum | 1300000 | 100% | 0 | 0% | Q1 2019 | Q1 2019 |  | The external consulting firm will be hired | Selection Based on the Consultants' Qualifications
Prepared by: | CBR/HUD |  | TOTALS | 2000000 |  |  | 2000000 | 100% | 0 | 0%
(1) Grouping together of similar procurement is recommended, such as publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) (i) Individual consultants: ICQ: Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection. Selection process to be done in accordance with AM-650.
(2) (ii) Consulting firms: Per GN-2765-1, Consulting Firm selection methods for Bank-executed Operations are: Single Source Selection (SSS); Simplified Competitive Selection (<=250K) (SCS); Fully Competitive (>250K) (FCS); and Framework Agreement Task Order (TO). All Consulting Firm selection processes under this policy must use the electronic module in Convergence.
(2) (iii) Goods: Per GN-2765-1, par. A.2.2.c: "The procurement of goods and related services, except when such goods and related services are necessary to achieve the objectives of the Bank-executed Operational Work and are included in the consulting services contract and represent less than ten percent (10%) of the consulting services contract value."