## Procurement Plan
PROCUREMENT PLAN - GPHRP ( June 2018 to December 2019)
WORKS
Process number | Activity: | Procurement Method | Review Method (Select one of the options): | Amount & Source of Funding in u$s : |  |  |  | Prequalification | Dates |  | Status (pending, in progress, awarded, cancelled) | Comments
|  |  |  | Estimated Amount, in US$ : | Estimated Amount, BID %: | Estimated Amount, EU %: | Estimated Amount, Counterpart %: |  | Specific Procurement notice | Contract Signature
| Section III. Rehabilitation from Iguana Creek Junction to Santa Elena Town. | ICB | Ex-Ante | 12373200 |  | 10% | 0% |  | 2018-01-29 | 2018-12-01 | Pending
| Maintenance | NCB | Ex-Ante | 312000 | 50% |  | 50% | No | 2019-01-02 | 2019-07-01 | Pending | Maitenance for the 3 sections will be separate contracts
Sub-total |  |  |  | 12685200
GOODS
Process number | Activity: | Procurement Method | Review Method (Select one of the options): | Amount & Source of Funding in u$s : |  |  |  | Prequalification | Dates |  | Status (pending, in progress, awarded, cancelled) | Comments
|  |  |  | Estimated Amount, in US$ : | Estimated Amount, IDB %: | Estimated Amount, EU %: | Estimated Amount, Counterpart %: |  | Specific Procurement notice | Contract Signature
| 4 HDM4 equipment (Bump integrator) and Licences | Shopping | Ex-Ante | 25000 | 100% | 0% | 0% | No | 2018-08-15 | 2018-10-01 | pending | specification and bidding documents being finalized
| Vehicles - MOWT (2) | ICB | Ex-Ante | 125000 | 100% | 0% | 0% | No | 2018-10-27 | 2018-12-27 | Pending
Sub-total |  |  |  | 150000
NON CONSULTING SERVICES
Process number | Activity: | Procurement Method | Review Method (Select one of the options): | Amount & Source of Funding in u$s : |  |  |  | Prequalification | Dates |  | Status (pending, in progress, awarded, cancelled) | Comments
|  |  |  | Estimated Amount, in US$ : | Estimated Amount, IDB %: | Estimated Amount, EU %: | Estimated Amount, Counterpart %: |  | Specific Procurement notice | Contract Signature
| Structuring Performance Based Contracts training | Shopping | Ex-Ante | 100000 | 100% | 0% | 0% | No | 2018-01-10 | 2018-12-01 | Pending
| HDM-4 training | Shopping | Ex-Ante | 100000 | 100% | 0% | 0% | No | 2018-01-11 | 2019-01-15
| Environmental safeguards application, training | CQS | Ex-Ante | 200000 | 100% | 0% | 0% | No | 28/3/2018 | 2018-08-15 | contract signing pending
| Operating Costs |  | Ex-Post | 676000 | 100% | 0% | 0% | No | 2015-11-17 | 2021-06-28 | ongoing
Sub-total |  |  |  | 1076000
CONSULTING FIRMS
Process number | Activity: | Procurement Method | Review Method (Select one of the options): | Amount & Source of Funding in u$s : |  |  |  | Prequalification | Dates |  | Status (pending, in progress, awarded, cancelled) | Comments
|  |  |  | Estimated Amount, in US$ : | Estimated Amount, IDB %: | Estimated Amount, EU %: | Estimated Amount, Counterpart %: |  | Specific Procurement notice | Contract Signature
| Monitoring & Evaluation (including environmental audit) | QCBS | Ex-Ante | 350000 | 100% | 0% | 0% | No | 2018-07-01 | 2018-08-01 | Pending | ToR to be developed
| Financial Audit | LCS | Ex-Ante | 100000 | 100% | 0% | 0% | No |  | 2018-04-15 | contract signing pending | Grant Thornton has recommended for the award of contract
| Studies and designs | QCBS | Ex-Ante | 336485.5 | 100% | 0% | 0% | No | 2018-07-01 | 2018-08-01 | Pending | ToR to be developed
Sub-total |  |  |  | 786485.5
INDIVIDUAL CONSULTANTS
Process number | Activity: | Procurement Method | Review Method (Select one of the options): | Amount & Source of Funding in u$s : |  |  |  | Prequalification | Dates |  | Status (pending, in progress, awarded, cancelled) | Comments
|  |  |  | Estimated Amount, in u$s : | Estimated Amount, IDB %: | Estimated Amount, EU %: | Estimated Amount, Counterpart %: |  | Specific Procurement notice | Contract Signature
| Procurement Officer | QCIIC | Ex-Ante | 151091 | 100% | 0% | 0% | No | N/A | 2018-07-30 | ongoing
| Financial Specialist | QCIIC | Ex-Ante | 166200 | 100% | 0% | 0% | No | N/A | 2018-07-30 | ongoing
| Administrative Officer | QCIIC | Ex-Ante | 126916 | 100% | 0% | 0% | No | N/A | 2018-07-30 | ongoing
Sub-total |  |  |  | 444207
TOTAL - US$ |  |  |  | 15141892.5