| Project: BA-L1025 Public Sector Smart Energy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Number _______ and Loan Contract Number _______ [when available] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Period comprised in this Procurement Plan: From ___ month/year __ to ___ month/year __ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ref. No. 1 | Description of and category of procurement contract | Estimated cost in (US$ thousand) | Procurement method 2 | Review (ex-ante or ex-post) | Source of financing and percentage |  | Prequali-fication 3 (Yes/No) |  |  | Estimated Dates |  |  | Status 4 (pending, in process, awarded, cancelled) |  | Comments |  |
|  |  |  |  |  | IDB % | Local / Other % |  |  |  | Publication of specific procurement notice |  | Completion of contract |  |  |  |  |
| 1 | GOODS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Component 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Supply and installation of energy efficient lights | 9947 | ICB | ex ante | 43 | 57 |  |  |  | Q3 2013 |  | Q1 2015 | pending |  |  |  |
|  | Supply and installation-EE retrofit & solar PV systems for 12 public buildings inc: configuration study; baseline/optimization study. | 9600 | ICB | ex ante | 100 | 0 | Y |  |  | Q3 2013 |  | Q1 2015 | pending |  | pre-qual may be required |  |
|  | Component 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 8 electric vehicles ,1 double port charging station | 300 | PC | ex ante | 100 | 0 |  |  |  | Q3 2013 |  | Q4 2013 | pending |  |  |  |
|  | Component 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Data collection software | 100 | NCB | ex post | 100 | 0 |  |  |  | Q2 2013 |  | Q2 2013 | pending |  |  |  |
| 2 | CONSULTING SERVICES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Component 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Testing and assessment of EE retrofit -public lights | 50 | NCB | ex post | 43 | 57 |  |  |  | Q4 2014 |  | Q2 2015 | pending |  |  |  |
|  | Assessment of EE retrofit & PV systems -public buildings | 50 | NCB |  | 100 | 0 |  |  |  | Q4 2014 |  | Q2 2015 | pending |  |  |  |
|  | Component 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Ocean Power Studies | 999 | QCNI | ex post | 0 | 100 |  |  |  | Q2 2013 |  | Q4 2014 | pending |  |  |  |
| 3 | Component 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Institutional strengthening; ; training; public awareness campaing | 2,150 | QCBS | ex post | 100 | 0 |  |  |  | Q2 2013 |  | Q4 2017 | pending |  |  |  |
|  | Project Manager;Proc. Specialist; Accountant; Admin. Assistant | 950 | QCNI | ex post | 100 | 0 |  |  |  | Q1 2013 |  | Q4 2017 | pending |  |  |  |
| 1 If there are a number of similar individual contracts to be executed in different places or at different times, these can be grouped together under a single heading, with an explanation in the comments column, indicating the average individual amount and the period during which the contracts would be executed. For example: an education project that includes school construction might include an item labeled “School Construction” for an estimated cost of US$20 million and an explanation under the Comments column such as this: “This item encompasses some 200 contracts for school construction averaging US$100,000 each, to be awarded individually by the participating municipal governments over a three-year period between January 2006 and December 2008.” |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; Consulting Firms: QCBS: Quality- and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection; Individual Consultants: QCNI: Selection based on comparison of qualifications of national individual consultants; QCII: Selection based on comparison of qualifications of international individual consultants. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 Applicable only to Goods and Works in case the new Policies apply. In the case of previous Policies, it is applicable to Goods, Works and Consulting Services. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 Column “Status” will be used for retroactive procurement and when updating the procurement plan. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |