Document of the Inter-American Development Bank

Guyana

Support to Improve Maternal and Child Health

(GY-L1058)

Environmental and Social Management Report

(ESMR)

July 2016

This document was prepared by Fabiola Mercado (VPS/ESG), and the project team consisting of Clara Alemann (SCL/GDI); Luis Buscarons (SPH/CBO); Emilie Chapuis (FMP/CGY); Martha Guerra (SCL/SPH); Donna Harris (SPH/CJA), co-Team Leader; Ian Ho-a-Shu (SPH/CTT); Emma Iriarte (SPH/CPN); Javier Jiménez (LEG/SGO); Paula Louis-Grant (FMP/CGY); Jennifer Nelson (SPH/CPN); Sandro Parodi (SPH/CDR); Leticia Ramjag (CCB/CGY); Diego Rios (SPH/CPN); Karolina Schantz (SCL/SHP); Mark Wenner (CCB/CGY); and Marcella Distrutti (SCL/SPH), Project Team Leader.

Table of Contents

- Introduction

- Summary Table

- Project Description

- Key Project Infrastructure Components and Schedule

- Environmental and Social Setting

- Compliance Status and Project Standards

- Environmental and Social Appraisal Process

- Consistency with IDB Policies and Directives

- Project Standards and Requirements

- Key Environmental and Social Impacts, Risks and Mitigation

- Summary of Key Environmental  and Social Impacts and Risks

- Environmental and Health and Safety Impacts and Risks and Mitigation

- Social Impacts and Risks and Mitigation

- Natural Disasters Risks and Mitigation

- Other Risks

- Positive Impacts

- IDB Additionality

- Management and Monitoring of Environmental, Social, Health and Safety and Labor Impacts and Risks

- The Environmental and Social Management Plan

- Monitoring and Supervision

- Requirements to be Included in the Legal Agreement

- Prior to Board

- Prior to First Disbursement

- Prior to beginning construction work of Component 2

- Throughout the Life of the Loan

- Monitoring and Reporting

List of Annexes

Annex A - Compliance of Project with IDB Safeguard Requirements

List of Acronyms - Guyana GY-L1028

EMP		Environmental Management Plan

EPA		Environmental Protection Agency

ESA		Environmental and Social Analysis

ESMP		Environmental and Social Management Plan

GS&WC 	Guyana Sewerage and Water Commission

GUYWA 	Guyana Water Authority

IDB		Inter-American Development Bank

IFC 		International Finance Corporation

MoPH		Ministry of Public Health

MPR		Monitoring Program Report

OR 		Operating Regulations

RDCs 		Regional Democratic Councils

RM&ERP 	Risk Management and Emergency Response Plan

I. Introduction

  - Summary Table

| Country | Guyana |
| --- | --- |
| Sector | Health |
| Project Name | Support to Improve Maternal and Child Health |
| Borrower and/or Sponsor | Co-operative Republic of Guyana |
| Executing Agency | Ministry of Public Health (MoPH) |
| Transaction Type | Loan Agreement |
| Total Project Cost (US$) | US$8 million |
| Environmental Category | B |

- Project Description

- Key Project Infrastructure Components and Schedule

  - The objective of this project is to contribute to the reduction of maternal, perinatal, and neonatal deaths in Guyana. To meet this objective, the project has identified the following components:

  - Component 1. Strengthening reproductive, maternal, and neonatal health services.

  - Sub-component 1.1. Access and use of reproductive, maternal, and neonatal health services (US$1.130.000 million). The objective of this component is to increase access and use of reproductive, maternal, and neonatal health services. To achieve this objective, this component will finance: (i) strengthening of the community platform and the primary level of care for service delivery in regions 3, 4, and 9; (ii) procurement of equipment/supplies; (iii) strengthening of the maternity waiting home strategy, including the development of individual and community plans to support women and newborns to access facilities in Region 9; and (iv) design and implementation of behavior change communication strategies, including messages targeted at adolescents, men, and indigenous people.

  - Sub-component 1.2. Quality of reproductive, maternal, and neonatal health services (US$1.690.000 million). The objective of this component is to improve the quality of reproductive, maternal, and neonatal health services. To achieve this objective, this component will finance: (i) design and implementation of a QIS in hospitals of regions 3, 4, and 9, including the improvement of clinical and management practices and the promotion of patient-centered and culturally-appropriate care; (ii) revision and update of guidelines, protocols, and strategies; (iii) improvements in the supply chain for contraceptive methods, drugs, and blood products, including procurement of equipment; (iv) improvements in health information; and (v) development of skills in the workforce of regions 3, 4, and 9 related to reproductive, maternal, and neonatal health.

  - Component 2. Strengthening the healthcare network (US$3.534.000 million). The objective of this component is to increase the effectiveness of the maternal and neonatal health care network. To achieve this objective, this component will finance: (i) assessment and reorganization of Guyana’s healthcare and referral networks, including the revision and adjustment of the portfolio of services and the roles of different cadres of health workers; (ii) infrastructure improvements to C.C. Nicholson Hospital; (iii) procurement of equipment for health facilities, including GPHC, C.C. Nicholson Hospital, and the Georgetown maternity waiting home; and (iv) ambulances and communication system (radios for health facilities and ambulances) for regions 3, 4, and 9.

  - Component 3. Administration, auditing, and evaluation (US$1.196.000 million). The objective of this component is to support project administration and evaluation activities, including ancillary expenses and strengthening the capacity of the Maternal and Child Health (MCH) Unit of the MoPH, which will assume overall responsibility for project implementation (see paragraph 3.1). This component will support the recruitment of five staff: a project coordinator; two fiduciary officers; a health specialist; and a planning, monitoring, and evaluation officer (see paragraph 3.2 of the POD).

  - Calendar: It is anticipated that the entire project will be implemented in approximately five (5) years. It is estimated that the process of procuring equipment for Georgetown Public Hospital Corporation (GPHC) will last 6 months, while the construction activities of the CC Nicholson Hospital (CCNH) will last 12 months.

- Environmental and Social Setting

  - The activities of the project pertinent to this ESMR consist in the acquisition of equipment for the Georgetown Public Hospital Corporation (GPHC) and renovation activities of the CC Nicholson Hospital (CCNH). The type of equipment that will be provided to the new building of the GPHC is still under consideration and will be defined at a later stage. For the infrastructure activities of the CCNH, it is expected that these will include an expansion of the driveway and the construction of a ramp that will connect the first and the second floor.

  - Both hospitals are located in urban areas, in which the environment has been already modified by anthropic activities. For this operation involuntary resettlement or economic displacement it is not expected. The proposed activities of the project will be executed in buildings that are already functioning.

  - Georgetown Public Hospital Corporation (GPHC): This hospital is the largest hospital in Guyana. It operates as a general hospital and is located in the Political Administrative Region 4– Demerara to Mahaica. The hospital is located in the commercial-residential district of the city. The surrounding areas are already urbanized and developed. The area has a high traffic flow as it is located in a very busy zone. The hospital is surrounded by a combination of residential and commercial activities. The land use of the area of the hospital is for administration and governance activities of the country. The size of the area occupied by this hospital is approximately 12419.58 square meters.

  - The GPHC does not have a formal Environmental Management System in place. As part of its environmental management activities, the hospital has a waste management system (for non-infectious and infectious waste), and occupational health and safety measures. The hospital has two officers that are in charge of overseeing health, safety and environmental compliance. These officers perform monthly inspections to assess the level of compliance of the aforementioned activities.

Fig 1- Geographical location of the Georgetown Public Hospital Corporation

  - The Waste Management System of this hospital needs to be strengthened. Waste management in this hospital is segregated and managed separately by their waste types. Non-infectious waste is collected in bins to be shredded and compacted later. This waste is collected daily by a private contractor and transported to the Haags Bosch landfill, which is the municipal landfill. Infectious waste, consisting sharps and biomedical waste, is collected in special containers and stored in closed  waste holding area. This area is equipped with air conditioning to ensure proper management. The infectious waste is treated and shredded by a hydroclave in order to become non-infectious waste. After this treatment this waste is treated and disposed as non-infectious waste. In the case of body parts, these are stored at the mortuary to be transported and buried in the local cemetery, the Hope Cemetery, later.

  - The water supplied in the GPHC is distributed by the Guyana Water Incorporated. The hospital has two underwater tanks that distribute water to showers and toilets. Bottled water, in 5 gallon containers is procured from suppliers for drinking purposes. The GPHC has an underground storage tank with capacity of approximately 6,500 gallons. This hospital has its own water treatment plant to ensure water quality. In addition, water testing for micro-organisms and heavy metals is performed on a monthly basis by workers of the hospital.

  - The GPHC is linked to the Georgetown Sewage System. The wastewater of the GPHC does not receive any type of treatment and is disposed directly to the city sewage system.

  - The hospital has air conditioning systems working in surgery rooms, laboratories, and in the waste holding area. These systems are also inspected by the hospital personnel on monthly basis to ensure optimal functioning.

  - The energy for the GPHC is sourced from the Guyana Power and Light Company. Seven power generators are distributed in the entire area; three large and two small ones in the north block and two in the south block. All of these generators are not equipped with the sound proofing required; however, a new generator is currently being installed. It is expected that this will be installed with the necessary abatement measures.

  - The area where the GPHC is located is prone to flooding due to heavy rains and problems related to the clogging of the external drainage system (outside of GPHC, within the municipality).

  - Regarding the social setting, the city of Georgetown reported in 2012 a population of 134,497 habitants. The majority of the people of this city use the GPHC as their main hospital. Nonetheless, given that the GPHC is the biggest hospital in the country, many people from other regions also go to this hospital for treatment. Therefore, the attendance capacity is always over the limit.

  - CC Nicholson Hospital (CCNH): This hospital is a smaller hospital located at Nabaclis, East Coast Demerara, which is also part of the Political Administrative Region 4– Demerara to Mahaica.  The hospital was established in 1994 by the London-based Cyril Charles Nicholson Foundation, and was later upgraded by the Government of Guyana in 2003. This was done in order to provide an option of medical treatment for the residents of the surrounding communities  Even though CCNH was upgraded to be a facility that would be opened 24 hours and 7 days a week, due to lack of infrastructure and few doctors and nurses working full time, this target has not been met. The size of the area occupied by this hospital is approximately 796.49 square meters.

  - The hospital is located in an urbanized area. The land use of this area is mainly residential; however, it has some commercial activities in the surroundings. To the east of the facility there is an open vegetated area that leads to a mangrove reserve. To the north there is the Nabaclis Primary School, while in the west and south there are residencies and some established commerce.

  - The area where the CCNH is located is vulnerable to tropical depressions and extreme weather events. The Nabaclis village, located in the East Demerara area is protected from flooding from the Atlantic Ocean by a sea defense system consisting of mangroves and a seawall. The surrounding areas have a good drainage system which in turn prevents flooding events.

  - The CCNH does not have an Environmental Management System in place, although it follows some environmental practices like infectious and non-infectious waste management.

  - Regarding waste management, CCHN segregates and collects separately its infectious and non-infectious waste. The non-infectious waste is collected in bins and stored on site until is collected by the Neighborhood Democratic Council to and then disposed at the Lusignan Dumpsite. The infectious waste consisting of sharps and medical waste is collected in special containers and stored on site until a significant quantity has been accumulated. Then it is transported to the nearby Diamond Hospital and then taken to the GHPC for treatment and shredding at the hydroclave. Other medical waste that has been collected is burnt in a makeshift incinerator that is located inside the property of the hospital. Although this practice has been reduced because of the complaints of the neighbors, it is still ongoing.

  - The water distribution for CCNH is provided by the Guyana Water Incorporated. The hospital also has 2 water tanks, each of 450 gallons of capacity. These provide water for common use in the bathrooms, laundry, etc. Bottled water, in 5 gallon containers is procured from suppliers for drinking purposes. This hospital does not have a water treatment plant, and does not undertake water testing.

  - The wastewater is not treated in this hospital and is discharged into a soak away system, which subsequently drains into the neighborhood drainage system. Regarding the sewage, the hospital has two septic tanks for the collection of sewage. These tanks are periodically emptied by a private contractor when they are full.

Fig 2- Geographical location of the Dr CC Nicholson Hospital

  - The air condition system of the hospital is an issue. Only a few consultation rooms have air condition equipment installed.

  - The CCNH receives electricity from the Guyana Power and Light Company and does not have any backup generators.

  - Regarding the social setting, the population of the Nabaclis village, is approximately of 4,000 habitants. Currently, the hospital provides medical treatment to an average of 400 patients per month. The majority of the people using this hospital is from the local community; however, there have been cases of people from neighboring communities comming to the CCNH. This hospital only provides basic health care and refers all the complex cases to the Georgetown Public Hospital Corporation.

- Compliance Status and Project Standards

- Environmental and Social Appraisal Process

  - This Project is required to be in compliance with the institutional framework, national environment and health related policies. The regulatory and institutional framework applicable to this project involves directly the following institutions: Environmental Protection Agency, Ministry of Public Health, Regional and Neighborhood Democratic Councils, and Guyana Water Authority.

  - The Environmental Protection Agency has seven regulations which were enacted in 2000 as a consequence of the Environmental Protection Act of 1996. These are: (i) The Environmental Protection Authorizations Regulations 2000; (ii) The Environmental Protection Air Quality Regulations 2000; (iii) The Environmental Protection Water Quality Regulations 2000; (iv) The Environmental Protection Noise Management Regulations 2000; (v) The Environmental Protection Hazardous Wastes Management Regulations 2000; (vi)The Environmental Protection (Litter Enforcement) Regulations 2013; and (vii) The Environmental Protection (Expanded Polystyrene Ban) Regulations. The detail and application of the relevant regulation is explained in detail in the Environmental and Social Assessment (ESA).

  - The EPA within the Environmental Protection Authorizations Regulations establishes the list of projects that require an Environmental Authorization or Environmental Permit. Depending on the activities related to the project, their potential environmental, social as well as health and safety-related impacts and depending on whether it is an existing or new facility, the EPA may require an Environmental Impact Assessment (EIA) or an Environmental Management Plan (EMP).

  - The Agency is the responsible in assigning a category to the project based on the description of the activities that will be developed. These categories can be: (i) Category 1—low impacts; (ii) Category 2—medium impacts; (iii) Category 3—high impacts. The category assigned to the project determines the type of authorization that will be required.

  - In the case of the activities defined in this project, the category that was assigned as an Environmental Category 2. This means that the type of authorization that will be required by the EPA will be an Environmental Management Plan.

  - Under the Regional Health Facility Act of 2005, all health facilities require being licensed by the Minister of Health. It also provides for the Minister to make regulations related to licenses, renewals, maintenance and repair, additions and alterations to health facilities. The Health Facilities Regulations of 2008, enacted under the Health Facilities Licensing Act of 2007 provide specific guidance on areas of compliance by health facilities.

  - The Occupational Health and Safety Act of 1997 provides guidelines for registration and regulation of activities in establishments. The act covers areas such as administration, safety and health, hazardous chemicals, physical and biological agents, notifications of accidents and occupational diseases, offenses, penalties and procedures.

  - The EPA Guidelines for Storage, Transportation and Occupational Handling of Biomedical Waste of 2011, has the objective to provide best practices for the management of biomedical solid waste generated in Hospitals and other related health facilities. The detailed Guidelines can be found in the Annex F of the ESA.

  - Currently the Government of Guyana is working on developing the standards for Water Quality Regulations. Once these standards are defined their application will be necessary to all health facilities among other establishments.

  - The Air Quality Regulations under the Environmental Protection Act, 1996 came into force in 2000. In accordance with these Regulations anyone who emits any air contaminant in the construction, installation, operation, modification or extension of any facility related to industry, commerce, agriculture or any institution shall apply to the EPA for an environmental authorization at least ninety days before the date on which the emission is to commence. In accordance with the Regulations the EPA shall establish the desirable air pollution limits. Currently there are no nationally determined or established Air Quality Standards. However, the EPA is guided by and utilizes the World Health Organization and United States Environmental Protection Agency allowable limits which have been outlined in Annex C of the ESMP.

  - According to the national legislation, a public consultation process is only required if the EPA requests an EIA for the project.

- Consistency with IDB Policies and Directives

  - This operation is classified as Category B with moderate and temporary environmental and social impacts. The project will be implemented in existing infrastructure. There will be construction activities that will likely cause localized and short-term environmental and social impacts. These impacts will be managed through standard mitigation measures detailed in the Environmental and Social Management Plan (ESMP).

  - The Project triggers several of the IDB’s Environment and Social Safeguards policies and directives: Access to Information Policy (OP-102), Disaster Risk Management Policy (OP-704), Gender Equality in Development (OP-761), Indigenous Peoples (OP-765), and Environment Safeguards Compliance Policy (OP-703), specifically the following Directives: B.1. (Bank Policies), B.2 (Country Laws and Regulations), B.3 (Screening and Classification), B.4 (Other risks factors), B.5 (Environmental Assessment Requirements), B.6 (Consultations), B.7 (Supervision and Compliance), B.10 (Hazardous Materials), and B.11 (Pollution Prevention and Abatement). The project does not involve physical or economic displacement of beneficiaries, hence OP-710 is not applicable.

  - Annex A summarizes how the Project meets and/or will meet the requirements of the IDB’s Safeguard Policies and Directives.

- Project Standards and Requirements

  - This operation will comply with the policy, legislation and regulations of Guyana, especially those applicable to environment, disaster risk, labor and occupational, health and safety aspects as stated in the ESA. In addition, international standards such as the International Finance Corporation (IFC) General Environmental, Health, and Safety Guideline will be applied.

  - Following Direct B.5 this operation requires an ESA which includes an Environmental and Social Management Plan (ESMP). The ESA was developed and disclosed following the Bank’s Environment and Safeguards Compliance Policy (OP-703). The ESMP outlines compliance information for Environmental Health and Safety (EHS), Natural Disaster Risk Management (NDRM), and monitoring and auditing activities.

  - According to paragraph 3.3 and following the local regulation, a specific EMP will be developed for the GPHC and the CCNH. These Environmental and Social Management Plans will identify and close any gap on the local regulation and provide to any construction/remodeling activity with actions to prevent, mitigate and control any environmental and social negative impact and risk.

- Key Environmental and Social Impacts, Risks and Mitigation

- Summary of Key Environmental and Social Impacts and Risks

  - Environmental and social impacts are expected during the construction and operation phases of the project. The most negative environmental and social impacts will be related to the operation phase. The anticipated environmental and social impacts will be localized, temporary and short-term. In order to alleviate these impacts, effective mitigation measures will be put in practice. These measures will be developed specifically for the health infrastructure sector. The magnitude and intensity of the direct, indirect and cumulative impacts of the project are considered moderate. This in turn, will require the input of specialized technical knowledge and processes into the design and implementation of the activities that will be financed.

For the construction phase, the environmental and social impacts will be related directly to the construction activities. For the operation phase, the environmental and social impacts have the potential to be more complex. These are related to the presence of environmental passives like generation of hospital wastewater and hospital solid waste, and exposure to infections and diseases of workers, patients, visitors and communities. Anticipated impacts in both phases are described in detail in the next section.

- Environmental and Health and Safety Impacts and Risks and Mitigation

  - Construction phase. The infrastructure activities expected for this project in the CCNH hospital will be done over existing infrastructure. The impacts generated as a consequence of these construction activities may include: (i) soil removal; (ii) soil erosion; (iii) dust generation; (iv) vibration; (v) noise; (vi) debris and hazardous materials; (vii) surface and groundwater contamination; (viii) use of water for construction activities; (iv) community disturbance due to the increase of vehicle traffic and heavy equipment; (x) generation of wastewater (black and gray); (xi) domestic waste by daily activities of personnel involved in the works; (xii) generation of solid waste from residual construction materials (cement, concrete, stone, sand, iron, wood, boxes, bags); and (xiii) occupational health and safety hazards for the workforce; (xiv) emission of greenhouse gases  during construction by heavy machinery; (xv) fuel and lubricant spills.

  - Operation phase. The actions expected in this phase might generate negative impacts and risks which include: (i) generation of domestic solid waste; (ii) generation of hospital waste (infectious, pharmaceutical, chemical and sharps); (iii) common wastewater generated from daily activities of the hospital staff, patients and visitors; (iv) generation of hospital wastewater contaminated by activities in delivery rooms, and laboratories; (v) increased demand for power and water in the area; (vi) power shortages; (vii) air emissions from incinerators; (viii) occupational health and safety hazards for the workforce.

- Social Impacts and Risks

  - Construction Phase. The main risks during this stage are related to the safety of workers on the site, neighbors and pedestrians. The working conditions of construction workers, the lack of procedures and practices for occupational safety and health, could cause accidents affecting the workers and the public. The presence of workers in neighborhoods causes concern for the safety of the population due to social problems that may arise.

  - Operation Phase. A possible social impact during this phase is related to the increase of vehicular traffic and pedestrians, which in turn can result in an increase of accidents. The increase of the flow of patients and visitors can result in an increase of informal commerce in the surrounding areas of the hospitals.

## Natural Disasters Risks and Climate Change

  - The operation has been classified as moderate in terms of Disaster Risk. This classification was assigned because of the potential natural hazards—like floods, that may impact the project. In the case of the GPHC, there has been some flooding recorded only during extreme heavy rainfall periods. While for the CCNH, there are no records of flooding events. The Global Climate Models (GCMs) predict more intense weather events that could result in an increase of the rainfall in countries like Guyana.

  - For these reasons and in order to mitigate possible natural disaster risks, appropriate measures will be considered during the construction phase. Some actions may include

raising the floor, curbing the walls in the buildings and installing adequate drainage systems. General specifications to these actions are be defined in the ESMP. In addition and in compliance with the recommendation for a moderate disaster risk project, a rapid Disaster Risk Assessment and Disaster Risk Management Plan will be prepared and will be shared with the Executing Agency and the contractors.

- Other Risks

  - The project poses additional risks for the Executing Agency regarding the environmental and social management of the operation, as the country needs to strengthen its environmental management system in the health sector. It is anticipated that this risk will be addressed with the creation of a Sub-committee in the project’s Steering Committee. This Sub-committee will be focused on environmental and social matters and will have an environmental and social specialist as part of the team. The conformation of this Sub-committee is stated as a condition prior to disbursement detailed in Section VI.

  - Additional risks are related to the long-term sustainability of the operation, especially in the long term solution for sanitation and waste management in both hospitals. To address this, long term sustainability proposals are discussed in the ESA and the ESMP.

- Positive Impacts

  - The project will help improve the health conditions of the population at the regional level in Guyana. The improvement of the health infrastructure will integrate relevant regulations, as well as, social and environmental standards during construction and operation stages. In addition, this project will include the social participation of the community to review and to be informed of the measures that will be taken for the implementation of the ESMP. Specifically, throughout this operation, the socialization with the affected community will permit to reduce the problem related to air pollution consequence of the use of incinerators described in paragraph 2.15.

- IDB Additionality

  - In addition to the benefits that the operation will bring by improving the health conditions in the Guyana population, the Bank’s intervention will provide added value in some key social and environmental aspects. The added value will be focused on strengthening and improving the environmental and social management practices in both hospitals. In order to achieve these, specific actions will be implemented to provide long term sustainability solutions for the management and sanitation issues of these two hospitals. These actions will include the improvement of the waste and wastewater management systems to ensure that best practices are being used. It will also include water testing to guarantee the quality of water, implementation of energy and water efficiency practices, and the limitation of atmospheric emissions from incinerators.

- Management and Monitoring of Environmental, Social, Health and Safety and Labor Impacts and Risks

- Description of Management Systems and Plans

  - Environmental and Social Management Plan (ESMP). The Project will operate under the ESMP developed within the ESA which is in line with the requirements of the safeguards policies of the Inter-American Development Bank (IDB) and the Guyana Environmental Protection Act.

  - The ESMP includes coordination and planning activities, as well as, it defines clear functions and roles of the personnel of the hospitals. It also incorporates protection, mitigation and improvement measures. These measures include: (i) non-infectious and infectious waste management; (ii) wastewater management; (iii) efficient use of resources (water and energy); (iv) air emissions; and (vi) safety and occupational health.

  - The ESMP includes practices based on the IFC’s Environmental, Health and Safety Guidelines for Health infrastructure. In addition, it includes a Natural Disaster Risk Management Plan.

  - For the construction phase, the ESMP includes regular monitoring and quarterly reports of the facilities. For the construction activities, the concerns are related to noise, air emissions, traffic issues, waste management, occupational health and safety, labor performance, and trainings.

  - During the operation phase, the ESMP will contain procedures to strengthen the existing environmental practices of the hospitals. The objective of the ESMP is to address all the environmental and social risks and impacts that are generated, and implement plans/programs in order to develop good practices. These will include:

- Hospital Solid Waste Management. Internal and external waste management generated by the regular operation of the hospitals. This plan will follow local regulation and will be compatible with the IFC recommended standards for this type of operation.

- Wastewater Management. For the management of the hospital wastewater, this project will include activities like oil filtering and waste segregation to minimize the entry of solid waste into the wastewater stream.

- Air Emissions.  For the management of the emissions generated by the existing incinerators, it will be necessary to monitored them to ensure compliance with local regulations. The plan to manage these emissions will be compatible with the standards recommended by the IFC for this type of operations.

- Energy and Water Efficiency. It will be promoted the efficient use of energy and water for both hospitals. This will be done to reduce the energy and water consumption and encourage the sustainable use of these resources.

- Disaster Risk Management Plan. This plan will provide effective measures (See 4.7) for the management of potential natural hazards like floods that could affect both hospitals. The plan will outline specific measures for the construction activities in the CCNH, and for the equipment in the GPHC.

- Public Consultations. In order to comply with the Bank’s directive B.6 regarding public consultation, meetings with community members and local authorities will be conducted. The consultation sessions will provide an opportunity for interested people to learn about the project’s environmental and social management plan and have their doubts and concerns addressed by company representatives.  Community engagement will continue through the construction phase.

- Community Relations Plan. The goal of this plan is to establish community participation mechanisms and build positive relationships with interested groups to avoid or minimize potential social conflict situations during project execution. This plan provides both a general framework and specific procedural guidance for a continuous dialogue between the local population and representatives of the company.

- Grievance Mechanism. The project will implement a Grievance Mechanism to allow stakeholders an opportunity to voice their opinions, concerns, complaints, or comments outside of the public consultation meetings and throughout the construction phase of the project.  These comments will be recorded, as well as the Project’s responses to these comments.  Issues will be tracked to determine how the Project responds to complaints and interacts with the complainant to resolve outstanding issues.  The Grievance Mechanism will be accessible to individuals impacted by the project.

- Health and Safety. The project will incorporate health and safety practices in both hospitals to ensure the safety of their workers, patients and visitors. These measures will be in compliance with the best practices available in the local regulation as well as in international guidelines.

- Monitoring and Supervision

  - The monitoring and supervision activities for this project are described in the ESMP. The environmental and social monitoring and supervision of the project will be carried out by an Environmental Management Sub-Committee as part of the project’s Steering Committee, which will be institutionalized as part of the requirements of this loan. This Sub-Committee will be the entity responsible to conduct permanent monitoring of the implementation of the relevant plans and guidelines of the ESMP.

  - The Borrower will present to the Bank semi-annual reports of the compliance status of the objectives and results of the Annual Operative Plan (AOP) and the Monitoring Program Report (MPR). These reports will include the monitoring of the environmental and social aspects and the implementation of mitigation measures.

  - The Bank, through the Environmental Safeguards Unit (VPS/ESG) will conduct supervision missions once the project is approved by the bank. These missions will be during the construction and operating phase, to ensure that the environmental and social safeguards policies are implemented and are being complied.

- Requirements to be Included in the Legal Agreements

- Prior to Board

- A public consultation on the ESA/ESMP will be carried out starting on October of 2016.

  - Prior to First Disbursement

- The Executing Agency shall provide supporting documentation of the establishment of a Committee to address environmental, social and health and occupational safety issues. The supporting documentation required will include the objective of the commission, the institutions that will be involved, the structure and roles. As part of the committee’s structure, it will be required the appointment of a Principal Coordinator that will be the liaison with the Bank.

  - Prior to beginning construction work of Component 2

- In addition to the eligibility parameters agreed with the Executing Agency, before issuing the no objection to the execution of activities to the hospitals, the Executing Agency shall submit to the Bank the following supporting documentation:

  - The implementation of the ESMP for both hospitals. The ESMP will include an organizational structure with roles, and responsibilities defined for the implementation and management of the proposed plans that have been defined in the ESA.

  - Proposal for the design of an alternative wastewater management system for both hospitals.

  - For the construction phase, the Contractor(s) shall prepare and submit prior to initiation of construction, a Risk Management and Emergency Response Plan (RM&ERP) that will be reviewed by the Executing Agency and the Bank. It will outline the procedures for responding to environmental and social emergencies that may occur as a result of unforeseeable circumstances, such as a spill of hazardous materials or significant erosion events. The RM&ERP will provide procedures and will include at least the following aspects:

  - Health and safety of local residents, and employees;

  - Quality of soils, surface and groundwater;

  - Protection of environmentally sensitive areas; and

  - System for managing movement of construction personnel, public and traffic in an emergency situation.

  - Emergency procedures during operation for fire and other hazards.

  - Throughout the Life of the Loan

  - The IDB will require in the Loan Contract that the Project, the Beneficiary and the Executing Agency specified above, at all times during the life of the Grant Agreement, comply with the following requirements:

- All applicable environmental, social, health and safety, and labor regulatory requirements of Guyana.

- All relevant IDB policies such as the Environment and Safeguards Compliance Policy (OP-703), the Disaster Risk Management Policy (OP-704) and the Disclosure of Information Policy (OP-102), and the Gender and Equity in Development Policy (OP-270) and their respective guidelines

- All the plans and programs included in the Environmental and Social Management Plan (ESMP).

- The Works and Equipment Maintenance Plan that shall include a status report of all the works and equipment related to the environmental management improvement. This plan will also include environmental guidelines and occupational health and safety measures, to prevent and mitigate any negative impact during maintenance activities.

  - Allow the IDB, whether directly or through the contracting of consulting services, carry out supervision activities, including environmental and social audits of the Project, in order to confirm compliance with the environmental and social obligations set forth in the Loan

  - Monitoring and Reporting

  - The Executing Agency will provide evidence of supervision and oversight of the contractors for the implementation of the activities defined in Component 2.

  - Monitoring and Reporting, will include a brief section on environmental and social issues that might arise during construction phase, including any emergency situation. In case there are non-compliances found, the Executing Agency must prepare a Corrective Action Plan.

Annex A -Compliance of Project with IDB Safeguard Requirements

| Operational Policy | Aspect (if applicable) | Project Compliance Status |
| --- | --- | --- |
| - OP-702 |  |  |
| Access to Information | Disclosure of environmental and social aspects of the Project through the Bank's website | Compliance requirements met. The draft version of the Environmental and Social Analysis (ESA) and Environmental and Social Management Framework (ESMP) was published on June 23, 2016 prior to the analysis mission that took place in Georgetown from June 26th to July 1st. The final version of the ESA and ESMP were published on August 26, 2016. The ESA and ESMP can be found on: http://www.iadb.org/en/projects/project-description-title,1303.html?id=GY-L1058 |
| - OP-703 |  |  |
| B.1. Bank Policies | Compliance with policy guidelines | Compliance requirements met. According to the ESA and the field visit, the Project meets the guidelines of the Environmental Policy and Safeguards Compliance Policy (OP -703) and is consistent with the relevant provisions of other Bank policies. |
| B.2. Country laws and regulations | National legislation | Compliance requirements expected to be met. The project must comply with Guyanese laws and regulations on on environment and occupational, safety and health as stated in the ESA and the ESMP. |
| B.3. Screening and Classification | Classification of the risk level | Compliance requirement met. The Project has been screened for its potential environmental and social impacts and has been classified as a Category B operation. |
| B.4. Other Risk Factors | Executing Agency | Compliance requirement expected to be met. Risks on the environmental and social management of the operation for the Executing Agency. The risks will be addressed through the inclusion of clauses in the institutional arrangements of the conformation of the Sub-Committee which will be in charge of dealing specifically with environmental and social matters. The capacity building for both hospitals will take place Is through this Sub-Committee. |
| B5. Environmental Assessment Requirements | Environmental and Social Assessment (ESA) and ESMP | Compliance requirements expected to be met. A draft version of the Environmental and Social Assessment and the Environmental Social Management Plan has been prepared for the operation. The draft version has been disclosed. |
| B.6 Consultation | Stakeholder engagement Plan | Compliance requirements expected to be met. A consultation process is scheduled starting on October of 2016. The Team will share the ESA and the ESMP with the MoPH once we have the final version of these documents. |
| B.7. Supervision and Compliance | Supervision of Construction and Operation Phase | Compliance requirements expected to be met. The Bank will supervise and monitor the adequate implementation of the ESMP through the Executing Agency. |
| B.8. Transboundary Impacts | Not applicable | Not applicable. There are no transboundary environmental and social issues related to this project. |
| B.9. Natural Habitats and Cultural Sites | Not applicable | Not applicable. The project is located in urbanized areas that are not sensitive in natural habitat matters, cultural environments or archeological areas. |
| B.10. Hazardous Materials | Generation of infectious waste and wastewater | Compliance requirements expected to be met. The Executing Agency will implement the waste and wastewater management plan for the two hospitals. The ESMP will be the tool to ensure for the implementation of all the necessary measures. |
| B.11. Pollution Prevention and Abatement | Generation of gas emissions into the atmosphere, noise and solid waste. | Compliance requirements expected to be met. The ESMP developed for this project will contain specific measures for each activity in all the phases of the project. These measures will include mitigation and best practices guidelines for solid waste management, gas emissions and generation of dust and noise. In addition and prior to the activities of the loan that are pertinent to this ESMR, an audit of the existing facilities will be carried out to ensure an optimal execution of activities. |
| B.12. Project Under Construction | Not applicable | Not applicable. The hospitals of this project are already constructed. |
| B.13. Noninvestment Lending and Flexible Lending Instruments | Not applicable | Not applicable. The transaction type of this operation is an Investment Loan. |
| B.14. Multi Phase and Repeat Loans | Not applicable | Not applicable. The project is not part of a multi-phase operation. |
| B.15. Co-financing Operations | Not applicable | Not applicable. There will not be other borrowers or lending institutions participating. |
| B.16 In-country Systems | Not applicable | Not applicable. The operation will not use the country system of Guyana. |
| B.17 Procurement | Procurement of goods and services | Compliance requirements to be met. The Executing Agency should include environmental requirements in the descriptive text for the design, construction and operation of infrastructure (especially those requirements related to wastewater treatment and handling hospital waste). |
| - OP-704 |  |  |
| Disaster Risk Management | Operation classifies as Moderate | Compliance requirements expected to be met. The operation is expected to have moderate vulnerability to disaster risks, and the project is not anticipated to exacerbate these risks. However, mitigation measures are included in the ESMP to address flooding. |
| - OP-710 |  |  |
| Involuntary Resettlement | Not applicable | Not applicable. For this operation it is not expected any type of involuntary resettlement or economic displacement to take place. |
| - OP-761 |  |  |
| Gender Equality | Opportunity for equality | Compliance requirements expected to be met. The project represents a benefit for women given that the goal is to increase the supply and improve the quality of services for the population of Guyana. This project will contribute to promote gender equality by increasing women’s access and use of quality reproductive and maternal health services, by enhancing women’s and girl’s capacity to make informed decisions, by reducing adolescent pregnancy, and by promoting the involvement of men in reproductive, maternal, and neonatal care activities |
| - OP-765 |  |  |
| Indigenous Peoples | Not applicable | Compliance requirements expected to be met. The activities to be financed by the project are expected to improve the access of indigenous communities to health services. It is also expected that the project will not have a direct or indirect adverse impact on indigenous peoples. |

The distribution of repellent and insecticide-treated mosquito nets for the prevention of malaria and other mosquito-borne diseases, such as dengue and zika, will be included.

Link to access the ESA can be found in: http://www.iadb.org/en/projects/project-description-title,1303.html?id=GY-L1058