# Document of the Inter-American Development Bank

GUYANA

SUPPORT TO IMPROVE MATERNAL AND CHILD HEALTH

GY-L1058

- monitoring and evaluation plan

This document was prepared by: Sandro Parodi (SPH/CDR), Madiery Vásquez (SPH/CDR), Diego Rios-Zertuche (SPH/CPN); and Marcella Distrutti (SCL/SPH).

Content

Monitoring and Evaluation Plan Summary

- Introduction

- Monitoring

  - Indicators

  - Data Collection and Instruments

  - Health Facility Surveys

  - Reporting Monitoring Results

  - Monitoring Coordination, Work Plan and Budget

- Evaluation

  - Main Evaluation Question(s)

  - Existing Knowledge

  - Key Outcome Indicators

  - Evaluation Methodology

  - Technical Aspects of Selected Methodology

  - Reporting Evaluation Results

  - Evaluation Coordination, Work Plan and Budget

References

Abbreviations

AMTSL: Active Management of the Third Stage of Labor

AOG: Auditor General’s Office

AOP: Annual Operating Plan

CEA: Cost-Effectiveness Analysis

DALY: Disability-Adjusted Life Year

FP: Family Planning

GDP: Gross Domestic Product

ICER: Incremental Cost-Effectiveness Ratio

IHCS: Integrated Health Care Services

M&E: Monitoring and Evaluation

MCH: Maternal and Child Health

MPH: Ministry of Public Health

PCR: Project Completion Report

PEP: Project Execution Plan

PMR: Progress Monitoring Report

QI: Quality Improvement

SEPA: Procurement Plan Execution System (Sistema de Ejecución de Planes de Adquisiciones)

SPH: Social Protection and Health

- Introduction

  - This document describes the monitoring and evaluation arrangements of the investment loan project Support to Improve Maternal and Child Health (GY-L1058) and it aims to define a strategy to follow up and assess the implementation of the main activities agreed by the Bank and the Government of Guyana. The objective of the project is to contribute to the reduction of maternal, perinatal, and neonatal deaths in Guyana. To meet this objective, the project has identified the following components: (i) strengthening reproductive, maternal, and neonatal health services (sub-component 1: access and use of reproductive, maternal, and neonatal health services; sub-component 2: quality of reproductive, maternal, and neonatal health services); (ii) strengthening the healthcare network; and (iii) administration, auditing, and evaluation.

  - The monitoring arrangements, including key monitoring tools and responsibilities, are described in the second section of this document. The Ministry of Public Health (MPH), through its Maternal and Child Health (MCH) Unit and in coordination with the Bank, will be responsible for the monitoring activities. The MCH Unit will provide the Bank all the required information to assess the project execution. The Bank will supervise the execution and provide technical assistance when needed. The Bank and the borrower have agreed to use the Results Matrix and the activities defined in the Progress Monitoring Report (PMR) to monitor the operation. Other key monitoring tools are: (i) Semi-annual Monitoring Reports; (ii) Financial Audits Reports; (iii) Project Execution Plan (PEP); (iv) Procurement Plan; (v) Project Completion Report (PCR); and (vii) Supervision and monitoring meetings.

  - The third section presents the evaluation arrangements. A quasi-experimental evaluation will be performed at the end of the project to estimate the impact of one major project sub-component. The chosen methodology is synthetic control and the preliminary identified outcome indicators are those of the Result Matrix. This evaluation will be financed by the loan with close IDB’s technical support.

- Monitoring

The purpose of this section is to describe the monitoring process.

  - Indicators

  - The Result Matrix proposes a series of indicators to monitor the performance of the loan operation. Those indicators are proxies to capture outputs, outcomes and results. Table 1 presents the monitoring indicators agreed between the MPH and the Bank. The specific construction and formula for each indicator would be described in the Indicators Manual, to be included as an annex in the Operations Manual. A preliminary version of the Indicators Manual is attached at the end of this document (see Annex II).

  - Estimation of Maternal and Neonatal Mortality Targets

  - To estimate project targets for reductions in Guyana’s maternal mortality ratio and neonatal mortality rate, we followed several steps. First, we considered global and regional estimates for the annual change in mortality in different socioeconomic percentiles. Then, we estimated the national annual change in mortality in Guyana. The data is summarized in Annex I: Tables 1-2 for maternal mortality and Annex 1: Tables 3-4 for neonatal mortality. We considered the national annual change as the baseline change with no intervention. Our estimate is a combination of the expected change with no intervention plus the expected change with intervention. We also considered literature on international experiences for the reduction of maternal and neonatal mortality. The final target is based on expert judgment considering all information sources.

  - Data Collection and Instruments

  - The Result Matrix will be fed both by primary and secondary data. The MPH will be responsible for compiling the existing data and consolidating them in progress reports that must be submitted to the Bank according to this Monitoring and Evaluation (M&E) Plan. The MPH will share with the Bank official documentation on statistics and administrative records to support the update of the Results Matrix. Identified secondary sources are the MCH Reports, the Clinic Summary Reports, the Ministry of Health Statistical Bulletin, and the Chief Medical Officer Reports (see Table 1). The MPH must coordinate all the required arrangements to gather the information needed to meet the deadlines agreed with the Bank. Additionally, loan resources have been allocated for two rounds of Health Facilities Surveys. Those surveys will collect baseline and follow up information on the quality of care provided at the health facilities. The Bank will provide technical support during design and implementation of both surveys.

  - Health Facility Surveys

  - The objective of the health facility surveys is to collect before and after data to see the progress contributed by the project’s interventions. The surveys would collect data mainly related to quality of care, which is not available through other sources. Important components of the survey include the observation of available medicines, supplies and equipment in the facility, the review of administrative records (such as stock cards), and the review of medical records to analyze treatments and processes of care.

  - Methods. Surveys would be collected using standardized data collection instruments with computer assisted personal interviewing (CAPI) systems. CAPI supports skip patterns, inter-question answer consistency, and data entry ranges. The introduction of CAPI reduces survey time by prompting only relevant questions maintain a logical pattern across questions and decrease data entry errors. In addition, data may be uploaded in short time periods, allowing for quality assurance measures to be applied. Health facility surveys may be collected through different methods (or a combination of methods), depending on operational criteria to ensure the availability of timely quality data. These methods could include: 1) internal monitoring mechanisms by quality improvement teams established through the provision of technical assistance, 2) trained monitoring and evaluation staff from the Ministry of Health, or 3) external surveyors specifically trained for data collection.

  - Sampling. A stratified random sample of health facilities will be collected in intervention areas. The sample will be stratified according to three levels of Essential Obstetric and Neonatal Care (EONC): ambulatory, basic and complete. Depending on the number of facilities in each stratum, all facilities of that level may be surveyed. In each health facility selected in the sample, administrative records and medical records would be selected through systematic sampling methods, according to the cases needed, and reviewed. A minimum sample of 30 health facilities would be expected to be collected. In each facility, 20 records per case would be expected to be reviewed. Considering that there are around 153 health facilities in intervention regions (3, 4, and 9), with a confidence level of 90% and a percentage of 50%, the expected confidence interval would be around 13.3% for facility level indicators. For other indicators, the confidence interval would depend on the prevalence level of each case expected.

Table 1.

Results Matrix

Expected Impacts

| Indicators | Unit | Baseline |  | Goals |  | Means of verification | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Value | Year | Value | Year |  |  |
| Objective: Contribute to the reduction of maternal, perinatal, and neonatal deaths in Guyana by 2021 |  |  |  |  |  |  |  |
| Maternal Mortality Ratio (MMR). | Maternal deaths x 100,000 | 121.7 | 2014 | 87.9 | 2021 | Chief Medical Officer (CMO) Report | MMR at the national level estimated using preliminary data from the CMO Report. |
| Neonatal Mortality Rate (NMR). | Neonatal deaths x 1,000 | 21.7 | 2014 | 15.2 | 2021 | CMO Report | NMR at the national level estimated using preliminary data from the CMO Report. |

Expected Results

| Indicator | Unit | Baseline |  | Goals |  | Means of verification | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Value | Year | Value | Year |  |  |
| Component 1. StrengthenING reproductive, maternal, and neonatal health services |  |  |  |  |  |  |  |
| Sub-Component 1.1. Objective: Increase access and use of reproductive, maternal, and neonatal health services |  |  |  |  |  |  |  |
| First time users of family planning methods for the year. | Number of clients | 5,799 | 2014 | 9,799 | 2021 | MCH Report, Clinic Summary Report (CSR) | Calculated for intervention areas. |
| Pregnant women with anemia at first antenatal visit (hemoglobin under 11 g/dl). | % | 21.1% | 2014 | 11.1% | 2021 | MCH Report, CSR | Calculated for intervention areas. Excludes “result not known”. |
| Births from adolescent mothers (19 years and younger). | % | 19.1% | 2012 | 15.1% | 2021 | Vital Statistics, Ministry of Health Statistical Bulletin | Calculated for intervention areas. |
| Women who receive antenatal care before 12 weeks pregnant. | % | 23.9% | 2014 | 30.9% | 2021 | MCH Report, CSR | Calculated for intervention areas. Excludes “unknown”. |
| Women who gave birth in a health facility in the rural interior. | % | 15.8% | 2014 | 25.8% | 2021 | MCH Report, CSR | Calculated for region 9. Numerator considers “hospital” and “health center” deliveries. |
| Sub-Component 1.2. Objective: Improve quality of reproductive, maternal, and neonatal health services |  |  |  |  |  |  |  |
| Pregnant women receiving quality antenatal care according to best practices. | % | (1) | 2017 | +15PP | 2021 | Health Facility Surveys (HFS), Medical Record Review (MRR) module | Calculated for health facilities in intervention areas that provide antenatal care. |
| Deliveries for which the partograph was used according to best practices. | % | (1) | 2017 | +20PP | 2021 | HFS, MRR | Calculated for health facilities in intervention areas that provide routine birth services. |
| Institutional deliveries for which oxytocin was administered immediately following birth as part of Active Management of the Third Stage of Labor. | % | (1) | 2017 | 85% | 2021 | HFS, MRR | Calculated for health facilities in intervention areas that provide routine birth services. |
| Institutional deliveries for which immediate neonatal care was provided to the infant according to the norms | % | (1) | 2017 | 85% | 2021 | HFS, MRR | Calculated for health facilities in intervention areas that provide routine birth services. |
| Neonates with complications (prematurity, low birth weight, asphyxia and sepsis) managed according to norms. | % | (1) | 2017 | +20PP | 2021 | HFS, MRR | Calculated for health facilities in intervention areas that provide routine birth services. |
| Obstetric complications (sepsis, hemorrhage, severe pre-eclampsia and eclampsia) managed according to norms. | % | (1) | 2017 | +20PP | 2021 | HFS, MRR | Calculated for health facilities in intervention areas that provide routine birth services. |
| Women that received immediate postpartum care according to best practices (every 15 minutes in the first hour and every 30 minutes in the second hour). | % | (1) | 2017 | 85% | 2021 | HFS, MRR | Calculated for health facilities in intervention areas that provide routine birth services. |
| Component 2. Strengthening the healthcare network |  |  |  |  |  |  |  |
| Objective: Increase the effectiveness of the maternal and neonatal healthcare network |  |  |  |  |  |  |  |
| Women that are referred to the national hospital for obstetric conditions that could have been resolved at another level of care. | % | (1) | 2017 | Decrease by 50PP | 2021 | HFS, MRR | Calculated for health facilities in intervention areas. |
| Health facilities with continuous availability of inputs and equipment to provide essential and emergency obstetric and neonatal care. | % | (1) | 2017 | 85% | 2021 | HFS, MRR | Calculated for health facilities in intervention areas that provide routine birth services. |
| Health facilities with continuous availability of inputs and equipment to provide quality antenatal and post-natal care. | % | (1) | 2017 | 85% | 2021 | HFS, MRR | Calculated for health facilities in intervention areas that provide antenatal and postnatal care. |

(1) Data will be updated with the baseline Health Facility Survey results.

PP: Percentage Points to increase over baseline value.

Products

| Products | Estimated Cost (US$) | Unit | Baseline |  | Y1 |  |  | Y2 |  |  | Y3 |  | Y4 |  |  | Y5 |  |  | Final goal | Means of verification | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component 1. Strengthening reproductive, maternal, and neonatal health services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-Component 1.1. Access and use of reproductive, maternal, and neonatal health services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Community health workers (CHWs) trained and equipped to provide reproductive, maternal, and neonatal services. | 470.000 | CHWs | 0 | 00 |  | 200 |  |  | 225 |  |  | 0 |  |  | 0 |  |  | 425 |  | Report from technical assistance with documental evidence that CHWs have been trained and equipped | Calculated for CHWs in intervention areas. |
| Communities with plans for institutional birth implemented. | 225.000 | Communities | 0 | 0 |  | 50 |  |  | 38 |  |  | 0 |  |  | 0 |  |  | 88 |  | Report from technical assistance with documental evidence that plans have been implemented | Calculated for communities in region 9. “Implemented” refers to communities that have designed and operationalized plans for institutional birth. |
| Communities with communication strategy for behavior change implemented. | 535.000 | Communities | 0 | 0 |  | 50 |  |  | 100 |  |  | 75 |  |  | 0 |  |  | 225 |  | Report from technical assistance with documental evidence that the communication strategy was aired in each community | ”Implemented” refers to communities that have received the messages/spots aired by the communication strategy by radio, television, social media, printed media or others. |
| Sub-Component 1.2. Quality of reproductive, maternal, and neonatal health services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Health facilities with integrated health care strategy for women of reproductive age implemented. | 255.000 | Health facilities | 0 | 0 |  | 50 |  |  | 50 |  |  | 43 |  |  | 0 |  |  | 143 |  | Report from technical assistance with documental evidence that guidelines and procedures have been implemented | Calculated for health centers in intervention areas that provide primary care. “Implemented” refers to health facilities that have updated and operationalized guidelines and procedures on the health of women of reproductive age. |
| Health facilities with new family planning strategy implemented. | 170.000 | Health facilities | 0 | 0 |  | 50 |  |  | 50 |  |  | 43 |  |  | 0 |  |  | 143 |  | Report from technical assistance with documental evidence that guidelines and procedures have been implemented | Calculated for health centers in intervention areas that provide primary care. “Implemented” refers to health facilities that have updated and operationalized guidelines and procedures for family planning. |
| Health facilities with updated model for prenatal, birth, postnatal, and post-partum care implemented. | 125.000 | Health facilities | 0 | 0 |  | 100 |  |  | 50 |  |  | 0 |  |  | 0 |  |  | 150 |  | Report from technical assistance with documental evidence that guidelines and procedures have been implemented. | Calculated for health facilities in intervention areas. “Implemented” refers to health facilities that have updated and operationalized guidelines and procedures for prenatal, birth, postnatal, and post-partum care. |
| Hospitals with Quality Improvement Strategy (QIS) for maternal and neonatal health implemented. | 455.000 | Hospitals | 0 | 0 |  | 1 |  |  | 3 |  |  | 3 |  |  | 0 |  |  | 7 |  | Report from technical assistance with documental evidence that processes have been mapped and optimized | Calculated for hospitals in intervention areas. “Implemented” refers to hospitals that have mapped and optimized key clinical, management, and support processes. |
| Health facilities with supply chain management improved. | 100.000 | Health facilities | 0 | 0 |  | 0 |  |  | 90 |  |  | 60 |  |  | 0 |  |  | 150 |  | Report from technical assistance with documental evidence that supply chain have improved | Calculated for health facilities in intervention areas. “Improved” refers to health facilities that have adopted best practices in estimating need, planning, requesting, storing, and distributing critical supplies to the population |
| Health workforce trained to provide quality reproductive, maternal, and neonatal care. | 235.000 | Health staff | 0 | 0 |  | 120 |  |  | 90 |  |  | 46 |  |  | 0 |  |  | 256 |  | Report from technical assistance with documental evidence that workers have been trained | Calculated for health facilities in intervention areas. |
| Health facilities with health information system strengthened. | 350.000 | Health facilities | 0 | 0 |  | 0 |  |  | 60 |  |  | 60 |  |  | 30 |  |  | 150 |  | Report from technical assistance with documental evidence that health facilities have strenghtened health information system | Calculated for health facilities in intervention areas. “Strengthened” refers to health facilities that collect and report key statistics on a routine basis. |
| Component 2. Strengthening the healthcare network |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Integrated healthcare network for reproductive, maternal, and neonatal health enabled. | 759.000 | Network | 0 | 0 |  | 1 |  |  | 2 |  |  | 0 |  |  | 0 |  |  | 3 |  | Report from technical assistance with documental evidence that network has been enabled | Calculated for intervention areas. “Enabled” refers to regions that have revised and adjusted the service and referral and counter-referral networks |
| Health facilities with infrastructure improved to provide reproductive, maternal, and neonatal services. | 500.000 | Health facilities | 0 | 0 |  | 0 |  |  | 1 |  |  | 0 |  |  | 0 |  |  | 1 |  | Project’s semi-annual monitoring reports with documental evidence that infrastructure improvements have been concluded and that the health facility is in operation | Calculated for health facility in region 4. |
| Health facilities with equipment improved to provide reproductive, maternal, and neonatal services. | 2.250.000 | Health facilities | 0 | 0 |  | 0 |  |  | 2 |  |  | 2 |  |  | 0 |  |  | 4 |  | Project’s semi-annual monitoring reports with documental evidence that the new equipment is operating | Calculated for health facilities in intervention areas. |
| Ambulances equipped for emergency obstetric and newborn care delivered. | 225.000 | Ambulances | 0 | 0 |  | 3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 3 |  | Project’s semi-annual monitoring reports with documental evidence that ambulances are operating | Calculated for health facilities in intervention areas. |
| Component 3. Administration and Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Final evaluation conducted. | 20.000 | Evaluation | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1 |  |  | 1 |  |  | Evaluation completed and published in the Ministry’s webpage |  |
| Health facility survey conducted. | 100.000 | Survey | 0 | 1 |  |  | 0 |  |  | 0 |  |  | 0 | 1 |  |  | 2 |  |  | Survey completed and published in the Ministry’s webpage |  |

  - Reporting Monitoring Results

  - Mechanisms and instruments to report program monitoring results are:

Progress Monitoring Report (PMR). The PMR is a tool that integrates short- and medium-term information for tracking progress toward the targets set in the Results Matrix. The PMR strives to identify delays as well as early on deviations and changes needed during execution. The PMR presents metrics, budget and disbursement patterns. The MCH Unit must submit the required information to update the PMR, through the Semi-annual Monitoring Reports, no later than the first week of September and the first week of February each year of the program execution.

Semi-annual Monitoring Report. This report consists on detailed information of the level of achievement reached by project products and activities. The Semi-annual Report must include: physical and financial execution performance, difficulties encountered and institution or government official responsible for its implementation. In addition, it must present lessons learned, recommendations for feedback and activities planned for the following semester. Any actualization on the planning instruments should be included as annex. This report must be submitted within a maximum period of 30 days after the end of the corresponding semester. The executing agency is responsible for its development and delivery. The information must be presented according to the Bank system format to feed the PMR.

Financial Audit Reports. The MCH Unit will present to the Bank: (i) mid-term audited financial statements as of June 30 of each year of the project execution within the subsequent 60 days; (ii) annual audited financial statements of the project, within 120 days after fiscal year end of the executing agency; and (iii) final audited financial statements, within 120 days after the last disbursement.  The Auditor General’s Office (AOG) is currently eligible to audit all Bank-financed technical cooperation and loan operations deemed to be of low or medium complexity and risk and it will conduct the financial auditing of the project (please refer to Annex III of this project for more information – Project Fiduciary Agreements and Requirements).

Project Execution Plan (PEP). The MCH Unit, in coordination with the Bank, will elaborate the PEP. This document contains specifications, costs and dates for all the activities and products needed to achieve the project objectives. The annual version of PEP should be understood as a typical Annual Operating Plan (AOP). The MCH Unit will be trained in the management of MS PROJECT to carry out monitoring and updating of the PEP. At the beginning of each year, the Bank will review and agree on the activities to be updated. The PEP must be submitted biannually to the Bank for approval of any change.

Procurement Plan. The MCH Unit must formulate a Procurement Plan, including: (a) each contract for consulting services required to carry out the project during an initial period of at least 18 months; (b) the proposed methods for selection of consultants’ services; and (c) the related Bank review procedures. It must also include, if applicable, the methods for procurement of goods, works, and non-consulting services. Procurements must follow standard Bank policies (GN-2349-9, GN-2350-9). The MCH Unit must submit to the Bank the Procurement Plan and its actualizations for approval. It must be submitted annually through the Procurement Plan Execution System (SEPA).

Project Completion Report (PCR). This report assesses results achieved by the project, its long-term sustainability, and lessons learned to improve the design and execution of future operations. The PCR allows for a comprehensive project review from start to end, analyzing whether a project met its targets and achieved the desired development goals, as well as any challenges encountered during implementation. The PCR will be presented no more than 120 days after the last disbursement. The key inputs for the PCR are the reports compiled during execution as well as additional documents considered relevant.

Supervision and monitoring meetings. On the Bank´s behalf, the technical supervision of the program execution will be in charge of the Social Protection and Health (SPH) Division. In this regard, the MCH Unit will receive technical support from the SPH project team during the life of the project. Meetings with the authorities may be requested at the discretion of the IDB to discuss: (i) performance of the Results Matrix indicators; (ii) implementation risks identified; and (iii) any other subject identified as priority for the proper development of the operation.

  - The publication of the program monitoring results, consisting mainly of the documents described above, will be carried out gradually as the documents are presented and approved by the Bank. A file with all documents is expected to be available no later than one (1) year after the last disbursement.

  - Monitoring Coordination, Work Plan and Budget

  - Monitoring activities and responsibilities for the executing agency involves:

- Collecting, storing and delivering to the Bank information to monitor, measure and evaluate the results of the project;

- Identifying when to apply corrective or preventive actions in order to achieve the project objectives;

- Analyzing, tracking and mitigating, when possible, the project risks;

- Preserving a database of accurate and updated project deliverables and related documentation;

- Updating information on cost and schedule; and

- Monitoring the implementation of agreed changes.

  - The Bank may, if necessary, complement reports with monitoring visits and meetings with the health authorities, as described in section C of the second part of this document. A planning and monitoring and evaluation specialist will be hired by the executing agency to guarantee the implementation of this M&E Plan and establishment of monitoring and evaluation practices.

  - Table 2 shows the monitoring work plan, detailing date, budget and funding source for each activity.

Table 2

Monitoring Work Plan

| Key Monitoring Activities/Products per Activity | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Responsible | Cost (US $) | Funding |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |  |  |  |
| Progress Monitoring Report | X |  | X |  | X |  | X |  | X |  | X |  | X |  | X |  | X |  | X |  | IDB | Fixed cost | GY-L1058 |
| Semi-annual Monitoring Report | X |  | X |  | X |  | X |  | X |  | X |  | X |  | X |  | X |  | X |  | MCH Unit | Fixed cost | GY-L1058 |
| Project Execution Plan | X |  | X |  | X |  | X |  | X |  | X |  | X |  | X |  | X |  | X |  | MCH Unit | Fixed cost | GY-L1058 |
| Procurement Plan | X |  |  |  | X |  |  |  | X |  |  |  | X |  |  |  | X |  |  |  | MCH Unit | Fixed cost | GY-L1058 |
| Project Completion Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | IDB | Fixed cost | GY-L1058 |
| Supervision and monitoring meetings | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | IDB | Fixed cost | GY-L1058 |
| Monitoring and evaluation specialist | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | MCH Unit | 172,800 | GY-L1058 |
| Health Facilities Surveys | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  | IDB | 100,000 | GY-L1058 |
| Total Cost: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 272,800 |  |

  - Evaluation

The purpose of this section is to detail the evaluation methodology and the implementation of the evaluation.

- Main Evaluation Question(s)

  - The main evaluation question is related to the effectiveness of the interventions implemented in the Guyana’s rural interior to improve access and use of health services amongst indigenous people. There is very little knowledge on the literature regarding what works to improve the health of indigenous people; hence, this project will focus on the interventions implemented in region 9 to contribute to answering this question.

- Existing Knowledge

  - There is an extensive body of literature analyzing the effectiveness of the interventions proposed in this project. The 2006 Lancet Maternal Survival Series and the 2014 Lancet Neonatal Survival Series, for instance, include very detailed and evidence-based information on what works to reduce maternal and neonatal mortality. These are based on reviews of cost-effective interventions across the continuum of care (preconception, antenatal, intrapartum, and immediate postnatal period) in developing countries (see Bhutta et al. 2014 and Campbell et al. 2006). Delivery platforms and means of distribution are also analyzed; for instance which interventions are effective if delivered at the community level (by community health workers) or at a health post, health center, and/or hospital level. The focus on developing countries occurs because maternal and neonatal mortality is a challenge that affects developing countries disproportionally. Hence, most interventions are evaluated in this context. The factors contributing to maternal and neonatal mortality differ little across countries; they are usually related to: (i) difficulties to access and use health services in a timely manner due to supply (e.g. distance to health facility, unavailability of transport, unavailability of skilled personnel, and unavailability of culturally-appropriate services) or demand issues (e.g. money for treatment or transport, insecurity, gender matters); and (ii) insufficient quality of services. For instance, most maternal deaths occur in hospitals, either because the woman arrived in a moribund state too late to benefit from emergency care or because the woman developed a complication in the intrapartum period and did not receive the quality emergency care she needed (Ronsmans et al. 2006). Given that the main causes of maternal and neonatal deaths are very similar across low and low-middle income countries, and that these share common elements (e.g. low level and inefficient public health spending, low investment in infrastructure and equipment, low salaries for health workers, low level of institutional development, and social inequalities), interventions proven effective in one country are generally applicable to others.

  - The Lancet series provides evidence for a series of interventions, such as: (i) folic acid and iron supplementation, screening/preventive consultations, deworming, and family planning services for non-pregnant women of reproductive age; (ii) folic acid and iron supplementation, advice on planning for maternal emergencies; advice on maternal danger signs; advice on early referral for maternal emergencies; advice on early referral for newborn emergencies; advice on warmth and promotion of early and exclusive breastfeeding; advice on contraception; and antenatal care exams (urine testing, blood pressure measurement, etc.) for all pregnant women; (iii) clean delivery technique and environment; early detection of maternal and neonatal complications; referral of maternal and complications; resuscitation of newborns; use of partograph; and active management of third stage of labour for all intrapartum women; and (iv) advice on postnatal maternal danger signs; advice on contraception; advice on neonatal danger signs; advice on breastfeeding; advice on iron folate supplementation; and advice on insecticide treated bed nets for all postpartum women, among many others (Campbell et al. 2006).

  - This project has also drawn extensively from Safe Motherhood Strategies: a Review of the Evidence, published by De Brouwere and Van Lerberghe in 2001, not only analyzing the factors behind the spectacular declines in maternal mortality experienced by countries such as Malaysia, Siri Lanka, and Thailand, which have been factored in the project’s discussions related to the magnitude of effect expected with the proposed interventions, but also analyzing the evidence on strategies. For instance: (i) evidence on antenatal care strategies; (ii) evidence on the importance of skilled birth attendance at delivery, which informed decisions regarding the promotion of institutional births in Guyana’s rural interior and the training of health personnel, as well as decisions regarding key investments in infrastructure and equipment, which are crucial to guarantee an enabling environment; and (iii) evidence on task-shifting, which has informed decisions regarding the revision of the roles and responsibilities of health workers to identify opportunities to optimize the use of different cadres of health professionals.

  - Other brief literature reviews have been conducted. Regarding demand-side incentives, for example, Van den akker et al. 2011 analyzed the impact of locally valued, non-monetary incentives on the number of deliveries in health facilities in rural areas of Malawi (the package included soap, a baby blanket and a traditional baby wrap, costing approximately US$7). The number of institutional deliveries increased by 78% over a 2-year period. In Ethiopia, the provision of a bar of soap, a bucket, a mosquito net, sugar, cooking oil, a jerry can and a delivery kit (at a total cost of the incentive at US$ 10 for four visits) increased the number of first antenatal care visits by 48% in the first year and by 60% in the second year (Khogali et al. 2014).  In Zambia, where only 56% of rural women deliver in a health facility, a clustered randomized controlled trial was used to measure the impact of mama kits (valued at $4 USD and containing a cloth, a nappy, and a baby blanket) on facility delivery rates in thirty rural health facilities. Mama kits increased institutional deliveries by 47.4% (Wang et al. 2016). Regarding transportation vouchers for delivery and postnatal care visits, preliminary evidence from Chiapas, Mexico, in the context of the Mesoamerican Health Initiative (MHI), shows promising results (Bernal et al., forthcoming).

  - Community-based mobilization and initiatives have also been proven effective to improve maternal and neonatal outcomes (Ahluwalia et al. 2004, Bhutta et al. 2011). Regarding plans for birth and emergency transport, diverse studies show that community participation and support for community-based emergency transport systems have led to better care for pregnant women and sustained links between the communities and health facilities, reducing maternal and infant morbidity and mortality (Magoma et al. 2010, Moran et al. 2010). Studies have also shown that maternity waiting homes have a positive effect on encouraging facility-based delivery and reducing obstetric complications (Poovan et al. 1980, Kelly et al. 2010). Effective behavior change communication campaigns can also increase demand for key reproductive, maternal, and neonatal health services (Nanda et al. 2005, Fishbein 2005).

  - In terms of quality, a research study conducted by the Quality Assurance Project (QAP) to examine the process of institutionalizing a Continuous Quality Improvement (CQI) process in a Maternity in Ecuador, though Quality Improvement Teams (QIT) composed of staff from the hospital, as the model proposed in Guyana, achieved important results in terms of compliance with quality standards for key management and clinical processes. Before the intervention, “barely half of the women who had delivered in these facilities were being monitored for important vital signs during labor. After improvement activities, CQI teams were able to bring compliance with this standard to 100%” (Hermida et al. 2005, pg.22). The correct use of the partograph was improved from less than a fifth of the patients, to 71%. This was one of the most difficult standards to achieve because of the lack of previous training in the use of the partograph for most professionals (Hermida et al. 2005, pg.23). In terms of newborn care, “seven tasks were included in the standard for newborn care. From 53%, teams improved newborn care to 100% compliance with the standard” (Hermida et al. 2005, pg.23).

  - Continuing training and education of health workers has been proven to improve technical knowledge and skills, consequently improving care and health outcomes. In several developing countries, programs have also been set up to upgrade the skills of health professionals in rural areas, promoting task-shifting and a more optimal use of existing personnel (Nanda et al. 2005, Floyd et al 2016). Finally, the organization of the health care and referral networks have also been proven effective to improve maternal and neonatal outcomes (Nanda et al. 2005, De Brouwere and Van Lerberghe in 2001, Mascia et al 2015).

- Key Outcome Indicators

  - The preliminary identified outcome indicators are those of the Results Matrix. Those indicators will be discussed, validated and adjusted, if needed, by the expert to be hired to conduct the analysis in order to answer the main evaluation question. The indicators included in this list will be available at national, regional, community, and/or health facility level, depending on the source used. Time series will be collected from Ministry of Health’s administrative sources. All health facilities report monthly selected outcome indicators described in the following table. This data will be aggregated.

YN=δt+θtZi+λtμi+εYNYNδtZiθtλtδtμiε

Table 3. Outcome indicators for impact evaluation

| Indicator | Unit | Frequency | Source |
| --- | --- | --- | --- |
| Reducing maternal, perinatal, and neonatal deaths |  |  |  |
| Maternal Mortality Ratio (maternal deaths x 100,000) | Ratio | Quarterly | Ministry of Health Statistics |
| Neonatal Mortality Rate (neonatal deaths x 1,000) | Ratio | Quarterly | Ministry of Health Statistics |
| Access and use of reproductive, maternal, and neonatal health services: |  |  |  |
| First time users of family planning methods for the year | number of clients | monthly | Ministry of Health Statistics |
| Pregnant women with hemoglobin under 11 g/dl at first antenatal visit | Percentage | Monthly | Ministry of Health Statistics |
| Births from adolescent mothers (19 years and younger) | Percentage | Monthly | Ministry of Health Statistics |
| Women who receive antenatal care before 12 weeks pregnant | Percentage | Monthly | Ministry of Health Statistics |
| Women who gave birth in a health facility in the rural interior | Percentage | Monthly | Ministry of Health Statistics |

  - Following Abadie et al. (2010), the basic model would be

Y=YN+αD

Y=YN+αD is the observed outcome for intervened region i at time t;

YN is the outcome that would be observed for region i at time t in the absence of the intervention;

D takes value one if unit i is exposed to the intervention at time t, and value zero otherwise

Program impact is captured by:

α1t=Y1tI−Y1tN=Y1t−Y1tN ;

And YN is determined by:

YN=δt+θtZi+λtμi+ε

Where

δt is an unknown common factor with constant factor loadings across units;

Zi is a (r ×1) vector of observed covariates (not affected by the intervention). In this study in particular, observed covariates will include aggregated individual, household and region characteristics know to be associated with selected outcomes.

θt is a (1×r) vector of unknown parameters;

λt is an unknown common factor with varying factor loadings, and μi , across units;

ε are error terms.

Finally, α1t is estimated by:
α1t=Y1t−j=2J+1wjYjt

where wj represents each particular weighted average of control regions.

- Evaluation Methodology

  - The implementation of a rigorous impact evaluation for this project presents significant challenges. First, since the main treatment units are administrative regions, few observations are available in such a small country, namely: there are only ten administrative regions and, therefore, ten units of analysis. Secondly, since the three regions that will be intervened cover almost 60% of the Guyanese population, finding a valid comparison group among the remaining non-treated regions is difficult. Given those limitations, only region 9, in the rural interior, will be evaluated and all non-treated regions will be used to create the control group. The indigenous people in Guyana, 70,000 in total, exhibit the lowest health indicators in the country and have historically been marginalized in terms of access to quality health services. By evaluating the interventions in region 9, the project will contribute to generate valuable information on what works to improve indigenous people’s access and use of health services. The schedule of the interventions is shown below. Communities from region 9 will have implemented its plan for institutional delivery by April 2019, community health workers will be trained and equipped by September 2021 and the communication strategy will be completed by December 2021. Since the evaluation will be implemented in 2022, the minimum exposure to capture project impacts would be 6 months. In the case of communities plan for institutional delivery program exposure would be 30 months.

Table 4. Schedule of interventions

| Interventions in Region 9 | Start | End |
| --- | --- | --- |
| Community health workers (CHWs) trained and equipped to provide reproductive, maternal, and neonatal services. | 6-Nov-17 | 10-Sept-21 |
| Communities with plans for institutional birth implemented. | 13-Nov-17 | 26-Abr-19 |
| Communities with communication strategy for behavior change implemented. | 28-May-18 | 12-Nov-21 |

  - The chosen methodology to implement the described evaluation is synthetic control. It uses time series for treated and untreated units, and constructs a synthetic control that simulates the trend of the treated unit before treatment. Thus, it is possible to estimate the counterfactual (i.e. what would happen in the absence of the intervention) and then compare it to the treated unit. Under this methodology, the difference between treated and synthetic control unit on key impact/outcome indicators after the intervention is the estimated project's impact.

  - Ideally this methodology requires long time series as well as a large universe of potential controls to build the synthetic control more precisely. However, it is possible to use a minimum of two pre-intervention observations. The main sources of information will be the routine health information system and Guyana’s vital statistics, which provide yearly-measured indicators. While those sources have important limitations as to the quality of the data and comparability through the years, they constitute a valuable resource that can serve the proposed evaluation if used with caution. All the data management must be detailed described in the impact evaluation report, especially regarding the counterfactual estimation.

  - An intensive and comprehensive monitoring is of great importance, as this will provide key inputs for the evaluation. The monitoring reports will be made available to the evaluator. The MCH Unit will be responsible for coordinating dialogues and meetings between the evaluator consultant and government actors involved in the project who can provide relevant information for the analysis. Considering the above, no additional primary information is needed. However, the evaluator may incur in data collection if the available information is not reliable, not valid or not enough to answer the evaluation questions. Any additional data gathering must be agreed by the Bank and the borrower, considering budget constraints.

- Technical Aspects of Selected Methodology

  - The synthetic control methodology was developed by Abadie and Gardeazabal (2003) as an impact evaluation tool to estimate what would have happened in the absence of a program and, therefore, quantify the program impact comparing the estimation with the results observed under the program exposure. It consists on creating a synthetic control unit that replicates at the aggregated level the results of the treated unit prior to the program. This is achieved through an algorithm that selects control units to minimize the observed differences with the treated unit in some key features. This algorithm gives weights to each individual control unit to replicate the treated unit as accurately as possible, creating a synthetic control unit.

  - This way, a control unit is created which, at the time of the intervention (and in previous periods), only differs from the treated unit in that it does not receive the treatment. When a synthetic control unit that replicates precisely the tendency of the treated unit before the intervention is obtained, it can be assumed that the trend of the synthetic control after the intervention corresponds to what would have happened to the treated unit in the absence of the program.

  - If robustness checks are needed for the counterfactual´s validity, balance of dependent and independent variables between treated and synthetic control unit must be verified, and even placebo testing should be done using regions or time periods that are not relevant for the program.

- Reporting Evaluation Results

  - The MCH Unit will be responsible for the evaluation process. The hired consultant should submit an evaluation proposal by May 2022 for approval. In August, the consultant must submit a midterm report with the evaluation draft. A final report is expected by November 2022. The evaluation has an estimated cost of US$ 20,000 and will be fund through the GY-L1058.

- Evaluation Coordination, Work Plan and Budget

  - The evaluation work plan is presented next, including the evaluation timeframe, budget allocated for each main activity and funding source.

Table 5

Evaluation Work Plan

| Key Evaluation Activities/Products per Activity | 2022 |  |  |  |  |  |  |  |  |  |  |  | Responsible | Cost (US $) | Funding |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  |  |  |
| Quasi-experimental evaluation (synthetic control) | X | X | X | X | X | X | X | X | X | X | X |  | MCH Unit | 20,000 | GY-L1058 |
| Terms of Reference | X |  |  |  |  |  |  |  |  |  |  |  | MCH Unit | - | GY-L1058 |
| Advertising |  | X |  |  |  |  |  |  |  |  |  |  | MCH Unit | - | GY-L1058 |
| Contract process |  |  | X | X |  |  |  |  |  |  |  |  | MCH Unit | - | GY-L1058 |
| Evaluation proposal review |  |  |  |  | X |  |  |  |  |  |  |  | MCH Unit / IDB | - | GY-L1058 |
| Midterm evaluation report |  |  |  |  |  |  |  | X |  |  |  |  | MCH Unit | - | GY-L1058 |
| Final evaluation report |  |  |  |  |  |  |  |  |  |  | X |  | MCH Unit | - | GY-L1058 |
| Total Cost: |  |  |  |  |  |  |  |  |  |  |  |  |  | 20,000 |  |

References

Abadie, A., Diamond, A. and Hainmueller, J. (2010). “Synthetic Control Methods for Comparative Case Studies: Estimating the Effect of California’s Tobacco Control Program”. American Statistical Association.

Abadie, A. and Gardeazabal, J. (2003). “The Economic Costs of Conflict: A Case Study of the Basque Country.” American Economic Review, 93(1), pp. 113–32.

Ahluwalia, I. B., et al. "An evaluation of a community-based approach to safe motherhood in northwestern Tanzania." International Journal of Gynecology & Obstetrics 82.2 (2003): 231-240.

Blundell R, C. D. M. (2000). Evaluation methods for non-experimetal data. Fiscal Studies; 21:427-68.

Bhutta ZA, Soofi S, Cousens S, Mohammad S, Memon ZA, Ali I, et al. (2011). Improvement of perinatal and newborn care in rural Pakistan through community-based strategies: a cluster-randomised effectiveness trial. Lancet.;377(9763):403–12. doi: 10.1016/S0140-6736(10)62274-X.

Bhutta, Zulfiqar A., et al. "Can available interventions end preventable deaths in mothers, newborn babies, and stillbirths, and at what cost?." The Lancet 384.9940 (2014): 347-370.

Campbell, Oona MR, Wendy J. Graham, and Lancet Maternal Survival Series steering group. "Strategies for reducing maternal mortality: getting on with what works." The lancet 368.9543 (2006): 1284-1299.

De Brouwere, Vincent, and Wim Van Lerberghe, eds. Safe motherhood strategies: a review of the evidence. Vol. 17. Antwerp: iTG Press, 2001.

Fishbein M. (1995). “Developing effective behavior change interventions: some lessons learned from behavioral research.” In T.E. Becker, S.L. David, and G. Saucy (Eds.) Reviewing the behavioral science knowledge base on technical transfer. NIDA Research Monograph 155. Rockville: National Institute on Drug Abuse.

Hausman JA, Wise DA. (1985). Social experimentation. Chicago: University Chicago Press for National Bureau of Economic Research.

Heckman J, Hotz V. (1989). Choosing among altenative nonexperimental methods for stimating the impact of social programs: the case of manpower training. J Am Stat Assoc; 84:862-74.

Hermida, J., Robalino, M.E., Vaca, L., Ayabaca, P., Romero, P., and Vieira, L. 2005. Scaling Up and Institutionalizing Continuous Quality Improvement in the Free Maternity and Child Care Program in Ecuador. LACHSR Report Number 65. Published for the U.S. Agency for

International Development (USAID) by the Quality Assurance Project.

Parodi S, Stoelinga D. Evaluating the Impact of the ParSalud Health Program in Peru, Harvard Kennedy School of Government, 2008.

Poovan P, Kifle F, and Kwast BE. (1990). A maternity waiting home reduces obstetric catastrophes. World Health Forum.; 11(4):440–5.

Kelly J, Kohls E, Poovan P, Schiffer R, Redito A, Winter H, and MacArthur C. The role of a maternity waiting area (MWA) in reducing maternal mortality and stillbirths in high-risk women in rural Ethiopia. BJOG : an international journal of obstetrics and gynaecology. 2010;117(11):1377– 83. doi: 10.1111/j.1471-0528.2010.02669.x.

Khogali, M., et al. "Do non-monetary incentives for pregnant women increase antenatal attendance among Ethiopian pastoralists?." Public health action 4.1 (2014): 12-14.

Magoma, M., Requejo, J., Campbell, O. M., Cousens, S., & Filippi, V. (2010). High ANC coverage and low skilled attendance in a rural Tanzanian district: a case for implementing a birth plan intervention. BMC pregnancy and childbirth, 10(1), 1.

Moran, A. C., Sangli, G., Dineen, R., Rawlins, B., Yaméogo, M., & Baya, B. (2006). Birth-preparedness for maternal health: findings from Koupéla district, Burkina Faso. Journal of health, population and nutrition, 489-497.

Nanda, G., Switlick, K., & Lule, E. (2005). Accelerating progress towards achieving the MDG to improve maternal health: a collection of promising approaches. HNP, World Bank. See http://siteresources. worldbank. org/HEALTHNUTRITIONANDPOPULATION/Resources/281627-1095698140167/NandaAcceleratingProgresswithCover. pdf.

Ronsmans, Carine, Wendy J. Graham, and Lancet Maternal Survival Series steering group. "Maternal mortality: who, when, where, and why." The Lancet 368.9542 (2006): 1189-1200.

Van den Akker, Thomas, et al. "Can non-monetary incentives increase health facility deliveries? The experience in Thyolo District, Malawi." International Health 3.1 (2011): 66-68.

Wang, P., et al. "Measuring the impact of non‐monetary incentives on facility delivery in rural Zambia: a clustered randomised controlled trial." Tropical Medicine & International Health 21.4 (2016): 515-524.

Annex I

Guyana Target Setting Guidelines

June 2016

Maternal Mortality Rate

Table 1. Maternal mortality rate by percentiles, 2008 (181 countries analyzed)

| Percentile | Rate per 100,000 Live Births | Lower Bound | Upper Bound |
| --- | --- | --- | --- |
| 90 | 7.4 | 6.8 | 8.9 |
| 75 | 20.8 | 14.2 | 28.0 |
| 50 | 51.6 | 43.8 | 79.0 |
| 25 | 322.2 | 233.3 | 448.0 |
| 10 | 622.8 | 582.9 | 799.8 |

Source: IHME (2011). Guatemala Target Setting Guidelines. Institute for Health Metrics and Evaluation, University of Washington. Seattle, WA. Pp. 28-29

Table 2. Improvement targets for the maternal mortality rate in Guyana

| Target | Average annual change | Lower Bound | Upper Bound | Guyana Baseline (2015) |
| --- | --- | --- | --- | --- |
| Global |  |  |  |  |
| 90th percentile | -0.06 | -0.07 | -0.05 | 229* |
| 75th percentile | -0.04 | -0.04 | -0.03 | 229* |
| 50th percentile | -0.02 | -0.03 | -0.02 | 229* |
| Regional |  |  |  |  |
| 90th percentile | -0.07 | -0.07 | -0.02 | 229* |
| 75th percentile | -0.03 | -0.07 | -0.02 | 229* |
| 50th percentile | -0.02 | -0.03 | -0.01 | 229* |
| National |  |  |  |  |
| Guyana (2010-2015) | -0.01* |  |  | 229* |

Source: Adapted from IHME (2011). Guatemala Target Setting Guidelines. Institute for Health Metrics and Evaluation, University of Washington. Seattle, WA. Pp. 28-29

* Data from WHO, UNICEF, UNFPA, World Bank Group, and the United Nations Population Division. Trends in Maternal Mortality: 1990 to 2015. Geneva, World Health Organization, 2015. http://data.worldbank.org/indicator/SH.STA.MMRT?locations=GY

Neonatal Mortality Rate

Table 3. Neonatal mortality rate by percentiles, 2010 (191 countries analyzed)

| Percentile | Deaths per 100,000 Live Births | Lower Bound | Upper Bound |
| --- | --- | --- | --- |
| 90 | 2.5 | 2.2 | 2.8 |
| 75 | 4.7 | 3.4 | 6.5 |
| 50 | 11.3 | 9.3 | 14.2 |
| 25 | 25.6 | 21.1 | 29.2 |
| 10 | 33.3 | 31.2 | 39.0 |

Source: IHME (2011). Guatemala Target Setting Guidelines. Institute for Health Metrics and Evaluation, University of Washington. Seattle, WA. P. 31

Table 4. Improvement targets for the neonatal mortality rate in Guyana

| Target | Average annual change | Lower Bound | Upper Bound | Guyana Baseline (2015) |
| --- | --- | --- | --- | --- |
| Global |  |  |  |  |
| 90th percentile | -0.22 | -0.34 | -0.04 | 22.8* |
| 75th percentile | 0.12 | 0.04 | 0.19 | 22.8* |
| 50th percentile | 0.36 | 0.26 | 0.44 | 22.8* |
| Regional |  |  |  |  |
| 90th percentile | -0.23 | -0.25 | 0.09 | 22.8* |
| 75th percentile | 0.03 | -0.25 | 0.27 | 22.8* |
| 50th percentile | 0.24 | -0.01 | 0.95 | 22.8* |
| National |  |  |  |  |
| Guyana (2010-2015) | -0.01* |  |  | 22.8* |

Source: Adapted from IHME (2011). Guatemala Target Setting Guidelines. Institute for Health Metrics and Evaluation, University of Washington. Seattle, WA. Pp. 31

* Data from Estimates developed by the UN Inter-agency Group for Child Mortality Estimation ( UNICEF, WHO, World Bank, UN DESA Population Division ) at childmortality.org. http://data.worldbank.org/indicator/SH.DYN.NMRT?locations=GY

Annex II

GUYANA

SUPPORT TO IMPROVE MATERNAL AND CHILD HEALTH

GY-L1058

- Indicator Manual

August 26, 2016

This document will be discussed with Guyana´s Ministry of Health and reviewed to ensure alignment of indicator criteria with country norms and the country’s operation. The Indicator Manual will be an Annex in the Operations Manual.

Indicator Manual

Contents

CHAPTER 1: IMPACT INDIATORS	3

1.1. Maternal mortality rate	3

CHAPTER 2: RESULTS INDICATORS. STRENGTHENING REPRODUCTIVE, MATERNAL, AND NEONATAL HEALTH SERVICES	4

2.1. First time users of family planning methods	4

2.2. Anemia in first antenatal visit	4

2.3. Births from adolescents	4

2.4. Early antenatal care	4

2.5. Institutional birth in rural interior	5

2.6. Antenatal care according to best practices	5

2.7. Partograph according to best practices	5

2.8. Oxytocin administration after birth	6

2.9. Immediate neonatal care	6

2.10. Neonatal complications managed according to norms	7

2.11. Obstetric complications managed according to norms	9

2.12. Immediate postpartum care according to best practices	11

CHAPTER 3: RESULTS INDICATORS. STRENGTHENING THE HEALTHCARE NETWORK	13

3.1. Unnecessary referrals	13

3.2. Inputs and equipment for emergency obstetric and neonatal care	13

3.3. Inputs and equipment for quality antenatal and postnatal care	14

Indicator Manual

- CHAPTER1: IMPACT INDICATORS

- 1.1. Maternal mortality rate

Indicator: Number of maternal deaths per 100, 000 live births

Measurement Period: Yearly

Formula:

Numerator: Number of maternal deaths at the national level

Denominator:  Number of live births at the national level

Indicator calculation: Number of maternal deaths / number of live births x 100,000

Source of Verification: Vital Statistics, Chief Medical Officer (CMO) Report

1.2. Neonatal mortality rate (1020)

Indicator: Number of deaths during the first 28 days of life per 1,000 live births in a given year or period

Measurement Period: Yearly

Formula:

Numerator: Number of deaths in the first 28 years of life

Denominator:  Number of live births at the national level

Indicator calculation: Number of maternal deaths / number of live births x 1,000

Source of Verification: Vital Statistics, Chief Medical Officer (CMO) Report

- CHAPTER 2: RESULTS INDICATORS. STRENGTHENING REPRODUCTIVE, MATERNAL, AND NEONATAL HEALTH SERVICES

- 2.1. First time users of family planning methods

Indicator: First time users of family planning methods for the year.

Measurement Period: Yearly

Formula:

Indicator calculation: Number of clients attended a health facility and reported using family planning methods for the first time each year.

Source of Verification: Maternal and Child Health Report: Clinic Summary Report.

- 2.2. Anemia in first antenatal visit

Indicator: Pregnant women with anemia at first antenatal visit (hemoglobin under 11 g/dl).

Measurement Period: Yearly

Formula:

Numerator: Pregnant women with hemoglobin < 11 g/dl in the first antenatal care visit

Denominator:  Pregnant women who attended at least 1 antenatal care visit

Indicator calculation: Women with hemoglobin < 11 g/dl / Women who attended at least 1 antenatal visit x 100

Source of Verification: Maternal and Child Health Report: Clinic Summary Report.

- 2.3. Births from adolescents

Indicator: Births from adolescent mothers (19 years old and younger).

Measurement Period: Yearly

Formula:

Numerator: Births from adolescent mothers (19 years old and younger) registered in health facilities

Denominator:  Total number of births registered in health facilities

Indicator calculation: Births from adolescent mothers / Total number of births x 100

Source of Verification: Vital Statistics, Ministry of Health Statistical Bulletin.

- 2.4. Early antenatal care

Indicator: Women who receive antenatal care before 12 weeks pregnant.

Measurement Period: Yearly

Formula:

Numerator: Women who attended their first antenatal visit before 12 weeks of pregnancy

Denominator:  Total number of pregnancies

Indicator calculation: Women who attended antenatal care before 12 weeks / Total number of pregnancies x 100

Source of Verification: Maternal and Child Health Report: Clinic Summary Report.

- 2.5. Institutional birth in rural interior

Indicator: Women who gave birth in a health facility in the rural interior.

Measurement Period: Yearly

Formula:

Numerator: Births in a health facility registered in region 9

Denominator:  Total number of births registered in region 9 (in or outside a health facility).

Indicator calculation: Births in health facilities / Total number of births x 100

Source of Verification: Maternal and Child Health Report: Clinic Summary Report.

- 2.6. Antenatal care according to best practices

Indicator: Women receiving quality antenatal care according to best practices.

Measurement Period: Yearly

Formula:

Numerator: Women that received antenatal care by doctor or nurse according to best practices

- We generated a variable ANTENATAL_BESTPRA to represent 4 antenatal visits according to best practices. The variable ANTENATAL_BESTPRA takes a value of 1 for medical records that have the following:

  - Basic EONC Health Facility Antenatal care records: four antental visits by doctor or nurse + (in each visit: weight + blood pressure) + (after 13 weeks of gestation: fundal height) + (after 20 weeks of gestation: fetal movements + fetal heart rate) + (lab tests at least once: blood type + Rh factor + glucose + HIV test + hemoglobin + urine test)

Denominator: Total number of antenatal care records in the sample

Indicator calculation: 	ANTENATAL_BESTPRA / total number of antenatal records in the simple = ANTENATAL_BESTPRA1

ci ANTENATAL_BESTPRA

Source of verification: Health Facility Survey (medical record review)

- 2.7. Partograph according to best practices

Indicator: Deliveries for which the partograph was used according to best practices.

Measurement Period: Yearly

Formula:

Denominator:	 Total number of birth records in the sample

Numerator:  Number of records for which partograph was filled according to the norm. A variable PARTOGRAH was created that takes a value of 1 for medical records that have the following:

  - Medical records from Basic and Complete EONC health facilities: partograph included and filled (when the woman did not arrive on imminent birth or planned C-section) + fetal heart rate and alert curve are registered if dilation > 4.5 cm + there is a note on the partograph or medical records within 30 min if the fetal heart rate < 120 bm or the alert curve was surpassed.

Indicator calculation: PARTOGRAH / Total number of birth records in our sample = PARTOGRAH1

ci PARTOGRAH1, binomial

Source of verification: Health Facility Survey (medical record review)

- 2.8. Oxytocin administration after birth

Indicator: Institutional deliveries for which immediate neonatal care was provided to the infant according to the norms

Measurement Period: Yearly

Formula:

Numerator: Number of records with oxytocin administration after delivery

- We generated a variable OXYTOCIN to represent oxytocin administration after delivery.

- This variable OXYTOCIN carries a value of 1 if: oxytocin (or any other uterotonics) were administered after delivery

Denominator: Total number of delivery records in our sample

Indicator calculation: 	OXYTOCIN / total number of delivery records in our sample = OXYTOCIN1

ci OXYTOCIN1

Source of verification: Health Facility Survey (medical record review)

- 2.9. Immediate neonatal care

Indicator: Institutional deliveries for which immediate neonatal care was provided to the infant according to the norms

Measurement Period: Yearly

Formula:

Numerator: Number of neonates who received care according to standards from medical personnel within the first 48 hours following birth:

- We generated a variable NEONATALCARE to represent this indicator. For indicator calculation we took into account all checkups that are recorded.

- This variable NEONATALCARE carries a value of 1 when all below mentioned items are observed:

  - IMMEDIATE POSTNATAL RECORDS BASIC HEALTH FACILITY:  newborn was attended by doctor, nurse or midwife + all procedure and checkups recorded (vitamin K + Application oxytetracycline ophthalmic prophylaxis or chloramphenicol + Apgar score + Heart rate + Respiratory rate + Weight + Height + Head circumference)

  - IMMEDIATE POSTNATAL RECORDS COMPLETE HEALTH FACILITY:  newborn was attended by doctor, nurse or midwife + all procedure and checkups recorded (vitamin K + Application oxytetracycline ophthalmic prophylaxis or chloramphenicol + Apgar score + Heart rate + Respiratory rate + Weight + Height + Head circumference)

Denominator: Total number of postpartum care records in the sample

Indicator calculation: 	NEONATALCARE / total number of postpartum care records in our sample = NEONATALCARE1

ci NEONATALCARE1

Source of verification: Health Facility Survey (medical record review)

- 2.10. Neonatal complications managed according to norms

Indicator: Neonates with complications (prematurity, low birth weight, asphyxia and sepsis) managed according to norms.

Measurement Period: Yearly

Selection criteria:

| Diagnosis | ICD 10 |
| --- | --- |
| Low Birth Weight: |  |
| Extremely low birth weight | P07.0 |
| Other low birth weight | P07.1 |
| Preterm: |  |
| Extreme immaturity | P07.2 |
| Other preterm infants | P07.3 |
| Asphyxia: |  |
| Severe birth asphyxia | P21.0 |
| Mild and moderate birth asphyxia | P21.1 |
| Birth asphyxia, unspecified | P21.9 |
| Sepsis: |  |
| Sepsis of newborn due to streptococcus, group B | P36.0 |
| Sepsis of newborn due to other and unspecified streptococci | P36.1 |
| Sepsis of newborn due to Staphylococcus aureus | P36.2 |
| Sepsis of newborn due to other and unspecified staphylococci | P36.3 |
| Sepsis of newborn due to Escherichia coli | P36.4 |
| Sepsis of newborn due to anaerobes | P36.5 |
| Other bacterial sepsis of newborn | P36.8 |
| Bacterial sepsis of newborn, unspecified | P36.9 |

Formula:

Denominator: Total number of neonatal complication records in the sample

Numerator: Number of neonates with complications (low birth weight, prematurity, birth asphyxia and sepsis) managed according to standards in the last two years

- We generated a variable [NEO_COMP_MAN_NORM] to represent management of complications according to the norm. For indicator calculation we took into account all checkups, lab tests (where applicable) and medications are recorded.

- This variable [NEO_COMP_MAN_NORM] carries a value of 1 when all below mentioned items are observed:

  - LOW BIRTH WEIGHT RECORDS (BASIC): Evaluated by doctor + Gestational age (Capurro or Ballard) + Weight + classification according to weight (Low weight<2500 gr or extreme low weight < 1500 gr) + Heart rate + Respiratory rate + Length + Head circumference + Skin color + Early breastfeeding or any glucose solution (oral or IV) + Warm Chain (warm sheets or radiant warmer or incubator) +  if no complications are present: (observation or Transfer to Complete) + if complications are present {(respiratory: pneumonia or respiratory distress) or (neurologic: convulsions) or digestive(diarrhea) or metabolic(hypoglycemia if glucose< 25mg/dl)} or weight less than 1500gr: Transfer to Complete

  - LOW BIRTH WEIGHT RECORDS (COMPLETE): Evaluated by specialist or doctor + Gestational age + Weight + classification according to weight (Low weight<2500 gr or extreme low weight < 1500 gr) + Heart rate + Respiratory rate + Length + Head circumference + Skin color + Early breastfeeding or any glucose solution (oral or IV) + Warm Chain (warm sheets or radiant warmer or incubator) + (if pneumonia: antibiotics) or (if diarrhea: IV solution + antibiotics) or (if convulsions: anticonvulsive) or (if hypoglycemia if glucose< 25mg/dl: glucose IV)

  - PRETERM RECORDS (BASIC): Evaluated by doctor + Gestational age (Capurro or Ballard)  + Classification of newborn according to gestational age (small, large or adequate) + Weight + Heart rate + Respiratory rate + Glycemia + Head circumference + Skin color + Warm Chain (warm sheets or radiant warmer or incubator) + Breastfeeding or any glucose solution (oral or IV) + if no complications are present: (observation or Transfer to Complete) + if complications are present {(respiratory: pneumonia or respiratory distress) or (neurologic: convulsions) o digestive(diarrhea) or metabolic(hypoglycemia if glucose< 25mg/dl } or less than or equal to 34 weeks of gestation: Transfer to Complete}

  - PRETERM RECORDS (COMPLETE): Evaluated by specialist or doctor + Gestational age (Capurro or Ballard)  + Classification of newborn according to gestational age (small, large or adequate) + Weight + Heart rate + Respiratory rate + Glycemia + Oxygen saturation + Head circumference + Skin color + Warm Chain (warm sheets or radiant warmer or incubator) + Breastfeeding or any glucose solution (oral or IV) + (if pneumonia: antibiotics) or (if diarrhea: IV solution + antibiotics) or (if convulsions: anticonvulsive) or (if hypoglycemia if glucose< 25mg/dl: glucose IV)

  - ASPHYXIA (BASIC) [Only if birth was in the hospital]: Evaluated by doctor + Warm Chain (warm sheets or radiant warmer or incubator) +  Heart rate + Respiratory rate + APGAR score at 1 minute + APGAR score at 5 minutes + if APGAR score at 5 minutes <3 [Oxygen (mask or head box or cone or hood or nasal cannula or mechanic ventilation or oxygen tank) + Ambu (Positive pressure ventilation) + Transfer to Complete (unless child died)]

  - ASPHYXIA (COMPLETE) [Only if birth was in the hospital]: Evaluated by specialist or doctor + Warm Chain (warm sheets or radiant warmer or incubator) + Heart rate + Respiratory rate + APGAR score at 1 minute + APGAR score at 5 minutes + if APGAR score at 5 minutes <3 [Oxygen (mask or head box or cone or hood or nasal cannula or mechanic ventilation or oxygen tank) + Ambu (Positive pressure ventilation) or endotraqueal intubation or chest compressions + Oxygen saturation]

  - SEPSIS RECORDS (BASIC): Evaluated by doctor + Temperature + Heart rate + Respiratory rate + Antibiotic + (if no pediatrician present: transfer to Complete) + (if pediatrician present: admission or [if hemodynamic failure or shock: transfer to Complete])

  - SEPSIS RECORDS (COMPLETE): Evaluated by specialist or doctor + Temperature + Heart rate + Respiratory rate + Oxygen saturation + Complete blood count  (platelets + leukocytes + neutrophil count + hemoglobin + hematocrit) + Antibiotic + Protein C Reactive + Abdominal exam

Indicator calculation: 	NEO_COMP_MAN_NORM / total number of neonatal complication records in the sample = NEO_COMP_MAN_NORM1

ci  NEO_COMP_MAN_NORM1

Source of verification: Health Facility Survey (medical record review)

- 2.11. Obstetric complications managed according to norms

Indicator: Obstetric complications (sepsis, hemorrhage, severe pre-eclampsia and eclampsia) managed according to norms.

Measurement Period: Yearly

Selection criteria:

| Diagnosis | ICD 10 |
| --- | --- |
| Hemorrhage: |  |
| Delayed or excessive hemorrhage following incomplete spontaneous abortion | O03.1 |
| Delayed or excessive hemorrhage following complete or unspecified spontaneous abortion | O03.6 |
| Delayed or excessive hemorrhage following abortion and ectopic and molar pregnancy | O08.1 |
| Placenta previa with hemorrhage | O44.1 |
| Premature separation of placenta with coagulation defect | O45.0 |
| Premature separation of placenta, unspecified | O45.9 |
| Rupture of uterus during labor | O71.1 |
| Postpartum inversion of uterus | O71.2 |
| Third-stage hemorrhage | O72.0 |
| Other immediate postpartum hemorrhage | O72.1 |
| Delayed and secondary postpartum hemorrhage | O72.2 |
| Severe Pre-Eclampsia / Eclampsia: |  |
| Severe pre-eclampsia | O14.1 |
| HELLP syndrome | O14.2 |
| Eclampsia in pregnancy | O15.0 |
| Eclampsia in labor | O15.1 |
| Eclampsia in the puerperium | O15.2 |
| Eclampsia, unspecified as to time period | O15.9 |
| Sepsis: |  |
| Puerperal sepsis | O85 |

Formula:

Denominator: Total number of maternal complications records in our sample

Numerator: Number of women with obstetric complications (sepsis, hemorrhage, severe pre-eclampsia and eclampsia) managed according to the norm in the last two years

- We generated a variable [MAT_COMP_MAN_NORM] to represent management of complications according to the norm. For indicator calculation we took into account all checkups, lab tests (where applicable) and medications are recorded.

- This variable [MAT_COMP_MAN_NORM] carries a value of 1 when all below mentioned items are observed:

  - HEMORRHAGE RECORDS (BASIC):  Pulse +  blood pressure + Ringer/Hartman lactate or saline solution + (adequate management or transfer to Complete)

    - Management options:

      - If hemorrhage following incomplete or complete abortion: MVA or instrumental curettage or transfer to Complete

      - If ectopic pregnancy: laparotomy or salpingectomy or surgical repair or transfer to Complete

      - If placenta previa with hemorrhage: C-section or hysterectomy or transfer to Complete

      - If uterine rupture: laparotomy or hysterectomy or surgical repair or C-section  or transfer to Complete

      - If uterine atony:  uterotonics (oxytocin or others) + bimanual compression or uterine massage or hydrostatic balloon  or uterine tamponade or hypogastric artery ligation or uterine artery ligation or B-lynch suture or transfer to Complete

      - If uterine inversion: uterotonics (oxytocin or others) + repositioning of the uterus with anesthesia or sedation (nonsurgical procedures or surgical procedures) hysterectomy or transfer to Complete

      - If retained product: uterotonics (oxytocin or others) + manual extraction or instrumental curettage or transfer to Complete

  - HEMORRHAGE RECORDS (COMPLETE):  Pulse + Hematocrit + Hemoglobin + platelet count + blood pressure + Ringer/Hartman lactate or saline solution + adequate management

    - Management options:

      - If hemorrhage following incomplete or complete abortion: MVA or instrumental curettage

      - If ectopic pregnancy: laparotomy or salpingectomy or surgical repair

      - If placenta previa with hemorrhage: C-section or hysterectomy

      - If uterine rupture: laparotomy or hysterectomy or surgical repair or C-section

      - If uterine atony: uterotonics (oxytocin or others) or bimanual compression or uterine massage or hydrostatic balloon  or uterine tamponade or hypogastric artery ligation or uterine artery ligation or B-lynch suture or hysterectomy

      - If uterine inversion: uterotonics (oxytocin or others) + repositioning of the uterus with anesthesia or sedation (nonsurgical procedures or surgical procedures) or hysterectomy

      - If retained product: uterotonics (oxytocin or others) + manual extraction or instrumental curettage

  - SEVERE PRE-ECLAMPSIA AND ECLAMPSIA (BASIC):  systolic BP + diastolic BP + check for urine protein + Ringer/Hartman lactate or saline solution + magnesium sulfate + transfer to Complete

  - SEVERE PRE-ECLAMPSIA AND ECLAMPSIA  (COMPLETE):  systolic BP + diastolic BP + pulse + respiratory rate + patellar reflex + if diastolic BP>110: (hydralazine or labetalol or nifedipine) +  magnesium sulfate + check for urine protein+ platelet count + (Aspartate aminotransferase or serum glutamic oxaloacetic transaminase) + (Alanine aminotransferase or serum glutamate-pyruvate transaminase) + if 24=< gestational age <34 weeks: (Dexamethasone or betamethasone)

  - SEPSIS (BASIC): Temperature + pulse + blood pressure + antibiotic administration + adequate treatment

    - Treatment options:

      - If septic abortion: MVA or instrumental curettage or hysterectomy or transfer to Complete

      - If uterine perforation: surgical repair or hysterectomy or transfer to Complete

      - If pelvic abscess: laparotomy or drainage or hysterectomy or surgical repair or transfer to Complete

      - If postpartum endometritis: antibiotic administration or transfer to Complete

      - If retained product: instrumental curettage or laparotomy or hysterectomy  or transfer to complete

      - If puerperal fever: antibiotic administration or transfer to Complete

  - SEPSIS (COMPLETE): Temperature + pulse + blood pressure + complete blood count (hemoglobin + hematocrit + platelets + leukocytes) + antibiotic administration + adequate treatment

    - Treatment options:

      - If septic abortion: MVA or instrumental curettage or hysterectomy

      - If uterine perforation: surgical repair or hysterectomy

      - If pelvic abscess: laparotomy or drainage or hysterectomy or surgical repair

      - If postpartum endometritis: antibiotic administration

      - If retained product: instrumental curettage or laparotomy or hysterectomy

      - If puerperal fever: antibiotic administration

Indicator calculation: 	MAT_COMP_MAN_NORM / total number of obstetric complication records in the sample = MAT_COMP_MAN_NORM1

ci  MAT_COMP_MAN_NORM1

Source of verification: Health Facility Survey (medical record review)

- 2.12. Immediate postpartum care according to best practices

Indicator: Women that received immediate postpartum care according to best practices (every 15 minutes in the first hour and every 30 minutes in the second hour).

Measurement Period: Yearly

Formula:

Numerator: Number of postpartum patients, evaluated and recorded in medical records at least once every 15 minutes during the first hour after birth, then every 30 minutes until completing two hours, and at discharge.

- We created a variable [ALL_CHECK_DIS] to represent this indicator. To calculate the indicator we consider all checkups registered.

- This variable [ALL_CHECK_DIS] takes a value of 1 when all the following items are observed:

  - BASIC EONC IMMEDIATE POSTPARTUM RECORDS: 4 times during the first hour (blood pressure + temperature + respiratory rate + pulse) + 2 times during the second hour: (blood pressure + temperature + respiratory rate + pulse) + at discharge (blood pressure + temperature + respiratory rate + pulse)

  - COMPLETE EONC IMMEDIATE POSTPARTUM RECORDS: 4 times during the first hour (blood pressure + temperature + respiratory rate + pulse) + 2 times during the second hour: (blood pressure + temperature + respiratory rate + pulse) + at discharge (blood pressure + temperature + respiratory rate + pulse)

Denominator: Total number of immediate postpartum records in our sample

Indicator calculation: 	[ALL_CHECK_DIS] / total number of postpartum care records in our sample = [ALL_CHECK_DIS1]

ci ALL_CHECK_DIS1

Source of verification: Health Facility Survey (medical record review)

- CHAPTER 3: RESULTS INDICATORS. STRENGTHENING THE HEALTHCARE NETWORK

- 3.1. Unnecessary referrals

Indicator: Women that are referred to the national hospital for obstetric conditions that could have been resolved at another level of care.

Measurement Period: Yearly

Formula:

Numerator: Number of delivery patients referred to the national hospital that could be attended elsewhere

- We created a variable [UNNECESSARY_REFERRALS] to represent this indicator.

- This variable [UNNECESARY_REFERRALS] takes a value of 1 when all the following items are observed:

  - RECORDS OF DELIVERY PATIENTS REFERRED TO NATIONAL HOSPITAL: Patient referred for normal delivery + Patient age is younger than 18 or older than 25 years old or (prior C-section or low birth weight baby or preterm birth) or risk of birth before 37 weeks of pregnancy or (underlying conditions: diabetes, high blood pressure, anemia or epilepsy) or (pregnancy complications) or (multiple pregnancy)

Denominator: Total number of delivery patients referred to the national hospital in the sample

Indicator calculation: 	[UNNECESSARY_REFERRALS] / total number of postpartum care records in our sample = [UNNECESSARY_REFERRALS1]

ci [UNNECESSARY_REFERRALS1]

Source of verification: Health Facility Survey (medical record review)

- 3.2. Inputs and equipment for emergency obstetric and neonatal care

Indicator: Health facilities with continuous availability of inputs and equipment to provide essential and emergency obstetric and neonatal care.).

Measurement Period: Trimestral

Criteria:

| Health Faclity Level | Items checked |
| --- | --- |
| basic | Emergency obstetric and neonatal care room Oxygen tank or central oxygen supply Reanimation resuscitation bag for adult Neonatal resuscitation bag Laryngoscope |
|  | Pharmacy: Dexamethasone or Betamethasone Atropine or Epinephrine Penicillin crystals or ampicillin or amoxicillin Gentamicin Magnesium sulfate Hydralazine Ergometrine or Oxytocin |
| Complete | Emergency obstetric and neonatal care room Pediatric stethoscope or neonatal stethoscope Oxygen tank or central oxygen supply Reanimation resuscitation bag for adult Neonatal resuscitation bag Laryngoscope MVA kit Equipment for anesthesia Equipment for C-section |
|  | Pharmacy: Dexamethasone or Betamethasone Amikacin sulfate Atropine or Epinephrine Ampicillin or Penicillin crystals or Amoxicillin Ceftriaxone Chloramphenicol or Metronidazole Magnesium sulfate Hydralazine or Hydralazine chlorohydrate Nifedipine Furosemide Diazepam or Midazolam chlorohydrate Sevoflurane 100% or Isoflurane Succinylcholine chloride (suxamethonium) Ergometrine or Oxytocin |

Formula:

Denominator: Total number of basic and complete health facilities in our sample that provides emergency care

Numerator: Health facilities with continuous availability of supplies and equipment needed for emergency obstetric and neonatal care

- We generated a variable [INPUTS_EMERGENCY] to represent the availability of all inputs and equipment needed for emergency obstetric and neonatal care.

- This variable [INPUTS_EMERGENCY] carries a value of 1 when all below mentioned items are observed:

- BASIC HEALTH FACILITY that have the following: Oxygen Tank or Central oxygen supply + Reanimation resuscitation bag for adult + Neonatal resuscitation bag + Laryngoscope + Starter kit for curettage + no stock out of all drugs for emergency obstetric and neonatal care in the last 1month + 2months + 3months

- COMPLETE HEALTH FACILITY that have the following: Pediatric stethoscope  or neonatal stethoscope  + Oxygen Tank or Central oxygen supply + Reanimation resuscitation bag for adult  + Neonatal resuscitation bag +  Laryngoscope   + MVA kit + Equipment for anesthesia + Equipment for C-section +  no stock out of all drugs for emergency obstetric and neonatal care in the last 1month + 2months + 3months

Indicator calculation: 	 [INPUTS_EMERGENCY] / total number of basic and complete health facilities in our sample that provides emergency care = [INPUTS_EMERGENCY1]

ci [INPUTS_EMERGENCY1]

Source of verification: Health Facility Survey (observation and stock card review)

- 3.3. Inputs and equipment for quality antenatal and postnatal care

Indicator: Health facilities with continuous availability of inputs and equipment to provide quality antenatal and post-natal care.

Measurement Period: Trimestral

Criteria:

| Health Facility Level | Items checked |
| --- | --- |
| Ambulatory | Pre and postnatal care room: Scale with measuring rod Gynecological examination table or stretcher Obstetric tape for CLAP or measuring tape Swan neck lamp or pelvic examination lamp or headlight Sphygomanometer (tensiometer) Stethoscope Oral or axillary thermometer Perinatal maternal medical history Perinatal maternal card |
|  | Pharmacy: Multivitamin or (iron and folic acid) |
| Basic | Equipment and supplies: Autoclave or Dry heat sterilizer Scale with measuring rod Gynecological examination table or stretcher Obstetric tape for CLAP or measuring tape Swan neck lamp or pelvic examination lamp or headlight Sphygmomanometer (tensiometer) Stethoscope Set for IUD insertion Fetoscope (Pinard stetoscope or doppler) Oral or axillary thermometer Perinatal maternal medical history Perinatal maternal card |
|  | Pharmacy: Multivitamin or (iron and folic acid) Tetanus vaccine Nitrofurantoin Eritromicine or Ampiciline or Bensatinic penicillin Ayre palettes (for consideration of cervical cytology) or swabs PAP Smear slides |
|  | Lab: Rapid syphilis test’s kit Rapid HIV/AIDS test’s kit Urine protein strips (Urine dipstick) Blood glucose strip Hemocue Microcuvettes Pregnancy test kit If syphilis rapid test is not observed check Dark field microscope If syphilis rapid test or dark microscope is not observed check Equipment for enzyme immunoassay If HIV/AIDS rapid test is not observed check Fluorescence Microscope If Urine protein strips are not observed check Urinanalysis equipment If Blood glucose strips are not observed check Glucose meter If glucose meter is not observed check Automated equipment for blood chemistry If hemocue is not observed check Automated cell counter or (manual cell counter + optic microscope) |
|  | Reagents: If Equipment for enzyme immunoassay is observed Syphilis antigen HIV/AIDS antigen Checking in any case Blood type antibody RH factor antibody |
| Complete | Equipment and supplies: Autoclave or Dry heat sterilizer Scale with measuring rod Gynecological examination table or stretcher Obstetric tape for CLAP or measuring tape Swan neck lamp or pelvic examination lamp or headlight Sphygmomanometer (tensiometer) Stethoscope Set for IUD insertion Fetoscope (Pinard stetoscope or doppler) Oral or axillary thermometer Perinatal maternal medical history Perinatal maternal card |
|  | Pharmacy: Multivitamin or iron and folic acid Tetanus Nitrofurantoin Cefalexin Ayre palettes (for consideration of cervical cytology) or swabs PAP Smear slides |
|  | Lab: Rapid syphilis test’s kit Rapid HIV/AIDS test’s kit Urinanalysis equipment Glucose meter or automated equipment for blood chemistry Automated cell counter or (manual cell counter + optic microscope) If rapid tests for HIV/AIDS are not observed check: Fluorescence Microscope If rapid tests for syphilis are not observed check: Dark field microscope If rapid tests for syphilis or dark field microscope are not observed check: Equipment for enzyme immunoassay |
|  | Reagents: If Equipment for enzyme immunoassay is observed Syphilis antigen HIV/AIDS antigen Checking in any case Blood type antibody RH factor antibody |

Formula:

Denominator: Total number of health facilities that provides pre and postnatal services (and lab for basic and complete type of health facilities) in our sample

Numerator: Health facilities with continuous availability of supplies and functional equipment needed for pre and postnatal care

- We generated a variable [INPUTS_ANTENATAL] to represent the availability of all inputs and functional equipment needed for pre and postnatal care.

- This variable [INPUTS_ANTENATAL] carries a value of 1 when all below mentioned items are observed:

  - AMBULATORY that have the following:  Scale with measuring rod + Gynecological examination  table or stretcher + Obstetric tape for CLAP or measuring tape + Swan neck lamp or pelvic examination lamp or headlight+ Sphygmomanometer (tensiometer) + Stethoscope + Oral or axillary thermometer + Perinatal maternal medical history + Perinatal maternal card + no stock out of all drugs for pre and postnatal care in the last 1month + 2months + 3months

  - BASIC HEALTH FACILITY that have the following: Autoclave or Dry heat sterilizer + Scale with measuring rod + Gynecological examination table or stretcher + Obstetric tape for CLAP or measuring tape + Swan neck lamp or pelvic examination lamp or headlight + Sphygmomanometer (tensiometer) +Stethoscope + Set for IUD insertion + Fetoscope (Pinard stetoscope or doppler) + Oral or axillary thermometer + Perinatal maternal medical history + Perinatal maternal card + no stock out of all drugs for pre and postnatal care in the last 1month + 2months + 3months + lab equipment or rapid test (if lab is available) +  no stock out of lab inputs in the last 1 month + 2months + 3months + no stock out of lab reagents in the last 1 month+2months+3months)  (if lab is available)

  - COMPLETE HEALTH FACILITY that have the following: Autoclave or Dry heat sterilizer + Scale with measuring rod + Gynecological examination table or stretcher + Obstetric tape for CLAP or measuring tape + Instrument or equipment cart or stand + Swan neck lamp or pelvic examination lamp or headlight + Sphygmomanometer (tensiometer) +Stethoscope + Set for IUD insertion + Fetoscope (Pinard stetoscope or doppler) + Oral or axillary thermometer + Perinatal maternal medical history + Perinatal maternal card + no stock out of all drugs for pre and postnatal care in the last 1month + 2months + 3months + lab equipment (if lab is available) + no stock out of lab reagents in the last 1 month + 2months + 3months (if lab is available)

Indicator calculation: 	INPUTS_ANTENATAL] / total number of health facilities that provides pre and postnatal services (and lab for basic and complete type of health facilities) in our sample = [INPUTS_ANTENATAL1]

ci [INPUTS_ANTENATAL1]

Source of verification: Health Facility Survey (observation and stock card review)

IHME. 2011. “Target Setting Guidelines.” Seattle, WA: Institute for Health Metrics and Evaluation, University of Washington.

Maternal mortality in Guyana, according to available information, has reduced approximately 1.8 percentage points per year (Hogan, MC et al. 2010. Maternal mortality for 181 countries, 1980–2008: a systematic analysis of progress towards Millennium Development Goal 5. The Lancet, 1609-1623). With the project, an additional reduction of 3.8 percentage points per year is expected. This rate was estimated based on trend analysis published in Hogan, MC et al. (2010).

Maternal mortality is a “rare” event. Therefore, the maternal mortality ratio in small areas is difficult to estimate. In addition, although the actual death may occur in one location, the onset of the problem usually originates in another location. Guyana, as many other countries, reports maternal mortality ratios at the national level.

Neonatal mortality in Guyana, according to available information, has reduced approximately 1 percentage points per year (World Bank data, in http://data.worldbank.org/indicator/SH.DYN.NMRT?locations=GY). With the project, an additional reduction of 5 percentage points per year is expected. This rate was estimated based on trend analysis published in Hogan, MC et al. (2010).

Neonatal mortality is a “rare” event. Therefore, the neonatal mortality ratio in small areas is difficult to estimate. In addition, although the actual death may occur in one location, the onset of the problem may originate in another location. Guyana, as many other countries, reports neonatal mortality ratios at the national level.

Measurement criteria for indicators measured through the Health Facility Surveys will be defined in the Indicators Manual included as an annex in the Operations Manual.

External link: http://idbdocs.iadb.org/wsdocs/getdocument.aspx?docnum=774392

External link: http://idbdocs.iadb.org/wsdocs/getdocument.aspx?docnum=774394

Available in http://www.thelancet.com/series/maternal-survival.

Available in http://www.thelancet.com/series/everynewborn.

Continuous quality improvement is understood as the group of activities, structures, and values that an organization develops, allowing it to systematically measure, report and improve the quality of its main healthcare processes (Hermida et al. 2005, pg. scientific evidence, as well as the definition of quality from the users’ perspective

Only region 4, where the capital city is located, covers 42% of the population and has a density of 140.43 per km2 (national average of 3.48 per km2).