# Document of the Inter-American Development Bank

Nicaragua

Broadband Program

(NI-L1090)

Monitoring and Evaluation Plan

This document was prepared by the project team consisting of: Antonio García Zaballos (IFD/CMF), Project Team Leader; Diego Herrera (IFD/CMF), Alternate Team Leader; Enrique Iglesias (IFD/CMF); Santiago Alejandro Castillo (FMP/CNI); Jorge Osmín Mondragón (FMP/CNI); Taos Aliouat (LEG/SGO); Fabiola Mercado (VPS/ESG); Meri Helleranta (SPH/CNI); and Cecilia Bernedo (IFD/CMF).

index

Monitoring and Evaluation Plan Summary

- Introduction	1

- Monitoring	4

  - Indicators	4

  - Data Collection and Instruments 	6

  - Reporting Monitoring Results	6

  - Monitoring Coordination, Work Plan and Budget	6

- Evaluation	10

  - Reflective evaluation	11

  - Economic Evaluation (CBA)	12

  - Data Collection Management and Analysis 	16

Annex I: Evaluation Consultancy – Draft Terms of Reference	18

abbreviations

| AOP |  | Annual Operational Plan |
| --- | --- | --- |
| CBA | Cost-Benefit Analysis |  |
| ea | Executing Agency |  |
| GDP | Gross Domestic Product |  |
| M&E | Monitoring and Evaluation |  |
| pep | Project Execution Plan |  |
| PET | PRODEV Evaluation Tool |  |
| pEu | Project Execution Unit |  |
| PMR | Progress Monitoring Report |  |
| PP | Procurement Plan |  |

# Introduction

  - The objective of this document is to describe the monitoring as well as the evaluation plans for the project “Broadband Program” (NI-L1090).

  - The general objective of this project is to increase broadband penetration in Nicaragua with the ultimate goal of contributing to the economic and social development of the country. The specific objectives are to: (i) expand the infrastructure (backbone and last-mile networks); (ii) update the regulatory framework to ensure that networks can be used in fair price and quality conditions; and (iii) increase ICT capacities and use of broadband for citizens and public institutions.

  - Component 1. Infrastructure (US$39.7 million). This component will support the government in improving the coverage of backbone and last mile networks. To that end, it will finance the necessary civil works and equipment to expand the reach of ENATREL’s existing backbone network and provide last mile access, maximizing the connection of municipalities currently not reached.

  - Component 2. Strategic regulation (US$2.5 million). This component will support the government in the development of the regulatory mechanisms that establish the open and equal access conditions and define the operational, quality and network availability indicators for both, backbone and last mile networks, so that ISPs can use the infrastructure in fair price and quality conditions.

  - Component 3. Development of Pilot Programs (US$5 million). This component will support the government in developing the use of broadband in health and agriculture through the execution of pilot programs.  The health pilot program will also have a strong gender component having the objective of reducing mother-child mortality whereas the agriculture program will train agricultural workers in the use of ICT to improve the efficiency and productivity of their businesses.

  - The main expected Impacts and results are:

| Table 1: Key Results / Indicators |  |  |
| --- | --- | --- |
| Impacts | Baseline 2015 | Target 2019 |
| - Penetration of broadband services | 0.51% | 46.14% |
| Results | 2015 | 2019 |
| - Percentage of households connected by broadband networks in the area of project intervention | 0.51% | 20.90% |
| - Percentage of companies connected by broadband networks in the area of project intervention | n.a. | 27.00% |
| - Average broadband price per Mbps in the area of project intervention | 41.9 | 7,34 |
| - Average Number of ISPs providing telecommunications services in the area of project intervention | 1 | 2 |

  - The M&E Plan of this Project will use the following monitoring tools and mechanisms to report project monitoring results: (i) the Results Matrix; (ii) the Annual Operating Plan (AOP); (iii) the Procurement Plan (PP); (iv) the Project Execution Plan (PEP); (v) Administration Missions or Inspection Visits; (vi) the Semi-Annual Report; and (vii) the Progress Monitoring Report. The monitoring exercises of these instruments and mechanisms are described in Section II – D. Monitoring Coordination, Work Plan and Budget.

  - ENATREL will execute Component I deploying the planned infrastructure. Prior to the deployment, TELCOR should have developed a draft Reference Interconnection Offer (RIO) that allows equal and open access to the financed infrastructure by third parties (other backbone operators or ISPs).

  - TELCOR will execute Components II and III.

  - MHCP will transfer loan resources received from the Bank pursuant to interinstitutional agreements signed with each of TELCOR and ENATREL, as Executing Agencies (EA). TELCOR and ENATREL will then each manage separately the financial resources received for the project execution of their respective components. Likewise, each EA will manage the procurement aspects and the financial accounting of the resources corresponding to the components they are responsible for.

  - Each executing agency will be staffed with at least: (i) a procurement specialist; and (ii) a financial specialist. Both EA will be fully staffed by the end of the first year of the Project’s execution. The EA’s specific responsibilities will include: (i) coordinating and supporting the preparation of the Annual Operating Plans (AOPs); (ii) preparation of budgets, project accounting, and preparation of requests for advances of Project funds; (iii) preparation of the annual procurement plan for the Project and the procurement of goods and the contracting of services for the Project; (iv) coordinating the preparation of technical reports and preparing periodic and end-of-year financial reports; (v) monitoring of the Project’s activities progress and analyzing variances of actual results against plans; (vi) contracting the external auditor and ensuring-through the application of the external audit or recommendations; (vii) monitoring and evaluating project activities; and (viii) serving as a liaison for the Project with the Bank.

  - Maintenance. The Borrower commits to the maintenance of the works and goods described in this project in accordance to the generally accepted technical standards. The Borrower, through the corresponding EA, must present to the Bank, as part of the Semi Annual Reports once the works are finalized and during the period for disbursements or its extension, a report with the status of the works and equipment and the corresponding maintenance plan for the following 2 semesters. Additionally, this report and maintenance plan must be presented by the borrower during the first quarter of each calendar year, during 3 years from the second year after the expiry of the disbursements period or its extension. If Bank’s inspection or the reports conclude that the maintenance is performed under the agreed levels, the Borrower and the EA must adopt the necessary measures to fully correct the identified deficiencies.

  - Annual Operating Plans (AOP). The Project will be executed following the AOP that will include for each programmed annual activity its goals, budget, source of funding, and responsibility for its execution. The project’s Operating Regulations will set forth the details regarding Project execution including coordination of activities amongst the different offices. The need to update the project’s Operating Regulations will be assessed during the midterm review.

# Monitoring

#### Indicators

  - The Results Matrix comprises the project’s indicators. Project indicators have been selected to represent the essential activities within the project scope and are in line with the principles of SMART indicators. In order to evaluate effective operations of the project, the M&E Plan will include indicators related to achievement of performance targets, outputs and outcomes. The approach for the monitoring was agreed between the Bank and the Government of Nicaragua.

Table 2 - Monitoring Indicators

| Output Indicator | Formula/Definition | Frequency of Measurement | Source |
| --- | --- | --- | --- |
| 1.1 Optical Fiber acquired and deployed | Cable | On an annual basis | ENATREL, progress report |
| 1.2 Acquisition of irrevocable Rights of Use (IRUs). Submarine Cable Capacity (10Gbps links). | IRUs | One time, after the first year | ENATREL, progress report |
| 1.3 Main nodes installed (40 GE) | Nodes | On an annual basis | ENATREL, progress report |
| 1.4 Medium nodes installed (10 GE) | Nodes | On an annual basis | ENATREL, progress report |
| 1.5 Small nodes installed (1 GE) | Nodes | On an annual basis | ENATREL, progress report |
| 1.6 Amplifier nodes installed | Nodes | On an annual basis | ENATREL, progress report |
| 1.7 Towers installed | Towers | On an annual basis | ENATREL, progress report |
| 1.8 Base Stations installed | Antennas | On an annual basis | ENATREL, progress report |
| 1.9 Software for the Network Equipment acquired | Software | One time, after the first year | ENATREL, progress report |
| 1.10 Equipment kits for the health units acquired | Equipment | On an annual basis | Reports of the delivery of the equipment kits |
| 1.11 Equipment kits for the telecentres acquired | Equipment | On an annual basis | Reports of the delivery of the equipment kits |
| 1.12 System to support the provision of health services installed | System | One time, after the first year | ENATREL, progress report |
| 1.13 Civil registry system installed | System | One time, after the first year | ENATREL, progress report |
| 1.14 Finance administration System installed | System | One time, after the first year | ENATREL, progress report |
| 2.1 Development of costing models that help calculation of tariffs | Financial Models | On an annual basis | Report from TELCOR indicating the acceptance of the developed cost models |
| 2.2 Development of applications to measure quality of service | Software | On an annual basis | Report from TELCOR indicating the correct functioning of the developed applications |
| 2.3 Training workshops in terms of interconnection and access | Training Program | On an annual basis | Certificate of attendance issued by the IDB. Training satisfaction surveys. |
| 3.1 Training: ICT for the provision of innovative health services | Training Program | On an annual basis | Report from TELCOR that includes certificates of attendance issued by the IDB and satisfaction surveys. |
| 3.Development of innovative applications or services that make use of broadband and may improve mother-child mortality | Application | On an annual basis | Applications in digital format along with a report describing its functioning. |
| 3.3 Equipment kit for the provision of the selected applications | Equipment | On an annual basis | Report from TELCOR indicating the acquired equipment, matching with the application needs. |
| 3.4 Evaluation of the health pilot results and development of a scale-up plan | Evaluation and scale-up plan | On an annual basis | Report with the evaluation of the pilot program. Report with the scale-up plan. |
| 3.5 Training: ICT to improve the agriculture productivity | Training Program | On an annual basis | Report from TELCOR that includes certificates of attendance issued by the IDB and satisfaction surveys. |
| 3.6 Development of innovative applications or services that make use of broadband and may improve the agriculture productivity | Application | On an annual basis | Applications in digital format along with a report describing its functioning. |
| 3.7 Equipment kit for the provision of the selected applications | Equipment | On an annual basis | Report from TELCOR indicating the acquired equipment, matching with the application needs. |
| 3.8 Evaluation of the agriculture pilot results and development of a scale-up plan | Evaluation and scale-up plan | On an annual basis | Report with the evaluation of the pilot program. Report with the scale-up plan. |

Table 3 – Project Costs grouped by Output and Annual Expected Amounts

| Output Indicator | Total Cost (US$ million) | Year 1 (US$ million) | Year 2 (US$ million) | Year 3 (US$ million) | Year 4 (US$ million) |
| --- | --- | --- | --- | --- | --- |
| 1.1 Optical Fiber acquired and deployed | 16.5 | 4.125 | 4.125 | 4.125 | 4.125 |
| 1.2 Acquisition of irrevocable Rights of Use (IRUs). Submarine Cable Capacity (10Gbps links). | 10 | 2.5 | 2.5 | 2.5 | 2.5 |
| 1.3 Main nodes installed (40 GE) | 2 | 0.5 | 0.5 | 0.5 | 0.5 |
| 1.4 Medium nodes installed (10 GE) | 2 | 0.5 | 0.5 | 0.5 | 0.5 |
| 1.5 Small nodes installed (1 GE) | 1 | 0.25 | 0.25 | 0.25 | 0.25 |
| 1.6 Amplifier nodes installed | 0.5 | 0.125 | 0.125 | 0.125 | 0.125 |
| 1.7 Towers installed | 1.2 | 0.3 | 0.3 | 0.3 | 0.3 |
| 1.8 Base Stations installed | 1 | 0.25 | 0.25 | 0.25 | 0.25 |
| 1.9 Software for the Network Equipment acquired | 2 | 0.5 | 0.5 | 0.5 | 0.5 |
| 1.10 Equipment kits for the health units acquired | 1.75 | 0.35 | 0.35 | 0.35 | 0.35 |
| 1.11 Equipment kits for the telecentres acquired | 1.25 | 0.3125 | 0.3125 | 0.3125 | 0.3125 |
| 1.12 System to support the provision of health services installed | 0.5 | 0.125 | 0.125 | 0.125 | 0.125 |
| 2.1 Methodology for Market Analysis defined | 0.5 | 0.125 | 0.125 | 0.125 | 0.125 |
| 2.2 Tariffs set up according to defined models | 0.5 | 0.125 | 0.125 | 0.125 | 0.125 |
| 2.3 Regulatory framework and the secondary legislation reviewed | 0.5 | 0.125 | 0.125 | 0.125 | 0.125 |
| 2.4 Applications to measure quality of service implemented | 0.5 | 0.125 | 0.125 | 0.125 | 0.125 |
| 2.5 Specific legislations and decrees to guarantee open and equal access reviewed and drafted | 0.375 | 0.09375 | 0.09375 | 0.09375 | 0.09375 |
| 2.6 Training workshops in terms of interconnection and access | 0.125 | 0.03125 | 0.03125 | 0.03125 | 0.03125 |
| 3.1 Training: ICT for the provision of innovative health services | 1 | 0.25 | 0.25 | 0.25 | 0.25 |
| 3.Development of innovative applications or services that make use of broadband and may improve mother-child mortality | 0.5 | 0.125 | 0.125 | 0.125 | 0.125 |
| 3.3 Equipment kit for the provision of the selected applications | 0.5 | 0.125 | 0.125 | 0.125 | 0.125 |
| 3.4 Evaluation of the health pilot results and development of a scale-up plan | 0.5 | 0.125 | 0.125 | 0.125 | 0.125 |
| 3.5 Training: ICT to improve the agriculture productivity | 1 | 0.25 | 0.25 | 0.25 | 0.25 |
| 3.6 Development of innovative applications or services that make use of broadband and may improve the agriculture productiviry | 0.5 | 0.125 | 0.125 | 0.125 | 0.125 |
| 3.7 Equipment kit for the provision of the selected applications | 0.5 | 0.125 | 0.125 | 0.125 | 0.125 |
| 3.8 Evaluation of the agriculture pilot results and development of a scale-up plan | 0.5 | 0.125 | 0.125 | 0.125 | 0.125 |

#### Data collection and instruments

  - The data for monitoring output and expected outcome indicators will be extracted from the administrative systems and records provided by the PEU.

#### Reporting

  - Multiple mechanisms and instruments will be used to report project monitoring results. The following tools and mechanisms will be a source of information for the Progress Monitoring Report (PMR):(i) Results Matrix; (ii) Annual Operating Plan (AOP); (iii) Procurement Plan (PP); (iv) Project Execution Plan (PEP); (v) Administration Missions or Inspection Visits; (vi) the Progress Monitoring Report; and (vii) Semi-annual Progress Reports.

  - At Project completion, tracked history of all mechanism and instrumental data will be compiled into an Expanded Performance Monitoring Report (XPMR) to present a complete picture of project performance. This report will be prepared by the Bank at 90 days after the last disbursement.

#### Monitoring Coordination, Work Plan and Budget

  - The objective of the monitoring is to detect the factors that can facilitate or obstruct the project to achieve its results according to the activities programed, as well as the expected goals and respective Result Matrix indicators.

  - The monitoring of the Project is fundamentally the responsibility of TELCOR with the support of the PEU. The PEU will be responsible for accompanying the execution of all the planned activities in accordance with the Project Execution Plan (PEP).

#### Main Monitoring Questions:

  - Conformity Monitoring: The activities and processes to be performed are aligned with the objectives established and the methodology adopted for the project?

  - Financing monitoring: There are availability and timeliness in the assignation of funds for the project?

  - Monitoring and activities: The programed actives are being planned and executed following the sequence and the timetable established?

  - Products monitoring: The primary, intermediate, and final products are being executed in the desirable sequence?

  - Monitoring and risks: The Project identified risks jeopardizes the project’s objectives?

- The monitoring coordination will be based on the following instruments:

          - Results Matrix. Included as Annex II of this document, the Results Matrix will be used to guide the planning, monitoring, and evaluation of the project. This document reflects the following: (i) indicators for the project’s results with respective baselines and goals to achieve; (ii) outputs for each component; and (iii) an impact of the Project’s long-term outcome. The Results Matrix will be referred to when the AOP undergoes modifications and will act as an instrumental tool for the design, monitoring and evaluation of each of the Project’s components and subcomponents.

          - Annual Operating Plan (AOP). Included as a Mandatory Electronic Link of the Loan Proposal, this instrument consolidates all the components’ activities that will be developed during the Project implementation as well as the project’s projected financial resources, disbursement projections, and executing timetable. The first AOP will cover the Project’s first 18 months, which initiates upon the signing of the Loan Contract. The subsequent AOP will cover the period following the revision of the first AOP to the 5th of December of the corresponding year. For the following years of Project implementation, the project team shall present the AOP to the Bank no later than the 5th of December of the year prior to its coverage.

          - Procurement Plan (PP). Included as a Mandatory Electronic Link of the Loan Proposal, this instrument reflects a list of works, goods, training, and both non-consulting and consulting services that will be carried out each year during Project implementation. The Project team have worked together to elaborate on the following: (i) the methods of procurement; (ii) estimated amounts; and (iii) the timeframe estimated for each element of the PP. Terms of Reference will be elaborated for each consulting service (consultants and firms). The procurement of works, goods and services will be conducted in accordance with the Bank's Policies and Procedures for the Procurement of Goods and Works (GN˗2349-9) and for the Selection and Contracting of Consultants (GN˗2350-9). Procurement of goods, works and consulting services will be reviewed using ex-ante methodology. The need for this review procedure will be periodically assessed by the Bank through procurement inspection visits and performance reviews. The Procurement Specialist of the PEU will be responsible for updating the PP on an annual basis, coinciding with the planned annual evaluation in conjunction with the AOP, or when substantial changes are proposed. Any proposed revision of the PP should be presented to the Bank for its approval. The procedures applied by the Bank for the revision of the procurement are also illustrated in the fiduciary agreements and requirements (see Annex III).

          - Project Execution Plan (PEP). Presented as a Mandatory Electronic Link of the Loan Proposal, this instrument lists all the activities to be contracted during the entire operation. The PEP specifies the financial amount and time required for each activity of the Project. In order to assure an adequate operational planning, the PEU, with the support from the Bank and using the Bank formats, will prepare a PEP for multi-year execution, which will demonstrate how the project will achieve the objective and goals mentioned in the RM. Also, an AOP for the first 18 months of execution, in which activities to be carried out in each component to achieve the objectives and goals established for that period will be detailed.

          - Project execution plan. This tool lists all the hiring and execution of contracts that will occur during the Project’s implementation. The PEP specifies the monetary resources and time needed for each of the outputs and activities of the project.

          - Project Performance Monitoring Report (PMR). This instrument will be used to follow-up on the Project’s outputs and outcomes achieved during the Project’s implementation. The PMR will integrate the following information as defined in the Results Matrix and the Project’s Detailed Budget during the preparation phase of the project: (i) annual targets for output indicators; (ii) total costs for each expected output; and (iii) total sum of planned costs for all outputs.

          - Semi-annual Project Progress Reports. The PEU will submit two semi˗annual progress reports throughout Project execution, within 60 days following the end of each semester. The progress reports will contain at least the following elements: (i) narrative description of activities executed under each component, including a description of the procurement processes carried out and issues affecting implementation during the reported period; (ii) update on attainment of Result Matrix indicators; (iii) statement of costs incurred by component activities as well as Results Matrix indicator; and (iv) identification of risks/events that may potentially affect the future implementation of the project, as well as proposed mitigation measures.

  - Technical supervision will be the responsibility of the Capital Markets and Financial Institutions Division (IFD/CMF) with support from the Office of Fiduciary Monitoring and Procurement for Operations (VPC/FMP) and the Country Office of the Bank in Nicaragua (CID/CNI). The project team responsible for the design of the Project will continue to be involved during implementation.

  - The collection and compilation of data from the different sources will be monthly carried out in-house by TELCOR and ENATREL, in partnership with the component’s team leaders and will be consolidated by the PEU in the Semiannual Progress Report. These reports will be used to update the Project Monitoring Report (PMR). The products’ annual costs are detailed in a spreadsheet prepared by the project team. The budget assigned for the Project’s monitoring activities is estimated in US$30,000.

  - For data collection will be necessary to identify all sources/systems and responsible from where the information will be extracted, aiming at to create a direct relation with the supervisors of the corresponding entities, aiming at to facilitate the collection of the information according to the timetable presented in Table 3.

  - The information will be registered using a set of forms (questionnaires), according to the indicators presented in the Result Matrix, which will provide timely progress information for consultation. The information will be consolidated by year and the distortion will justified.

  - Additionally, in a trimestral basis, the PEU coordinator will carry out interviews with the main stakeholders to review the collection and consolidation of information, as well as will evaluate the objective’s deviations and possible actions for mitigation.

| Table 4 – Data Collection Activates and Timetable |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Key Monitoring Activities/Products per Activity | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Responsible | Cost |
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |  |  |
| 1. Identification of the sources/systems/responsible from where the information will be collected |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | PEU Monitoring Specialist, Bank Project Team | US$30,000, from Project budget. |
| 2. Preparation of the control forms to consolidate and evaluate the information |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  |  | PEU, and Bank Project Team |  |
| 3. Information collection |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x |  | x |  | x | PEU |  |
| 4. Auditing |  |  |  |  |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x | General Auditor |  |
| 5. Consolidation of the information |  |  |  |  |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x | PEU |  |
| 6. Interview with stakeholder responsible for the information |  |  |  |  |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x | PEU |  |
| 7. Semi-annual Progress Reports |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x | PEU |  |

  - The borrower will present Semiannual progress reports to the Bank. The reports will comprise information regarding the implementation of the activities. The PEU will count with a monitoring expert, which activities will include: (i) collect and update information; (ii) coordinate with all stakeholder involved in the execution of the project, about the collection and evaluation of the information generated by the execution; (iii) identify deviations, delays and all external factors that could jeopardize the project, applying the necessary corrections; and (iv) assist the internal meetings regarding monitoring and evaluation, as well as the supervision missions.

  - The Bank and the PEU will carry out semiannual meetings to monitor in partnership the pace of the project execution. Likewise, at least one inspection mission will be carried out, aiming at to supervise the progresses achieved.

  - When physical and financial delays are identified, an Acceleration Implementation Plan (AIP) will be established to clarify: (i) the main implementation difficult; (ii) the actions to mitigate; and (iii) the timetable and costs for mitigation. The AIP also will include a selection of project priority acquisitions, comprising the corresponding timetable and the costs.

# Evaluation

  - The Bank will carry out a Project Completion report (PCR). This report will be started when the project reaches 95% of its disbursements and will be presented during the following 180 days. In this context, a mid-term and a final evaluation reports will be prepared. The mid-term evaluation will be carried out when 50% of the loan resources (combining all sources) have been disbursed and the final evaluation of the Project will be carried out after 90% of the loan resources (combining all sources) have been disbursed, both comprising the information from the Reflective and CBA evaluations.

  - The final evaluation report will be published within 90 days of the last day of the project execution period. Potential users of this publication will be Bank personnel, TELCOR, ENATREL and other relevant stakeholders. The report will be a source of information for the preparation of the Project Completion Report (PCR).

  - The approach for the evaluation was agreed between the Bank and the Government of Nicaragua. The PEU will be the entity responsible for carrying out the evaluation activities including the planning, administration and execution of the financial resources and elaboration and submission of evaluation reports. The PEU will hire three independent consultants to carry out the mid-term and final evaluations. Annex I presents the Terms of reference for the consultancies.

  - The main objective of the evaluation plan is to determine whether the interventions supported by the project contributed to the expected impact and outcomes. Result indicators for each project component are included in the results matrix. The approach for the evaluation was agreed between the Bank and the Government of Nicaragua. The project evaluation will comprise two different ex-post evaluations: (i) reflective evaluation; and (ii) economic evaluation (CBA).

    - Reflective Evaluation.

  - Indicators to be evaluated.

| Table 5 -From the Result Matrix |  |  |  |
| --- | --- | --- | --- |
| Outcome Indicator | Definition | Frequency of Measurement | Source |
| - Percentage of households connected by broadband networks in the area of project intervention | Quantity | On an annual basis | PET evaluation |
| - Percentage of companies connected by broadband networks in the area of project intervention | Quantity | On an annual basis | PET evaluation |
| - Average broadband price per Mbps in the area of project intervention | US$/Mbps | On an annual basis | PET evaluation |
| - Number of ISPs providing telecommunications services in the area of project intervention | Quantity | On an annual basis | PET evaluation |

  - This evaluation methodology will try to establish how successful the project was by thinking about the answers to the questions the project’s stakeholders ask themselves.

  - The following main question will be asked by the independent consultant, hired to conduct a final evaluation of the project in order to guide the evaluation process:

- How the project impacted in the adoption of broadband services?

    - Ex post Economic Evaluation (CBA).

  - Indicators to be evaluated:

| Table 6 – Data to be collected for the exPost CBA |  |  |  |
| --- | --- | --- | --- |
| Outcome Indicator | Definition | Frequency of Measurement | Source |
| - Percentage of households connected by broadband networks in the area of project intervention | % | On an annual basis | PET evaluation |
| - Percentage of companies connected by broadband networks in the area of project intervention | % | On an annual basis | PET evaluation |
| - Sales of a selected number of companies in the area of project intervention | $ | On an annual basis | PET evaluation |
| - Average broadband price per Mbps in the area of project intervention | $/Mbps | On an annual basis | PET evaluation |
| - Percentage of households and companies contracting 1Mbps connections | % | On an annual basis | PET evaluation |
| - Percentage of households and companies contracting 2Mbps connections | % | On an annual basis | PET evaluation |
| - Percentage of households and companies contracting 4Mbps connections | % | On an annual basis | PET evaluation |

  - This evaluation will use the same methodology applied to estimate the project return benefits comparing and justifying the deviations. The ex post evaluation will update the current controls/tables with information related to the year of the evaluation. In this context, an ex ante Economic Evaluation was carried out presenting the following estimation and recommendation:

- The Project’s Cost Benefit Analysis (CBA) presents an Internal Rate of Return (IRR) of 21% with a Net Present Value of US$24.34 million in year 2025. This justifies the US$50 million investment by the Inter-American Development Bank.

- Based on this CBA, it is recommended to continue with the financial and technical support from the Bank, through the implementation of the Broadband Program under the operation NI-L1090.

  - The methodology for the CBA ex post evaluation is shown in the graph below:

  - As indicated in table 6, the information that will need to be collected is:

    - Percentage of connected households in the municipalities in the area of project intervention.

    - Percentage of connected companies in the municipalities in the area of project intervention.

    - Sales of a selected number of companies  in the area of project intervention

    - Average price per Mbps (US$/Mbps) in the area of project intervention.

    - Percentage of households and companies contracting 1Mbps connections

    - Percentage of households and companies contracting 2Mbps connections

    - Percentage of households and companies contracting 4Mbps connections

  - Taking into account the number of connected households, companies and the average price per Mbps, the analysis will calculate the following:

    - Income: considering the percentage of households and companies connected and the average price per Mbps measured. The income will result from multiplying the number of households and companies at the end of the project by the price.

    - Market surplus will be calculated taking into account the price reductions and the number of connected users (sum of connected households and companies). Specifically, the ex Post evaluation will calculate the area in the chart below, which is the market surplus. To that end the next steps will be followed:

      - Step 1: Number of connected households, companies and institutions will be collected from the annual data gathered

      - Step 2: Reduction in terms of price per Mbps will be collected from the annual data gathered

      - Step 3: As a reference, a study shows that in the Latin American and Caribbean countries, a reduction of 10% in the broadband price has an impacts of 22% increment in the penetration rate of broadband services. Complementarily, the elasticity can be calculated from the percentage of users (households and companies) that contract a particular service (1Mbps, 2Mbps or 4Mbps).

      - Step 4: The market surplus is determined

    - The business increase on productivity will be calculated following the next steps:

      - Step 1.- from the data gathered annually we will extract the volume of sales for the sample of companies connected to broadband (S_c);

      - Step 2.- from the data gathered annually we will extract the volume of sales for the sample of companies not connected to broadband (S_nc);

      - Step 3.- we will calculate the increase in sales attributable to the project as the difference in sales of the two samples described above;

- Increase = S_c – S_nc

      - Step 4.- we will estimate the total benefit as the expected Increase per company multiplied by the number of companies connected thanks to the project;

  - Finally, with the costs disbursed in the project, the resulting Social NPV and Social IRR will be calculated.

#### Data Collection Management and Analysis

  - Instruments. The information will be collected based on the Result Matrix and the ex ante Economic Analysis (CBA). Table 8 provides the timetable for the collection. The data will be consolidated in spreadsheets, preformatted according to the information required for the three different methodologies. The final report will be presented in Word, with the spreadsheet attached.

| Table 8 - Work Plan for ex-post Evaluation (Reflective and CBA) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Main Activities | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Responsible | Cost US$ |
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |  |  |
| - Reflective Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 Consultants Hiring | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  |  |  | PEU | US$40,000 |
| 1.2 Fine Tune of the Instruments and methodology | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3 Data Collection |  |  | x |  |  |  |  | x |  |  |  | x |  |  |  | x |  | x |  |  |  |  |
| 1.4 Data Analysis |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  | x | x | Consultant |  |
| 1.5 Draft Report |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  | x |  |  |  |
| 1.6 Final Report |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  | x |  |  |
| 1.7 Dissemination of information |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  | x | PEU |  |
| - Economic Evaluation (CBA) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 Consultants Hiring | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | PEU | US$40,000 |
| 2.2 Fine Tune of the Instruments and methodology | X | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3 Data Collection |  |  |  |  |  |  |  | x |  |  |  | x |  |  |  | x |  | x |  |  |  |  |
| 2.4 Data Analysis |  |  |  |  |  |  |  | x | x | x | x |  |  |  |  |  |  | x | x |  | Consultant |  |
| 2.5 Draft Report |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  | x |  |  |  |
| 2.6 Final Report |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  | x |  |  |
| 2.7 Dissemination of information |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  | x | PEU |  |
| 3. Final Report and PCR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1 Consultants Hiring |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  |  | PEU | US$20,000 |
| 4.2 Fine Tune of the Instruments and methodology |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x | x |  |  |  |  |
| 4.3 Data Collection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x | x |  |  |  |  |
| 4.4 Data Analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x | x | Consultant |  |
| 4.5 Draft Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  |
| 4.6 Final Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  |
| 4.7 Dissemination of information |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x | PEU |  |

| Table 9 – Evaluation Budget Summary |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Categories | Responsible | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total |
| Consultancy Reflective evaluation | PEU | 10,000 |  | 10,000 |  | 20,000 | 40,000 |
| Consultancy CBA evaluation | PEU | 10,000 |  | 10,000 |  | 20,000 | 40,000 |
| Consultancy Final Report and PCR | PEU |  |  |  |  | 20,000 | 20,000 |
| Total |  |  |  |  |  |  | 100,000 |

ANNEX I

Evaluation Consultancy

Draft Terms of Reference

- Objective of the Consultancy

  - Perform the Project evaluation using: (i) reflective; and (ii) ex-post Cost Benefit Analysis (CBA); as well as the preparation of the respective reports for review and submission to the Division. These reports will be an input to the Project Completion Report (PCR).

- Activities

  - In direct coordination with sector specialists, review the documentation for the execution of the project. In particular, assess the results and impact achieved according to the targets in the Results Matrix and CBA evaluations.

  - Perform a Reflective evaluation, based on the results and impacts related to the Project components’ activities, taking into account the baselines established in the Result Matrix.

  - Perform an ex post cost benefit analysis using the same methodology applied to estimate the project return benefits comparing and justifying the deviations.

  - Preparation of the respective reports, highlighting deviations, and related recommendations for improvement.

III. Expected Outputs

3.1	Intermediate Evaluation Report comprising the two mentioned methodologies, with text and graphics, to be reviewed by the sector specialist who oversees the project. The report should include all areas specified in the format, with special emphasis on the project results and lessons learned.

3.2	Final Evaluation Report comprising the two mentioned methodologies, incorporating comments made by the sectorial specialists.

IV. Characteristics of the Consultancy

- 4.1	Consultancy type: International individual consultant.

- 4.2	Duration: 120 non consecutives days in a period of five years.

- 4.3	Place of work: Place of residence and Nicaragua.

4.4	Qualifications: Graduate degree in economics with a career spanning over five years in evaluation of projects. Preference will be given to consultants with prior experience in the preparation of IDB projects or projects funded by multilateral agencies.

4.5	Payment: the consultant will be paid in the following manner:

- A first payment of 15% of the contract amount 15 days after signing it, upon delivery of a work plan to the satisfaction of the IDB.

- A second payment 30% upon delivery and approval of the interim evaluation including the 3 methodologies to the satisfaction of the IDB.

- A final payment of 55% upon delivery and approval of the final evaluation including the 3 methodologies to the satisfaction of the IDB.

4.6	Budget: The evaluations will be covered by Project funds. The cost of the evaluation is estimated at approximately 120 days during the five-year period between 2015 and 2019. There is no extra budget needed for data collection. All costs are detailed in Tables 8 and 9, under the assumption of that the daily rate of the consultant is US$500.

V. Supervision

5.1	The consultancy will be coordinated by Antonio García Zaballos (IFD/CMF), Team Leader of the operation.

The RM presented as part of the Proposal for Operation Development of the operation, focuses on: i) indicators of impacts and of expected results of the program with the respective baseline and targets to be achieved; and ii) on outputs for each component.  The RM is a fundamental tool to guide the planning, monitoring and evaluation of the program.  The information in the RM is the base for the information contained in the Project Monitoring Report (PMR), in which the bank will register physical progresses during the implementation of the program for the purpose of calculating the Performance Index of the program.  Also, the RM is referred to at each instance of the elaboration of the Annual Operative Plan (AOP).

SMART Indicators are specific, measurable, achievable, relevant, and time bound.

To make sure data is representative, the number of companies will be calculated taking into account the total number of companies in the area of project intervention, a confidence level of 95% and a confidence interval, i.e. margin of error, of 5

For more detail see: Galperin (2013): Price elasticity of demand for broadband: Evidence from Latin America and the Caribbean, Telecommunications Policy, Vol. 37, issue 6-7, pag. 429-438