- Appendix I

PROCUREMENT PLAN

Country: Regional

Executing agency: Inter-American Development Bank (ICF/ICS)

Project name: Addressing Crime and Violence in the Caribbean Region: New Approaches through Prevention

Project number: RG-T11525

Brief description of the project’s objectives and components: The general objective of this operation is to contribute to strengthening the knowledge on key issues related to violence prevention and citizen security and to promote mechanisms of collaboration among Caribbean nations to address this problem. The project will be implemented over a 14 months period and includes 3 components: (i) to analyze and discuss technical aspects and evidence-based practices on violence prevention through an International training workshop for the Caribbean region, (ii) to develop a regional Caribbean network on crime and violence prevention that will engage policymakers to address collectively crime and violence issues in the region, and (iii) to develop and implement a crime and violence data collection system in the Bahamas.

Estimated date of project approval: March 2008

Estimated date of signature of the contract: April 2008

Estimated date of the final disbursement: June 2009

Address of the executing agency responsible for the procurement plan:

- (http://www.iadb.org:Information on project procurements).

Project: Addressing Crime and Violence in the Caribbean region: New Approaches through Prevention

Project Number: RG-T1525

Period included in this Procurement Plan: From June 2008 until September 2009

| Ref. No. | Description of the contract and estimated cost of procurement | Estimated Contract Cost (US$ thousands) | Procurement method | Review (prior or post) | Source of financing and percentage |  | Prequalification (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | IDB % | Local/other % |  | Publication of specific procurement notice | Completion of contract |  |  |
|  | 1. Goods & Services |  |  |  |  |  |  |  |  |  |  |
| 1 | Publication materials | US$10,000 | Shopping | NA | 100 | - | No | Nov/08 | Dec/08 |  |  |
|  | 2. Civil Works: N/A |  |  |  |  |  |  |  |  |  |  |
|  | 3. Non-consulting Services: N/A | 0 |  |  |  |  |  |  |  |  |  |
|  | 4. Consulting Services |  |  |  |  |  |  |  |  |  |  |
| 2 | Consulting service 1: 7 individual consultants for thematic studies | US$50,000 | QCII | NA | 100 | - | No | June/08 | Dec/08 |  |  |
| 3 | Consulting service 2: International Training Workshop | US$85,000 | QCBS | NA | 100 | - | No | June/08 | Sept/08 |  |  |
| 4 | Consulting service 3: Individual Consultant-Editor | US$5,000 | QCII | NA | 100 | - | No | Sept/08 | Nov/08 |  |  |
| 5 | Consulting service 4: 2 Individual consultants (Violence prevention network) | US$60,000 | QCII | NA | 100 | - | No | Nov/08 | Nov/09 |  |  |
| 6 | Consulting service 5: Individual consultant for design and implementation of data collection system | US$ 40,000 | QCII | NA | 100 | - | No | Nov/08 | Nov/09 |  |  |
| 7 | Consulting service 6: Consulting firm to apply and analyze victimization survey | US$ 40,000 | QCBS | NA | 100 | - | No | Nov/08 | March/09 |  |  |

All project contracts should be included, even if not financed by the Bank, indicating the source of funding in each case.

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality- and cost-based selection QBS: Quality-based selection FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection;  3CV’s: Selection of Individual Consultant based on 3CV’s