## Sheet1
Inter-American Development Bank
VPC/FMP
PROCUREMENT PLAN FOR NON-REIMBURSABLE TECHNICAL COOPERATIONS
Country: Trinidad and Tobago |  |  |  |  | Executing agency: Caribbean Indsutrial Research Institute |  |  |  |  | Public or private sector: Private
Project number:TT-T1073 |  |  |  |  | Title of Project:Bridging the Gap to Commercial Application of Innovation
Period covered by the plan:36 months
Threshold for ex-post review of procurements: |  |  |  | Goods and services (in US$):____________ |  |  |  | Consulting services(in US$):____________
Item Nº | Ref. AWP | Description (1) | Estimated contract cost (US$) | Procurement Method (2) | Review of procurement (3) | Source of financing and percentage |  | Estimated date of the procurement notice or start of the contract | Technical review by the PTL (4) | Comments
[6 empty] | IDB/MIF % | Local/other % |  |  |  | Direct Contracting
1 |  | Component 1: Awareness Raising & Stakeholder Outreach | [8 empty] | International Competitive Bidding
National Competitive Bidding
|  | Goods | [8 empty] | Shopping
Least-Cost Selection
|  | Non consulting services | [8 empty] | Quality Based Selection
| 1.2 | Facilitation costs for ideation workshops | 80000 | SSS | ex post | 100% |  |  |  |  | Selection Based on the Consultants' Qualifications
| 1.4 | key note speakers | 25500 | SSS | ex post | 100%
| 1.1;1.3;1.8 | ideation workshop logistics | 113500 | PC | ex post | 100%
| 1.6 | Design and Implementation of social media campaign | 15000 | PC | ex post | 100%
Selection under a Fixed Budget
|  | Consulting services | [8 empty] | Individual Consultant
|  | Consulting service 1 (brief description) | [8 empty] | National System
Individual consultants
Consultant 1 (brief description)
2 |  | Component 2: Adaptation & Delivery of IAS
Goods
| 2.11 | Fab Lab equipment | 200000 | PC | ex post | 43% | 57%
Non Consulting Services
| 2.6 | Study tours | 52000 | PC | ex post | 100%
| 2.1 | Design and implementation of internal monitoring system | 10000 | SSS | ex post | 50% | 50%
| 2.14 | training costs for FAB LAB coordinator | 12000 | PC | ex post | 100%
Consulting Services
| 2.1 | Development of IAS Licensing Models | 60000 | SSS | ex post | 100%
| 2.2 | deluvery of training on IAS licensing models | 15000 | SSS | ex post | 100%
| 2.5 | partial financing for pilot innovations | 90000 | CQS | ex post | 66% | 34%
| 2.7 | Development of Business Model for IAS Services | 25000 | SSS | ex post | 100%
| 2.9 | Training in IAS Methodogies | 45000 | SSS | ex post | 66% | 34%
Component 3: Scaling of IAS Model
Non Consulting Services
| 3.2 | Participation in regional forums | 20000 | PC | ex post | 100%
| 3.3 | development of IAS network | 15000 | SSS | ex post | 66% | 34%
| 3.5 | facilitation of tech transfer visits | 16000 | PC | ex post | 25% | 75%
| 3.6 | Planning and dleivery of scaling workshop | 15000 | PC | ex post | 100%
Consulting Services
| 3.1 | Development of IAS Model | 25000 | SSS | ex post | 80% | 20%
| 3.4 | Development of corporate venture models | 10000 | CQS | ex post | 100%
Ex Ante
3 |  | Project Execution Unit | [8 empty] | Ex Post
Consulting Services
| 4.4 | Evaluation | 20000 | QCBS | ex post | 100%
Total |  |  | 0 | Prepared by: |  |  | Date:
(1) Grouping together of similar procurement is recommended, such as computer hardware, publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Goods and works: CB: Competitive bidding; PC: Price comparison; DC: Direct contracting.
(2) Consulting firms: CQS: Selection Based on the Consultants' Qualifications; QCBS: Quality and cost-based selection; LCS: Least Cost Selection; FBS: Selection nder a Fixed Budget; SSS: Single Source Selection; QBS: Quality Based selection.
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection.
(2) Country system: include selection Method
(3) Ex-ante/ex-post review: In general, depending on the institutional capacity and level of risk associated with the procurement, ex-post review is the standard modality. Ex-ante review can be specified for critical or complex process.
(4) Technical review: The PTL will use this column to define those procurement he/she considers "critical"or "complex"that require ex ante review of the terms of reference, technical specifications, reports, outputs, or other items.