## Sheet1
PROCUREMENT PLAN FOR NON-REIMBURSABLE TECHNICAL COOPERATIONS
Country: Regional |  |  |  |  | Executing agency: IDB |  |  |  |  | Public or private sector: PUBLIC
Project number: RG-T2489 |  |  |  |  | Title of Project: Establishment of the Caribbean Coastal Capital Center of Excellence
Period covered by the plan: 26 months (August 2014 - October 2016)
Threshold for ex post review of procurements: |  |  |  | Goods and services (in US$):45,000 |  |  |  | Consulting services(in US$):95,000
Item No. | Ref. AWP | Description (1) | Estimated contract cost (US$) | Procurement Method (2) | Review of procurement (ex-ante or ex-post) (3) | Source of financing and percentage |  | Estimated date of the procurement notice or start of the contract | Technical review by the PTL (4) | Comments
[6 empty] | IDB/MIF % | Local/other %
Consulting Services
1 |  | Component 1
|  | Individual Consultant: Preparation of Proposal for Caribbean Coastal Capital Center of Excellence | 89000 | IICQ | Ex-post | 100% | 0% | 2016-04-30
2 |  | Project Administration
|  | Consulting firm/Regional Organisation: Project Management Support | 15000 | SSS | Ex-post | 100% | 0% | 2016-04-30 |  | University of West Indies/Centre for Resource Management and Environmental Studies
Non- Consulting Services
|  | Regional Stakeholder Workshop | 26000 | PC | Ex-post | 100% | 0% | 2016-09-15
|  | PSC Meetings | 10000 | PC | Ex-post | 100% | 0% | 2016-07-01
Total |  |  | 140000