## RRF
INTER-AMERICAN DEVELOPMENT BANK
PROJECT RISK MANAGEMENT
RISKS AND PROBABILITY FACTORS
Nº | Project/ Component/ Product | Type of Risk | Risk | Impact | Probability Factor
1 | Guarantee Fund (unique component) | Macroeconomic and Fiscal Sustainability | Deterioration of macroeconomic framework as a result of external shocks or shift in macroeconomic policies or fiscal situation and overall economic conditions in the country or a change or failure in public management and governance of the Guarantee Fund could affect credit demand by IFI and SME. | Reduced demand for investment loans by SMEs | That exchange rate conditions deteriorate. | Development
[5 empty] | That international investments and financial flows are reduced. | Public Management and Governance
[5 empty] | Decrease in GDP and demand for goods and services. | Macroeconomic and Fiscal Sustainability
[5 empty] | That there are changes in government and or in governance of the CBB. | Environmental and Social Sustainability
Reputation
Monitoring and Accountability
Fiduciary
2 | Guarantee Fund (unique component) | Development | Overall sustainability of the Program - that SME access to finance will be reduced once the line of IDB financing is amortized. | Reduced access to credit by SMEs | That there would not be enough resources in the Guarantee Fund over time to maintain its sustainability
3 | Guarantee Fund (unique component) | Fiduciary | Lack of awareness of IDB disbursements and financial reporting procedures. | Because of institutional capacity of CBB to execute the loan according to IDB specific requirements, disbursements would be delayed. | That there would not be enough institutional capacity to understand and implement IDB requirements
4 | Guarantee Fund (unique component) | Monitoring and Accountability | Untimely monitoring and reporting on the guarantee scheme. (The CBB’s guarantee schemes are currently managed manually, using Microsoft Excel. As a result, the capacity to timely assess and provide for corrective actions regarding the conditions, operations and, ultimately, the demand, impact and performance of the guarantee schemes of the Loan is limited.) | Because of institutional limitations of CBB the treatment of guarantee requests would be delayed, discouraging demand. | That there would not be enough institutional capacity to develop electronic systems
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Note on D7: Select one type of risk from the list below

## RAM
INTER-AMERICAN DEVELOPMENT BANK
PROJECT RISK MANAGEMENT | [5 empty] | Risk Rating (Probability x Impact) | Risk Classification
[7 empty] | Value | Level
[6 empty] | 9 | 3 | High
[6 empty] | 6 | 3 | High
[6 empty] | 4 | 2 | Medium
[6 empty] | 3 | 2 | Medium
[6 empty] | 2 | 1 | Low
[6 empty] | 1 | 1 | Low
RISK ASSESSMENT MATRIX
Nº | Project/ Component/ Product | Type of Risk | Risk | Impact | Probability | Risk Rating (Probability x Impact) | Risk Classification
[7 empty] | Value | Level
1 | Guarantee Fund (unique component) | Macroeconomic and Fiscal Sustainability | Deterioration of macroeconomic framework as a result of external shocks or shift in macroeconomic policies or fiscal situation and overall economic conditions in the country or a change or failure in public management and governance of the Guarantee Fund could affect credit demand by IFI and SME. | 2 | 2 | 4 | 2 | Medium
2 | Guarantee Fund (unique component) | Development | Overall sustainability of the Program - that SME access to finance will be reduced once the line of IDB financing is amortized. | 2 | 1 | 2 | 1 | Low
3 | Guarantee Fund (unique component) | Fiduciary | Lack of awareness of IDB disbursements and financial reporting procedures. | 2 | 2 | 4 | 2 | Medium
4 | Guarantee Fund (unique component) | Monitoring and Accountability | Untimely monitoring and reporting on the guarantee scheme. (The CBB’s guarantee schemes are currently managed manually, using Microsoft Excel. As a result, the capacity to timely assess and provide for corrective actions regarding the conditions, operations and, ultimately, the demand, impact and performance of the guarantee schemes of the Loan is limited.) | 2 | 2 | 4 | 2 | Medium
5 |  |  |  | 1 | 1 | 1 | 1 | Low
6 |  |  |  | 1 | 1 | 1 | 1 | Low
7 |  |  |  | 1 | 1 | 1 | 1 | Low
8 |  |  |  | 2 | 2 | 4 | 2 | Medium
9 |  |  |  | 2 | 2 | 4 | 2 | Medium
10 |  |  |  | 2 | 2 | 4 | 2 | Medium
11 |  |  |  | 2 | 2 | 4 | 2 | Medium
12 |  |  |  | 2 | 2 | 4 | 2 | Medium
13 |  |  |  | 2 | 2 | 4 | 2 | Medium
14 |  |  |  | 2 | 2 | 4 | 2 | Medium
15 |  |  |  | 3 | 3 | 9 | 3 | High
16 |  |  |  | 3 | 3 | 9 | 3 | High
17 |  |  |  | 3 | 3 | 9 | 3 | High
18 |  |  |  | 3 | 3 | 9 | 3 | High
19 |  |  |  | 3 | 3 | 9 | 3 | High
20 |  |  |  | 3 | 3 | 9 | 3 | High

## RMM
INTER-AMERICAN DEVELOPMENT BANK
PROJECT RISK MANAGEMENT
Nº | Project/ Component / Product | Type of Risk | Risk | Risk Classification |  | RISK MITIGATION MATRIX
[6 empty] | Activity | How will the activity be carried out? | Budget | Start Date (Month/Day /Year) | End Date (Month/Day/Year) | Responsible Party |  | Compliance Indicator | Monitoring Date (Month/Day/Year)
|  |  |  | Value | Level | [5 empty] | Name | Institution |  | Executing Agency | IDB
1 | Guarantee Fund (unique component) | Macroeconomic and Fiscal Sustainability | Deterioration of macroeconomic framework as a result of external shocks or shift in macroeconomic policies or fiscal situation and overall economic conditions in the country or a change or failure in public management and governance of the Guarantee Fund could affect credit demand by IFI and SME. | 2 | Medium | The loan will be provided through IDB partial disbursements based on the pipeline of demand for the guarantee from IFIs. Hiring of a project coordinator and continuous follow-up of the Guarantee Fund operations through reporting by CBB of the demand for guarantees received and its operations in accordance with the OR. | Periodic follow-up. | 0 | 2014-12-01 | Continuous throughout the program | Ian Collymore | Agencia Ejecutora | Percentage of unallocated capital to guarantees (target 0%). |  | Every 6 months
Denise Salabie
2 | Guarantee Fund (unique component) | Development | Overall sustainability of the Program - that SME access to finance will be reduced once the line of IDB financing is amortized. | 1 | Low
3 | Guarantee Fund (unique component) | Fiduciary | Lack of awareness of IDB disbursements and financial reporting procedures. | 2 | Medium | Technical follow up by the representation about IDB requirements. | Ongoing direct support by the country office and CMF project team. | 0 | 2014-04-04 | Continuous support throughout the program | Denise Salabie |  | Percentage of periodic reports submitted by the CBB that are validated by the IDB without the need for correction (target 100%). |  | Every 6 months
4 | Guarantee Fund (unique component) | Monitoring and Accountability | Untimely monitoring and reporting on the guarantee scheme. (The CBB’s guarantee schemes are currently managed manually, using Microsoft Excel. As a result, the capacity to timely assess and provide for corrective actions regarding the conditions, operations and, ultimately, the demand, impact and performance of the guarantee schemes of the Loan is limited.) | 2 | Medium | Support to develop electronic systems to porcess the guarantee requests. | Direct support by CMF project team. Additional support may be provided through a technical cooperation if approved. | The CBB will provide their own resources to develop electronic system. | 2014-12-01 | 2015-06-30 | Ian Collymore | Agencia Ejecutora | Percentage of transactions processed electronically through a dedicated system (target 100%). |  | Every 6 months
[11 empty] | Maria Netto | IDB
5 |  |  |  | 1 | Low
6 |  |  |  | 1 | Low
7 |  |  |  | 1 | Low
8 |  |  |  | 2 | Medium
9 |  |  |  | 2 | Medium
10 |  |  |  | 2 | Medium
11 |  |  |  | 2 | Medium
12 |  |  |  | 2 | Medium
13 |  |  |  | 2 | Medium
14 |  |  |  | 2 | Medium
15 |  |  |  | 3 | High
16 |  |  |  | 3 | High
17 |  |  |  | 3 | High
18 |  |  |  | 3 | High
19 |  |  |  | 3 | High
20 |  |  |  | 3 | High
Agencia Ejecutora
BID
Note on I10: Describe how the activity is going to be carried out to mitigate a risk. For example: hiring a consultant for ex-post review
Note on O10: Describe how the mitigation action performed will be verified. The compliance indicator should allow the measurement of the effectiveness of the mitigation action. For example: ex-post review report by consultant, discussed and accepted by the Client and the Bank.

## Settings (hidden)
SETTINGS
LABELS
ComponentLabel | Component
Component1
Component2
Component3
Component4
Component5
Component6
Component7
Component8
Component9
Component10
Component11
Component12
Component13
Component14
Component15
Component16
Component17
Component18
Component19
Component20
Type of Risk Label | Type of Risk
Typeofrisk1
Typeofrisk2
Typeofrisk3
Typeofrisk4
Typeofrisk5
Typeofrisk6
Typeofrisk7
Typeofrisk8
Typeofrisk9
Typeofrisk10
Typeofrisk11
Typeofrisk12
Typeofrisk13
Typeofrisk14
Typeofrisk15
Typeofrisk16
Typeofrisk17
Typeofrisk18
Typeofrisk19
Typeofrisk20
RiskLabel | Risk
Risk1
Risk2
Risk3
Risk4
Risk5
Risk6
Risk7
Risk8
Risk9
Risk10
Risk11
Risk12
Risk13
Risk14
Risk15
Risk16
Risk17
Risk18
Risk19
Risk20
Impact Statement Level | Impact Statement
Probability Factor Statement Label | Probability Factor Statement
Impact Value Label | Impact Value
Impact1
Impact2
Impact3
Impact4
Impact5
Impact6
Impact7
Impact8
Impact9
Impact10
Impact11
Impact12
Impact13
Impact14
Impact15
Impact16
Impact17
Impact18
Impact19
Impact20
Probability Value Label | Probability Value
Probability1
Probability2
Probability3
Probability4
Probability5
Probability6
Probability7
Probability8
Probability9
Probability10
Probability11
Probability12
Probability13
Probability14
Probability15
Probability16
Probability17
Probability18
Probability19
Probability20
Calification Value Label | Calification
Risk Value Label | Value
Value1
Value2
Value3
Value4
Value5
Value6
Value7
Value8
Value9
Value10
Value11
Value12
Value13
Value14
Value15
Value16
Value17
Value18
Value19
Value20
Risk Level Label | Level
Level1
Level2
Level3
Level4
Level5
Level6
Level7
Level8
Level9
Level10
Level11
Level12
Level13
Level14
Level15
Level16
Level17
Level18
Level19
Level20
Activity Label | Activity
How is the activity to be done Label | How is the activity to be done
Budget Label | Budget
Beginning Date Label | Beginning Date (DD. MM.YY)
Ending Date Label | Ending Date (DD.MM.YY)
Responsible Label | Responsible
Responsible Name Label | Name
Responsabible Institution | Institution
Monitoring Date Label | Monitoring Date
Executing Agency Monitoring Date | Executing Agency
IDB Monitoring Date | IDB