DRAFT

DEVELOPMENT OF A MICRO-ENTERPRISE TRAINING SERVICES MARKETING PROGRAM -ATN/MN-6750-GY

## MIF PROJECT COMPLETION REPORT -OCTOBER 2004

A.  FINAL MIF PROJECT PERFORMANCE MONITORING REPORT (PPMR) OF OCTOBER 19, 2004, ATTACHED.

# B. MIF PROJECT COMPLETION MEMORANDUM

- Historical Perspective of the Project.

The original objectives of the Micro Enterprise Training project was to test and demonstrate the feasibility of establishing, on a small scale, a sustainable market for training services to microenterprise in Guyana, in order to improve their competitiveness and productivity.  This objective was supported by three key components viz: (i) establishment of an information referral service to microentrepreneurs; (ii) stimulation of demand through the use of direct, partial subsidies (issuance of vouchers); and (iii) establishment of a training technologies development fund to induce and  accelerate the adaption of suppliers’ capacity to meet specific small and micro enterprises

Neither the project's original objectives nor its indicators of the project have changed since its initiation. The only significant change in its composition was a shift of funds from the Training Technology Development Fund (TTDF) to the voucher component.  This shift was made when it was evident, despite a diligent marketing effort, that there was virtually no demand for the fund.

- Execution of the Project.

Execution of this project is deemed to have had mixed results.  The final PPMR shows that while project outputs were achieved, development objectives were not attained.  During the life of the project the training market wad developed and functioned.  However, once the programme came to an end  (November 2004), GVC could not sustain the programme.

With respect to execution of project components, the records show that Execution Agency,  Guyana Volunteer Consultancy (GVC), lacked the capacity and financial resources to effectively implement and sustain the project.  GVC lost its two key staff members shortly after the project agreement was signed and   they were not replaced.  This staff loss resulted in a delay in meeting the conditions for first disbursement and as a result an eight-month extension in the final disbursement was necessary to allow the full utilization of the voucher component.

Despite the weaknesses of GVC, the   Project Coordinating Unit (PCU) was staffed with a core of competent professionals who exercised judicious management of the project.  Therefore, the extension of the disbursement period does not reflect any operational deficiency on the part of the PCU.

  - Achievement of Development Objective

The development objective for this program was aimed at establishing a sustainable private sector market for training services to microentrepreneurs in Guyana so as to improve their competitiveness and productivity.

The key indicator was a yearly value of program supported training market transactions representing not less than 30% of the estimated potential.

The executing agency, GVC did not have the financial nor human capacity to sustain a program of this nature.  In this regard, one IDB, USAID and CIDA funds were exhausted, GVC could not continue the program and indications are that the program will not recommence in the future.

  - Achievement of Project Outputs

a)	The information and referral system was installed effectively and without delay, with the assistant of the international consulting firm, GAMA.  Referral services were established in four main towns,  Georgetown, Berbice, Essequibo and Linden

- Vouchers system.   The first voucher was distributed only six months after the date of eligibility for first disbursement.  Given that staff had to be recruited and trained, procedures written, and the information and referral system installed, the six months period was remarkable.  Demand increased steadily, peaking a year after the first set of vouchers were distributed.  Toward the end of the program, an extension in the period for disbursements was necessary to: (a) allow payments on outstanding vouchers because actual payments lagged several months behind the distribution of vouchers and (b) facilitate utilization of an available balance in the voucher fund budget category of US$112,000 which existed because the cost of the vouchers were reduced from the recommended US$20 to US$16 each.

In summary, outputs in this component surpassed the target set in the project document by 23%.  Thirty four thousand, three hundred and eighty vouchers (34,380) were reimbursed over the life of the programme, equivalent to US$524,239.  Distribution of vouchers was done over a wide geographical area, namely Georgetown, Berbice, Essequibo and Linden.

- c)			Training Technology Development Fund.  The TTDF was scarcely used and the funds were eventually transferred to the voucher component.  The original output was never achieved because microentrepreneurs did not demonstrate an interest in the component.

3. Lessons Learned and Best Practices.

- First, as explained above, the GVC lacked staff and contributed little of substance to the program. It was intended that the GVC would provide links to the private sector and ensure that the training programs were relevant to the needs of the society.  This did not occur.  However, the loss of the two key staff members was totally unanticipated and could hardly be a fair criticism of the GVC or the PCU.  A PCU staffed with a core of well trained professionals carried on the program effectively with minimum supervision from GVC.

- The project was based on a free market concept, allowing the maximum of choice by the trainee clients, and depending on a rapid flexible response by the training institutions. This concept has clearly worked, as measured by the impressive number of trainees, approved training institutions and approved courses. However, the concept was implemented on a first-come, first-served basis. If the training institutions and courses met reasonable standards of quality, they were approved regardless of their relevance to the needs of the economy.  Both the institutions and students lacked information, on economic opportunities and labor market conditions that might have helped them make better choices.  As a result, several promising fields were relatively overlooked, particularly construction trades and agri-business.  The lack of GVC orientation was a drawback.

- The Information and Referral Component, a database with extensive information on trainees and training institutions and their course offerings, did not include relevant economic, financial market information. One reason was the lack of pertinent  staff in the GVC and the PCU.

- The trainee-clients were micro-entrepreneurs who needed training in both technical and rudimentary business topics.  Although a few did, more of the courses could have included a business component, covering matters such as simple bookkeeping, cost calculations, customer relations, etc.

- The Training Technology Development Fund (TTDF) criteria were limited to training on pedagogical topics. As a result, the fund generated virtually no interest. At the same time, if the funds had been available for tools and modest equipment, the project might have stimulated courses in other fields such as construction skills and vehicle-appliance repairs.

- The program was limited to micro-entrepreneurs with demonstrated business experience.  However, business qualifications were interpreted generously.  Even part-time peddlers were included who were not likely to; contribute a significant value-added. At the same time, two categories that included many promising potential entrepreneurs were excluded from the project: young people without business experience and older people who have lost jobs in the formal labor market and need retraining. In other words, the program design with respect to trainee selection should have been more oriented toward business potential as well as   actual experience.

C. APPENDICES

- Executing Agency (EA) Memorandum. To be prepared by EA.

2. Basic Project Statistics.

2.1	Historical MPPMR Ratings

| Month Year | June 2002 | Dec 2002 | June 2003 | Dec 2003 | June 2004 | Oct 2004 |
| --- | --- | --- | --- | --- | --- | --- |
| IP | S | S | S | S | S | S |
| AS Components | H | H | H | H | H | H |
| DO | LP | LP | LP | LP | LP | LP |
| AS Objectives | L |  | L | L |  | L |

2.2`	.Basic Data on the Project

Registered  the project in the pipeline 			N.A.

CRG Review 						N.A.

Donor Approval 					10 Nov 1999

Agreement Signature 				28 Mar 2000

Eligibility for First Disbursement 			15 Mar 2001

Actual First Disbursement 				27 Mar 2001

Midterm Review 					   June 2002

Final Disbursement, Original Date 		28 Mar 2004

Current Date 					30 Nov 2004

Total Project Cost, Original Estimate 		 $1,435,000

Current Estimate 				 $1,324,550

MIF Financing, Original Amount			    $900,000

Current Amount					    $899,979

.	Project Cost and Financing by Source (Original and Final)

| SOURCE OF FUNDING | APPROVED CATEGORY | BUDGET (US$) | ACTUAL (US$) |
| --- | --- | --- | --- |
| IDB/MIF | Total | 900,000 | 899,979 |
|  | Information, referral sys. | 100,000 | 125,530 |
|  | Vouchers | 380,000 | 349,892 |
|  | Training Development Fund, TTDF | 50,000 | 1,567 |
|  | Program coordination | 174,000 | 293,937 |
|  | International Tech. Assist. | 145,000 | 118,474 |
|  | Evaluations, surveys | 30,000 | 10,596 |
| USAID | International Technical Assistance | 119,000 | 119,000 |
|  | Promotion | 50,000 | 50,000 |
|  | Evaluation | 31,000 | 31,000 |
| CIDA | Voucher Fund | 180,000 | 176,806 |
|  | TTDF | 25,000 | O |
|  | International TA | 25,000 | 9,433 |
| Training Institution | TTDF | 75,000 | 1,577 |
| GVC | General Support | 30,000 | 35,875(in kind contributions) |
| Totals |  | 1,435,000 | 1,324,550 |

Schedule of Expenditures by Source of Financing.

| YEAR | 2001 | 2002 | 2003 | 2004 | TOTALS |
| --- | --- | --- | --- | --- | --- |
| MIF | 220,702 | 320,359 | 356,344 | 2,586 | 899.979 |
| USAID | 32,604 | 56,369 | 92,343 | 18,684 | 200,000 |
| CIDA |  |  | 9,433 | 176,806 | 186,239 |
| GVC | 12,915 | 8,260 | 8,400 | 7,200 | 35,875, |
| Tis |  | 1,537 |  |  | 1,537 |
| TOTALS | 266,221 | 386,525 | 466,528 | 205,276 | 1,324,550 |

MIF data from Representation; other data from PCU, through Sept. 2004

MIF data from Representation; other data from PCU, through Sept. 2004.