| Ref. No. | Description of the contract and estimated cost of procurement | Procurement method | Source of financing and percentage |  | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/other % | Publication of specific procurement notice | Completion of contract |  |  |
|  | - Goods - Good 1 CZMU Equipment Estimated cost (US150,000.00) | N/A | 0 | 100 | N/A | N/A | COMPLETED |  |
|  | - Civil works - Work 1 Brief description Rockley to Coconut Court Beach Improvement Contract Cost (US$ $9,199,304.25) - Work 2 Brief description Holetwon Beach Improvement Contract Cost ( US$3,450,282.10) - Work 3 Brief description Crane Beach Improvement Estimated Cost (US$1,933,260) - Work 4 Brief description Holetown Lagoon Water Quality Improvement Estimated cost ( US$616,883.60) - Work 5 Brief description Tent Bay Boat Access Estimated Cost (US$667,773) | ICB ICB ICB NCB NCB | 80 80 80 80 70 | 20 20 20 20 30 | November 2006 March 2008 March 2008 December 2008 December 2008 | December 2007 February 2009 N/A April 2009 April 2009 | Awarded Awarded N/A Pending Pending | Acquisition process and legal issues delaying tendering of this. Tender documents complete. Project to be cancelled from this loan. Tender Process has been completed twice for this project. Only one tender submitted both times. Project being re -designed |
|  | - Consulting services - Consulting services 1 Final Designs & Supervision Estimated cost (US$397,676 plus 9.5% of construction cost for construction supervision) - Consulting services 2 Auditing Firm Estimated cost (US$11,000 per Annum) - Consulting services 3 Technical Quality Control Estimated Cost (US$100,00.00) - Consulting services 4 MEE Strategic Plan Estimated Cost (US$60,00.00) - Consulting services 4 MEE Public Education Strategy Estimated Cost (US$70,00.00) | ICB NCB N/A ICB ICB | 0 0 0 0 0 | 100 100 100 100 100 | July, 2001 January, 2003 N/A - - | January 2003 April 2004 February 2003 - - | Awarded Awarded Awarded - - | Contract currently being extended to April 2009 Contract currently being extended to April 2009 Contract currently being extended to April 2009 Project to be re-defined. New proposals expected by November 2008 |

If there are a number of similar individual contracts to be executed in different places or at different times, these can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contracts would be executed. For example: an education project that includes school construction might include an item “school construction”, for a total value of US$20 million, and an explanation in the comments column such as: “This encompasses some 200 contracts for school construction averaging US$100,000 each to be awarded individually by the participating municipal governments over a three-year period between January 2006 and December 2008.”

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality- and cost-based selection QBS: Quality-based selection FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection.