## PEP
JA-L1056 PLURIANNUAL EXECUTION PLAN (PEP)
Task Name | Duration (days) | Start | Finish | Cost | Procurement Method | Works/Goods/Consultancy/Training/Transfers
ENERGY MANAGEMENT AND EFFICIENCY PROGRAMME |  |  |  | 30000000 |  | 30000000
START |  |  |  | -
COMPONENT 1. RETROFITTING HEPA GOVERNMENT FACILITIES |  |  |  | 21135000
1.1 - PROCUREMENT OF RE TECHNOLOGY AND EE MEASURES (HOSPITALS AND SCHOOLS) |  |  |  | 8390000 |  | Works
1.1.1 KPH-VJ | 450 days | Mon 11/6/17 | Fri 7/26/19 | 4110000 | ICB
1.1.2 Cornwall | 300 days | Mon 10/1/18 | Fri 11/22/19 | 2500000 | ICB
1.1.3 Mandeville | 250 days | Mon 9/30/19 | Fri 9/11/20 | 550000 | ICB
1.1.4 Falmouth | 250 days | Mon 10/2/17 | Fri 9/14/18 | 500000 | ICB
1.1.5 Ebony Heart | 250 days | Mon 7/9/18 | Fri 6/21/19 | 525000 | ICB
1.1.6 Marcus Garvey | 180 days | Mon 8/7/17 | Fri 4/13/18 | 205000 | ICB
1.2 - PROCUREMENT OF RE TECHNOLOGY AND EE MEASURES (PUBLIC AGENCIES) |  |  |  | 7055000 |  | Works
1.2.1 Electoral Office/Duke Stree | 200 days | Mon 4/1/19 | Fri 1/3/20 | 290000 | ICB
1.2.2 Ministry of Agriculture | 150 days | Mon 7/1/19 | Fri 1/24/20 | 115000 | ICB
1.2.3 Ministry of Finance | 420 days | Mon 10/8/18 | Fri 5/15/20 | 3260000 | ICB
1.2.4 KSAC Church St. | 200 days | Mon 1/20/20 | Fri 10/23/20 | 250000 | ICB
1.2.5 Halfway Tree Transport Center | 350 days | Mon 4/2/18 | Fri 8/2/19 | 820000 | ICB
1.2.6 BSJ | 280 days | Mon 10/12/20 | Fri 11/5/21 | 705000 | ICB
1.2.7 MLSS | 250 days | Mon 2/8/21 | Fri 1/21/22 | 670000 | ICB
1.2.8 UDC | 200 days | Mon 10/12/20 | Fri 7/16/21 | 355000 | ICB
1.2.9 PCJ | 200 days | Mon 4/12/21 | Fri 1/14/22 | 220000 | ICB
1.2.10 Jamaica Library Service Headquarters | 250 days | Mon 4/12/21 | Fri 3/25/22 | 370000 | ICB
1.3 - PROCUREMENT OF RE TECHNOLOGY AND EE MEASURES (EDUCATION) |  |  |  | 1380000 |  | Works
1.3.1 Russeas | 200 days | Mon 1/13/20 | Fri 10/16/20 | 230000 | ICB
1.3.2 St James High | 200 days | Mon 1/13/20 | Fri 10/16/20 | 220000 | ICB
1.3.3 Holmwood | 180 days | Mon 7/6/20 | Fri 3/12/21 | 200000 | ICB
1.3.4 Port Antonio | 150 days | Mon 10/5/20 | Fri 4/30/21 | 135000 | ICB
1.3.5 Camperdown | 230 days | Mon 4/12/21 | Fri 2/25/22 | 265000 | ICB
1.3.6 Knox CollegE | 180 days | Mon 7/5/21 | Fri 3/11/22 | 190000 | ICB
1.3.7 Morant Bay High | 160 days | Mon 7/5/21 | Fri 2/11/22 | 140000 | ICB
1.4 - LIGHT RETROFITTING |  |  |  | 2850000 |  | Works
1.4.1 Energy efficiency lights in 20 buldings (Phase 1) | 600 days | Mon 10/9/17 | Fri 1/24/20 | 1150000 | ICB
1.4.2 Energy efficiency lights in 30 buldings (Phase 2) | 800 days | Mon 10/1/18 | Fri 10/22/21 | 1700000 | ICB
1.5 - CONSULTANCIES AND TRAINING |  |  |  | 1460000
1.5.1 Combined Selection of firm to undertake 17 Investment Grade Audits | 475 days | Mon 8/5/19 | Fri 5/28/21 | 300000 | QCBS | Consulting Firm
1.5.2 Environmental Plan & Waste Disposal Measure | 515 days | Mon 7/6/20 | Fri 6/24/22 | 750000 | SBCQ | Consulting Firm
1.5.3 Trainning and manuals in EE Maintenance to be extended to facilitities teams in each building | 515 days | Mon 7/6/20 | Fri 6/24/22 | 160000 | SBCQ | Trainning
1.5.4 Communications & Raising awareness | 515 days | Mon 7/6/20 | Fri 6/24/22 | 250000 | SBCQ | Training
COMPONENT 2. Implementation of an Urban Traffic Management System |  |  |  | 3500000
2.1 CENTRAL CONTROL SYSTEM |  |  |  | 122600 | ICB | Works
2.1.1 Server | 20 days | Mon 5/1/17 | Fri 5/26/17 | 10000
2.1.2 Workstation | 20 days | Mon 5/29/17 | Fri 6/23/17 | 16000
2.1.3 Firewall | 10 days | Mon 6/26/17 | Fri 7/7/17 | 5000
2.1.4 Printer | 10 days | Mon 7/10/17 | Fri 7/21/17 | 600
2.1.5 Forniture | 5 days | Mon 7/24/17 | Fri 7/28/17 | 5000
2.1.6 Local network wiring | 10 days | Mon 7/31/17 | Fri 8/11/17 | 2000
2.1.7 SunGide software | 30 days | Mon 8/14/17 | Fri 9/22/17 | 80000
2.1.8 VMA Software | 15 days | Mon 9/25/17 | Fri 10/13/17 | 1000
2.1.9 Virtual Loop Software | 15 days | Mon 10/16/17 | Fri 11/3/17 | 1000
2.1.10 ALPR Software | 20 days | Mon 11/6/17 | Fri 12/1/17 | 1000
2.1.11 CCTV Software | 20 days | Mon 12/4/17 | Fri 12/29/17 | 1000
2.2 COMMUNICATIONS |  |  |  | 1153380 | ICB | Works
2.2.1 Switch FX | 50 days | Mon 6/5/17 | Fri 8/11/17 | 316200
2.2.2 Switch ITS SFP | 20 days | Mon 8/14/17 | Fri 9/8/17 | 41800
2.2.3 Switch GE rack | 30 days | Mon 9/11/17 | Fri 10/20/17 | 60000
2.2.4 Power Supply | 20 days | Mon 10/23/17 | Fri 11/17/17 | 24480
2.2.5 SFP GX | 10 days | Mon 11/20/17 | Fri 12/1/17 | 6300
2.2.6 SFP FX | 15 days | Mon 12/4/17 | Fri 12/22/17 | 10080
2.2.7 FO patch cord | 10 days | Mon 12/25/17 | Fri 1/5/18 | 3040
2.2.8 CAT5 patch cord | 30 days | Mon 1/8/18 | Fri 2/16/18 | 25280
2.2.9 FO service cable | 30 days | Mon 2/19/18 | Fri 3/30/18 | 61200
2.2.10 FO splice closure | 30 days | Mon 4/2/18 | Fri 5/11/18 | 64800
2.2.11 Communications cabinet | 20 days | Mon 5/14/18 | Fri 6/8/18 | 13200
2.2.12 FO cable | 100 days | Mon 6/11/18 | Fri 10/26/18 | 450000
2.2.13 HDPD Duct | 30 days | Mon 10/29/18 | Fri 12/7/18 | 25000
2.2.14 Radio | 50 days | Mon 12/10/18 | Fri 2/15/19 | 52000
2.3 PERIPHERIAL DEVICES |  |  |  | 1543200 | ICB | Works
2.3.1 Variable message sign | 50 days | Mon 11/6/17 | Fri 1/12/18 | 125000
2.3.2 Virtual loop detector | 120 days | Mon 1/15/18 | Fri 6/29/18 | 306000
2.3.3 Bluetooth WiFi sensor | 50 days | Mon 7/2/18 | Fri 9/7/18 | 175500
2.3.4 ALPR | 120 days | Mon 9/10/18 | Fri 2/22/19 | 560000
2.3.5 CCTV Camera | 100 days | Mon 2/25/19 | Fri 7/12/19 | 217000
2.3.6 Conflic monitor | 50 days | Mon 7/15/19 | Fri 9/20/19 | 47000
2.3.7 ATM Modem | 30 days | Mon 9/23/19 | Fri 11/1/19 | 40250
2.3.8 Memory module | 50 days | Mon 11/4/19 | Fri 1/10/20 | 72450
2.4 OPERATIONAL CAPACITY AND TRAINING |  |  |  | 200000 | ICB | Training
2.4.1 Baseline and impact documentation | 30 days | Mon 9/4/17 | Fri 10/13/17 | 15000
2.4.2 Traffic model software | 30 days | Mon 10/16/17 | Fri 11/24/17 | 40000
2.4.3 Traffic planning software | 10 days | Mon 11/27/17 | Fri 12/8/17 | 10000
2.4.4 SOP development | 30 days | Mon 12/11/17 | Fri 1/19/18 | 40000
2.4.5 System training | 30 days | Mon 1/22/18 | Fri 3/2/18 | 25000
2.4.6 Planning traning | 10 days | Mon 3/5/18 | Fri 3/16/18 | 15000
2.4.7 SunGuide training | 15 days | Mon 3/19/18 | Fri 4/6/18 | 25000
2.4.8 Coaching | 40 days | Mon 4/9/18 | Fri 6/1/18 | 30000
2.5 OTHERS |  |  |  | 180000 | ICB | Works
2.5.1 Lift truck | 20 days | Mon 11/13/17 | Fri 12/8/17 | 70000
2.5.2 Fiber splicer | 30 days | Mon 12/11/17 | Fri 1/19/18 | 25000
2.5.3 Fiber blower | 60 days | Mon 1/22/18 | Fri 4/13/18 | 50000
2.5.4 Portable ground penetrating radar | 30 days | Mon 4/16/18 | Fri 5/25/18 | 35000
2.6 ADMINISTRATION, UTILITY, UNFORSEEN EXPENSES | 300 days | Mon 5/8/17 | Fri 6/29/18 | 300820 | ICB
COMPONENT 3. SUPPORT TO ELECTRICITY PLANNING |  |  |  | 1780000
3.1 ELECTRICITY AND ENERGY PLANNING SYSTEM |  |  |  | 550000
3.1.1 Diagnostic study on IT | 80 days | Mon 5/14/18 | Fri 8/31/18 | 100000 | QCBS | Consulting Firm
3.2.2 IT software for coordination IRP (puchase, installation, operation and trainning) | 200 days | Mon 9/3/18 | Fri 6/7/19 | 450000 | ICB | Goods
3.2 CONSULTANCIES |  |  |  | 1230000
3.2.1 Institutional capacity building of the MSET for wider energy planning and supervision | 1085 days | Mon 5/1/17 | Fri 6/25/21 | 350000 | SBCQ | Trainning
3.2.2 Technical Study to support the IRP | 250 days | Mon 5/13/19 | Fri 4/24/20 | 260000 | QCBS | Consulting Firm
3.2.3 Technical Experts to support Electricity and Energy Planning in MSET | 800 days | Mon 4/2/18 | Fri 4/23/21 | 620000 | NICQ | Individual consultant
4. OTHER COSTS |  |  |  | 3585000
4.1 MONITORING, EVALUATION AND AUDITS |  |  |  | 530000
4.1.1 Mid-term Evaluation Report | 60 days | Mon 9/2/19 | Fri 11/22/19 | 50000 | SBCQ | Consultancy Firm
4.1.2 Final Evaluation Report | 60 days | Mon 11/7/22 | Fri 1/27/23 | 50000 | SBCQ | Consultancy Firm
4.1.3 Financial Audits | 1565 days | Wed 2/1/17 | Tue 1/31/23 | 180000 | SSS | Consultancy Firm
4.1.4 Programme Monitoring and Evaluation | 1565 days | Wed 2/1/17 | Tue 1/31/23 | 250000 | QCBS | Consultancy Firm
4.2 PEU PROJECT MANAGEMENT |  |  |  | 3055000
4.2.1 Project Manager | 1565 days | Wed 2/1/17 | Tue 1/31/23 | 480000 | NICQ | Individual consultancy
4.2.2 MSET - Sub Project Manager | 1565 days | Wed 2/1/17 | Tue 1/31/23 | 240000 | NICQ | Individual consultancy
4.2.3 NWA - Sub Project Manager | 1565 days | Wed 2/1/17 | Tue 1/31/23 | 240000 | NICQ | Individual consultancy
4.2.4 Finance Officer | 1565 days | Wed 2/1/17 | Tue 1/31/23 | 360000 | NICQ | Individual consultancy
4.2.5 Procurement Officer | 1565 days | Wed 2/1/17 | Tue 1/31/23 | 360000 | NICQ | Individual consultancy
4.2.6 Administrative Officer | 1565 days | Wed 2/1/17 | Tue 1/31/23 | 180000 | NICQ | Individual consultancy
4.2.7 Monitoring and Evaluation Specialist | 1565 days | Wed 2/1/17 | Tue 1/31/23 | 210000 | NICQ | Individual consultancy
4.2.8 Quantity Surveyor | 1565 days | Wed 2/1/17 | Tue 1/31/23 | 300000 | NICQ | Individual consultancy
4.2.9 ESG Coordinator | 1565 days | Wed 2/1/17 | Tue 1/31/23 | 240000 | NICQ | Individual consultancy
4.2.10 Electrical Consultant | 1565 days | Wed 2/1/17 | Tue 1/31/23 | 180000 | NICQ | Individual consultancy
4.2.11 Internal control and technical studies | 1565 days | Wed 2/1/17 | Tue 1/31/23 | 80000 | SBCQ | Consultancy
4.2.12 Motor vehicle A and Upkeep | 1565 days | Wed 2/1/17 | Tue 1/31/23 | 85000 | Shopping | Goods
4.2.13 Office supplies and financial software tool | 1565 days | Wed 2/1/17 | Tue 1/31/23 | 100000 | Shopping | Goods
END |  |  |  | -
(1) Goods and Works: ICB: international competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: procurement through specilaized agencies; PA: procrement agents; IA: inspection Agents; PLFI: procurement in loans to financial intermediaries; BOO/BOT/BOOT: build own, operate/build, operate, transfer/build, own,operate, transfer; PBP: performance-based procurement; PLGB: procurement under loans guaranteed by Bank; PCP: community participation procurement. Consulting Firms: QCBS: quality and cost-based selection; QBS: quality-based selection; FBS: selection under a fixed budget; LCS: least-cost selection; CQS: selection based on the Consultant's Qualifications; SSS: single-source selection. Individual Consultants: NICQ: national individual consultant selection based on qualifications; IICQ: international individual consultant selection based on qualifications.

## Implementation Plan
SECTION 2
IMPLEMENTATION PLAN
No. of component | COMPONENT | SUB-COMPONENT | OUTPUT | MILESTONE ACTIVITY1 | IDB COSTS |  |  | JICA COSTS |  |  | TOTAL INDICATIVE | ESTIMATED START DATE | ESTIMATED END DATE |  |  |  | RESPONSIBILITY (PERSON/AGENCY)
[5 empty] | INDICATIVE | ACTUAL | VARIANCE | INDICATIVE | ACTUAL | VARIANCE |  |  |  | PLANNED OUTPUT FOR THE YEAR | ACTUAL CUMULATIVE OUTPUT TO DATE | REMAINING OUTPUT TO BE ACHIEVED
Component 1: Retrofitting HEPA Government Facilities | [10 empty] | 21135000
Output 1.1 HEPA government facilities with Energy Efficiency (EE) equipment replaced, installed and operating. |  |  |  |  | 8562500 |  |  | 8562500 |  |  | 17125000
1.1 | 1 |  | 23 buildings retrofitted with EE/RE | Investment Grade Audits on remaining 17 buildings | 150000 |  |  | 150000 |  |  | 300000 | [5 empty] | PCJ
|  |  |  | Works completed in 23 buildings | 8412500 |  |  | 8412500 |  |  | 16825000 | [5 empty] | PCJ
Output 1.2 EE light technology replaced, installed and operating in HEPA government facilities |  |  |  |  | 1425000 |  |  | 1425000 |  |  | 2850000
1.2 | 1 |  | 50 buldings with EE light retrofitted | Energy efficiency lights in 20 buldings (Phase 1) | 575000 |  |  | 575000 |  |  | 1150000 | [5 empty] | PCJ
|  |  |  | Energy efficiency lights in 30 buldings (Phase 2) | 850000 |  |  | 850000 |  |  | 1700000 | [5 empty] | PCJ
Output 1.3: Workshops completed on EE management & maintenance in HEPA government facilities |  |  |  |  | 80000 |  |  | 80000 |  |  | 160000
1.3 | 1 |  | 5 workshops completed | Workshops on EE management & maintenance | 80000 |  |  | 80000 |  |  | 160000 | [5 empty] | PCJ
Outpu 1.4: EE manuals developed for management and maintenance of HEPA government facilities |  |  |  |  | 500000 |  |  | 500000 |  |  | 1000000
1.4 | 1 |  | 3 EE manuals developed | EE Manuals for management | 375000 |  |  | 375000 |  |  | 750000 | [5 empty] | PCJ
|  |  | Communications developed | Communications awareness | 125000 |  |  | 125000 |  |  | 250000 | [5 empty] | PCJ
Component 2: Implementation of an Urban Traffic Management System | [10 empty] | 3500000
Output 2.1: Equipment necessary to upgrade the central control system purchased, installed and operating. |  |  |  |  | 61300 |  |  | 61300 |  |  | 122600
2.1 | 2 |  | One (1) Central Control System installed | Traffic monitoring, operation, planning and modelling. | 61300 |  |  | 61300 |  |  | 122600 | [5 empty] | PCJ/NWA
Output 2.2: Equipment necessary to modernize and coordinate traffic signals purchased, installed and operating. |  |  |  |  | 1438290 |  |  | 1438290 |  |  | 2876580
2.2 | 2 |  | Traffic signals purchased, installed and operating | Communications | 576690 |  |  | 576690 |  |  | 1153380 | [5 empty] | PCJ/NWA
|  |  |  | Pheripherial devices | 771600 |  |  | 771600 |  |  | 1543200 | [5 empty] | PCJ/NWA
|  |  |  | Other costs (Fibers, lifth truck, radar) | 90000 |  |  | 90000 |  |  | 180000 | [5 empty] | PCJ/NWA
Output 2.3: Number of Packages of Support for Training and Capacity Building in Intelligent Transportation System delivered |  |  |  |  | 250410 |  |  | 250410 |  |  | 500820
2.3 | 2 |  | Four (4) packages delivered | Operational Capacity and Training | 100000 |  |  | 100000 |  |  | 200000 | [5 empty] | PCJ/NWA
|  |  |  | Administration, utility, unforseen expenses | 150410 |  |  | 150410 |  |  | 300820 | [5 empty] | PCJ/NWA
Component 3: Support to Electricity Planning | [10 empty] | 1780000
Output 3.1: Number of technical studies to support IRP revision or update completed |  |  |  |  | 130000 |  |  | 130000 |  |  | 260000
3.1 | 3 |  | One (1) Technical study developed | Studies on electrical losses, and integrated energy planning. | 130000 |  |  | 130000 |  |  | 260000 | [5 empty] | PCJ/MSET
Output 3.2: Number of training modules completed to support technical capacity in MSET to revise or update IRP |  |  |  |  | 175000 |  |  | 175000 |  |  | 350000
3.2 | 3 |  | Three (3) modules training developed | Institutional capacity building of the MSETfor wider energy planning and supervision | 175000 |  |  | 175000 |  |  | 350000 | [5 empty] | PCJ/MSET
Output 3.3: Number of technical experts contracted to reinforce capacity and develop training plans within MSET to enable staff to revise or update IRP |  |  |  |  | 310000 |  |  | 310000 |  |  | 620000
3.3 | 3 |  | Three (3) technical experts contracted | Experts in Energy Efficiency and Demand-Side Management; Electricity Sales and Rates; and Transmission & Distribution. | 310000 |  |  | 310000 |  |  | 620000 | [5 empty] | PCJ/MSET
Output 3.4: Diagnostic study completed on IT software required in MSET to support IRP coordination |  |  |  |  | 50000 |  |  | 50000 |  |  | 100000
3.4 | 3 |  | One (1) diagnostic study comleted | Diagnostic study on IT | 50000 |  |  | 50000 |  |  | 100000 | [5 empty] | PCJ/MSET
Output 3.5: Appropriate IT software for coordinating IRP purchased, installed and operating |  |  |  |  | 225000 |  |  | 225000 |  |  | 450000
3.5 | 3 |  | One (1) IT software operating | IT software for coorditanio IRP (puchase, installation, operation and training) | 225000 |  |  | 225000 |  |  | 450000 | [5 empty] | PCJ/MSET
PEU Project Management |  |  |  |  | 1527500 |  |  | 1527500 |  |  | 3055000
|  |  | PEU Established and Operational |  | 1527500 |  |  | 1527500 |  |  | 3055000 | [5 empty] | PCJ
Audit and Evaluation |  |  |  |  | 265000 |  |  | 265000 |  |  | 530000
|  |  | Mid-term Evaluation Report |  | 25000 |  |  | 25000 |  |  | 50000 | [5 empty] | PCJ
|  |  | Final Evaluation Report |  | 25000 |  |  | 25000 |  |  | 50000 | [5 empty] | PCJ
|  |  | Financial Audits |  | 90000 |  |  | 90000 |  |  | 180000 | [5 empty] | PCJ
|  |  | Programme Monitoring and Evaluation |  | 125000 |  |  | 125000 |  |  | 250000 | [5 empty] | PCJ
TOTAL |  |  |  |  | 15000000 |  |  | 15000000 |  |  | 30000000
Authorized Signature(s) | [5 empty] | Name(s) and Title(s)
1 The milestone activities must reflect the procurement methodology employed.
Note on F8: IADB: Total cost of Output / Project 1 (sum of all milestone activities)
Note on F11: IADB: Total cost of Output / Project 1 (sum of all milestone activities)
Note on I8: IADB: Total cost of Output / Project 1 (sum of all milestone activities)
Note on I11: IADB: Total cost of Output / Project 1 (sum of all milestone activities)
Note on I40: IADB: Total cost of Output / Project 2

## Detailed Procurement Plan
PROCUREMENT PLAN INITIAL LOAD INFORMATION (ONGOING AND/OR LAST PRESENTED)
WORKS | [16 empty] | National System
Executing Agency | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method |  | Ex-Post
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount JICA % |  | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature |  |  | Ex-Ante
PCJ | Procurement of RE Technology and EE Measures (Hospitals and Schools) | Pending | International Competitive Bidding |  |  | 8390000 | 50 | 50 |  | 0 | 1 | Ex-Ante | 2017-04-01 | 2017-09-01 |  |  | Cancelled
PCJ | Procurement of RE Technology and EE Measures (Public Agencies) | Pending | International Competitive Bidding |  |  | 7055000 | 50 | 50 |  | 0 | 1 | Ex-Ante | 2018-04-01 | 2018-09-01 |  |  | Contract Concluded
PCJ | Procurement of RE Technology and EE Measures (Education) | Pending | International Competitive Bidding |  |  | 1380000 | 50 | 50 |  | 0 | 1 | Ex-Ante | 2019-04-01 | 2019-09-01 |  |  | Contract in Execution
PCJ | Energy efficiency lights in 20 buldings (Phase 1) | Pending | International Competitive Bidding |  |  | 1150000 | 50 | 50 |  | 0 | 1 | Ex-Ante | 2018-04-01 | 2018-09-01 |  |  | Contract Terminated
PCJ | Energy efficiency lights in 30 buldings (Phase 2) | Pending | International Competitive Bidding |  |  | 1700000 | 50 | 50 |  | 0 | 1 | Ex-Ante | 2017-04-01 | 2017-09-01 |  |  | Null and Void
[6 empty] | 19675000 | [10 empty] | Ongoing
Planned
GOODS | [16 empty] | Rejection of all Bids
Executing Agency | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method |  | Re-Tendering
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount JICA % |  | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature
PCJ | Procurement for the design of an Urban Traffic Management Program in Kingston to Support fuel efficiency in the Transport Sector | Pending | International Competitive Bidding |  |  | 3500000 | 50 | 50 |  | 0 | 2 | Ex-Ante | 2017-05-01 | 2017-10-01 |  |  | International Competitive Bidding
PCJ | IT software for coordination IRP | Pending | International Competitive Bidding |  |  | 450000 | 50 | 50 |  | 0 | 3 | [5 empty] | National Competitive Bidding
PCJ | Office supplies and financial software tool | Pending | Shopping |  |  | 100000 | 50 | 50 |  | 0 | 4 | Ex-Ante | 2017-04-01 | 2017-05-01 |  |  | Shopping
PCJ | Motor vehicle A and Upkeep | Pending | Shopping |  |  | 85000 | 50 | 50 |  | 0 | 4 | [5 empty] | Direct Contracting
[6 empty] | 4135000 | [10 empty] | National System
Limited Competitive Bidding
NON CONSULTING SERVICES | [16 empty] | Prequalification
Executing Agency | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method |  | Two-envelope International Competitive Bidding
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: |  |  | Estimated Amount Counterpart %: |  |  | Bidding Documents | Contract Signature |  |  | International Competitive Bidding by Lots
Comparison of Qualifications - National Individual Consultant
[6 empty] | 0 | [10 empty] | Comparison of Qualifications - International Individual Consultant
CONSULTING FIRMS | [16 empty] | Quality and Cost Based Selection
Executing Agency | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method |  |  | Quality Based Selection
[5 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount JICA % |  | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature |  |  |  | Selection Based on the Consultants' Qualifications
Petroleum Corporation of Jamaica | Combined Selection of firm to undertake 17 investment grade audits | Pending | Quality and Cost Based Selection |  | 300000 | 50% | 50% | 0% |  | 1 | Ex-Ante | 2017-12-01 | 2018-04-01 |  |  |  | Single Source Selection
Petroleum Corporation of Jamaica | Environmental Plan & Waste Disposal Measure | Pending | Selection Based on the Consultants' Qualifications |  | 750000 | 50% | 50% | 0% |  | 1 | Ex-Ante | 2017-10-01 | 2017-12-01 |  |  |  | National System
Petroleum Corporation of Jamaica | Diagnostic study on IT | Pending | Quality and Cost Based Selection |  | 100000 | 50% | 50% | 0% |  | 3 | Ex-Ante | [5 empty] | Least cost Selection
Petroleum Corporation of Jamaica | Technical Study to support the IRP | Pending | Quality and Cost Based Selection |  | 260000 | 50% | 50% | 0% |  | 3 | Ex-Ante | [5 empty] | Selection under a Fixed Budget
Petroleum Corporation of Jamaica | Mid-term Evaluation Report | Pending | Selection Based on the Consultants' Qualifications |  | 50000 | 50% | 50% | 0% |  | 4 | Ex-Ante
Petroleum Corporation of Jamaica | Final Evaluation Report | Pending | Selection Based on the Consultants' Qualifications |  | 50000 | 50% | 50% | 0% |  | 4 | Ex-Ante | [5 empty] | Comparison of Qualifications - National Individual Consultant
Petroleum Corporation of Jamaica | Financial Audits | Pending | Single Source Selection |  | 180000 | 50% | 50% | 0% |  | 4 | Ex-Ante | [5 empty] | Comparison of Qualifications - International Individual Consultant
Petroleum Corporation of Jamaica | Programme Monitoring and Evaluation | Pending | Quality and Cost Based Selection |  | 250000 | 50% | 50% | 0% |  | 4 | [6 empty] | Turnkey | Goods
Petroleum Corporation of Jamaica | Internal control and technical studies | Pending | Quality and Cost Based Selection |  | 80000 | 50% | 50% | 0% |  | 1 | Ex-Ante | 2017-10-01 | 2018-03-01 |  |  |  | Unit Prices | Goods
[5 empty] | 2020000 | [11 empty] | Lump-Sum | Goods
[17 empty] | Turnkey | Works
INDIVIDUAL CONSULTANTS | [16 empty] | Unit Prices | Works
Executing Agency | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  |  |  | Estimated Number of Consultants: | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method |  | Lump-Sum | Works
[5 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount JICA % |  | Estimated Amount Counterpart %: |  |  |  | No Objection to TOR's | Contract Signature |  |  |  | Non-Consulting Services
Petroleum Corporation of Jamaica | Technical Experts to support Electricity and Energy Planning in MSET | Pending | Comparison of Qualifications - National Individual Consultant |  | 620000 | 50% | 50% |  |  | 1 | 3 | Ex-Ante | 2017-10-01 | 2017-10-01 |  |  |  | Non-Consulting Services
Petroleum Corporation of Jamaica | Project Manager | Pending | Comparison of Qualifications - National Individual Consultant |  | 480000 | 50% | 50% |  |  | 1 | 4 | [5 empty] | Lump-Sum | Non-Consulting Services
Petroleum Corporation of Jamaica | MSET - Sub Project Manager | Pending | Comparison of Qualifications - National Individual Consultant |  | 240000 | 50% | 50% |  |  | 1 | 4 | [5 empty] | Lump-Sum | Consulting Firms
Petroleum Corporation of Jamaica | NWA - Sub Project Manager | Pending | Comparison of Qualifications - National Individual Consultant |  | 240000 | 50% | 50% |  |  | 1 | 4 | Ex-Ante | 2017-10-01 | 2017-10-01 |  |  | Lump-Sum + Reimbursable Expenses | Consulting Firms
Petroleum Corporation of Jamaica | Finance Officer | Pending | Comparison of Qualifications - National Individual Consultant |  | 360000 | 50% | 50% |  |  | 1 | 4 | [5 empty] | Time-Based | Consulting Firms
Petroleum Corporation of Jamaica | Procurement Officer | Pending | Comparison of Qualifications - National Individual Consultant |  | 360000 | 50% | 50% |  |  | 1 | 4 | Ex-Ante | 2017-10-01 | 2017-10-01 |  |  |  | Individual Consultants
Petroleum Corporation of Jamaica | Administrative Officer | Pending | Comparison of Qualifications - National Individual Consultant |  | 180000 | 50% | 50% |  |  | 1 | 4 | [6 empty] | Individual Consultants
Petroleum Corporation of Jamaica | Monitoring and Evaluation Specialist | Pending | Comparison of Qualifications - National Individual Consultant |  | 210000 | 50% | 50% |  |  | 1 | 4 | Ex-Ante | 2017-10-01 | 2017-10-01
Petroleum Corporation of Jamaica | Quantity Surveyor | Pending | Comparison of Qualifications - National Individual Consultant |  | 300000 | 50% | 50% |  |  | 1 | 4 | Ex-Ante | 2017-10-01 | 2017-10-01 |  |  | Procurement of Textbooks and Reading Materials | Goods
Petroleum Corporation of Jamaica | ESG Coordinator | Pending | Comparison of Qualifications - National Individual Consultant |  | 240000 | 50% | 50% |  |  | 2 | 4 | Ex-Ante | 2018-08-01 | 2018-10-01 |  |  | Procurement of Goods | Goods
Petroleum Corporation of Jamaica | Electrical Consultant | Pending | Comparison of Qualifications - National Individual Consultant |  | 180000 | 50% | 50% |  |  | 1 | 4 | Ex-Ante | 2017-05-01 | 2017-06-01 |  | 3410000 | Procurement of Health Sector Goods | Goods
[5 empty] | 3410000 | [11 empty] | Price Comparison for Goods | Goods
[17 empty] | Technical Specifications | Goods
TRAINING | [16 empty] | Procurement of plant Design , Supply and Installation | Goods
Executing Agency | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method |  |  | Procurement of IT Products and/or Services | Goods
[5 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount JICA % |  |  |  |  | Annual Training Plan (ATP) | End of Activity
Petroleum Corporation of Jamaica | Trainning and manuals in EE Maintenance to be extended to facilitities teams in each building | Pending | Selection Based on the Consultants' Qualifications |  | 160000 | 50% | 50% |  |  | 1 | Ex-Ante | 2017-09-01 | 2021-12-01 |  |  |  | Price Comparison for Works | Works
Petroleum Corporation of Jamaica | Communications & Raising awareness | Pending | Selection Based on the Consultants' Qualifications |  | 250000 | 50% | 50% |  |  | 1 | Ex-Ante | 2017-09-01 | 2021-12-01 |  |  |  | Procurement for Works | Works
Petroleum Corporation of Jamaica | Institutional capacity building of the MSET for wider energy planning and supervision | Pending | Selection Based on the Consultants' Qualifications |  | 350000 | 50% | 50% |  |  | 3 | Ex-Ante | [5 empty] | Procurement for Smaller Works | Works
[5 empty] | 760000 | [11 empty] | Prequalification for Procurement of Works | Works
TRANSFERS | [16 empty] | Price Comparison | Non-Consulting Services
Executing Agency | Transfer Purpose: | Additional Information: | Process Number: | Estimated Amount |  |  | Associated Component: |  |  | Estimated Number of Transfers: | Dates |  | Comments - for UCS include selection method |  |  |  | Terms of Reference | Non-Consulting Services
|  |  |  | Estimated Amount, in US$: | Estimated Amount IDB %: | [5 empty] | Contract Signature | Transfer Date |  |  |  |  | Procurement of Non-Consulting Services | Non-Consulting Services
|  |  |  | 0 | [12 empty] | Technical Specifications | Non-Consulting Services
|  |  |  | 0 | [12 empty] | Request for Proposals and Terms of Reference | Consulting Firms
[17 empty] | Terms of Reference | Consulting Firms
|  |  |  | TOTAL | 30000000
Lump-Sum
Time-Based
Single Source Selection
Comparison of Qualifications - National Individual Consultant
Comparison of Qualifications - International Individual Consultant
3CV
Note on F35: Peter Ruddock: Monies in year 1 iicludes standards and dsposal Year 2-5 covers disposal only

## Procurement Plan
INFORMATION FOR PROCUREMENT PLAN INITIAL UPLOAD ONGOING AND/OR LAST PRESENTED
1. Procurement Plan Coverage
Data | From | Until
Procurement Plan Coverage: | 2017-01-01 | 2022-12-01
2. Procurement Plan Details
Version 1 (2016) :
3. Amounts by Investment Category
Investment Category | Amount Financed by the Bank | Total Amount (Including counterpart)
Works | 9837500 | 19675000
Goods | 2067500 | 4135000
Non Consulting Services | 0 | 0
Trainning | 380000 | 760000
Operative Costs | 0 | 0
Consulting Services (Firms + Individuals) | 2715000 | 5430000
Transfers | 0 | 0
Community Participation | 0 | 0
Contingencies | 0 | 0
Total | 15000000 | 30000000
4. Components
Project Components | Amount Financed by the Bank | Total Amount (Including counterpart)
Component 1: Retrofitting HEPA Government Facilities | 10567500 | 21135000
Component 2: Implementation of an Urban Traffic Management System | 1750000 | 3500000
Component 3: Support to Electricity Planning | 890000 | 1780000
Other Costs | 1792500 | 3585000
Total | 15000000 | 30000000

## Consolidated Financial Plan
CONSOLIDATED FINANCIAL PLAN
INTERNATIONAL DEVELOPMENT BANK
PROJECT LIFE
Programme Components (1) | Year 1 |  |  | Year 2 |  |  | Year 3 |  |  | Year 4 |  |  | Year 5 |  |  | Year 6 |  |  | PROJECT TOTAL
| Source of Funding (USD) |  |  | Source of Funding (USD) |  |  | Source of Funding (USD) |  |  | Source of Funding (USD) |  |  | Source of Funding (USD) |  |  | Source of Funding (USD) |  |  | Source of Funding (USD)
| IDB | JICA | Total | IDB | JICA | Total | IDB | JICA | Total | IDB | JICA | Total | IDB | JICA | Total | IDB | JICA | Total | IDB | JICA | Total
Component 1: Retrofitting HEPA Government Facilities | [20 empty] | 21135000
Output 1.1 HEPA government facilities with Energy Efficiency (EE) equipment replaced, installed and operating | 638852.5 | 638852.5 | 1277705 | 1340250 | 1340250 | 2680500 | 2110147.5 | 2110147.5 | 4220295 | 1891916.6667 | 1891916.6667 | 3783833.3333 | 1279416.6667 | 1279416.6667 | 2558833.3333 | 1301916.6667 | 1301916.6667 | 2603833.3333 | 8562500 | 8562500 | 17125000
- EE Retrofitting 23 buildings | 638852.5 | 638852.5 | 1277705 | 1340250 | 1340250 | 2680500 | 2048382.7941 | 2048382.7941 | 4096765.5882 | 1847799.0196 | 1847799.0196 | 3695598.0392 | 1235299.0196 | 1235299.0196 | 2470598.0392 | 1301916.6667 | 1301916.6667 | 2603833.3333 | 8412500 | 8412500 | 16825000 | 731521.7391 | 16825000 | 0
- Investment Grade Audists (IGAs) | 0 | 0 | 0 | 0 | 0 | 0 | 61764.7059 | 61764.7059 | 123529.4118 | 44117.6471 | 44117.6471 | 88235.2941 | 44117.6471 | 44117.6471 | 88235.2941 |  |  |  | 150000 | 150000 | 300000 | 17647.0588
Output 1.2 EE light technology replaced, installed and operating in HEPA government facilities | 0 | 0 | 0 | 0 | 0 | 0 | 285000 | 285000 | 570000 | 570000 | 570000 | 1140000 | 570000 | 570000 | 1140000 |  |  |  | 1425000 | 1425000 | 2850000 | 57000
Output 1.3: Workshops completed on EE management & maintenance in HEPA government facilities | 0 | 0 | 0 | 16000 | 16000 | 32000 | 16000 | 16000 | 32000 | 16000 | 16000 | 32000 | 16000 | 16000 | 32000 | 16000 | 16000 | 32000 | 80000 | 80000 | 160000 | 32000
Outpu 1.4: EE manuals developed for management and maintenance of HEPA government facilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166666.6667 | 166666.6667 | 333333.3333 | 166666.6667 | 166666.6667 | 333333.3333 | 166666.6667 | 166666.6667 | 333333.3333 | 500000 | 500000 | 1000000 | 1000000
- EE Manuals for management | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 125000 | 125000 | 250000 | 125000 | 125000 | 250000 | 125000 | 125000 | 250000 | 375000 | 375000 | 750000 | 250000
- Communications awareness | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41666.6667 | 41666.6667 | 83333.3333 | 41666.6667 | 41666.6667 | 83333.3333 | 41666.6667 | 41666.6667 | 83333.3333 | 125000 | 125000 | 250000 | 83333.3333
Subtotal Component 1 | 638852.5 | 638852.5 | 1277705 | 1356250 | 1356250 | 2712500 | 2411147.5 | 2411147.5 | 4822295 | 2644583.3333 | 2644583.3333 | 5289166.6667 | 2032083.3333 | 2032083.3333 | 4064166.6667 | 1484583.3333 | 1484583.3333 | 2969166.6667 | 10567500 | 10567500 | 21135000
Component 2: Component 2: Implementation of an Urban Traffic Management System | [20 empty] | 3500000 | 1750000
Output 2.1: Equipment necessary to upgrade the central control system purchased, installed and operating. | 30650 | 30650 | 61300 | 30650 | 30650 | 61300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61300 | 61300 | 122600 | 40866.6667
Output 2.2: Equipment necessary to modernize and coordinate traffic signals purchased, installed and operating. | 719145 | 719145 | 1438290 | 719145 | 719145 | 1438290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1438290 | 1438290 | 2876580 | 958860
Output 2.3: Number of Packages of Support for Training and Capacity Building in Intelligent Transportation System delivered | 62602.5 | 62602.5 | 125205 | 125205 | 125205 | 250410 | 62602.5 | 62602.5 | 125205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250410 | 250410 | 500820 | 500820
Subtotal Component 2 | 812397.5 | 812397.5 | 1624795 | 875000 | 875000 | 1750000 | 62602.5 | 62602.5 | 125205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000 | 1750000 | 3500000 | 1750000
Component 3: Support to Electricity Planning | [20 empty] | 1780000
Output 3.1: Number of technical studies to support IRP revision or update completed | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 65000 | 130000 | 65000 | 65000 | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | 130000 | 130000 | 260000 | 130000
Output 3.2: Number of training modules completed to support technical capacity in MSET to revise or update IRP[1] | 58333.3333 | 58333.3333 | 116666.6667 | 0 | 0 | 0 | 58333.3333 | 58333.3333 | 116666.6667 | 0 | 0 | 0 | 58333.3333 | 58333.3333 | 116666.6667 | 0 | 0 | 0 | 175000 | 175000 | 350000 | 116666.6667
Output 3.3: Number of technical experts contracted to reinforce capacity and develop training plans within MSET to enable staff to revise or update IRP | 0 | 0 | 0 | 103333.3333 | 103333.3333 | 206666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 206666.6667 | 206666.6667 | 413333.3333 | 0 | 0 | 0 | 310000 | 310000 | 620000 | 206666.6667
Output 3.4: Diagnostic study completed on IT software required in MSET to support IRP coordination | 0 | 0 | 0 | 50000 | 50000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 100000 | 100000
Output 3.5: Appropriate IT software for coordinating IRP purchased, installed and operating | 0 | 0 | 0 | 0 | 0 | 0 | 112500 | 112500 | 225000 | 0 | 0 | 0 | 112500 | 112500 | 225000 | 0 | 0 | 0 | 225000 | 225000 | 450000 | 225000
Subtotal Component 3 | 58333.3333 | 58333.3333 | 116666.6667 | 153333.3333 | 153333.3333 | 306666.6667 | 235833.3333 | 235833.3333 | 471666.6667 | 65000 | 65000 | 130000 | 377500 | 377500 | 755000 | 0 | 0 | 0 | 890000 | 890000 | 1780000
Other Costs | [20 empty] | 3585000
Mid-term Evaluation Report | 0 | 0 | 0 | 25000 | 25000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 50000
Final Evaluation Report | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 50000 | 25000 | 25000 | 50000
Financial Audits | 15000 | 15000 | 30000 | 15000 | 15000 | 30000 | 15000 | 15000 | 30000 | 15000 | 15000 | 30000 | 15000 | 15000 | 30000 | 15000 | 15000 | 30000 | 90000 | 90000 | 180000 | 30000
Programme Monitoring and Evaluation | 20833.3333 | 20833.3333 | 41666.6667 | 20833.3333 | 20833.3333 | 41666.6667 | 20833.3333 | 20833.3333 | 41666.6667 | 20833.3333 | 20833.3333 | 41666.6667 | 20833.3333 | 20833.3333 | 41666.6667 | 20833.3333 | 20833.3333 | 41666.6667 | 125000 | 125000 | 250000 | 41666.6667
PEU Project Management | 254583.3333 | 254583.3333 | 509166.6667 | 254583.3333 | 254583.3333 | 509166.6667 | 254583.3333 | 254583.3333 | 509166.6667 | 254583.3333 | 254583.3333 | 509166.6667 | 254583.3333 | 254583.3333 | 509166.6667 | 254583.3333 | 254583.3333 | 509166.6667 | 1527500 | 1527500 | 3055000 | 509166.6667
Subtotal | 290416.6667 | 290416.6667 | 580833.3333 | 315416.6667 | 315416.6667 | 630833.3333 | 290416.6667 | 290416.6667 | 580833.3333 | 290416.6667 | 290416.6667 | 580833.3333 | 290416.6667 | 290416.6667 | 580833.3333 | 315416.6667 | 315416.6667 | 630833.3333 | 1792500 | 1792500 | 3585000
Total | 1800000 | 1800000 | 3600000 | 2700000 | 2700000 | 5400000 | 3000000 | 3000000 | 6000000 | 3000000 | 3000000 | 6000000 | 2700000 | 2700000 | 5400000 | 1800000 | 1800000 | 3600000 | 15000000 | 15000000 | 30000000
|  |  | 12% |  |  | 18% |  |  | 20% |  |  | 20% |  |  | 18% |  |  | 12%
|  |  | 12% |  |  | 18% |  |  | 20% |  |  | 20% |  |  | 18% |  |  | 12% |  |  | 30000000 | 100%
Total |  |  | 3600000 |  |  | 5400000 |  |  | 6000000 |  |  | 6000000 |  |  | 5400000 |  |  | 3600000
|  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 1436038.33 | 116666.6633 | 1319371.6667 | 3028500 | 306333.3333 | 2722166.6667 | 3947961.67 | 190470.5849 | 4138432.2549 | 3365000 | 372264.7059 | 3737264.7059 | 3028500 | 516235.2941 | 2512264.7059 | 2019000 | 376500 | 2395500
[7 empty] | 422999.9967 |  |  | 232529.4118 |  |  | 139735.2941

## Budget
JA-L1056 - Energy Management and Efficiency Program |  | IDB | JICA | TOTAL
|  | US$ | US$ | US$
1 | Component 1: Retrofitting HEPA Government Facilities | 10567500 | 10567500 | 21135000
1.1 | Investment Grade Audits (17 buildings) | 150000 | 150000 | 300000
1.2 | Lighting (50 buildings) | 1425000 | 1425000 | 2850000
1.3 | Deep EE and RE measures execution (23 buildings) | 8412500 | 8412500 | 16825000
1.4 | Environment & Waste Disposal Measures | 375000 | 375000 | 750000
1.5 | Training Facilities Managers | 80000 | 80000 | 160000
1.6 | Communications & Raising awareness (Public and Private) | 125000 | 125000 | 250000
2 | Component 2: Implementation of an Urban Traffic Management System | 1750000 | 1750000 | 3500000
2.1 | Purchase Installation of Urban Traffic Management System and Operational Capacity | 1750000 | 1750000 | 3500000
3 | Component 3: Support to Electricity Planning | 890000 | 890000 | 1780000
3.1 | Electricity and Energy Planning in MSET | 890000 | 890000 | 1780000
4 | Other Costs | 1792500 | 1792500 | 3585000
4.1.1 | Financial Audit | 90000 | 90000 | 180000
4.1.2 | Mid-term and Final Evaluation Reports | 50000 | 50000 | 100000
4.1.3 | Project Monitoring and Evaluation | 125000 | 125000 | 250000
4.2 | Project Management | 1527500 | 1527500 | 3055000
TOTAL |  | 15000000 | 15000000 | 30000000

## Results Indicators
Indicator | Formula | Frequency of Measurement | Source of Verification
Results Indicators
Component 1: Retrofitting HEPA Government Facilities
Expected Result 1: Reduced electricity consumed in 80 Health, Education and Public Agency (HEPA) government facilities
Total kilowatt hours (kWh) consumed in 73 HEPA government facilities | kWh | End of the project | Biannual Report from Petroleum Corporation of Jamaica (PCJ) M&E consulting firm report
Expected Results 2: Reduced CO2 emissions resulting from reduced electricity consumption in 80 HEPA government facilities
CO2 equivalent emissions resulting from kWh consumed in 73 HEPA government facilities | Tons of CO2 equivalent | End of the project | Biannual Report from PCJ M&E consulting firm report
Component 2: Implementation of an Urban Traffic Management System
Expected Result 3: Avoided transport fuel consumed in the Kingston Metropolitan Region (KMR)
Annual Fuel consumption in the KMR | Millions litres | End of the project | Biannual report from National Works Agency (NWA) Independent M&E Report
Expected Result 4: Avoided CO2 emissions resulting from avoided reduced transport fuel consumed in the KMR
CO2 equivalent emissions resulting from transport fuel consumed in KMR | Tons of CO2 equivalent | End of the project | Biannual Report from PCJ M&E consulting firm report
Expected Result 5: Reduced hours of annual travel time in the KMR
Total annual hours of travel time in the KMR | Million hours | End of the project | Biannual Report from PCJ M&E consulting firm report
Component 3: Support to Electricity Planning
Expected Result 6: Number of formal updates or revisions of the Integrated Resource Plan (IRP) performed by Ministry of Science, Energy and Technology (MSET)
Number of formal updates or revisions of the IRP performed by MSET | # | Annually | Biannual Report from PCJ M&E consulting firm report

## Output Indicators
Indicator | Formula | Frequency of Measurement | Source of Verification
Output Indicators
Component 1: Retrofitting HEPA Government Facilities
Expected Output 1:
HEPA government facilities with Energy Efficiency (EE) equipment replaced, installed and operating. | # of buildings retrofitted | Annually | 17 Investment Grade Audits (IGAs) will be completed to achieve these outputs. Biannual reports from PCJ
Expected Output 2:
EE light technology replaced, installed and operating in HEPA government facilities | # of buildings retrofitted | Annually | Biannual reports from PCJ EE light technology may include Light-Emitted Diode (LED).
Expected Output 3:
Workshops completed on EE management & maintenance in HEPA government facilities | # of workshop completed | Annually | Biannual reports from PCJ List of participant and follow-up monitoring to participants per workshop
Expected Ouput 4:
EE manuals developed for management and maintenance of HEPA government facilities | # of manuals | Annually | Biannual reports from PCJ
Component 2: Implementation of an Urban Traffic Management System
Expected Output 3:
Equipment necessary to upgrade the central control system purchased, installed and operating | Binary (yes =1 no = 0) | Annually | To be used for traffic monitoring, operation, planning and modelling Biannual report from NWA Independent M&E Report
Expected Output 4:
Equipment necessary to modernize and coordinate traffic signals purchased, installed and operating. | Binary (yes =1 no = 0) | Annually | Includes upgraded traffic controllers, closed-circuit television cameras, detectors, and communication switches at intersections. Biannual report from NWA Independent M&E Report
Expected Output 5:
Number of Packages of Support for Training and Capacity Building in Intelligent Transportation System delivered | # | Annually | Includes System training; Planning training; Sun-Guide training and Coaching Biannual report from NWA Independent M&E Report
Component 3: Support to Electricity Planning
Expected Output 6:
Number of technical studies to support IRP revision or update completed | # | Annually | This includes studies on electrical losses, and integrated energy planning Biannual report from MSET Independent M&E Report.
Expected Output 7:
Number of training modules completed to support technical capacity in MSET to revise or update IRP | # | Annually | Training includes: distributed generation and reliability modelling in IRP; Dispatch, Production Costing Procedures and Systems and Policy Parameters and Trade-off Measures. Biannual report from MSET Independent M&E Report
Expected Output 8:
Number of technical experts contracted to reinforce capacity and develop training plans within MSET to enable staff to revise or update IRP | # | Annually | Experts to be contracted in the following areas: Energy Efficiency and Demand-Side Management; Electricity Sales and Rates and Transmission & Distribution Biannual report from MSET Independent M&E Report.

## Result Matrix (Physical Plan)
Indicator | Unit | Baseline (2015) | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Final Target (EOP) | Source of Verification
Component 1: Retrofitting HEPA Government Facilities
Expected Result 1: Reduced electricity consumed in 73 Health, Education and Public Agency (HEPA) government facilities
Annual electricity consumed in 73 HEPA government facilities | kWh | 31377402 | - | - | - | - | - | - | 16004807 | Biannual Report from PCJ M&E consulting firm report
Expected Results 2: Reduced CO2 emissions resulting from reduced electricity consumption in 73 HEPA government facilities
Annual GHG emissions resulting from kWh consumed in 73 HEPA government facilities | Tons of CO2 equivalent | 52401 | - | - | - | - | - | - | 26729 | Biannual Report from PCJ M&E consulting firm report
Component 1 Outputs
HEPA government facilities with Energy Efficiency (EE) equipment replaced, installed and operating | # of buildings retrofitted | 0 | 0 | 2 | 4 | 7 | 5 | 5 | 23 | 17 Investment Grade Audits (IGAs) will be completed to achieve these outputs. Biannual reports from PCJ
EE light technology replaced, installed and operating in HEPA government facilities | # of buildings retrofitted | 0 | 0 | 0 | 0 | 20 | 30 | 0 | 50 | Biannual reports from PCJ. EE light technology may include Light-Emitted Diode (LED).
Workshops completed on EE management & maintenance[1] in HEPA government facilities | # of workshop completed | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 5 | Biannual reports from PCJ List of participant and follow-up monitoring to participants per workshop
EE manuals developed for management and maintenance of HEPA government facilities | # of manuals | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | Biannual reports from PCJ
Component 2: Implementation of an Urban Traffic Management System
Expected Result 3: Avoided transport fuel consumed in the Kingston Metropolitan Region (KMR)
Annual Fuel consumption in the KMR | Millions litres | 296.8 | 0 | 0 | 0 | 0 | 0 | 0 | 192.7 | Biannual report from National Works Agency (NWA) Independent M&E Report
Expected Result 4: Avoided CO2 emissions resulting from avoided reduced transport fuel consumed in the KMR
CO2 equivalent emissions resulting from transport fuel consumed in KMR | Tons of CO2 equivalent | 579203 | 0 | 0 | 0 | 0 | 0 | 0 | 376044 | Biannual Report from PCJ M&E consulting firm report
Expected Result 5: Reduced hours of annual travel time in the KMR
Total annual hours of travel time in the KMR | Million hours | 155.2 | 0 | 0 | 0 | 0 | 0 | 0 | 99.96 | Biannual Report from PCJ M&E consulting firm report
Component 2 Outputs
Equipment necessary to upgrade the central control system purchased, installed and operating | Binary (yes =1 no = 0) | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | To be used for traffic monitoring, operation, planning and modelling Biannual report from NWA Independent M&E Report
Equipment necessary to modernize and coordinate traffic signals purchased, installed and operating. | Binary (yes =1 no = 0) | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | Includes upgraded traffic controllers, closed-circuit television cameras, detectors, and communication switches at intersections. Biannual report from NWA Independent M&E Report
Number of Packages of Support for Training and Capacity Building in Intelligent Transportation System delivered | # | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 4 | Includes System training; Planning training; Sun-Guide training and Coaching Biannual report from NWA Independent M&E Report
Component 3: Support to Electricity Planning
Expected Result 6: Number of formal updates or revisions of the Integrated Resource Plan (IRP) performed by MSET.
Number of formal updates or revisions of the IRP performed by MSET | # | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | Biannual Report from PCJ M&E consulting firm report
Component 3 Outputs
Number of technical studies to support IRP revision or update completed | # | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | This includes studies on electrical losses, and integrated energy planning. Biannual report from MSET Independent M&E Report.
Number of training modules completed to support technical capacity in MSET to revise or update IRP[1] | # | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 3 | Training includes: distributed generation and reliability modelling in IRP; Dispatch, Production Costing Procedures and Systems and Policy Parameters and Trade-off Measures. Biannual report from MSET Independent M&E Report
Number of technical experts contracted to reinforce capacity and develop training plans within MSET to enable staff to revise or update IRP | # | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 3 | Experts to be contracted in the following areas: Energy Efficiency and Demand-Side Management; Electricity Sales and Rates and Transmission & Distribution. Biannual report from MSET Independent M&E Report.
Diagnostic study completed on IT software required in MSET to support IRP coordination | # | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | Study to prioritize software and IT platforms that would add value to IRP coordination and planning. Biannual report from MSET Independent M&E Report
Appropriate IT software for coordinating IRP purchased, installed and operating | # | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2 | Biannual report from MSET Independent M&E Report

## Ouputs
Indicator | Unit | Baseline (2015) | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Final Target (EOP) | Source of Verification
Component 1: Retrofitting HEPA Government Facilities
HEPA government facilities with Energy Efficiency (EE) equipment replaced, installed and operating | # of buildings retrofitted | 0 | 0 | 2 | 4 | 7 | 5 | 5 | 23 | 17 Investment Grade Audits (IGAs) will be completed to achieve these outputs. Biannual reports from PCJ
EE light technology replaced, installed and operating in HEPA government facilities | # of buildings retrofitted | 0 | 0 | 0 | 0 | 20 | 30 | 0 | 50 | Biannual reports from PCJ. EE light technology may include Light-Emitted Diode (LED).
Workshops completed on EE management & maintenance in HEPA government facilities | # of workshop completed | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 5 | Biannual reports from PCJ List of participant and follow-up monitoring to participants per workshop
EE manuals developed for management and maintenance of HEPA government facilities | # of manuals | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | Biannual reports from PCJ
Component 2: Implementation of an Urban Traffic Management System
Equipment necessary to upgrade the central control system purchased, installed and operating | Binary (yes =1 no = 0) | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | To be used for traffic monitoring, operation, planning and modelling. Biannual report from NWA Independent M&E Report
Equipment necessary to modernize and coordinate traffic signals purchased, installed and operating. | Binary (yes =1 no = 0) | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | Includes upgraded traffic controllers, closed-circuit television cameras, detectors, and communication switches at intersections. Biannual report from NWA Independent M&E Report
Number of Packages of Support for Training and Capacity Building in Intelligent Transportation System delivered | # | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 4 | Includes System training; Planning training; Sun-Guide training and Coaching Biannual report from NWA Independent M&E Report
Component 3: Support to Electricity Planning
Number of technical studies to support IRP revision or update completed | # | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | This includes studies on electrical losses, and integrated energy planning. Biannual report from MSET Independent M&E Report.
Number of training modules completed to support technical capacity in MSET to revise or update IRP[1] | # | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 3 | Training includes: distributed generation and reliability modelling in IRP; Dispatch, Production Costing Procedures and Systems and Policy Parameters and Trade-off Measures. Biannual report from MSET Independent M&E Report
Number of technical experts contracted to reinforce capacity and develop training plans within MSET to enable staff to revise or update IRP | # | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 3 | Experts to be contracted in the following areas: Energy Efficiency and Demand-Side Management; Electricity Sales and Rates and Transmission & Distribution. Biannual report from MSET Independent M&E Report.
Diagnostic study completed on IT software required in MSET to support IRP coordination | # | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | Study to prioritize software and IT platforms that would add value to IRP coordination and planning. Biannual report from MSET Independent M&E Report
Appropriate IT software for coordinating IRP purchased, installed and operating | # | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2 | Biannual report from MSET Independent M&E Report

## Financial Plan
Indicator | Unit | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Final Target (EOP)
Component 1: Retrofitting HEPA Government Facilities
Outputs (Expected Results)
HEPA government facilities with Energy Efficiency (EE) equipment replaced, installed and operating | US$ | 1277705 | 2680500 | 4220295 | 3783833.3333 | 2558833.3333 | 2603833.3333 | 17125000
EE light technology replaced, installed and operating in HEPA government facilities | US$ | 0 | 0 | 570000 | 1140000 | 1140000 | 0 | 2850000
Workshops completed on EE management & maintenance[1] in HEPA government facilities | US$ | 0 | 32000 | 32000 | 32000 | 32000 | 32000 | 160000
EE manuals developed for management and maintenance of HEPA government facilities | US$ | 0 | 0 | 0 | 333333.3333 | 333333.3333 | 333333.3333 | 1000000
Component 2: Implementation of an Urban Traffic Management System
Outputs (Expected Results)
Equipment necessary to upgrade the central control system purchased, installed and operating | US$ | 61300 | 61300 | 0 | 0 | 0 | 0 | 122600
Equipment necessary to modernize and coordinate traffic signals purchased, installed and operating. | US$ | 1438290 | 1438290 | 0 | 0 | 0 | 0 | 2876580
Number of Packages of Support for Training and Capacity Building in Intelligent Transportation System delivered | US$ | 125205 | 250410 | 125205 | 0 | 0 | 0 | 500820
Component 3: Support to Electricity Planning
Outputs (Expected Results)
Number of technical studies to support IRP revision or update completed | US$ | 0 | 0 | 130000 | 130000 | 0 | 0 | 260000
Number of training modules completed to support technical capacity in MSET to revise or update IRP[1] | US$ | 116666.6667 | 0 | 116666.6667 | 0 | 116666.6667 | 0 | 350000
Number of technical experts contracted to reinforce capacity and develop training plans within MSET to enable staff to revise or update IRP | US$ | 0 | 206666.6667 | 0 | 0 | 413333.3333 | 0 | 620000
Diagnostic study completed on IT software required in MSET to support IRP coordination | US$ | 0 | 100000 | 0 | 0 | 0 | 0 | 100000
Appropriate IT software for coordinating IRP purchased, installed and operating | US$ | 0 | 0 | 225000 | 0 | 225000 | 0 | 450000
Evaluation
Mid-term evaluation | US$ | 0 | 50000 | 0 | 0 | 0 | 0 | 50000
Final Evaluation | US$ | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
Project management
PEU Project Managament | US$ | 509166.6667 | 509166.6667 | 509166.6667 | 509166.6667 | 509166.6667 | 509166.6667 | 3055000
Other costs
Program Monitoring and Evaluation | US$ | 41666.6667 | 41666.6667 | 41666.6667 | 41666.6667 | 41666.6667 | 41666.6667 | 250000
Financial Audits | US$ | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 180000
Total Project
Component 1: Retrofitting HEPA Government Facilities | US$ | 1277705 | 2712500 | 4822295 | 5289166.6667 | 4064166.6667 | 2969166.6667 | 21135000
Component 2: Implementation of an Urban Traffic Management System | US$ | 1624795 | 1750000 | 125205 | 0 | 0 | 0 | 3500000
Component 3: Support to Electricity Planning | US$ | 116666.6667 | 306666.6667 | 471666.6667 | 130000 | 755000 | 0 | 1780000
Mid-term and Final Evaluation Reports | US$ | 0 | 50000 | 0 | 0 | 0 | 50000 | 100000
Project Management | US$ | 509166.6667 | 509166.6667 | 509166.6667 | 509166.6667 | 509166.6667 | 509166.6667 | 3055000
Other Costs | US$ | 71666.6667 | 71666.6667 | 71666.6667 | 71666.6667 | 71666.6667 | 71666.6667 | 430000
Total Project | US$ | 3600000 | 5400000 | 6000000 | 6000000 | 5400000 | 3600000 | 30000000
% of total | % | 12% | 18% | 20% | 20% | 18% | 12% | 100%
Max | % | 12% | 18% | 20%