## PEP (hidden)
JA-G1003 PLURIANNUAL EXECUTION PLAN (PEP)
Task Name | Duration (days) | Start | Finish | Cost | Procurement Method | Works/Goods/Consultancy/Training/Transfers
ENERGY MANAGEMENT AND EFFICIENCY PROGRAMME-IGR |  |  |  | 10000000.0018 |  | 10000000.0018 | -0.0018212
START |  |  |  | -
COMPONENT 1. RETROFITTING OF PUBLUIC BUILDINGS |  |  |  | 9531897.4918
1.1 - PROCUREMENT OF RE TECHNOLOGY AND EE MEASURES (HOSPITALS) |  |  |  | 9331897.4918 |  | Works
1.1.1 UH West Indies | 450 | 2019-01-15 | 2020-10-06 | 6412892.5783 | ICB
1.1.2 Ministry of Health: Bustamante Children Hospital Kingston 5, Kingston | 250 | 2019-01-15 | 2019-12-31 | 783759.2742 | ICB
1.1.3 Ministry of Health: St Anns Bay Hospital St.Anns Bay P.O., St. Ann | 250 | 2019-01-15 | 2019-12-31 | 924142.9277 | ICB
1.1.4 Ministry of Health: Burke RD Spanish Town #1 P.O., St. Catherine | 250 | 2019-01-15 | 2019-12-31 | 578896.9018 | ICB
1.1.5 Annotto Bay Public Hospital Annotto Bay P.O., St. Mary | 150 | 2019-01-15 | 2019-08-13 | 227418.1456 | ICB
1.1.6 Port Antonio, Portland | 150 | 2019-01-15 | 2019-08-13 | 138980.6826 | ICB
1.1.7 Port Maria, St Mary | 150 | 2019-01-15 | 2019-08-13 | 265806.9817
1.2 - CONSULTANCIES AND TRAINING |  |  |  | 200000
1.2.4 Communications & Raising awareness (Workshops and Multimedia Campaign) | 500 | 2018-03-01 | 2021-03-31 | 200000 | SBCQ | Training
2. COMPONENT 2. SUPPORT TO CAPACITY BUILDING FOR ENERGY PLANNING |  |  |  | 250000
2.1 Electricity and Energy Planning in MSET |  |  |  | 250000
3.1.1 Complementary Technical Studies to supportelectricity and energy planning |  |  |  | 250000 | NICQ | Individual consultancy
ADMINISTRATION FEE |  |  |  | 218102.51
[5 empty] | NICQ | Individual consultancy
[5 empty] | NICQ | Individual consultancy
END |  |  |  | -
(1) Goods and Works: ICB: international competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: procurement through specilaized agencies; PA: procrement agents; IA: inspection Agents; PLFI: procurement in loans to financial intermediaries; BOO/BOT/BOOT: build own, operate/build, operate, transfer/build, own,operate, transfer; PBP: performance-based procurement; PLGB: procurement under loans guaranteed by Bank; PCP: community participation procurement. Consulting Firms: QCBS: quality and cost-based selection; QBS: quality-based selection; FBS: selection under a fixed budget; LCS: least-cost selection; CQS: selection based on the Consultant's Qualifications; SSS: single-source selection. Individual Consultants: NICQ: national individual Consultant selection based on qualifications; IICQ: international individual Consultant selection based on Qualifications.
Formulas:
Finish = +WORKDAY([Start],[Duration (days)])

## PEP-Implementation Plan (hidden)
SECTION 2
IMPLEMENTATION PLAN
No. of component | COMPONENT | SUB-COMPONENT | OUTPUT | MILESTONE ACTIVITY1 | EU-CIF |  |  | TOTAL INDICATIVE | ESTIMATED START DATE | ESTIMATED END DATE |  |  |  | RESPONSIBILITY (PERSON/AGENCY)
[5 empty] | INDICATIVE | ACTUAL | VARIANCE |  |  |  | PLANNED OUTPUT FOR THE YEAR | ACTUAL CUMULATIVE OUTPUT TO DATE | REMAINING OUTPUT TO BE ACHIEVED
Component 1: Retrofitting of Public Buildings | [7 empty] | 9531897.4918
Output 1.1 Hospitals with Energy Efficiency (EE) equipment replaced, installed and operating. |  |  |  |  | 9531897.4918 |  |  | 9531897.4918
1.1 | 1 |  | Hospitals retrofitted with EE/RE | Communications & Raising awareness (Workshops and Multimedia Campaign) | 200000 |  |  | 200000 | 2018-01-01 | 2021-12-01 |  |  |  | PCJ
|  |  |  | Works completed in 7 buildings | 9331897.4918 |  |  | 9331897.4918 | 2018-01-01 | 2021-12-01 |  |  |  | PCJ
Component 2: Support to Capacity Building for Energy Planning | [7 empty] | 250000
Output 2.2 Number of complementary technical studies to support Electricity Planning and Jamaica’s IRP |  |  |  |  | 250000 |  |  | 250000
|  |  | Electricity and Energy Planning in MSET | Complementary Technical Studies to supportelectricity and energy planning | 250000 |  |  | 250000 | 2021-01-01 | 2021-12-01 |  |  |  | PCJ
FEES |  |  |  |  | 218102.51 |  |  | 218102.51 | 2018-01-01 | 2018-12-01
TOTAL |  |  |  |  | 10000000.0018 |  |  | 10000000.0018
Authorized Signature(s) | [5 empty] | Name(s) and Title(s)
1 The milestone activities must reflect the procurement methodology employed.

## POA-Consolidated Financial Plan (hidden)
CONSOLIDATED FINANCIAL PLAN
INTER-AMERICAN DEVELOPMENT BANK
PROJECT LIFE
Programme Components (1) | Year 1 -2018 |  |  | Year 2-2019 |  |  | Year 3-2020 |  |  | Year 4-2021 |  |  | PROJECT TOTAL
| Source of Funding (USD) |  |  | Source of Funding (USD) |  |  | Source of Funding (USD) |  |  | Source of Funding (USD) |  |  | Source of Funding (USD)
| IDB | EU-CIF | Total | IDB | EU-CIF | Total | IDB | EU-CIF | Total | IDB | EU-CIF | Total | IDB | EU-CIF | Total
Component 1: Retrofitting of Public Buildings | [14 empty] | 9781897.4918
Output 1.1 Hospitals with Energy Efficiency (EE) equipment replaced, installed and operating | 0 | 0 | 0 | 0 | 3110632.4973 | 3110632.4973 | 0 | 3110632.4973 | 3110632.4973 | 0 | 3310632.4973 | 3310632.4973 | 0 | 9531897.4918 | 9531897.4918
> EE Retrofitting 7 buildings | 0 | 0 | 0 | 0 | 3110632.4973 | 3110632.4973 | 0 | 3110632.4973 | 3110632.4973 | 0 | 3110632.4973 | 3110632.4973 | 0 | 9331897.4918 | 9331897.4918
> Communications and visibility Plan developed for raising awareness of EE/RE measures in targetted buildings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 0 | 200000 | 200000
Component 2: Support to Capacity Building for Energy Planning | [14 empty] | 250000
>2 Complementary Technical Studies to support Electricity Planning and IRP (studies will focus on fuel switching options, infrastructure, policy and regulation that can make a real difference to final energy cost, reliability and environmental externalities) | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 180000 | 45000 | 45000 | 250000
Total | #REF! | 70000 | 0 | 0 | 3110632.4973 | 3110632.4973 | 0 | 3110632.4973 | 3110632.4973 | 0 | 3490632.4973 | 3490632.4973 | 45000 | 9576897.4918 | 9781897.4918
|  | 0.7156% |  |  | 31.8% |  |  | 31.8% |  |  | 35.68% |  |  |  | 100%
[11 empty] | Contingencies |  |  | Contingencies | 0
[11 empty] | Fees |  |  | Fees | 218102.51
[11 empty] | TOTAL EU-CIF |  |  | TOTAL EU-CIF | 10000001.0018
|  |  | 1436038.33 | 116666.6633 | 1319371.6667 | 3028500 | 306333.3333 | 2722166.6667 | 3947961.67 | 190470.5849 | 4138432.2549 | 3365000 | 376500 | #REF!
[7 empty] | 422999.9967 |  |  | 232529.4118

## POA-Financial Plan (hidden)
Indicator | Unit | Year 1 | Year 2 | Year 3 | Year 4 | Final Target (EOP)
Outputs (Expected Results)
Component 1: Retrofitting of Public Buildings | US$ | 0 | 3110632.4973 | 3110632.4973 | 3310632.4973 | 9531897.4918
7 Hospitals government facilities with Energy Efficiency (EE) equipment replaced, installed and operating | US$ | 0 | 3110632.4973 | 3110632.4973 | 3110632.4973 | 9331897.4918
Communications and visibility Plan developed for raising awareness of EE/RE measures in targetted buildings (Workshops) | US$ | 0 | 0 | 0 | 50000 | 50000
Communications and visibility Plan developed for raising awareness of EE/RE measures in targetted buildings (Multimidia Campaigns) | US$ | 0 | 0 | 0 | 150000 | 150000
Component 2: Support to Capacity Building for Energy Planning | US$ | 70000 | 0 | 0 | 180000 | 250000
2 Complementary Technical Studies created to support electricity andJamaica's (IRP) | US$ | 70000 | 0 | 0 | 180000 | 250000
Total Project
Component 1: Retrofitting of Public Buildings | US$ | 0 | 3110632.4973 | 3110632.4973 | 3310632.4973 | 9531897.4918
Component 2: Support to Capacity Building for Energy Planning | US$ | 70000 | 0 | 0 | 180000 | 250000
FEES | US$ | 218102.51 |  |  |  | 218102.51
Total Project | US$ | 288102.51 | 3110632.4973 | 3110632.4973 | 3490632.4973 | 10000000.0018
% of total | % | 2.881% | 31.11% | 31.11% | 34.91% | 100%
Max | % | 12% | 18% | 20%

## Budget (hidden)
JA-L1056 - Energy Management and Efficiency Program |  | IDB | EU-CIF | TOTAL
|  | US$ | US$ | US$
1 | Component 1: Retrofitting of Public Buildings |  | 9531897.4918 | 9531897.4918
1.2 | Deep EE and RE measures execution (7 buildings) |  | 9331897.4918 | 9331897.4918
1.3 | Communications & Raising awareness (workshops and Multimidia Campaigns) |  | 200000 | 200000
2 | COMPONENT 2. Support to Capacity Building for Energy Planning |  | 250000 | 250000
2.1 | Complementary technical studies to support Electricity Planning and IRP (studies will focus on fuel switching options, infrastructure, policy and regulation that can make a real difference to final energy cost, reliability and environmental externalities) |  | 250000 | 250000
FEES |  |  | 218102.51 | 218102.51
TOTAL |  | 0 | 10000000.0018 | 9781897.4918

## Outcome Indicators (hidden)
Indicator | Formula | Frequency of Measurement | Source of Verification
Results Indicators
Component 1: Retrofitting of Public Buildings
Expected Result 1: Reduced electricity consumed in 7 Health government facilities
Total kilowatt hours (kWh) consumed in 7 Public Hospitals | kWh | End of the project | Annual Report from Petroleum Corporation of Jamaica (PCJ) M&E consulting firm report
Expected Results 2: Reduced CO2 emissions resulting from reduced electricity consumption in 7 Hospitals government facilities
CO2 equivalent emissions resulting from kWh consumed in 7 Public Hospitals | Tons of CO2 equivalent | End of the project | Annual Report from PCJ M&E consulting firm report
Component 2: Support to Capacity Building for Energy Planning
Expected Results 3: Complementary technical studies that enable MSET to consider at least 1 additional EE/RE initiative or stretch target to further support the update of the IRP (2020)
2 complementary technical studies that enable MSET to consider at least 1 additional EE/RE initiative or stretch target to further support the update of the IRP (2020) | # of proposal RE/EE received | End of the project | Annual Report from PCJ M&E consulting firm report

## Output Indicators (hidden)
Indicator | Formula | Frequency of Measurement | Source of Verification
Output Indicators
Component 1: Retrofitting of Public Buildings
Expected Output 1:
Public Hospitals with EE equipment replaced, installed and operating | # of public buildings retrofitted | Annually | Annual reports from PCJ
Expected Output 2:
Communication activities completed to raise awareness on EE management & maintenance in the 7 public hospitals retrofitted | # of activities completed (workshop) | Annually | Annual reports from PCJ
Expected Output 3:
Communication activities completed to raise awareness on EE management & maintenance in the 7 public hospitals retrofitted | # of activities completed (multimidia campaigns) | Annually | Annual reports from PCJ
Component 2: Support to Capacity Building for Energy Planning
Expected Output 4:
Number of complementary technical studies to support Electricity Planning and Jamaica’s IRP | # studies | End of project | Annual reports from PCJ

## Result Matrix (Physical Plan) (hidden)
Indicator | Unit | Baseline (2015) | Year 1 | Year 2 | Year 3 | Year 4 | Final Target (EOP) | Source of Verification
Component 1: Retrofitting of Public Buildings
Expected Result 1: Reduced electricity consumed in 7 Public Hospitals
Annual electricity consumed in 7 Hospitals government facilities | kWh | 18037260 | - | - | - | - | 9785499 | Annual Report from PCJ M&E consulting firm report
Expected Results 2: Reduced CO2 emissions resulting from reduced electricity consumption in 7 Hospitals government facilities
Annual GHG emissions resulting from kWh consumed in 7 Hospitals government facilities | Tons of CO2 equivalent | 19679.6774 |  | - | - | - | 10676.6774 | Annual Report from PCJ M&E consulting firm report
Component 1: Outputs
7 Hospitals government facilities with Energy Efficiency (EE) equipment replaced, installed and operating | # of public buildings retrofitted | 0 | 0 | 2 | 3 | 2 | 7 | Annual reports from PCJ
Communications and visibility Plan developed for raising awareness of EE/RE measures in targetted buildings (Multimedia Campaign) | # Multimedia Capmpaigns | 0 | 0 | 0 | 0 | 3 | 3 | Annual reports from PCJ
Communications and visibility Plan developed for raising awareness of EE/RE measures in targetted buildings (Workshop) | # Workshop | 0 | 0 | 0 | 0 | 1 | 1 | Annual reports from PCJ
Component 2: Support to Capacity Building for Energy Planning
Expected Results 3:
2 complementary technical studies that enable MSET to consider at least 1 additional EE/RE initiative or stretch target to further support the update of the IRP (2020) | #of additional proposals for RE/EE project received | 0 | 0 | 0 | 0 | 1 | 1 | Annual reports from PCJ
Component 2: Outputs
2 Complementary technical studies to support Electricity Planning and IRP(Studies will focus on fuel switching options, infrastructure, policy and regulation that can make a real difference to final energy cost, reliability and environmental externalities) | # Study | 0 | 1 | 0 | 0 | 1 | 2 | Annual reports from PCJ

## Procurement Plan
INFORMATION FOR PROCUREMENT PLAN INITIAL UPLOAD ONGOING AND/OR LAST PRESENTED
1. Procurement Plan Coverage
Data | From | Until
Procurement Plan Coverage: | 2018-01-01 | 2021-01-01
2. Procurement Plan Details
Version 1 (2016) :
3. Amounts by Investment Category
Investment Category | Amount Financed by the EU-CIF | Total Amount (Including counterpart)
Works | 9331897.4918 | 9331897.4918
Goods | 0 | 0
Non Consulting Services | 0 | 0
Training | 0 | 0
Operative Costs (Fees) | 218102.51 | 218102.51
Consulting Services (Firms + Individuals) | 450000 | 450000
Transfers | 0 | 0
Community Participation | 0 | 0
Contingencies | 0 | 0
Total | 10000000.0018 | 0
4. Components
Project Components | Amount Financed by EU-CIF | Total Amount (Including counterpart)
Component 1: Retrofitting of Public Buildings | 9531897.4918 | 9531897.4918
Component 2: Support to Capacity Building for Energy Planning | 250000 | 250000
FEES | 218102.51 | 218102.51
Total | 10000000.0018 | 10000000.0018

## Detailed Procurement Plan
PROCUREMENT PLAN INITIAL LOAD INFORMATION (ONGOING AND/OR LAST PRESENTED)
WORKS | [15 empty] | National System
Executing Agency | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method | Ex-Post
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount JICA % | Estimated Amount EU-CIF | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature |  | Ex-Ante
PCJ | PROCUREMENT OF RE TECHNOLOGY AND EE MEASURES (7 PUBLIC HOSPITALS) | Pending | International Competitive Bidding |  |  | 9331897.4918 |  |  | 100% | 0 | 1 | Ex-Ante | 2018-10-03 | 2019-01-01 |  | Contract Concluded
[6 empty] | 9331897.4918 | [9 empty] | Ongoing
GOODS | [15 empty] | Planned
Executing Agency | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method | Rejection of all Bids
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount JICA % | Estimated Amount EU-CIF | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature |  | Re-Tendering
[6 empty] | 0 | [9 empty] | National System
NON CONSULTING SERVICES | [15 empty] | Limited Competitive Bidding
Executing Agency | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method | Prequalification
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount JICA % | Estimated Amount EU-CIF | Estimated Amount Counterpart %: |  |  | Bidding Documents | Contract Signature |  | Two-envelope International Competitive Bidding
Quality Based Selection
[6 empty] | 0 | [9 empty] | Selection Based on the Consultants' Qualifications
CONSULTING FIRMS | [15 empty] | Single Source Selection
Executing Agency | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method |  | National System
[5 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount JICA % | Estimated Amount EU-CIF | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature |  |  | Least cost Selection
Petroleum Corporation of Jamaica | Communications and visibility Plan developed for raising awareness of EE/RE measures in targetted buildings | Pending | Selection Based on the Consultants' Qualifications |  | 200000 | 0% | 0% | 100% |  | 1 | Ex-Ante | 2017-12-01 | 2018-03-01
Petroleum Corporation of Jamaica | Complementary technical studies to support Electricity Planning and IRP (Studies will focus on fuel switching options, infrastructure, policy and regulation) - 1 | Pending | Selection Based on the Consultants' Qualifications |  | 70000 | 0% | 0% | 100% |  | 2 | Ex-Ante | 2017-11-03 | 2018-02-01
Petroleum Corporation of Jamaica | Complementary technical studies to support Electricity Planning and IRP (Studies will focus on fuel switching options, infrastructure, policy and regulation) - 2 | Pending | Selection Based on the Consultants' Qualifications |  | 180000 | 0% | 0% | 100% |  | 2 | Ex-Ante | 2020-12-01 | 2021-05-01
Petroleum Corporation of Jamaica |  | Pending |  |  |  | 50% | 50% | 0% |  | 1 | Ex-Ante | 2017-12-01 | 2018-03-01
[5 empty] | 450000 | [10 empty] | Unit Prices | `
INDIVIDUAL CONSULTANTS | [15 empty] | Lump-Sum
Executing Agency | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  |  |  | Estimated Number of Consultants: | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method | Turnkey
[5 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount JICA % | Estimated Amount EU-CIF | Estimated Amount Counterpart %: |  |  |  | No Objection to TOR's | Contract Signature |  | Unit Prices
[5 empty] | 0 | [10 empty] | Lump-Sum + Reimbursable Expenses
TRAINING | [15 empty] | Time-Based
Executing Agency | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[5 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount JICA % | Estimated Amount EU-CIF |  |  |  | Annual Training Plan (ATP) | End of Activity
[5 empty] | 0 | [10 empty] | Price Comparison for Goods
TRANSFERS | [15 empty] | Technical Specifications
Executing Agency | Transfer Purpose: | Additional Information: | Process Number: | Estimated Amount |  |  | Associated Component: |  |  | Estimated Number of Transfers: | Dates |  | Comments - for UCS include selection method |  |  | Procurement of plant Design , Supply and Installation
|  |  |  | Estimated Amount, in US$: | Estimated Amount IDB %: | [5 empty] | Contract Signature | Transfer Date |  |  |  | Procurement of IT Products and/or Services
0
0
Price Comparison
|  |  |  | TOTAL | 9781897.4918 | [10 empty] | Terms of Reference
Formulas:
Dates = +[Contract Signature]-90
Dates = +[Dates]-90