## Sheet1
Inter-American Development Bank
PROCUREMENT PLAN FOR IDB-EXECUTED OPERATIONS
Country: JAMAICA | [5 empty] | Executing Agency: IDB | [6 empty] | UDR: CSD
Project number: JA-T1158 |  |  |  |  | Project name: Support to the Ministry of Agriculture of Jamaica to Update Sector Policies and Investment Plans and for Project Preparation
Period covered by the Plan: 24 months |  |  |  |  | Total Project Amount: |  | 350000
Component | Procurement Type (1) (2) | Service type (1) (2) | Description | Estimated contract cost (US$) | Selection Method (2) | Type of Contract | Source of Financing and Percentage |  |  |  | Estimated date of the procurement notice | Estimated contract start date | Comments
[7 empty] | IDB/MIF |  | Other External Donor
[7 empty] | Amount | % | Amount | % |  |  |  | Direct Contracting
Select comp | Select Proc. Type | Goods Included in Firm Cons. RFP | Consultant 1: brief description |  | select method | Select Cont. Type |  |  |  |  | 2016-03-01 |  |  | International Competitive Bidding
Component 1 | A. Consulting services | Individual Consultant (AM-650) | Sector scan: descriptive analysis of the agriculture sector in Jamaica | 20000 | ICQ | Lump Sum | 20000 | 100% | 0 | 0% |  |  | Individual consultant | National Competitive Bidding
Component 1 | A. Consulting services | Individual Consultant (AM-650) | Analyses of development constraints for the sector | 70000 | ICQ | Lump Sum | 70000 | 100% | 0 | 0% |  |  | Individual consultant | Shopping
Component 1 | A. Consulting services | Individual Consultant (AM-650) | Analysis of Jamaica's policies for the agricultural sector | 25000 | ICQ | Lump Sum | 25000 | 100% | 0 | 0% |  |  | Individual consultant | Shopping
Component 1 | A. Consulting services | Individual Consultant (AM-650) | Review of performance-based agricultural policies | 15000 | ICQ | Lump Sum | 15000 | 100% | 0 | 0% |  |  | Individual consultant | Shopping
Component 2 | A. Consulting services | Individual Consultant (AM-650) | Evaluation of Agro-Parks | 35000 | ICQ | Lump Sum | 35000 | 100% | 0 | 0% |  |  | Individual consultant | Shopping
Component 2 | A. Consulting services | Individual Consultant (AM-650) | Agro-Park Strategy and Plan | 10000 | ICQ | Lump Sum | 10000 | 100% | 0 | 0% |  |  | Individual consultant | Shopping
Component 3 | A. Consulting services | Individual Consultant (AM-650) | Feasibility analysis and detailed design of proposed infrastructure works | 70000 | ICQ | Lump Sum | 70000 | 100% | 0 | 0% |  |  | Individual consultant | Shopping
Component 3 | A. Consulting services | Individual Consultant (AM-650) | Ex-ante carbon footprint balance estimation of proposed investments | 25000 | ICQ | Lump Sum | 25000 | 100% | 0 | 0% |  |  | Individual consultant | Shopping
Component 3 | A. Consulting services | Individual Consultant (AM-650) | Environmental and social impact assessment | 30000 | ICQ | Lump Sum | 30000 | 100% | 0 | 0% |  |  | Individual consultant | Shopping
Component 3 | A. Consulting services | Individual Consultant (AM-650) | Ex-ante economic analysis of operation | 20000 | ICQ | Lump Sum | 20000 | 100% | 0 | 0% |  |  | Individual consultant | Shopping
Component 3 | A. Consulting services | Individual Consultant (AM-650) | Institutional capacity analysis | 15000 | ICQ | Lump Sum | 15000 | 100% | 0 | 0% |  |  | Individual consultant | Shopping
Component 3 | A. Consulting services | Individual Consultant (AM-650) | Monitoring and evaluation plan | 15000 | ICQ | Lump Sum | 15000 | 100% | 0 | 0% |  |  | Individual consultant | Shopping
Prepared by: |  |  | TOTALS | 350000 |  |  | 350000 | 100% | 0 | 0%
(1) Grouping together of similar procurement is recommended, such as publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) (i) Individual consultants: ICQ: Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection. Selection process to be done in accordance with AM-650.
(2) (ii) Consulting firms: Per GN-2765-1, Consulting Firm selection methods for Bank-executed Operations are: Single Source Selection (SSS); Simplified Competitive Selection (<=250K) (SCS); Fully Competitive (>250K) (FCS); and Framework Agreement Task Order (TO). All Consulting Firm selection processes under this policy must use the electronic module in Convergence.
(2) (iii) Goods: Per GN-2765-1, par. A.2.2.c: "The procurement of goods and related services, except when such goods and related services are necessary to achieve the objectives of the Bank-executed Operational Work and are included in the consulting services contract and represent less than ten percent (10%) of the consulting services contract value."
Table for Data Validation
Select Comp: | Select Procurement Type: | Select Service Type: | description | amount | Select Method: | Select Cont. Type:
Component 1 | A. Consulting services | Individual Consultant (AM-650) |  |  | SSS | Lump Sum
Component 2 | B. Goods (2)(iii) | Consulting Firm (GN-2765) |  |  | ICQ | Framework Agreement
Component 3 | C. Non consulting services | Goods included in Cons. Firm RFP |  |  | SCS
Component 4 |  | Corporate Procurement (GN-2303) |  |  | FCS
Component 5 |  |  |  |  | TO
Component 6
Component 7
Component 8
Other