## Sheet1
Inter-American Development Bank
PROCUREMENT PLAN FOR IDB-EXECUTED OPERATIONS
Country: Regional | [5 empty] | Executing Agency: IDB | [7 empty] | UDR: CSD/CCS
Project number: RG-T3283 |  |  |  |  | Project name: Financing the Design and implementation of Nationally Determined Contributions (NDCs)
Period covered by the Plan: 24 months |  |  |  |  | Total Project Amount: |  | 1000000
Component | Procurement Type (1) (2) | Service type (1) (2) | Description | Estimated contract cost (US$) | Selection Method (2) | Type of Contract | Source of Financing and Percentage |  |  |  | Estimated date of the procurement notice | Estimated contract start date | Estimated contract length | Comments
[7 empty] | IDB/MIF |  | Other External Donor
[7 empty] | Amount | % | Amount | % |  |  |  |  | Direct Contracting
Select comp | Select Proc. Type | Goods Included in Firm Cons. RFP | Consultant 1: brief description |  | select method | Select Cont. Type |  |  |  |  | 2016-03-01 |  |  |  | International Competitive Bidding
Component 1 | A. Consulting services | Individual Consultant (AM-650) | Pilot to apply PER methodology with climate considerations in Jamaica. | 50000 | SSS | Lump Sum | 50000 | 5% | 0 | 0% | NA | 2019-07-01 | 6 months |  | National Competitive Bidding
Component 1 | A. Consulting services | Individual Consultant (AM-650) | Pilot to apply PER methodology with climate considerations in Dominican Republic. | 50000 | SSS | Lump Sum | 50000 | 5% | 0 | 0% | NA | 2020-05-01 | 6 months |  | Shopping
Component 1 | A. Consulting services | Consulting Firm (GN-2765) | Consultancy to develop the document of a Financial Strategy for Climate Change in Chile | 92000 | TO | Framework Agreement | 92000 | 9.2% | 0 | 0% | NA | 2019-07-01 | 4 months
Component 1 | A. Consulting services | Consulting Firm (GN-2765) | Consultancy to develop the document of a Sustainable Finance Strategy for Mexico. | 40000 | SCS | Lump Sum | 40000 | 4% | 0 | 0% | 2019-08-01 | 2020-01-01 | 6 months
Component 1 | A. Consulting services | Consulting Firm (GN-2765) | Consultancy to develop the document of a Financial Strategy for Climate Change for a country in LAC. | 68000 | SCS | Lump Sum | 68000 | 6.8% | 0 | 0% | 2020-07-01 | 2020-11-01 | 6 months
Component 2 | A. Consulting services | Consulting Firm (GN-2765) | Consultancy to update the NDC of Suriname. | 100000 | SCS | Lump Sum | 100000 | 10% | 0 | 0% | 2019-07-01 | 2019-08-15 | 6 months |  | Least-Cost Selection
Component 2 | A. Consulting services | Consulting Firm (GN-2765) | Consultancy to carry out a revision of the NDC of Barbados. | 80000 | SCS | Lump Sum | 80000 | 8% | 0 | 0% | 2019-11-01 | 2020-03-01 | 6 months |  | Quality and Cost Based Selection
Component 2 | A. Consulting services | Consulting Firm (GN-2765) | Consultancy to carry out a revision of the NDC of Bolivia. | 80000 | SCS | Lump Sum | 80000 | 8% | 0 | 0% | 2019-11-01 | 2020-03-01 | 6 months |  | Quality Based Selection
Component 2 | A. Consulting services | Consulting Firm (GN-2765) | Consultancy to draft a Decarbonization Plan for Ecuador. | 60000 | SCS | Lump Sum | 60000 | 6% | 0 | 0% | 2019-11-01 | 2020-03-01 | 6 months |  | Selection Based on the Consultants' Qualifications
Component 2 | A. Consulting services | Individual Consultant (AM-650) | Consultant to support design of new NDCs and LTS in LAC. | 35000 | ICQ | Lump Sum | 35000 | 3.5% | 0 | 0% | NA | 2020-02-01 | 12 months |  | Selection under a Fixed Budget
Component 2 | A. Consulting services | Consulting Firm (GN-2765) | Consultany to develop a cost-benefit assessments of the descarbonization of the transport sector in Costa Rica. | 38000 | SSS | Lump Sum | 38000 | 3.8% | 0 | 0% | NA | 2019-07-01 | 5 months
Component 2 | A. Consulting services | Consulting Firm (GN-2765) | Consultancy to develop sectoral assessments to inform NDC or LTS design. | 20000 | SSS | Lump Sum | 20000 | 2% | 0 | 0% | NA | 2020-02-01 | 6 months
Component 2 | A. Consulting services | Individual Consultant (AM-650) | Consultant to develop and oversee a methodogical apporach to support NDC and LTS design in LAC. | 33000 | ICQ | Lump Sum | 33000 | 3.3% | 0 | 0% | NA | 2020-02-01 | 5 months
Component 2 | A. Consulting services | Consulting Firm (GN-2765) | Consultancy to develop an Investment Plan for the implementation of the NDC of Costa Rica. | 63000 | TO | Framework Agreement | 63000 | 6.3% | 0 | 0% | NA | 2019-07-01 | 3 months
Component 2 | A. Consulting services | Individual Consultant (AM-650) | Consultant to develop and oversee a methodological apporach to support the development of climate investments plans in LAC. | 91000 | ICQ | Lump Sum | 91000 | 9.1% | 0 | 0% | NA | 2019-07-01 | 18 months
Component 3 | C. Non consulting services | Corporate Procurement (GN-2303) | Development of a workshop to socialise and inform IDB's Public Expenditure Review methodology including climate considerations. | 20000 | SCS | Lump Sum | 20000 | 2% | 0 | 0% | NA | 2019-10-01 | 1 month
Component 3 | A. Consulting services | Individual Consultant (AM-650) | Consultant to organize and capture the outcomes of the workshops to socialise and inform IDB's Public Expenditure Review methodology including climate considerations. | 40000 | ICQ | Lump Sum | 40000 | 4% | 0 | 0% | NA | 2019-07-01 | 6 months
Component 3 | A. Consulting services | Individual Consultant (AM-650) | Consultant to carry out research on best practices and opportunities for fiscal policy apporaches in LAC that support climate objectives. | 20000 | SSS | Lump Sum | 20000 | 2% | 0 | 0% | NA | 2020-02-01 | 5 months
Component 3 | A. Consulting services | Individual Consultant (AM-650) | Consultant to carry out research on best practices and opportunities for public budgets management in LAC that support climate objectives. | 20000 | SSS | Lump Sum | 20000 | 2% | 0 | 0% | NA | 2020-11-01 | 5 months
Prepared by: |  |  | TOTALS | 1000000 |  |  | 1000000 | 100% | 0 | 0%
(1) Grouping together of similar procurement is recommended, such as publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) (i) Individual consultants: ICQ: Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection. Selection process to be done in accordance with AM-650.
(2) (ii) Consulting firms: Per GN-2765-1, Consulting Firm selection methods for Bank-executed Operations are: Single Source Selection (SSS); Simplified Competitive Selection (<=250K) (SCS); Fully Competitive (>250K) (FCS); and Framework Agreement Task Order (TO). All Consulting Firm selection processes under this policy must use the electronic module in Convergence.
(2) (iii) Goods: Per GN-2765-1, par. A.2.2.c: "The procurement of goods and related services, except when such goods and related services are necessary to achieve the objectives of the Bank-executed Operational Work and are included in the consulting services contract and represent less than ten percent (10%) of the consulting services contract value."
Table for Data Validation
Select Comp: | Select Procurement Type: | Select Service Type: | description | amount | Select Method: | Select Cont. Type:
Component 1 | A. Consulting services | Individual Consultant (AM-650) |  |  | SSS | Lump Sum
Component 2 | B. Goods (2)(iii) | Consulting Firm (GN-2765) |  |  | ICQ | Framework Agreement
Component 3 | C. Non consulting services | Goods included in Cons. Firm RFP |  |  | SCS
Component 4 |  | Corporate Procurement (GN-2303) |  |  | FCS
Component 5 |  |  |  |  | TO
Component 6
Component 7
Component 8
Other