LEGIII/TT-674074-06

## THE ANNEX

THE PROJECT

## Improving Health, Safety and Environmental Standards

## Among Smaller Enterprises in the Energy Sector

I.	Objective

1.01	The overall objective of the Project is to increase market opportunities for small and medium enterprises in Trinidad & Tobago, especially in the energy sector. The purpose of the Project is to develop and promote the widespread use of internationally acceptable industry-wide health, safety and environmental standards and improve the related performance among small and medium-sized enterprises (SMEs).

II.	Description

2.01	To achieve this objective, the Project will include the following components: (i) development of uniform health, safety and environmental standards; (ii) development of local capacity for training and certification; (iii) implementation of health, safety and environmental (HSE) standards among SMEs; and (iv) promotion of HSE standards and dissemination of results.

- Component I: Development of uniform health, safety and environmental standards

  - The objective of this component is to develop a uniform series of health, safety and environmental standards specific to the energy sector in the country.  These standards should be on par with international standards used in the energy sector.  For this, the following activities are expected: (i) a gap analysis to review the current HSE related standards used in the industry; (ii) definition of priority HSE standards for the sector; (iii) definition of tier certification system and oversight; (iv) stakeholder consultations; and (v) publication of HSE standards.

  - Carrying out a gap analysis of the HSE Management Systems of the major oil and gas exploration and production companies is a key activity to understanding the companies’ requirements of the standards that will be developed or sanctioned.  For this, a consultant will be contracted to facilitate the work to be conducted by a team comprising the HSE Managers and operations managers of all the major oil and gas exploration and production companies. The gap analysis will involve a review of the documented Safety and Environmental Management Systems of all the companies. This will identify the commonalities between all the systems, and document where a simple acknowledgement of a common standard can be achieved. Where gaps between systems are identified, the development of agreeable bridging documentation will close the gaps and ensure that all participating organizations are able to understand why and how the relevant standards are acceptable.

  - Once the bridging document is completed, the consultant will assist the HSE Working Committee with defining an appropriate number of priority standards to be addressed in the Project. After the standards have been developed, the consultant, in consultation with the HSE Working Committee, will further develop and fully define the certification system for HSE service providers and for service companies/contractors.  As part of this, the consultant will fully define the roles and responsibilities of the eventual National HSE Board, its governance structure and the financial model for the Board (including the commercial terms under which companies are to be certified).  The certification system will have a tiered structure, allowing companies to be certified at various levels for relevant energy sector activities. The documented standards, tiered certification system, compliance and supervision process will be made available for public consultation.  Once concluded, the HSE standards will be published and disseminated.

- Component II: Development of local capacity for training and certification

  - In order to provide the necessary HSE services to companies operating in the energy sector, this component seeks to develop the local capacity of potential HSE implementation and certification service providers.  Local HSE service providers will be trained to advise and assist companies in the implementation of the new HSE standards and to audit and certify compliance with these standards. A consultant will be hired to develop the training methodology and materials and to conduct the training.

  - Personnel from service companies or individuals that have the institutional capacity and competency to become HSE service providers to SMEs will be trained in how to implement HSE standards. Similarly, potential HSE certification service providers will be trained in how to certify SMEs to the HSE standards.  Companies that have undergone the training will be audited by one or more competent and experienced international HSE auditor(s) to assess their capacity and competency for delivering the HSE implementation and certification services to SMEs. Upon satisfactory completion of this audit, these companies will become certified to implement and/or audit HSE standards among SME’s in the local energy sector in Trinidad and Tobago.  This process of accreditation will be overseen by the HSE Steering Committee, and will be consistent with the process developed in Component I.

- Component III: Implementation of HSE standards among SMEs

  - The purpose of this component is to implement HSE standards in SMEs to enhance their competitiveness and performance. The Project will establish a matching grants mechanism to facilitate the implementation of HSE standards among SMEs.  For this, there will be two groups of companies: a pilot group of ten SMEs; and a subsequent larger group of some 30 SMEs. Two types of technical assistance will be provided to companies: (i) technical assistance to implement the HSE standards; and (ii) technical assistance to certify that the particular company is in compliance with those standards.

  - In order to be selected, companies must: (i) be small or medium-sized enterprises (fewer than 100 employees and less than US$5 million in annual sales); (ii) be legally constituted; (iii) belong to the energy sector or a related sector; (iv) express interest in implementing definitive, economically viable solutions; and (v) make all due payments for receiving the technical assistance pursuant to the agreements.  Considering that the costs will be shared, the SMEs are expected to be interested in taking part and to make a commitment to implementing the standards.

  - The ten SME companies selected for the pilot group will come from a range of different services offered to the energy sector, and including companies at various levels in terms of their existing HSE policies and procedures.  The application and selection process to be part of the pilot group will be published on the Project website and other means.  Companies participating in the pilot group will receive a matching grant of up to 50% of the cost of implementing the HSE standards, with the balance being met by the companies.  The Project will consider up to a maximum of US$5,000/SME for implementation costs in this pilot group. Upon completion of the implementation phase, the SMEs in the pilot group will then be audited for compliance with the standards. After satisfying the pre-determined criteria, they will be certified as HSE compliant for the relevant activity area and at the relevant competency level.  In order to receive their certification, each SME will have to be certified by an accredited entity.  Each SME in the pilot group will receive a matching grant of up to 50% of the cost of certification, with the balance being paid by the company itself.  The Project will consider up to a maximum of US$2,000/SME for certification fees in this pilot group.

  - The experiences gained in the implementation and certification of the pilot group of SMEs will be documented and shared with the HSE Steering Committee, HSE Working Committee, HSE service providers and beneficiaries, through a workshop and made available on the Project website.  Taking into account the lessons learned from the pilot phase, a wider group of 30 SMEs will be selected for implementation and certification assistance.  The SME companies will be selected for the wider group on a first come, first served basis, though efforts will be made to ensure a diverse set of SMEs are included to strengthen the demonstration effect of the Project. Companies taking part in the activity will receive a grant of up to 30% of the technical assistance costs of implementing the HSE standards, with the balance of fees being met by the company itself.  The Project will consider up to a maximum grant of US$3,000/SME for implementation related costs for this group.  Similar to the pilot group, interested SMEs that have implemented the HSE standards will be eligible to solicit Project support for obtaining HSE certification from an accredited entity.  Each SME in this group will receive a grant of up to 30% of the cost of implementation, with the balance being paid by the company itself.  The Project will consider up to a maximum grant of US$1,200/SME for certification costs.

- Component IV: Promotion of HSE standards and dissemination of results

  - The objective of this component is to promote the opportunities and actions of the Project and to disseminate the results.  For this, the component includes the following activities: (i) development and update of Project related website linked to STCIC’s existing website; (ii) development of promotional materials; (iii) organize a launching event for the Project that will target media and Project stakeholders to increase their knowledge of the Project; (iv) periodic events such as luncheons, seminars and workshops designed to promote Project goals and activities, as well as disseminate the interim results and accomplishments of the Project; and (v) a final conference designed to disseminate the results and accomplishments of the Project.  The dissemination of the results and lessons learned from this Project are expected to be extended to and replicated by other sectors of the economy.

III.	Total Cost of the Project

3.01	The estimated cost of the Project is the equivalent of five hundred and ninety thousand dollars (US$590,000), in accordance with the following Budget:

Budget

(in US$)

| Activities | BANK | Executing Agency | Total | % |
| --- | --- | --- | --- | --- |
| Development of uniform health, safety and environmental standards | 9,950 | 25,600 | 35,550 | 6.0 |
| Development of local capacity for training and certification | 49,200 | 6,360 | 55,560 | 9.4 |
| Implementation of HSE standards among SMEs | 186,000 | 6,000 | 192,000 | 32.5 |
| Promotion of HSE standards and dissemination of results | 24,000 | 74,000 | 98,000 | 16.6 |
| Administration | 93,000 | 59,850 | 152,850 | 25.9 |
| Evaluations | 20,000 | 0 | 20,000 | 3.4 |
| Financial Audits | 11,000 | 0 | 11,000 | 1.9 |
| Contingencies | 21,850 | 3,190 | 25,040 | 4.2 |
| TOTAL | 415,000 | 175,000 | 590,000 | 100 |
| Percentage | 70% | 30% | 100% |  |

IV.	Execution

  - For the administration of the activities, the Executing Agency  will hire a Project Coordinator and a Project Assistant. The Project Coordinator will be responsible for: (i) managing Project activities in accordance with the annual plans; (ii) supervising any consultants; (iii) monitoring the management and handling of the budget; (iv) employing established procedures; (iv) processing requests for disbursement of the Bank’s contribution; (v) submitting administrative and technical reports to the Bank; and (vi) coordinating necessary actions with the institutional partners and other entities involved. The Project Coordinator will report to the CEO of the STCIC.

  - There will be an HSE Project Steering Committee that will oversee the implementation of the Project and will comprise representatives of the STCIC, the Association of Trinidad & Tobago Insurance Companies (ATTIC), Point Lisas Energy Association (PLEA), the Trinidad & Tobago Bureau of Standards (TTBS), Ministry of Labour and Small and Micro Enterprise (MoLSME), Ministry of Energy & Energy Industries (MOEEI) and major oil & gas production companies.  It is anticipated that this Steering Committee will be transformed into a permanent energy sector HSE Board by the end of the Project.  An HSE Working Committee will be appointed to report to the Steering Committee and to provide technical advice and assistance to the Steering Committee members.

- Monitoring and Evaluation

  - The Executing Agency will prepare and submit to the Bank Project progress reports within 30 days after the completion of each semester and a final report within 30 days from the final disbursement.  These reports will follow a format previously agreed with the Bank and will address Project activities and finances (such as annual procurement plans), as well as results measured in terms of the indicators and benchmarks identified in the Project’s Logical Framework. The Bank will utilize these reports to monitor Project implementation progress and to prepare a Project Completion Report within 3 months of the last disbursement.  For each project supported in Component II, the Bank may undertake periodic visits as part of its monitoring efforts.

  - An intermediate and a final evaluation of the Project will be undertaken by external consultants to be contracted directly by the Bank with Project resources. The mid-term evaluation will be prepared 18 months after the commencement of Project implementation or when 50% of the resources have been disbursed. A final evaluation will be conducted 3 months prior to the end of Project disbursement period.  For the intermediate evaluation, the consultant will consider, among other items: (i) financial analysis of the implementation; (ii) evaluation of the schedule and of the results obtained; (iii) characterization of progress indicators and of difficulties and limitations encountered; and (iv) a review of the implementation plan for the following phase.  For the final evaluation, the consultant will take into account: (i) the quality of the results obtained in technological and business terms; (ii) the identification of measures that can be incorporated to improve the identification and implementation in replicating the Project in other sectors of the economy; and (iii) assess the sustainability of the HSE Board.

  - In addition, the Executing Agency will organize a completion workshop to discuss the evaluations’ findings and other Project conclusions with the Bank and the Project’s key stakeholders.  During the Project’s execution, the Executing Agency will compile supervision and Project evaluation indicators. These indicators are set forth in the Logical Framework and will be used by the Country Office, the Office of the Multilateral Investment Fund and the Executing Agency to gauge the overall impact and to assess the results.  The Executing Agency will provide access to all the information and documentation needed to conduct these evaluations so the Bank can prepare the Project Completion Report.