LEGIII/MIF-TT-675572-06

ANNEX

THE PROGRAM

Computer Programming Training for Development of Tobago’s

Information Technology Outsourcing Capability

I.	Objective

  - The broad goal of this training initiative is to develop Information Technology outsourcing capabilities in Tobago by creating a cadre of skilled and experienced individuals in the area of computer programming and software development using the PROGRESS toolset. This toolset represents a comprehensive set of software development tools created by Progress Software Corporation based in Bedford, Massachusetts.

II.	Description

2.01	The training program is structured in three distinct phases as follows.

- Phase I: Theoretical Training

2.02	This phase has encompassed training in the theory of computer programming/software development and the use of the PROGRESS toolset to develop software application. Secondary school graduates from low-income communities have been offered the opportunity to participate in the theoretical training phase. This phase has already been undertaken and successfully completed by the Empowerment Foundation of Tobago (EFOT) between the period of October 2004 to June 2005 with sixteen Tobagonians graduating.

- Phase II: The Practicum

2.03	The second phase of this project involves a practicum, which provides graduates of Phase I the opportunity to undertake a series of programming assignments to test the application of their training and skills set in commercial service delivery. During this phase, nine graduates of Phase I will work on pilot projects for locally based clients under the supervision and guidance of their instructor. Graduates of this phase will be qualified to work on assignments requiring PROGRESS’s “Junior 4GL Programmer” skill sets worldwide.

- Phase III: Job Placement Opportunities

2.04	Phase III of the project allows participants successfully completing the practicum to be contracted by a locally registered consulting firm, (SMAT Tobago), which will promote and provide programming services on a fully commercial basis.

2.05	The contribution will provide financial support for Phase II of the training program in collaboration with EFOT. The objective is to pilot the commercial delivery of programming skills of graduates of Phase I of the computer programming training program completed in June 2005. Phase I graduates have entered a nine month “practicum” in which they will, under supervision of their instructor, undertake a series of programming assignments including some from locally based SMEs to test the application of their training in commercial service delivery. Course participants successfully completing the practicum will be recruited by a locally registered consulting firm (SMAT Tobago), which will continue to provide programming services on a commercial basis. The project also seeks to pilot new types of business activity in Tobago by establishing offshore programming capacity via SMAT Tobago. This type of business opportunity is complementary to Tobago’s existing focus on tourism with no negative environmental impact and good prospects for youth employment. The SMAT Tobago firm together with EFOT offers young persons alternate opportunities to train for and work in the knowledge economy without leaving the island.

2.06	Key activities to implement Phase II of the Program include the following:

- Final structuring and design of the practicum involving extensive industry consultation and promotion of services

- Delivery of practicum

- Job Placement of trainees

- Evaluation of Program impact, distillation of lessons learned for incorporation in the next round of training targeted for 2007

III.	Total Cost of the Program

3.01	The estimated cost of the Program is the equivalent of US$67,000, in accordance with the following Budget:

### Budget

(in thousands of US$)

| Item | EFOT Counterpart Resources | MIF Contribution | ## Total |
| --- | --- | --- | --- |
| ###### Instructors Fees |  | $12,000 | $12,000 |
| ###### Trainee Stipend | $9,800 |  | $9,800 |
| ###### Facilities | $4,800 |  | $4,800 |
| ###### Equipment - Server - Networking - Furniture - Projector | $24,500 |  | $24,500 |
| ###### Administration, Communication and Utility Costs | $5,900 | $3,200 | $9,100 |
| ###### Software License Costs |  | $5,000 | $5,000 |
| ###### Audit and Evaluation |  | $1,800 | $1,800 |
| TOTAL | $45,000 | $22,000 | $67,000 |