LEGIII/MIF-TT-556604-05

ANNEX

THE PROJECT

Standards in the Energy Sector:  Definition of an Action Plan

I.	Objective

1.01	The key project objective is to develop and gain consensus on an approach and action plan to address the development of national health safety and environmental standards in the Trinidad & Tobago energy sector.

II.	Description

2.01	The primary activities required for execution of the project are as follows:

- The Beneficiary will hire a consultant with excellent knowledge of international standards and the local energy sector who will meet with all of the major operators, the TTBS National HSE Standards Committee, the Point Lisas HSE managers, the Ministry of Energy and Energy Enterprises and any other relevant stakeholders.

- Based on these meetings the consultant will develop a set of guiding principles and draft an action plan outlining priority actions to be undertaken by the various Associations, ad. hoc committees, and other organizations and companies.

- The guiding principles and action plan will be presented to all stakeholders at a half-day workshop and the consultant will facilitate dialogue and discussion to ensure consensus on the guiding principles and action plan.

- The consultant will finalize the action plan and develop the project implementation plan of the proposed medium term project to Develop National Standards in the Trinidad & Tobago Energy Sector.

III.	Total Cost of the Project

3.01	The estimated cost of the Project is the equivalent of US$13,000, in accordance with the following Budget:

Budget

(in thousands of US$)

| T&T Standards in the Energy Sector: Development of an Action Plan |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Activities | Unit Cost | # Units required | Total Cost | MIF | STCIC | STCIC |
|  |  |  |  |  | Cash | In Kind |
| Consulting Services (man days) | 650 | 15 | 9750 | 9750 |  |  |
| Workshop Expenses |  |  |  |  |  |  |
| Rental | 250 | 1 | 250 |  | 250 |  |
| Refreshments | 6 | 50 | 300 |  | 300 |  |
| Copies/Documents |  |  | 300 |  | 300 |  |
| Administrative Support and /Project Oversight |  |  | 1500 |  |  | 1500 |
| Audit |  |  | 650 |  | 650 |  |
| General Expenses |  |  | 250 | 250 |  |  |
| Total |  |  | 13000 | 10000 | 1500 | 1500 |