LEG/SGO/TT-1892007-09

THE ANNEX

THE PROJECT

Implementation of Sustainable Farming Practices in Trinidad’s

Northern Range Communities

I.	Objectives

  - The project’s objective is to develop a community based model for sustainable hillside farming which will deliver greater economic gain to small scale hillside farmers, while alleviating current environmental threats caused by current practices and sustaining the natural resource base of the Northern Range.

  - The objective will be achieved by piloting a replicable model for protecting the ecosystem and alleviating negative downstream impacts within watershed communities through the introduction and adoption of sustainable agricultural practices by small scale farmers in the Northern range. Additionally, the project will support the social and economic development of participating farmers and their communities through the implementation of these alternative farming practices and communicate this approach and assist in the scaling up and replication of this model.

II.	Description

Component I: Pilot Project on Sustainable Farming Practices

  - This component of the project focuses on the development and implementation of a pilot programme of sustainable farming practices within two selected watershed communities of the Northern Range. These two watershed areas of Caura/Tacarigua and St. Joseph have been selected out of 35 watersheds of the Northern Range, based on criteria developed by The Cropper Foundation. These criteria were based on a range of socio-economic and ecological factors. Using the criteria, these 2 watershed areas have been chosen for this pilot based on the existence, extent and nature of farming practices; terrain type; a preliminary assessment of farmers’ willingness to participate in the project; and signs of transformation being undertaken within a community.

  - Within the two watershed areas identified by the Cropper Foundation, communities will be identified and invited to participate in the pilot project based on a series of weighted criteria as follows (weights are ranked 1 to 5 with 5 being the highest):

- (i)	existence of unsustainable agricultural practices - 4;

- (ii)	existence of community governance structures (even rudimentary) - 3;

- (iii)	land tenure system (whether resident farmers have legal access to lands under hillside cultivation) – 2;

- (iv)	minimal bias of intervention results from nearby development initiatives - 3; and

- (v)	complementarity of proposed program with existing community initiatives (if any) – 1.

  - The implementation of this pilot project on sustainable farming practices will begin with the creation of baseline data to measure the potential environmental and economic impact of adopting environmentally sustainable cultivation practices on participating farmers. It will be important to work with hillside community members within the selected watersheds to create an understanding of the impact of their actions on the environment, as well as the link between environmental management and the sustainability of their own livelihoods. This step is critical in building understanding of the project, the implications and impact of existing farming and other activities by the community on the sustainability of community livelihoods Working with hillside community members, the baseline data including results of community/stakeholder consultations from this component will enable The Cropper Foundation and key stakeholders (including targeted farmers in the selected areas) to:

- (i)	make an overall and in-depth assessment of current agricultural practices and the impact of these practices on the immediate community, the natural environment, downstream communities, and consumers (within the larger spectrum of an impact on local food security);

- (ii)	understand the opportunities and possibilities for technical interventions. A salient element of this project is to provide farmers with alternative practices which will not only have a positive impact on the environment, but also have positive effects on their income level and living standards. As such, instructive information in this regard will include: the availability and suitability of more profitable, sustainable and/or more environmentally adaptable crops; feasible and sustainable agricultural techniques, such as a shift from short cropping to forest gardening, modifying high input to low input agriculture, changing crop mixes to suit the community and the environmental objectives and/or land preparation with emphasis on soil conservation; the potential for receptivity of new technology to ensure ownership and application; and the propensity for capacity building and replication within this community and others with similar circumstances;

- (iii)	assist in the identification of farmers from selected hillside watershed communities for participation within the pilot program;

- (iv)	understand the possibilities for effective intervention by the project team, rationalising constraints and opportunities for leverage; and

- (v)	provide information for a research overlay necessary for future comparisons and analysis of results and impact over time, which will inform the process of dissemination and replication of the model as well as raising awareness of key stakeholder groups so as to inform national policies and planning.

  - While the exact numbers of farmers selected will depend on information from the baseline assessment and each watershed community, the selection of farmers to participate in the pilot program will be based on a series of transparent weighted criteria as presented below (weights being ranked on a scale of 1 to 5 with 5 being the highest).

- (i)	Farmer is currently engaged in unsustainable farming practices – 4.

- (ii)	Land tenure system governing areas under the farmer’s cultivation – 2.

- (iii)	Demonstrated willingness to participate in the project – 5.

- (iv)	Interest in and capacity for the transfer of knowledge of alternative practices to others – 4.

- (v)	Initial indication of commitment to continue with proposed farming methods beyond the project period (based on oral commitments and indications of practices continued from other programs or interventions) 4.

  - Following the creation of baseline information on the communities selected and the identification of farmers, a major sub-component of this project will be the provision of technical support to participating farmers in selected pilot communities to teach and transfer practical skills and knowledge of alternative cultivation practices. These interventions will be conducted via a series of workshops and demonstration projects including land preparation and management, crop selection, agronomic practices. Such workshops will include:

- (i)	Workshops with farmers in pilot sites for participatory design of interventions.

- (ii)	Workshops with farmers and technical experts to:

- - Assess findings of baseline information;

- - Gain consensus on the design of interventions for pilot sites; and

- - Finalise the design of the research overlay.

- (iii)	Workshops with farmers and technical experts to:

- - Share experiences and knowledge;

- - Assess status of project; and

- - Allow for improvement in project design.

  - While specific elements of the actual interventions will result from analysis of the baseline assessment, it is envisioned the detailed design of technical support for farmers will be finalised through participatory focused meetings, workshops and site visits. The implementation of interventions and monitoring and evaluation will be based on field work in community demonstration sites, at farmers’ experimental plots, as well as through focused meetings and workshops. Evaluation at the end of the project will be based on monitoring and evaluation reports developed throughout the project to measure progress in terms of stated project objectives and specific analysis of environmental changes measured against data collated in the baseline assessment. Information will be collected and assessed by the project’s technical team as well as by farmers. The mechanism for data collection would include surveys, site visits, sampling (e.g. soil and water) and focused stakeholder meetings/forums.

  - Technical results of the interventions will be monitored over time and measured against the baseline assessments and measurements to clearly document project results. The analysis of project results will be supported through the provision of technical and other resources from the institutional partners as documented in Annex VI.

## Component II: Strengthening of Local Networks and Dissemination of Results

  - Following on from the baseline assessment and the design and implementation of technical support for participating farmers, a crucial step to achievement of broader project objectives will be networking with the selected communities, other similarly affected communities, and public and private stakeholder organisations to disseminate information on the environmental and socio-economic benefits of adopting alternative farming practices.

  - While the ultimate goal of this effort will be to effect and/or inform public policy and programmes at the national and regional levels, with a view to replicating the project in other areas, the dissemination of the actual results achieved within participating communities is a key factor in ensuring buy in for the alternative approaches introduced and the sustainability of improved practices beyond the project execution and investment period. In essence, this component will document and disseminate information on a community-based model for sustainable hillside farming, which will deliver greater economic gain to small-scale hillside farmers while alleviating environmental threats caused by current practices.

  - As such, in an effort to achieve mainstreaming and sustainability of this approach to food cultivation in vulnerable environments and communities, it is proposed that key stakeholder organisations from the public and private sectors be involved in steerage of this pilot project, the distillation of lessons learned and the recommendation for expansion and mainstreaming of this approach, initially at the national level.

  - The Cropper Foundation tries to be catalytic and strategic in its initiatives implemented with limited resources and therefore realises the key to project sustainability and expansion is to secure buy-in. With this project, buy-in would be needed from farmers, technical organisations as well as government institutes, mainly the Trinidad and Tobago Ministry of Agriculture. This Ministry has the mandate for agriculture in the country and is therefore the only entity that can support or implement a nationwide programme to promote sustainable agricultural practices. The main approach to replication would be to actively engage key stakeholders, such as the Inter American Institute for Co-operation in Agriculture (IICA), Caribbean Agricultural Research and Development Institute (CARDI), and the Food and Agriculture Organisation (FAO) and the Trinidad and Tobago Ministry of Agriculture, to disseminate information on the project and results achieved. The IICA, FAO and CARDI have already indicated their support for and technical contributions to the project at a meeting of thee institutional partners, the Cropper Foundation and the IDB/MIF.

  - Broader dissemination efforts which will be supported by institutional partners including the FAO, IICA and CARDI will include a national conference for public and private stakeholders.

  - Ultimately, the project is intended to deliver two main outputs: transformed hillside practices within participating communities and dissemination of lessons learnt, of which the sharing of lessons and replication of practices introduced under Component I, can be considered as indicators of project sustainability. The participating farmers can play a role in outreach and sharing and this can serve to further validate the project for them as well as motivate them to continue to implement the practices adopted within the project.

III.	Total Cost of the Program

  - The total  cost of the Program is expected to be US$294,500 of which MIF would contribute US$150,000 in non-reimbursable funds, and the remainder of US$144,500 will be provided by the Cropper Foundation as counterpart resources. At least 50% or US$72,250 of the counterpart resources will be constituted via cash contributions.

### Budget

|  | Budget Categories | Bank (MIF) | Counterpart | Total | % of Total |
| --- | --- | --- | --- | --- | --- |
|  | Technical Co-ordination | 84,000 | 6,000 | 90,000 | 31% |
|  | Baseline Assessment, Research and Documentation of Results | 22,000 | 18,000 | 40,000 | 14% |
|  | Implementation of Alternative Farming Practices | 34,000 | 96,000 | 130,000 | 44% |
|  | Seminars and Workshops | 5,000 | 2,000 | 7,000 | 2% |
|  | Project Administration | 3,000 | 19,500 | 22,500 | 7% |
|  | Audit |  | 3,000 | 3,000 | 1% |
|  | Evaluation | 2,000 |  | 2,000 | 1% |
|  | Total | 150,000 | 144,500 | 294,500 | 100% |

#### Executing Agency and Mechanism

  - The Program’s Executing Agency will be The Cropper Foundation.

  - The Cropper Foundation will convene a Project Steering Committee to provide oversight and monitor the achievement of project objectives and will resolve any issues referred to the Committee that are deemed to negatively impact project implementation or performance. An officer of the IDB’s Trinidad y Tobago office may also sit on the above-mentioned committee.

  - The FAO, IICA and CARDI have committed to providing additional technical resourcing and support for the program, particularly for the analysis and dissemination of results and in influencing longer term change in national policy and programming initiatives, particularly in the areas of agriculture and environmental management.

  - Day to day project operations will be managed by a full time technical co-ordinator designated by the Cropper Foundation. The technical co-ordinator will report to the Project Steering Committee as well as to the assigned supervising officer designated by the Multilateral Investment Fund (MIF)/IDB.

  - The Cropper Foundation will be responsible for the financial administration of the project including maintenance of financial records to facilitate reporting by source of funding and category of investment as well as the retrieval and verification of relevant supporting documentation. The Cropper Foundation will also ensure that adequate controls are implemented in the management of project resources.