LEGIII/JA-687503-06

THE ANNEX

THE PROJECT

# Upper Rio Grande & Holywell Commercial Development Project

I.	Objective

1.01	The objective of the Project is to create a viable centre of sustainable commerce and development in the Upper Rio Grande Valley and Holywell areas, through a synergy of existing national park management initiatives, local community, small business enterprise, and the expertise and clientele from the tourism sector.

II.	Description

2.01	In order to achieve its objectives, the Project has four (4) main components:

- Tourism product definition and development;

- Training of community groups e.g. Bowden Pen Farmers Association;

- Promotion of tour packages; and

- Program sustainability.

2.02	A consulting firm or specialized institution will be contracted to carry out the following activities, working in close association with the JCDT.  JCDT will also contract a Project Coordinator who will become a staff member and will be responsible for the day-to-day coordination of the Project with other related programs of the BJCMNP.  The activities in each component is as follows:

Component I: Tourism product definition and development

(a)	Selection/confirmation and preparation of sites/trails within the areas, including the conduct of environmental assessment;

(b)	Establishment of linkages and partnerships with the private sector in the tourist centers of the north coast and other areas of Jamaica, including incentives for cooperation with communities of the national park’s buffer zones and the JCDT;

(c)	Design and preparation of tour packages to the BJCMNP and its buffer zones; and

(d)	Product Development – audits and provision of guidelines, development of plans e.g. architect’s drawings, estimates for infra-structural work etc.

Component II:  Training of community groups e.g. Bowden Pen Farmers Association

(a)	Training and capacity building in accommodations e.g. bed and breakfast, cabins, camping; merchandise e.g. craft, value-added agro-produce; transportation and other services/amenities;

(b)	Environmental management including principles of carrying capacity, visitor management and ecosystems management; and

(c)	Book-keeping, accounting and other small business and organizational skills.

Component III: 	Promotion of tour packages

(i)	Preparation of a marketing plan;

(ii)	Design and preparation of brochures and other materials for promotion; and

(iii)	Formalize arrangements with the tourist centers – this will include frequency, approximate number of visitors, and sites to be visited.

## Component IV:	Program sustainability

(i)	Mobilization and securing of partnerships among trainees, tourists’ centers and JCDT;

(ii)	Establishment of a management framework for the commercial center;

(iii)	Preparation and implementation of Sustainability Plan for the commercial center; and

(iv)	Documentation as a Case Study.

III.	Total Cost of the Project

3.01	The estimated cost of the Project is the equivalent of US$170,500, in accordance with the following Budget:

#### Budget

(in US$)

| Activities | BANK/MIF | LOCAL | TOTAL |
| --- | --- | --- | --- |
| 1. Project Coordinator | 10,000 | 12,000 | 22,000 |
| 2. Consultants’ Fees | 60,000 | 35,000 | 95,000 |
| 3. Materials Development e.g. training materials, marketing materials | 500 | 4,500 | 5,000 |
| 4. Transportation, Accommodation, Communication | 3,000 | 5,000 | 8,000 |
| 5. Product Development/Training | 3,000 | 20,000 | 23,000 |
| 6. Launch/Presentation of Findings/PR | 500 | 2,000 | 2,500 |
| Sub-Total | 77,000 | 78,500 | 155,500 |
| Administrative Fee | 15,000 |  | 15,000 |
| TOTAL | 92,000 | 78,500 | 170,500 |