LEGIII/JA-755616-06

ANNEX

# THE PROJECT

Documenting HIV/AIDS Intervention Programs for Jamaican Children

I.	Objective

  - The objective of the Project is to increase the information available regarding intervention Programs for children in Jamaica made vulnerable by HIV/AIDS, in order to direct response efforts of interested persons or groups, and to strengthen networking among organizations carrying out HIV/AIDS intervention Programs for children.

  - Specifically, the project aims to: (i) identify the various institutions/organizations with projects or programs for children in Jamaica made vulnerable by HIV/AIDS; (ii) document the programs and assess how and to what extent evaluations have been done; (iii) develop a database including all the programs identified in both print and electronic formats which will be searchable and updatable; and (iv) create a networking mechanism for organizations carrying out HIV/AIDS Programs for children.

II.	Description

2.01	In order to achieve the above-mentioned objective, the Project will finance the following activities:

Identifying and listing organizations with HIV/AIDS intervention Programs for children

  - A search will be made for all the organizations with HIV/AIDS Programs for children working in Jamaica. The search will be done through a network of contacts including: the Ministry of Health (MOH), the Ministry of Education, Youth and Culture, the Ministry of Labour and Social Security, the University of West Indies and other tertiary institutions, the Jamaica Council of Churches, Jamaica AIDS Support, and the National AIDS Committee. A list of organizations will be generated as a preliminary output of the Project.

### Development and Piloting of an information-gathering instrument

  - An information-gathering instrument will be developed to comprise a set of questions including a description of each program, the focus, sites and setting of programs, sources of funding, and evaluation procedure(s). This instrument will be piloted and modified accordingly to ensure that the required information will be relevant, and can be easily recorded in the Jamaican context.

### Site visits

  - The research team will carry out a semi-structured interview with the identified organizations’ managers or their appointees, and printed reports or other documents about the HIV/AIDS programs will be collected.

Compilation of information in print and electronic formats

  - The information collected will be entered and stored in an appropriate format for easy access and easy updating. The most appropriate format for data entry and storage will be ascertained with the assistance of Mona Information Technology Services (MITS) based at the UWI. The requirements are that the database with the information that have been collected will be ‘user-friendly’, searchable using different search terms, and will be easy to maintain and update as new information is collected.

  - A critical review of the programs will be undertaken. A report (including a matrix) of the programs describing the target populations served, the types of services provided to groups of children, overlap in services and areas of unmet needs will be prepared. The findings of this report will inform stakeholders of the various gaps and overlaps in policies and services, in the knowledge base (that is, research findings and best practices) and in available resources (including expertise and funding sources). The Caribbean Child Development Centre (CCDC) of the University of the West Indies will monitor comments and suggestions from users in order to continually update and improve the database.

### Dissemination Strategies

2.07	A one-day workshop will be held to share the findings of this initiative. The objectives of the workshop with stakeholders will be to: (i) share the findings of the Project in a summary report and present the data base; (ii) identify the priorities and responsibilities for the development and maintenance of the database; (iii) establish a collaborative structure to support the database, to communicate and cooperate in addressing emergent issues; (iv) formulate a plan to inform and encourage colleagues, students and the public to utilize the database.

2.08	The database will have, if agreed by stakeholders, linkages with the sites of the National AIDS Committee, Ministry of Health, Ministry of Education Youth and Culture, the Planning Institute of Jamaica, the University of the West Indies including the School of Continuing Studies and their library databases, and Jamaica Information Service.

2.09	As part of the dissemination strategy, factors such as when, how, what, and for whom stakeholders generate information, will be examined. Documentation of the different types of program outputs (general record keeping, evaluation reports, progress reports to donors, paper report, electronic report, press releases, evaluation reports, call for proposals from donors, brochures, etc.) will be produced, and a user-friendly format for presenting the information on the database will be developed. This process will identify the best approaches, modes, and times to disseminate information, which will set the stage for an active, on-going dissemination strategy.

2.10	The emergent dissemination strategy may include electronic circulation of announcements of recent findings or new programs, a regular electronic newsletter, regular workshops and meetings on recent findings and/or calls for proposals. The website that hosts the database will be updated with new information accordingly and will be maintained by the Caribbean Child Development Centre’s Information Officer.

2.11	A project report will be given to all consulted stakeholders and other interested parties, including government and donors agencies, as an output of the Project. The report will describe the consultation process, the strategies developed for the dissemination of information to the various agencies and stakeholders, lessons learned in the development of the database, emergent issues and actions, and recommendations for further database development and dissemination, including advocacy. Oral and visual presentations of this project will also be made to policymakers through participation in seminars and conferences – at local, national and international levels.

III.	Total Cost of the Project

3.01	The estimated cost of the Project is the equivalent of seventy seven thousand five hundred dollars (US$77.500), in accordance with the following Budget:

Budget

(US$)

| ## Budget Categories | Bank | Local Contribution | Total |
| --- | --- | --- | --- |
| 1. Project Technical Direction 1.1 Principal investigators 1.1 Research Assistant | 24,000 10,000 14,000 | 28,200 28,200 | 52,200 38,200 14,000 |
| 2. Transportation | 9,500 | - | 9,500 |
| 3. Administration 3.1 Office space 3.2 Communication (telephone, fax, etc.) 3.3 Computer and peripherals 3.4 Office supplies (stationery, printing, photocopying) 3.5 Administrative support | 4,000 500 2,500 1,000 | 7,800 5,800 2,000 | 11,800 5,800 500 2,500 1,000 2,000 |
| 4. Database development | 1,500 | - | 1,500 |
| 5. Dissemination meeting and database launch | 1,000 | - | 1,000 |
| 6. External Audit | 1,500 |  | 1,500 |
| TOTAL | 41,500 | 36,000 | 77,500 |

IV.	Execution

  - The Project execution period will be ten months and the disbursement period will be twelve months. The Project will be implemented by the Beneficiary under the direction of the Head of the CCDC.

  - The Beneficiary will prepare and submit to the Bank a Final Project Report at the time of the final disbursement, recording project activities, outcomes to date and expected future impact.