LEGIII/JA-927409-07

THE ANNEX

THE PROJECT

Expanding Access to Rural Micro Credit in Jamaica

I.	Objective

- 1.01	The goal of the Project is to increase the access to financial services to at least 4,500 microenterprises in the rural areas and secondary cities of Jamaica. The purpose of the Project is to strengthen the capacity and sustainability of MEFL, so that it can diversify its services and reach a greater number of microenterprises in rural areas and secondary cities. This will be accomplished through the development of new products, the establishment of new branch offices and the targeting of new clients.

II.	Description

- 2.01	To achieve these objectives, the following four components are included: (i) Human resources for rural expansion and scale; (ii) Establishment of two new branch offices; (iii) Design and deployment of three new financial products for microenterprises; and (iv) Establishment of an enhanced information system for portfolio growth and streamlining of credit approval and processing time.

Component I: Human resources for rural expansion and scale

2.02	The objective of this component is to build the human resources needed to strengthen the rural microfinance enterprise industry in Jamaica, specifically through training and technical assistance provided to MEFL. Activities to be financed include: (i) assistance in the recruiting and training procedures of MEFL in the rural areas; (ii) technical assistance for the adaptation and development of human resource management policies and procedures; (iii) development of a consistent and adequate performance monitoring scheme for rural micro credit offices; (iv) training in the areas of agriculture and rural enterprise development for credit officers and branch staff; (v) exchange visits to recognized rural microfinance practitioners in the region; and (vi) training in the areas of credit risk analysis, cash flow projections, and payment capacity for rural micro enterprises and agriculture.

2.03	The results of this component after the three years of implementation will be: (i) at least 8 credit officers and four branch managers trained in the areas of rural microfinance best practice and agricultural lending (1 existing branch and 3 new ones); (ii) a complete package of policies and procedures for human resource management and training for rural branches; and (iii) a performance monitoring scheme implemented in the branch offices for credit officers and branch managers.

Component II: Establishment of two new branch offices

2.04	The objective of this Component is to assist MEFL in the expansion of its operations and the establishment of two new branch offices, in order to reach a total of 2,500 new clients over the next three years (in these new branch locations). The key activities of this component will include: (i) in depth market study and assessment of selected regions for branch offices, with a special emphasis on characterization of the demand and supply of microfinance services; (ii) implementation of three new branch offices which includes the physical adaptation of office space and office supplies; (iii) establishment of security equipment and monitoring to better serve rural clients; and (iv) the purchase of computer equipment and technology for communications with the central office. While MEFL will cover all the costs related to the building and infrastructure for the new branches, MIF funds will be directed to implementing the new branch offices with equipment and technology.

2.05	As a result of this Component, the Project expect to achieve the following: (i) the establishment of two new branch offices that serve at least 2.500 new clients; (ii) improved operational efficiency indicators for the central office due to a broader client base; and (iii) a total portfolio of at least US$1 million for the two new branches.

- Component III: Design and deployment of three new financial products for microenterprises

2.06	The objective of this Component is to design and deploy three new financial products for MEFL, specifically the development and implementation of at least three new products within the branches and main office of MEFL along with its corresponding manuals, policies and procedures, and software and hardware adjustments necessary for implementation.

2.07	As a result of this Component, the following activities will be implemented: (i) a diagnostic analysis of the existing financial services offered by MEFL, with specific recommendations on how these can be enhanced or improved on to better serve the rural areas; (ii) a market analysis of other potential products such as remittances, differentiated savings, agricultural and value chain loans, among others; (iii) development of a marketing strategy to promote the new products and services, specially among the rural enterprises and farmers; and (iv) training to the MEFL leadership and staff on the management and marketing of the new products.

### Component IV: Establishment of an enhanced information system for portfolio growth and streamlining of credit approval and processing time.

2.08	The objective of this component is to carry out following activities: (i) a systems and procedures assessment and diagnostic, to verify and identify key constraints of the existing information and credit approval system; (ii) identification and presentation of alternative technologies and platforms to implement with MEFL in its branch offices, that will enable the organization to streamline and reduce the transaction costs of the application, analysis and approval procedure for rural clients; (iii) the implementation of the selected system within the organization; and (iv) training of the key branch staff and credit officers in the use of the technology .

2.09	As a result of this component, MEFL will have a cost effective information system and platform to manage the loan portfolio and credit system at the branch level, which will in turn allow for: (i) improved processes for identification, analysis and approval of loans; (ii) cost reduction and improved efficiencies at the credit officer level and their productivity; and (iii) enhanced consolidated reporting between branch offices and the central office.

III.	Total Cost of the Project

3.01	The estimated cost of the Project is the equivalent of three hundred thousand dollars ($300,000), in accordance with the following Budget:

##### Budget

(in US$)

| ACTIVITY | MIF/BANK | LOCAL | TOTAL US$ | % |
| --- | --- | --- | --- | --- |
| Component 1: Human Resources for Rural Expansion |  |  |  |  |
|  | 61,600 | - | 61,600 | 21% |
| Component 2: Establishment of Three New Branches | 27,800 | 90,000 | 117,800 | 39% |
| Component 3: New Product Development | 42,000 | 3,000 | 45,000 | 15% |
| Component 4: Establishment of Enhanced Information System | 20,000 | 7,000 | 27,000 | 9% |
| Support for the Execution, Evaluation and Audit | 48,600 |  | 48,600 | 16% |
| Technical Assistant to the Coordinator | 36,000 |  | 36,000 | 12% |
| Mid-term evaluation | 6,000 |  | 3,000 | 1% |
| Auditing | 3,000 |  | 3,000 | 1% |
| Contingencies | 3,600 |  | 3,600 | 1% |
| # TOTAL | 200,000 | 100,000 | 300,000 | 100% |

IV.	Execution

- 4.01	The Bank will sign an agreement with MEFL in order to execute this Project. The General Manager of MEFL will be responsible for coordinating all aspects of the execution of the Project. The General Manager will be responsible for the following tasks: (i) selecting and hiring the consultants; (ii) organizing the training seminars as well as the purchase of any of the equipment or software needed to implement the technical aspects of the Project; (iii) ensuring an adequate flow of information to the Bank as to the monitoring and follow up of the activities and results of the Project; and (iv) hiring an operations assistant using the resources of the Bank.  The operations assistant will provide support to the General Manager specifically as to the monitoring and follow up of the Project activities. The goals and indicators of the Project will be used to monitor the performance of MEFL and the advances made during the Project.

#### Monitoring and Evaluation

5.01	Monitoring. Within 60 days of the completion of each six-month period, the Executing Agency will prepare and submit reports to COF/CJA, which will include at minimum: (i) information on progress toward Project objectives; (ii) a description of technical assistance and training received and its quality and outcomes; (iii) a summary of budget execution and counterpart contributions; (iv) statistical and financial information on performance, indicator situation and trends and on whether the annual targets set for the indicators established have been met; and (v) information on MEFL’s financial situation.

5.02	Specifically, the progress reports will contain information on: (i) the level of completion and implementation of the new products developed with the Project; (ii) the strengthening of the managerial and human resource capacity within the organization and specially in the branch offices; (iii) the learning and implementation of lessons learned from exchange visits to other microfinance organizations in the area; and (iv) the level of growth and financial sustainability of the organization as a whole and for each branch opened with the assistance of Bank funds.

5.03	COF/CJA will have the basic responsibility for the supervision of the operation and ensure that all the components are coordinated and executed as planned, assisting MEFL on key issues regarding training, supervision and quality of service delivery.  In reviewing progress reports, COF/CJA will verify that there does not exist a 20% negative deviation from the indicators proposed in the Project, specially the indicators tracking progress in the sustainability of the organization. In case of a deviation, the Bank could stop further disbursements until the issues or problems which are affecting the accomplishment of the goals, are adequately addressed to the Bank’s satisfaction.

5.04	Evaluations. A mid term evaluation will be conducted after 50% of the Project budget has been disbursed or after 18 months of execution. With funds provided for in the Project budget, the Bank, through COF/CJA, will select and hire an external consultant specializing in financial cooperatives to carry out the evaluation.  The evaluation will look at the progress achieved in meeting Project intended objectives, results and performance targets by MEFL, and will use the logical framework as a reference point.

The Project will specifically assist MEFL in the establishment of three new branch offices, located in the Parish of St. Catherine’s and the Parish of Westmoreland.