# PROJECT PROCUREMENT PLAN

Model A - for specific projects

General information

Country: Barbados

Borrower: Barbados

Executing agency: IDB

Project name: Fiscal Consolidation Program

Project and loan contract numbers: BA-T1021

Brief description of the project’s objectives and components:

The GoB has requested technical assistance for the implementation of the Fiscal Consolidation Program (BA-L1026). The analytical work that will result from the technical assistance is seen as a key input in achieving the Operation’s objectives. The purpose of the Technical Cooperation (TC) is, therefore, to support the Government of Barbados (GoB) in the implementation of the Fiscal Consolidation Program.

Estimated date of project approval by the Board of Executive Directors: July, 2012.

Estimated date of signature of the loan contract: August 2012.

Estimated date of the final disbursement: August 2014.

- Introduction

Procurements for the proposed project will be carried out in accordance with the Policies for the Procurement of Works and Goods Financed by the Inter-American Development Bank (GN-2349-9), of April 2011; and the Policies for the Selection and Contracting of Consultants Financed by the Inter-American Development Bank (GN-2350-9), of April 2011, and with the provisions established in the loan contract and this procurement plan.

- Procurement plan

The procurement plan for Fiscal Consolidation Program (BA-T1021) covering 18 months of project execution has been agreed between the Bank and the GoB. The plan, which is summarized in Appendix 1, indicates the procedure to be used for the procurement of goods, the contracting of works or services, and the method of selecting consultants, for each contract or group of contracts. It also indicates cases requiring prequalification; the estimated cost of each contract or group of contracts; the requirement for prior or post review by the Bank; and estimated dates for the publication of specific procurement notices and completion of the contracts included in this project. The procurement plan will be updated annually or whenever necessary or as required by the Bank.

- Project procurement

The following is a general description of the procurement planned for the proposed project.

Goods procurement: The goods to be procured for this project may include the following: Computer equipment including hardware, software, and licenses.

Project goods requiring international competitive bidding (ICB) will be procured using the standard bidding documents (SBDs) issued by the Bank. Procurement subject to national competitive bidding (NCB) will be undertaken using national bidding documents agreed upon with the Bank [or satisfactory to the Bank in the absence of an agreement].

Procurement of non-consulting services:

- Training and capacity building services in the areas of: (i) tax policy design and modernization of the tax and customs administrations, including the preparation of Tax Expenditure Budgets (TEBs) to enable MOF&EA staff to be sustain the reporting and analysis of tax expenditure and; (ii) public debt sustainability and management, including project management, cost-risk trade off modeling, yield curve calculations and alternative debt strategies, data security and development of managerial systems.

Procurement of consulting services: Consulting services for the project include:

- Tax Expenditure. The consultancy will assist the GoB in developing a tax expenditure budget for Barbados. In order to do that, the consultancy will: assess the current tax structure in Barbados; propose the methodology that will best adjust to the Barbadian reality; review the existing tax incentives and expenditure reports and information; develop a report that lists the main tax expenditures including, inter alia, those associated with the Income Tax (Personal and Corporate), the VAT, and Trade Taxes, which together account for approximately 90% of tax revenue, in order to provide an estimate of forgone revenue, and provide the authorities with information that will it to decide whether or not it should really be foregoing this revenue given its high debt to GDP ratio and worsening fiscal balance. There will also be technical studies to support the establishment of a Central Revenue Authority, in which a number of revenue collection agencies will be consolidated.

- Quality of Expenditure. Building on the outcomes of BA-T1015, which funded the Public Expenditure Review of five sectors of the economy, the consultancy will support the implementation of the main recommendations for improving the efficiency of public expenditure in critical areas of budgetary support. There will be a deliberate focus on expenditure reduction/containment while maintaining quality in the delivery of services.

- Public Debt Sustainability and Management. The consultancy would provide the assistance towards a review, design and implementation of the legal framework required for a sound policy for the management of public debt.  Strengthening and capacity building of the accountancy and timely reporting by public entities for both guaranteed and non-guaranteed public debt as well as contingent liabilities.

The consulting firms to be hired for the project will be selected using the standard request for proposals (RFP) issued by the Bank, or an RFP satisfactory to the Bank in cases where the standard RFP is not applicable. Individual consultants will be selected bearing in mind the provisions established in chapter V of the policy in document GN-2350-7.

Short lists of consultants for consulting services estimated to cost less than US$200,000.00 equivalent per contract may consist entirely of national firms.

Operating expenses: N/A.

Project operating expenses to be financed by the Bank may be contracted using the executing agency’s procedures that have been previously reviewed by the Bank and classified as satisfactory.

Others: N/A.

Advance contracting and retroactive financing: N/A.

- Bank review of procurement decisions

The Bank will procure goods, non-consulting and consulting services in accordance with Appendix 1 of the policies for the procurement of works and goods and the selection of consultants, namely: (i) contracts for non-consulting services with an estimated total cost of US$20,000.00 equivalent or more; (ii) all direct contracting; (iii) contracts for consulting services with firms with an estimated total cost of US$20,000.00 equivalent or more; (iv) contracts with individual consultants with an estimated total cost of US$20,000.00 equivalent or more; and (v) all single-source selection of consulting firms.

The remaining contracts will be subject to ex-post review by the Bank, in accordance with the aforementioned Appendix 1 of the policies.

- Domestic preference

Bids offering goods originating in the borrower’s country will receive a 15% price preference in contracts requiring international competitive bidding, as established in Appendix 2 of the procurement policies.

Appendix 1

# Procurement plan

Country: Barbados

Executing agency: IDB

Project: Fiscal Consolidation Program

Project and loan contract numbers:  BA-T1021

Brief description of the project’s objectives and components:

The GoJ has requested technical assistance for the implementation of the Fiscal Consolidation Program. The analytical work to rise from the technical assistance is seen as a key input in achieving the operation objectives. The purpose of the Technical Cooperation (TC) is to support the GoB in the implementation of the Fiscal Consolidation Program.

Estimated date of project approval by the Board of Executive Directors: July 2012.

Estimated date of signature of the loan contract: August 2012.

Estimated date of the final disbursement: August 2014.

Address of the executing agency office responsible for the procurement plan: IDB.

- Technical and Disbursement Responsibility at the Bank: Gerardo Reyes-Tagle IFD/FMM

Support the Implementation of the Fiscal Consolidation Program

(BA-T1021)

Period included in this Procurement Plan: From: 08/2012 month/year until 08/2014 month/year

| Ref. No. | Description and typeof the procurement contract | Estimated Contract Cost (US$) | Procurement method | Review (ex-ante or ex-post) | Source of financing and percentage |  | Pre-qualifi-cation (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | IDB % | Local/ Other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 1. | Goods: Computing equipment (hardware, software, and licenses). | 40,000 | PC | Ex-ante | 100 | 0 | No | August 2012 |  |  |  |
| 2. | Non-consulting services Training and capacity building services in the areas of: - Tax Policy Design and Modernization of the Tax and Customs Administrations, including the preparation of Tax Expenditure Budgets (TEBs) to enable MOF&EA staff to be sustain the reporting and analysis of tax expenditure; - Public Debt Sustainability and Management, including project management, cost-risk trade off modeling, yield curve calculations and alternative debt strategies, data security and development of managerial systems. | 85,000 | PC | Ex-ante | 100 | 0 | No | August, 2012 |  |  |  |
| 3. | Consulting services 1 - Experts on Tax Policy Design and Modernization of the Tax and Customs Administrations Brief description - The consultancy will assist the GOB in developing a tax expenditure budget for Barbados. In order to do that, the consultancy will: assess the current tax structure in Barbados; propose the methodology that will best adjust to the Barbadian reality; review the existing tax incentives and expenditure reports and information; develop a report that lists the main tax expenditures including, inter alia, those associated with the Income Tax (Personal and Corporate), the VAT, and Trade Taxes, which together account for approximately 90% of tax revenue, in order to provide an estimate of forgone revenue, and provide the authorities with information that will it to decide whether or not it should really be foregoing this revenue given its high debt to GDP ratio and worsening fiscal balance. - This consultancy will involve the preparation of technical studies, both by local and international experts, to assist the GOB in the review of the efficiency of the entire tax system and the design of a comprehensive and meaningful tax policy, including the impact on tax burden, economic efficiency and growth, and fiscal revenue. - Technical studies supporting the establishment of a Central Revenue Authority, in which a number of revenue collection agencies will be consolidated | 90,000 120,000 80,000 | IICC IICC DC | Ex-ante Ex-ante Ex-ante | 100 100 100 | 0 0 0 | No No No | August 2012 August 2012 August 2012 |  |  |  |
| 3. | Consulting services 2 - Experts on Public Debt Sustainability and Management Brief description The consultancy would provide the assistance towards a review, design and implementation of the legal framework required for a sound policy for the management of public debt. Strengthening and capacity building of the accountancy and timely reporting by public entities for both guaranteed and non-guaranteed public debt as well as contingent liabilities. | 80,000 | IICC | Ex-ante | 100 | 0 | No | August 2012 |  |  |  |
| 3. | Consulting services 3 Experts on Quality of Expenditure Brief description Building on the outcomes of BA-T1015, which funded the Public Expenditure Review of five (5) sectors of the economy, the consultancy will be geared at the implementation of the main recommendations for improving the efficiency of public expenditure in critical areas of budgetary support. There will be a deliberate focus on expenditure reduction/containment while maintaining quality in the delivery of services. | 80,000 | IICC | Ex-ante | 100 | 0 | No | August 2012 |  |  |  |

The first 18 months of project execution are counted from the date of publication of the general procurement notice, or the first specific procurement notice published following approval of the loan, whichever is earlier.

All project contracts should be included, even if not financed by the Bank, indicating the source of funding in each case.

The loan contract number should be entered as soon as one has been assigned.

Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through Specialized Agencies; PA: Procurement Agents; IA: Inspection Agents; PLFI: Procurement in Loans to Financial Intermediaries; BOO/BOT/BOOT: Build, Own, Operate/Build, Operate, Transfer/Build, Own, Operate, Transfer; PBP: Performance-Based Procurement; PLGB: Procurement under Loans Guaranteed by the Bank; PCP: Community participation procurement.  Consulting Firms: QCBS: Quality- and Cost-Based Selection QBS: Quality-Based Selection FBS: Selection under a Fixed Budget; LCS: Least-Cost Selection; CQS: Selection based on the Consultants’ Qualifications; SSS: Single-Source Selection.  Individual Consultants: NICQ: National Individual Consultant selection based on Qualifications; IICC: International Individual Consultant selection based on Qualifications

In the case of new Policies it applies only for Goods and Works.  In the case Old Procurement Policies it applies for Goods, Works and Consulting Services.