MIF PROJECT COMPLETION REPORT (MPCR)

PROJECT  NAME:				Support  for the Development of a Regional Credentialing

System for the Hospitality & Tourism Industry

PROJECT  NUMBER: 				TC9702459

LOAN AND TC NUMBER(S):			ATN/MH-5945-RG

BENEFICIARY COUNTRY: 			Regional

## EXECUTING AGENCY:			Caribbean Hotel Association (CHA)

SECTOR: 					Tourism

MODALITY: 					Non-reimbursable Technical Cooperation

DATE APPROVED: 				May 6, 1998

DATE SIGNED:				September 1998

TC AMOUNT: 					US$2,200,000.00

PROJECT IMPLEMENTATION

CLASSIFICATION: (HS, S, U, VU):		S

DEVELOPMENT OBJECTIVES

CLASSIFICATION (HP, P, LP, I): 		P

PROJECT OBJECTIVES AND COMPONENTS

- Objectives

1.	The Overall objective of the Programme was to increase the International competitiveness of the hospitality and tourism workforce of the Caribbean Region by developing a regional credentialing system.

2.	The Specific objectives were:

(a)	Bridge the gap that exists between the demand for specific skill sets and the supply of high quality education and training in hospitality and tourism occupations;

- 2 -

(b)	Promote consistent quality of service delivery by assisting in the design/adaptability of competency-based occupational standards;

(c)	Facilitate professional recognition of work experience, work-based learning and academic achievement which leads to increased opportunities for career growth and mobility;

(d)	Upgrade the quality of human resources available to the industry by increasing awareness of job and career opportunities in the sector through the promotion and marketing of career paths and career mobility throughout the region; and

(e)	Increase the number of “trained trainers” available to the sector.

B. 	Components

The components used to achieve the objectives were:

a.	Component 1 - Certification System.

b.	Component 2 - Credentialing System.

c.	Component 3 - Train the Trainer.

d.	Career Awareness

e.	Culinary Demonstration

f.	Organization of Eastern Caribbean States  (OECS) Demonstration Project

C.	Assumptions

The assumptions related to the implementation of the components are:

1.	Hotel and Tourism participators voluntarily participate in implementation of the system.

2.	There is a market demand for credentialing framework on the part of employers, workers, educators and trainers.

3.	Educators and Trainers accept new training approaches.

4.	Ability of project to change perception of job and career opportunities in the hotel and tourism industry.

The assumptions related to the development objectives are:

1.	Continued growth in global tourism industry.

2.	Favorable economic conditions for tourism industry in the Caribbean.

3.	Development of standards and credentialing are key ingredients in regional tourism competitiveness.

- 3 -

MIF PROJECT COMPLETION MEMORANDUM

1.	Historical Perspective

Significant changes to the project objectives or components that took place after project approval.

There were no changes in the original objectives and components but at the request of the CHA Project Coordinator, there were several reductions in performance target indicators  as follows:

1.	For certification from “Completion and acceptance of standards for 40 occupations; 50% of CHA member hotels in affected countries implement standards” percentage reduced to 30%.

2.	For credentialing from “10,000 (front line to supervisory) and diploma students trained in programs for targeted occupations” number reduced to 2,000. At a later date the CHA asked for a reduction of this figure to 86.  This was not accepted by the Country Office and eventually 590 individuals were registered.

3.	For train the trainer from 750 ‘trained trainers’ reduced to 600.

4.	The Simplified Logical Framework and Indicators were revised in June 2001 and reflected in the MPPMR in July 2001 at the request of the CHA in both cases.  New reduced targets were proposed by CHA and agreed by the Bank in the Logical Framework.

For example, originally the Performance Indicator for the Credentialing System asked for the enrollment of 5,000 workers and students in the new credentialing system and 75 hotels and tourism school/programs in the industry validation process. There were not 75 hotel/tourism schools’ programs in the Caribbean Tourism Credentialing Programme (CTCP) countries. Information from the Association of Caribbean Tertiary Institutions (ACTI) indicated that there are approximately 10. Details of the revised indicators are recorded in the most recent MPPMR.

5.	Other important changes included the last date of disbursement from March 14, 2002 to March 14, 2004 and then to July 31, 2004. The first extension was due to the delay in the start of the OECS Program referred to on page 4, item 2(a).  The other was to permit an increase in the number of individuals to be certified, to allow time for processing disbursements and to permit the preparation of the Accounting Statement for Financial Auditing.

- 4 -

6.	According to the Mid Term Assessment by the ARA Consulting Group of November 1999, the targets for each component in terms of job registration and certification were, in their view unrealistic. For Jamaica and the Bahamas they suggested a more reliable target would be between one third and one fifth of what had been proposed for the MIF projects there. This project was designed some time before May 1998 and suffered from the same unrealistic targets.

##### 2.	Execution Of The Project

(a)	The Conditions prior to First Disbursements at Third (ii) required “the execution of an agreement between the Executing Agency and the Caribbean Development Bank (CDB)….satisfactory to the Bank (IDB),  for the implementation of Subprogram B, component II of the Program …”. The CDB did not accept this commitment and eventually agreed to a Financial Agency Agreement between the IDB and the CDB.  This was dated July 20, 2000 and signed before July 24, 2000. This was more than two years after the approval of the project and made it necessary to extend the project by two years.

(b)	Of the six components four were 100% complete, and CHA estimates one at 99% and another at 86% complete. The overall progress of the project is estimated at 98% complete.

(c)	The main consultant was generally competent but failed to satisfy what COF/CBA thought were the requirements of his contract with respect to the registration of credentialing candidates.

(d)	In our opinion, the Executing Agency did a creditable job, although weakened by the absence of the Administrative Officer/Systems Analyst and other staff in the later stages of the project.

##### 3.	Lessons Learned

(a)	Avoid including as a condition prior to First Disbursement the requirement of an Agreement with a third party (i.e. the CDB), without first ensuring that the party is in full agreement with the condition proposed.

(b)	Ensure that Indicators are appropriate and realistic its make-up, e.g. For Credentialing the Indicator is just for one aspect i.e. the number of individuals credentialed, without reference to several other aspects equal to or more important, in the component.

(c)	The Beneficiary must maintain adequate staff to execute the project.  The Administrative Officer/Systems Officer ceased to work in the Executing Agency after the end of 2002.  This increased the workload on the Coordinating officer, who insisted that she needed no assistance. The resulting lack of staff impacted negatively on project implementation and caused delays in meeting some deadlines.

- 5 -

(d)	Culinary Demonstration Component was 100% successful.  Success was due mainly to the involvement of the persons in charge of this Component who were attached to the CHA, were involved in the programme and were interested in making it a success.

(e)	One oversight of the certification system is that it did not provide training in specific skill areas where there were gaps in education/training.  The onus lies on the individual employee and/or a progressive-thinking human resource development manager to provide the employee with the training necessary to acquire the skills required to fill the identified gap.  Ideally, this should have been the second and more important phase of the Train the Trainer program.

(f)	The CTCP was developed and executed after several national projects with outputs that duplicated those of the CTCP were already being implemented.  Though the national projects and the CTCP were all MIF-funded there were no real links between them.  This was a clear case of the cart preceding the horse.  All the related tourism MIF projects executed in the Caribbean would have been more effective if an entirely different approach had been taken.  A single regional project with objectives and outputs that benefit all participating countries should have been established.

(g)	The project was designed so that development of outputs and implementation would take place simultaneously.  The original period of execution (3 years) could not have been properly considered as it takes approximately 10 years to develop occupational standards and certification systems on this scale and to change the mindset of the people who are to benefit from such profound changes.  The project design did not take account of the fact that introduction of a regional tourism certification and credentialing system, primarily based on the recognition of work experience, would be new to the Caribbean, needed extensive ‘buy-in’ from industry and government alike and, because of its nature and regional scope, required a minimum of 5 years to have it properly developed and at least an additional 3-5 years post development to implement it, make revisions, and build in its sustainability.

(h)	Due to the general requirement of projects to focus exclusively on the named beneficiaries, the project design did not take account of the fact that the executing agency’s constituents (a) are three times as great as the specified beneficiaries, (b) also speak French, Dutch, and Spanish, (c) would eventually have to participate in the system after project completion if the system is to truly become regional in scope.

- Sole sourcing was a major issue from the outset and threatened to derail the entire project.  The executing agency maintained that the sole sourcing arrangements had been approved in Headquarters, during the design phase.  However, it was not mentioned in the Agreement.  As a result, the IDB office   in   Barbados   initially

- 6 -

rejected the sole sourcing arrangements used to acquire some services.  Exceptions to IDB procurement policies should be included in Agreements.

(j)	The project coordinator was hired several months after the project agreement was signed.   The project coordinator should be hired to be in place by the start of project implementation.

Appendix I

Page 1 of  15

Executing Agency’s Memorandum

ATN/MH–5945-RG

Support  for the Development of a Regional Credentialing

System for the Hospitality & Tourism Industry

Appendix I

Page 2 of 15

# PROJECT COMPLETION REPORT

## Executing Agency Memorandum

Project Name:

CARIBBEAN TOURISM CREDENTIALING PROGRAM (CTCP)

TC Number/Title:

TC9702459

Support for the Development of a Regional Credentialing System

for the Hospitality and Tourism Industry

IDB Project Number:

ATN/MH-5945-RG

Executing Agency:

CARIBBEAN HOTEL ASSOCIATION (CHA)

Memorandum Prepared and Submitted by:

Angela R Herbert, CTCP Project Coordinator

(with input from A Titcombe, CHA Director of Product Development)

Submitted to the Inter-American Development Bank

Barbados Field Office on:

20 August 2004

Appendix I

Page 3 of 15

PROJECT COMPLETION REPORT

The following represent responses to the areas of the Executing Agency Memorandum that were deemed to be relevant to the execution of the CTCP.

3.1.1.	OUTPUTS ATTAINED

| ### PLANNED |  | ACHIEVED |
| --- | --- | --- |
| Original | Revised |  |
| 1 Certification System: Completion and acceptance of standards for 40 occupations and 50% of CHA member hotels and training of 10,000 tourism workers and students. | 1 Certification System: Completion and acceptance of standards for 40 occupations and 30% of CHA member hotels in affected countries implement standards. | Standards completed and accepted -100% achieved 30% of CHA members implement standards - 91% achieved |
| 2 Credentialing System: Enrollment of 5,000 workers and students in new credentialing system and 75 hotels and tourism school/programs in the industry validation process. | 2 Credentialing System: 2,000 frontline/supervisory and diploma students trained in programs for targeted occupations. | 30% achieved |
| 3 Train the Trainer: Certification of 750 trained trainers | 3 Train the Trainer: Certification of 600 trained trainers | 100% achieved |
| 4 Career Awareness: Increase by 25% in number seeking employment in tourism sector | 4 Career Awareness: 5,000 attendees/registrants in career awareness programs/events. | 100% achieved |
| 5 Culinary Demonstration: Establishment of Caribbean culinary standards; creation of systems, policies and procedures for food and beverage apprenticeship and certification programs. | 5 Culinary Demonstration: No revisions made. | 100% achieved |
| 6 OECS Demonstration Project: No quantifiable indicators. | 6 OECS Demonstration Project: Proliferation of the project outputs in the OECS territories. No quantifiable indicators. | 100% achieved |

Appendix I

###### Page 4 of 15

3.1.2.	PROJECT OUTCOMES AND IMPACTS

#### Achievement of Project Objectives

| ### Overall Objective of the CTCP | Results | Reason for Non-Achievement (if applicable) and Recommendations for the Future |
| --- | --- | --- |
| To increase the international competitiveness of the hospitality and tourism workforce in the Caribbean by developing a regional credentialing system | The regional system has been developed and growth in both tourism arrivals and expenditure in the region have been recorded since the system was developed, however, it is practically impossible to demonstrate which inputs to the tourism sector, region-wide, this growth can be attributed to. No measurement systems (objective or otherwise) were developed, proposed, or specified for gauging whether the Caribbean tourism workforce has become more internationally competitive. But there is documented proof that, in recent years, several non-Caribbean cruise lines as well as hotels in the USA and Canada, in particular, have been recruiting Caribbean tourism employees in increasing numbers. The project coordinator believes that while the CTCP could take credit for a small percentage of this activity, there are several other factors that could be more directly responsible, including but not limited to: (i) deliberate recruitment drives introduced/supported by several Caribbean governments (that are not dissimilar from the farm labour programs that supply agricultural workers to North America), (ii) initiatives from North American hoteliers to fill positions for which North American labour may be in limited supply, (iii) efforts by Caribbean tourism personnel to find employment abroad in order to garner wider/different experiences, salaries paid in hard currency, etc. Irrespective of the causative factors, it is also documented that Caribbean tourism personnel who work outside the region demonstrate a high level of competency and that the need for additional training is often unnecessary or minimal. |  |

Appendix I

Page 5 of 15

| ### Specific Objectives of the CTCP | Results | Reason for Non-Achievement (if applicable) and Recommendations for the Future |
| --- | --- | --- |
| a) To bridge the gap that exists between the demand for specific skill sets and the supply of high quality education and training in hospitality and tourism occupations | The capacity to bridge the mentioned gap between skill demands and education/training supply is partially built into the certification system developed by the CTCP. One flaw of the system is that it was not designed to train personnel in specific skill areas where the gaps in education/training are revealed. In essence, the CTCP certification system points out where the gaps are and how to fill them, and takes the candidate no further. This means that once a gap is identified, the onus lies on the individual employee and/or a progressive-thinking human resource development manager to provide the employee with the training necessary to acquire the skills required to fill the identified gap. The project coordinator believes that this design feature may have been deliberate as the project would have needed a minimum of an additional 2-3 years, and possibly twice the amount of funding provided overall to address this specific area. Ideally, this should have been the second and more important phase of the Train the Trainer program, but it was not included in that component. As this feature was not built into the project, it can only be highlighted as a design flaw and not an area of non-achievement. This objective, therefore, based on the structure of the CTCP, must be considered 100% achieved despite the design flaw highlighted. | The project coordinator recommends that the executing agency factors this matter into the sustainability program it is currently developing and that (if it is unable to fund this work itself) it submits a project proposal to solicit funding from agencies that might be interested in funding work of this nature. |

Appendix I

Page 6 of 15

| ### Specific Objectives of the CTCP | Results | Reason for Non-Achievement (if applicable) and Recommendations for the Future |
| --- | --- | --- |
| b) To promote consistent quality of service delivery by assisting in the design/adaptation of competency-based, occupational standards | This is a primary feature of the certification system and has therefore been 100% achieved. |  |
| c) To facilitate professional recognition of work experience, work-based learning and academic achievement which leads to increased opportunities for career growth and mobility | This is a primary feature of both the certification and credentialing systems and has therefore been 100% achieved. |  |
| d) To upgrade the quality of human resources available to the industry by increasing job and career opportunities in the sector through the promotion and marketing of career paths and career mobility throughout the region | This is a primary feature of the certification and credentialing systems and the career awareness programs; it has therefore been 100% achieved. |  |
| e) To increase the number of trained trainers available to the sector | This is the sole feature of the train the trainer component and has therefore been 100% achieved. |  |

3.2.1.3/3.2.1.3		LESSONS LEARNED FROM EXECUTION OF THE PROJECT

| ### Issues | Recommendations for Improvement of Future Projects |
| --- | --- |
| 1) The CTCP was developed and executed after several national projects with outputs that duplicated those of the CTCP were already being implemented. Though the national projects and the CTCP were all MIF-funded, and though they were similar in scope, objective, and outputs, each was autonomous and there were no real links between them. Project managers of the national projects demonstrated great territoriality regarding their respective projects/outputs and were extremely reluctant to share information with or become involved in the CTCP. In the end, the CTCP standards referenced those developed/adopted by the national projects, but no real cohesion was ever achieved among the national projects themselves or between them and the CTCP. The project coordinator considers this to have been a significant design flaw. | This was a clear case of the cart preceding the horse. The project coordinator believes that all the related tourism MIF projects executed in the Caribbean would have been more effective if an entirely different approach had been taken. In a region as small as the Caribbean, a single regional project with objectives and outputs that benefit all participating countries should have been established rather than setting up a multiplicity of similar (but independent) projects that encouraged territoriality and duplication of effort/resources. |

Appendix I

Page 7 of 15

| ### Issues | Recommendations for Improvement of Future Projects |
| --- | --- |
| 2) The project was designed so that development of outputs and implementation would take place simultaneously. Moreover, the original period of execution (3 years) could not have been properly considered as it takes approximately 10 years to develop occupational standards and certification systems on this scale and to change the mindset of the people who are to benefit from such profound changes. This is especially so in cases where outputs are to be applied across an entire geographic region comprising several independent countries and including countries in which the same funding source established similar but separate, distinct, and autonomous projects with similar objectives and outputs and no real links among them to engender cohesion, as indicated in (1) above. The project design did not take account of the fact that introduction of a regional tourism certification and credentialing system, primarily based on the recognition of work experience, would be new to the Caribbean, needed extensive ‘buy-in’ from industry and government alike and, because of its nature and regional scope, required a minimum of 5 years to have it properly developed and at least an additional 3-5 years post development to implement it, make revisions, and build in its sustainability. It is noteworthy that the Canadian system from which the CTCP draws extensively took millions of dollars and approximately 10 years to develop and implement and that the participation record in Canada is not significantly different from that of the CTCP situation to date. | Projects need to be structured with distinct (possibly modular) phases that link to form a cohesive process –: (1) There should be a design phase during which the executing agency is fully apprised of the procedures it is expected to follow and the beneficiaries are properly consulted so that they make significant input in matters that are to affect them rather than inherit systems/processes/outputs conceptualised with a North American flavour for implementation in a Caribbean context; it is not always easy to make the two fit if the beneficiaries have not been properly consulted (in this case, the beneficiaries are not deemed to be the executing agency only but also the tourism/hospitality personnel at the national level). It is important also at this time to secure the ‘buy-in’ of agencies (government and non-government alike) whose support is necessary to ensure achievement of objectives and sustainability of the outputs. During the design phase, the project manager/coordinator should also be hired and should undergo a proper orientation program which would familiarize him/her with the nature of the project, its objectives, systems/procedures, and so on. As the project manager has expertise in the field for which the project was developed, that person could envision, anticipate, or highlight areas that need special focus that the ‘technical’ personnel might otherwise overlook. (2) During a development phase the project manager and other technical personnel would develop the terms of reference and consultants would be hired to produce outputs that need to be in place before implementation commences. (3) In the implementation phase outputs developed during the second phase would be executed, monitored, and evaluated, and structures put in place to ensure sustainability and/or cost recovery would be closely monitored. Additionally, any revisions necessary to ensure the project’s viability and effectiveness would be made; it is important that the beneficiaries are consulted again at this stage in case any sensible and feasible amendments they propose need to be taken on board before the project proceeds any further. It would also be important during this phase to retain the services of relevant consultants to ensure that all systems developed by them are working and can be amended as necessary (a clause to this effect would be included in the consultants’ contracts from the outset). (4) During the final phase, evaluation and reporting, the entire project would be examined and assessed by the project execution unit and an external assessor to ascertain whether the objectives (general and specific) were achieved and to document any lessons learned. The project coordinator believes that if the above approach is not seriously considered, the region’s best interests will not be kept uppermost, the duplication of projects which currently exists will be exacerbated, resources will not be put to their best use, and the region will acquire outputs that have a distinctive non-regional stamp which might be difficult, if not impossible to remove or alter/adapt at a later stage. It would be sad if this continues to happen as projects such as the CTCP are of immense value and, if properly structured and implemented, have the potential to bring about great improvements in several economies and in the personal development of thousands of persons. Note: As a case in point, an alternative plan for a more effective design for and implementation of the credentialing and certification systems is illustrated on page 6.1. |

Appendix I

Page 8 of 15

| ### Issues | Recommendations for Improvement of Future Projects |
| --- | --- |
| 3) Due to the general requirement of projects to focus exclusively on the named beneficiaries, the project design did not take account of the fact that the executing agency’s constituents (a) are three times as great as the specified beneficiaries, (b) also speak French, Dutch, and Spanish, (c) would eventually have to participate in the system after project completion if the system is to truly become regional in scope. | This means that even though no MIF funds would have been used on these non-beneficiary countries during project implementation – for that is not what was being advocated in the issue raised – the design should have taken account of the fact that they would eventually become involved and should either have made recommendations for this in the long term or should have permitted participation of all the executing agency’s constituents with the proviso that the executing agency pay all costs related to non-beneficiary territories. Factors for consideration would have included foreign language translation of technical manuals as well as future interface of systems developed for the English-speaking Caribbean with French/Dutch/Spanish systems of education/training/certification. The project coordinator acknowledges that this feature of project design is, unfortunately, not unique to the CTCP but is, in fact, replicated across most projects involving funding agencies who want to ensure that their resources are not used in non-member/non-beneficiary territories. However, such policies ignore the fact that executing agencies often serve wider constituencies than those designated by the donor. More often than not, these restrictive approaches, though understandable, have great potential to create disharmony among the ‘disadvantaged’ groups and can lead to a withdrawal or reduction of participation in other programs being spearheaded by the executing agency. More important, such prohibitive approaches result in greater expense being incurred eventually as it is more costly to involve participation after the fact. |

Appendix I

Page 9 of 15

| ### Issues | Recommendations for Improvement of Future Projects |
| --- | --- |
| 4) Sole-sourcing was a major issue from the outset and threatened to derail the entire project. The Bank’s view was that wherever the executing agency sole-sourced one of its agencies/subsidiaries (in this case, the Caribbean Culinary Federation for the culinary component, and the Caribbean Hospitality Training Institute for the Train the Trainer component), the executing agency was in fact channelling the project funds to itself and not to a third party, as was intended, and that this, in fact, constituted a conflict of interest. The executing agency, on the other hand, maintained that the sole sourcing arrangements had been approved in Washington, DC, during the design phase. However, the IDB office in Barbados felt that the procurements affected by these arrangements should have been put out to international public bidding. No minutes were ever produced - either by the executing agency or IDB/MIF - of the (initial CTCP design) meetings at which this matter was discussed to verify what had actually been approved. As a result, the IDB office in Barbados initially rejected the sole sourcing arrangements (used to acquire some services) but subsequently approved them. | For the future, similar situations, particularly when they are highly contentious, could be prevented if minutes or other documentation recording such agreements could be incorporated into the formal agreement between the funding agency and the executing agency. Major approvals or prohibitions as well as all special conditions must always be reduced to writing. |

Appendix I

Page 10 of 15

| ### Issues | Recommendations for Improvement of Future Projects |
| --- | --- |
| 5) Credentialing versus Certification – For the entire duration of the project, there were disagreements between the Bank and the executing agency about what was the focus of the CTCP. The Bank argued that the credentialing component was the nucleus of the project while the executing agency maintained that certification held that position. The project coordinator, who supports the view that certification was always intended to be the focus of the CTCP, believes that the title of the project itself created the confusion that arose and this was worsened by the fact that the credentialing component was erroneously designed to be implemented simultaneously with the certification component. Though both are intended to recognise skills, knowledge, competencies, achievements, etc, they are not synonymous and should have been phased in at entirely different times for the greatest level of effectiveness (see the illustration on page 6.1). The project coordinator feels strongly that the shortcomings of the implementation of the credentialing component were built into the design of the project itself, not only in how and when it was to be implemented, but also the fact that no funds were provided in the project budget to credential anyone – a review of the project budget would confirm this. This means that the log frame and the budget were incompatible in this regard. | The project coordinator feels that though the matter of project titles may seem insignificant on the surface, those responsible for this task should give it the attention it deserves in order that (a) valuable time is not wasted (several months in case of the CTCP) trying to decide what the project is really about, (b) judgments, evaluations, and decisions made about project elements and their success are reasoned and justified, (c) project components can be implemented in their logical order so that project objectives are realised in the given time frame. Moreover, the project coordinator recommends that where disputes about project elements arise, those supervising the process from the lending/donor agency need to exercise some flexibility to allow for needed amendments to be made to the project overall or to particular aspects of its structure. The project coordinator does not support the Bank’s claims that the funds spent on credentialing were wasted because the credentialing component did not achieve its objectives. Instead, the project coordinator acknowledges that the necessary, separate and distinct, sequential implementation phases for the certification and credentialing systems (as proposed in the alternative design on page 6.1) were not incorporated into the project design and that this accounts for the bulk of the difficulty the Association of Caribbean Tertiary Institutions (ACTI), the credentialing sub-contractor, encountered in getting candidates to enrol in the system. The credentialing system needed a pool of certified persons from which to draw – in every certification system with which the project coordinator is familiar, a candidate must first be certified before that person can carry the related credentials behind his/her name; the CTCP certification/credentialing system is the first one encountered by the project coordinator in which the opposite was proposed. The fact that the CTCP system (with its structural flaws) did not work, is compelling. In summary, therefore, the certification of candidates should have taken place first, then those same persons should have participated (after certification) in the credentialing pilot, in other words, a candidate would first be certified in order to become eligible for credentialing based on certification and other achievements. The credentialing process should not have preceded the certification process, nor should they have been executed simultaneously. Despite this, the project coordinator is convinced that should the credentialing/certification sequences be switched, the credentialing system would be workable; it is already a worthwhile system that could be replicated in other economic sectors across the region. The project coordinator further recommends that the executing agency should temporarily shelve implementation of the credentialing system until a predetermined number of persons (possibly 3,000 or thereabouts) have successfully completed the certification process, thereby providing an automatic pool from which to draw credentialing candidates; those already credentialed would be assured that their ‘credentials’ are still worthwhile but that the program is being revamped for the time being. As the sub-contract for the credentialing component was a condition prior to first disbursement, and as the log frame provided for the actual credentialing of candidates, the project coordinator believes that it was a design oversight that no funds were budgeted for the credentialing of candidates. |

Appendix I

Page 11 of 15

| ### Issues | Recommendations for Improvement of Future Projects |
| --- | --- |
| 6) The executing agency (CHA) was inexperienced in implementing projects like the CTCP and this created some problems initially, including several strained moments for the project coordinator who possessed previous international project experience but who was unable, on several occasions, to persuade CHA to trust her judgment, particularly as it related to providing for the sustainability of outputs from year one of the project’s implementation. CHA possesses a typical private sector style of conducting business where decisions are made quickly and procedures are flexible to accommodate this. This style ran counter to the Bank’s where procedures are fairly rigid and are expected to be followed even when what were perceived by CHA as unnecessary delays were encountered. The sole-sourcing issue outlined above is a case in point. Before the situation deteriorated, it appeared that most of the Bank’s concern was about following established procurement procedure and having a transparent system. CHA’s concern focused on getting the job done efficiently but with the minimum of delay. And CHA perceived the Bank’s procedural requirements to be counterproductive. The project coordinator at all times tried to help both parties achieve their respective goals and paid particular attention to the provisions of the signed Agreement. The project coordinator was hired several months after the project agreement was signed, after the credentialing component had already been subcontracted, and the sole-sourcing matter was already a major issue. She was therefore unable to contribute to these matters as it was made clear by the Bank that no changes would be facilitated. | The project coordinator believes that if the project coordinator had been recruited earlier, many misunderstandings would have been resolved early, several areas of the agreement and the project design would have been structured differently, and the project would have had a smoother run. This is therefore recommended for future projects, particularly in areas where the project coordinator/manager has expertise in the subject area of the project and is not functioning only as an administrator. Fortunately, from the midpoint of the project onward, the executing agency demonstrated maturity in learning from the CTCP experience. The coincidence of this change with the departure of the IDB official who initially supervised the CTCP in Barbados is noteworthy. However, it is the project coordinator’s view that though this particular IDB official went to great lengths to frustrate the efforts of the project, and actually threatened on several occasions to “bring the project to its knees”, the executing agency contributed to some of the frustrations and delays experienced. The executing agency did not initially possess any relevant, formalised, or systematic procurement procedures or systems and initially resisted the rigidity of the Bank’s procedures. In the end, the executing agency accepted that using the Bank’s procedures resulted in efficiencies and efficacies derived from using structured systems. The executing agency, having been exposed to the Bank’s procedures, is now in a better position to improve its own institutional systems as well as to benefit from funding from similar sources in the future. In fact, the executing agency was recently able to attract funding for some of its institutional strengthening and other activities from the European Union. CHA still has several areas that require improvement, but the project coordinator feels that the executing agency is well on its way to improving many of its activities as a result of its involvement in the CTCP. The recommendation in this regard is that all projects, during the design phase, should assess the proposed executing agency to determine areas where it needs institutional strengthening or other support in order to make it more efficient and effective. This initial activity should also include an orientation session to familiarise the executing agency with the procedures and processes of the funding agency that would impact implementation. This was noticeably lacking from the CTCP where the Bank’s role, instead of being facilitative and supportive, revolved primarily around giving instructions and directives and being punitive when any infractions (imagined or real) were incurred by CHA. In relation to the sustainability issue, the executing agency is currently putting in place a sustainability program to ensure that the project outputs reach many tourism/hospitality personnel for many years to come. This sustainability program includes developing relationships with several implementation partners (including hospitality schools, hotel associations, and others) who will enter formalised arrangements through Memoranda of Understanding specifying what they will implement at the national level and the terms of the understanding. While the project coordinator supports this effort, she feels that the sustainability plan was developed very late and should have been put in place from year one of the project. A sustainability plan as part of the project design should be required for all future projects. |

Appendix I

Page 12 of 15

| ### FINAL RECOMMENDATION BY PROJECT COORDINATOR |  |
| --- | --- |
| The project coordinator firmly believes that the outputs produced by the CTCP are both worthwhile and needed, particularly at this time when the governments of the English-speaking Caribbean are promoting a single market and economy for the region. The certification component, in particular, would be most useful in this regard in promoting mobility of labour as the project has produced a certificate of a high standard that is recognised region-wide. However, in order to build on the momentum started by the CTCP, additional occupational standards and certification would need to be developed for all occupations not captured in the 40 developed by the project. Additionally, as mentioned in the certification issues above, funding would be required to further develop the training element so that individuals who need to fill skills/knowledge gaps in order to become certified can do so in a structured program. The project coordinator therefore strongly recommends that the executing agency seeks additional funding from IDB/MIF or some other source to have the additional work done. The work accomplished by the CTCP is of great significance to the Caribbean region and should be expanded and strengthened. |  |
| Additional Comments by the Executing Agency’s Project Supervisor (A Titcombe) | # Recommendations for Improvement of Future Projects |
| ### Specific Objectives of the CTCP | Ref a) The Project Coordinator notes that the credentialing/certification system was not designed to train personnel in specific skill areas where the gaps in education/training are revealed. Whilst the standards do provide some guidelines (or ‘how to’ statements), she is correct. The system would benefit from the development of curricula/training programs and their subsequent delivery. CHA is already trying to address this through its various national partners, some of which are developing and offering specific training. CHA met recently with MIF in Washington and will submit a proposal to address this. In addition, certain outputs planned through the funding from the European Development Fund will also focus on developing CARIBCERT linked training programs and the training of trainers. |
| ### Issues under Lesson learned | - The Project Supervisor would agree that the delays in start up which put the regional project behind the national projects was a major problem. The national partners initially saw CTCP as an intrusion. The lesson therefore is that the design of national and regional projects should have been better coordinated or even have been part of the same project proposal. - CHA was pleased that the bank agreed to an extension to the project. As stated in the body of the report, the original timeline was ambitious - given the norm for such programs. Even now there is still much work required to institutionalize the outputs. - The Project Coordinator’s comments relating to the executing agency’s constituency are pertinent. Project design should wherever possible acknowledge the realities that exist. The MIF should also be aware that there is great interest particularly with the CARIBCERT program outside the beneficiary countries. Following its meeting with the MIF, CHA will assist the Dominican Republic in putting forward a proposal for translation and implementation of a Spanish language version of the standards. - No further comment. |

Appendix I

Page 13 of 15

|  | - CHA would agree with the recommendation that more effort initially be focused on the development of CARIBCERT which would feed into the credentialing system. As noted in earlier reports, the market is greatly confused by the differences between credentialing and certification and promoting both programs simultaneously is unlikely to assist either. The bank should note that in any case the certification data is automatically linked to the credentialing database, thus reducing admin workload in implementing credentialing. However, it should be noted that there are some significant challenges in establishing a fully integrated regional credentialing system. Its success will depend on strong national leadership and support - it is the executing agency’s view through its experiences with ACTI and the national associations that there is limited capacity to allow this to happen in a sustainable manner at this time. It should also be noted that the Canadian model on which it was based has gone out of business. CHA will carefully consider its options in taking the credentialing element forward, once a significant number of persons are certified through CARIBCERT. - The Project Coordinator is correct in pointing out CHA’s relative lack of experience in project execution- in fact this was the first project of its kind that CHA had undertaken. Whilst the Project Supervisor has extensive international experience with European funded projects (in the Caribbean and South Asia), CHA as an organization has had difficulty in adapting to and accommodating the world of project management. This was exacerbated by the project management being undertaken away from its home base. However, that being said CHA and its Project Supervisor has learnt much from the experience which has now allowed it to become involved in wider project activity both directly and through its subsidiary CAST (Caribbean Alliance for Sustainable Tourism). It also has a strengthened capacity through its Project Management Unit in Barbados. CHA makes no apology for ‘possessing a typical private sector style of conducting business’ and would expect the IDB also to recognize that in administering projects on behalf of the MIF through the private sector, that they also have to recognize this. However, lessons have been learnt, and CHA believes that it is well prepared to undertake similar initiatives and programs. Most of the challenges relate to logistical and cultural differences. Although this may be a cliché, ‘if it was going to be easy, there would be no need for a technical assistance project’. It is the nature of all projects of this type that there needs to be close working relationship and better understanding on each side. Not every problem is as black and white as the Project Coordinator suggests and this project had its fair share of design and interpretation problems to contend with. CHA has learnt that it needs to be selective about the projects it entertains to ensure that they meet the needs of its core constituents and the industry as a whole, and not view technical assistance as an easy way to attract funding - which it is not. CHA recognizes the commitment and hard work undertaken on its behalf (and the IDB) by the Project Coordinator in achieving the necessary outputs in almost all cases. As the person charged with the responsibility for coordinating project activity through the bank, she is much better placed to produce the final report. CHA respects her views and comments as included in this report and has made no attempt to influence the content of the report. - I do not wish to dwell on the report’s various references to relationship issues and opinions expressed about them, except to say this. The Project Coordinator fiercely represented the interests of the project and CHA at all times, for which CHA is grateful. However, she was frustrated at times by the lack of clarity and direction provided, both by CHA and the bank. This direct approach coupled with the more diplomatic style of the Supervisor did create certain frictions. Both parties however, were able to manage their differences due to their joint commitment to achieving a successful conclusion to CTCP in the interests of the Caribbean tourism industry and its current and potential employees. |
| --- | --- |
|  | - One should not underestimate the impact of 9/11 on the tourism sector during a critical period of project implementation. Both the executing agency and its constituents faced severe challenges both economic and organizational in nature. In spite of this, CHA and the project team and CHA’s constituents continued to support the project and met their obligations in all respects. - MIF/IDB should revisit the Mid-Term Assessment entitled “MIF Project Cluster on Skill-Based Standards and Certification for the Tourism Sector’ prepared by ARA Consulting Group in November 1999. Many of the recommendations made then are still relevant and strongly support the recommendations made in this report. |

Appendix I

Page 14 of 15

| # Appreciation | Although stated earlier, CHA would like to thank the MIF and the IDB for their support for this project. It would also like to put on record its thanks to its members and other stakeholders who provided the substantial input both in cash and in-kind. For CHA this project was certainly not a waste of time (a view shared earlier in the report). Unlike many other projects these outputs have a real chance of sustainability due to the commitment of the executing agency to take the outputs forward in the interest of the various stakeholders. CHA hopes that MIF will seriously consider providing further support either through CHA or its various national partners. |
| --- | --- |

Appendix II

Page 1 of 4

| Final PPMR* Performance Classification | MPPMR Classifications During Project Execution |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Aug 2000 | July 2001 | June 2002 | Dec 2002 | June 2003 | Dec 2003 | June 2004 | Oct 2004* |
| Development Objectives (DO) [HP, P, LP, I] | LP | P | P | P | P | P | P | P |
| Implementation Progress (IP) [HS, S, U, VU] | U | S | S | S | S | S | S | S |
| Probability of Assumptions Holding True [H, L] | L | L | H | H | H | H | H | H |

###### Appendix II

Page 2 of 4

###### BASIC PROJECT DATA

|  | Original | Actual |
| --- | --- | --- |
| Project Dates (month/year) |  |  |
| Date of inclusion in pipeline |  | March 1997 |
| Date of Loan Request |  |  |
| Project Profile | May 1997 |  |
| Date of Analysis Mission |  |  |
| MIF Eligibility |  |  |
| Date of Donor Committee Approval | November 1997 | May 6, 1998 |
| CRG Meeting |  |  |
| Date of Contract Effectiveness |  | September 14, 1998 |
| Date of Compliance with Prior Conditions |  | November 16, 1998 |
| Disbursement calendar: |  |  |
| -- First disbursement | March 1998 | December 16, 1998 |
| -- Last disbursement | March 14, 2002 | July 28, 2004 |
| Date of Physical Initiation of Works | / | / |
| Date of Loan Commitment | ___/___ | ___/___ |
| Date(s) of Cancellation(s) |  |  |

| Evaluation Mission: |  |  |
| --- | --- | --- |
| Summary Cost Data |  |  |
| Total Amount of IDB Financing | 2,200,000 | 2,094,445 |
| IDB Financing as % of Total Cost | 56% | 53% |
| Total Cost of Project | 3,900,000 | 3,980,917 |
| Cumulative Investment as of |  |  |
| Remainder Required for Completion | 0 | 0 |

###### Appendix II

Page 3 of 4

PROJECT COST AND FINANCING (all amounts in US$)

- Project cost and source of financing

|  | #### Original |  |  |  | #### Actual |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Investment Category | IDB | Beneficiary | Total |  | IDB | Beneficiary | Total |
| 01.00 Certification | 550,000 | 200,000 | 750,000 |  | 552,343 | 323,690 | 876,033 |
| 02.00 Credentialing | 200,000 | 100,000 | 300,000 |  | 180,063 | 102,470 | 282,533 |
| 03.00 Train the Trainer | 250,000 | 600,000 | 850,000 |  | 250,000 | 652,902 | 902,902 |
| 04.00 Career Awareness | 100,000 | 300,000 | 400,000 |  | 98,521 | 191,523 | 290,044 |
| 05.00 Culinary Demonstration | 200,000 | 300,000 | 500,000 |  | 200,000 | 313,690 | 513,690 |
| 06.00 OECS Demonstration | 500,000 | 0 | 500,000 |  | 443,857 | 0 | 443,857 |
| 07.00 Evaluation | 50,000 | 0 | 50,000 |  | 74,263 | 0 | 74,263 |
| 08.00 Administration Costs | 200,000 | 200,000 | 400,000 |  | 295,373 | 302,197 | 597,570 |
| 09.00 Contingencies | 150,000 | 0 | 150,000 |  | 25 |  | 25 |
| Total | 2,200,000 | 1,700,000 | 3,900,000 |  | 2,094,445 | 1,886,472 | 3,980,917 |

2.	Schedule of Investments (all amounts in US$)

|  | Original |  |  |  | Actual |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Years | IDB | Beneficiary | Total |  | IDB | Beneficiary | Total |
| 1998/1999 | 1,128,750 | 591,750 | 1,720,500 |  | 59,509 | 119,470 | 178,979 |
| 1999/2000 | 565,750 | 608,250 | 1,174,000 |  | 345,445 | 327,013 | 672,458 |
| 2000/2001 | 505,500 | 500,000 | 1,005,500 |  | 323,069 | 106,952 | 430,021 |
| 2001/2002 |  |  |  |  | 547,489 | 495,983 | 1,043,472 |
| 2002/2003 |  |  |  |  | 397,157 | 739,481 | 1,136,638 |
| 2003/2004 |  |  |  |  | 421,776 | 97,573 | 519,349 |
| TOTAL | 2,200,000 | 1,700,000 | 3,900,000 |  | 2,094,445 | 1,886,472 | 3,980,917 |

###### Appendix II

Page 4 of 4

TC DATA  (all amounts in US$)

| Original TC amount | 2,200,000.00 |
| --- | --- |
| Amount disbursed | 2,094,444.95 |
| Amount canceled | 105,555.05 |
| First disbursement: |  |
| -- Original date (m/y) |  |
| -- Actual date (m/y) | December 16, 1998 |
| Last disbursement: |  |
| -- Original date (m/y) | March 14, 2002 |
| -- Actual date (m/y) | July 28, 2004 |