PROCUREMENT PLAN 2009

Loan/Technical Cooperation Number:  1332/OC-BA

Program Name:  Administration of Justice Programme

|  | # Financing Sources |  |  |  |  |  |  | Specific | Review |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Principal Project Procurement | IDB |  |  | Local/Other |  | Procurement Method | Prequalification | Procurement Notice | by Bank | Status |
|  | (%) |  |  | (%) |  |  | YES/NO | Tentative Publication Date | (Ex Ante Ex Post) |  |
| 1. SERVICES |  |  |  |  |  |  |  |  |  |  |
| - Technical Assistance |  |  |  |  |  |  |  |  |  |  |
| - Baseline Study |  |  |  |  |  |  |  |  |  |  |
| - Amount: US $10,000 | 79 |  |  | 21 |  | LCP | NO | 1st Semester 2003 | Ex Ante | Awarded |
| - Opinion Survey |  |  |  |  |  |  |  |  |  |  |
| - Amount: US $10,000 | 67 |  |  | 33 |  | LCP | NO | 2nd Semester 2003 | Ex Ante | Awarded |
| - Project Officers |  |  |  |  |  |  |  |  |  |  |
| - Amount US$ 44,436 | 67 |  |  | 33 |  | LCP | NO | 2nd Semester 2008 | Ex Post | In Process |
| - Procurement Specialist |  |  |  |  |  |  |  |  |  |  |
| - Amount US$ 50,000 | 67 |  |  | 33 |  | DC | NO | 1st Semester 2009 | Ex Post | In Process |
| - Sector Management |  |  |  |  |  |  |  |  |  |  |
| - Short Term Court Reporter |  |  |  |  |  |  |  | - |  |  |
| - Amount: US$36,000 | 79 |  |  | 21 |  | LCP | NO |  | Ex Ante | Awarded |
| - 2 Court Reporters |  |  |  |  |  |  |  |  |  |  |
| - Amount US $500,000 | 79 |  |  | 21 |  | ICP | NO | 1st Semester 2009 | Ex Ante | Pending |
| - Sector Wide Information System (IJIS) |  |  |  |  |  |  |  |  |  |  |
| Service Provider |  |  |  |  |  |  |  |  |  |  |
| - Amount: US $1.7 |  | 79 | 21 |  | ICB |  | YES | 1st Semester 2009 | Ex Ante | Pending |
| Preparation of System Specifications |  |  |  |  |  |  |  |  |  |  |
| - Amount: US $40,000 |  | 79 | 21 |  | LCP |  | NO |  | Ex Ante | Awarded |
| - CMIS Coordinator |  |  |  |  |  |  |  |  |  |  |
| - Amount US$50,000 |  | 79 | 21 |  | LCP |  | NO | 2nd Semester 2008 | Ex Ante | Awarded |
| - Information Technology Coordinator |  |  |  |  |  |  |  | - |  |  |
| - Amount: US $50,000 |  | 79 | 21 |  | LCP |  | NO |  | Ex Ante | Awarded |
| - Conversion of Laws |  |  |  |  |  |  |  |  |  |  |
| - Amount: US $200,000 |  | 79 | 21 |  | ICB |  | NO | 1st Semester 2009 | Ex Ante | In Process |
| - Civil Society Coordination |  |  |  |  |  |  |  |  |  |  |
| - Amount: US $50,000 |  | 79 | 21 |  | LCP |  | NO | 1st Semester 2009 | Ex Post | Pending |

|  | # Financing Sources |  |  |  | Specific | Review |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Principal Project Procurement | IDB | Local/Other | Procurement | Prequalification | Procurement Notice | by Bank | Status |
|  | (%) | (%) | Method | YES/NO | Tentative Publication Date | (Ex Ante Ex Post) |  |
| - Access to Justice |  |  |  |  |  |  |  |
| - Case Management |  |  |  |  |  |  |  |
| Coordinator + Trainer |  |  |  |  |  |  |  |
| - Amount: US $565,510 | 79 | 21 | ICP | NO | 2nd Semester 2007 | Ex Ante | In Process |
| - 2 Judicial Assistants |  |  |  |  |  |  |  |
| - Amount: US $60,000 | 79 | 21 | LCP | NO | 2nd Semester 2006 | Ex Ante | Awarded |
| 2 Judicial Assistants |  |  |  |  |  |  |  |
| - Amount US$60,000 | 79 | 21 | LCP | NO | 2nd Semester 2008 | Ex Ante | Awarded |
| - Alternative Dispute Resolution |  |  |  |  |  |  |  |
| - Amount: US $750,000 | 60 | 40 | ICP | NO | 1st Semester 2007 | Ex Ante | Awarded |
| - Alternative Dispute Resolution Secretariat |  |  |  |  |  |  |  |
| - Amount: US $10,000 | 60 | 40 | LCP | NO | 1st Semester 2009 | Ex-Post | Awarded |

|  | # Financing Sources |  |  |  | Specific | Review |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Principal Project Procurement | IDB | Local/Other | Procurement | Prequalification | Procurement Notice | by Bank | Status2 |
|  | (%) | (%) | Method | YES/NO | Tentative Publication Date | (Ex Ante Ex Post) |  |
| - Access to Justice (Cont’d) |  |  |  |  |  |  |  |
| - Legal Aid Study |  |  |  |  |  |  |  |
| - Amount US $40,000 | 67 | 33 | ICP | NO | 2nd Semester 2003 | Ex Ante | Awarded |
| - Youth & Rehabilitation |  |  |  |  |  |  |  |
| Institutional Strengthening |  |  |  |  |  |  |  |
| - Management Reorganization – Probation Department |  |  |  |  |  |  |  |
| - Amount: US $335,000 | 77 | 23 | ICP | YES | 1st Semester 2009 | Ex Ante | In Process |
| - Cognitive Behavioral Training – GIS Staff |  |  |  |  |  |  |  |
| - Amount US $200,000 | 77 | 23 | ICP | NO | 1st Semester 2009 | Ex Ante | In Process |
| Rehabilitative Capacity |  |  |  |  |  |  |  |
| - Inmate Rehabilitation - Staff |  |  |  |  |  |  |  |
| - Amount US $400,000 | 70 | 30 | ICP | NO | 2nd Semester 2008 | Ex Ante | In Process |
| - Literacy Testing - Amount US$50,000 | 70 | 30 | LCP | NO | 2nd Semester 2008 | Ex Post | Awarded |

|  | Financing Sources |  |  |  | Specific | Review |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Principal Project Procurement | IDB | Local/Other | Procurement Method1 | Prequalification | Procurement Notice | by Bank | Status2 |
|  | (%) | (%) |  | YES/NO | Tentative Publication Date | (Ex Ante Ex Post) |  |
| 2. GOODS |  |  |  |  |  |  |  |
| - Sector Management |  |  |  |  |  |  |  |
| - Court Reporting Equipment |  |  |  |  |  |  |  |
| - Amount US $150,000 | 79 | 21 | ICB | NO | 1st Semester 2009 | Ex Ante | Pending |
| - Court Management System Hardware |  |  |  |  |  |  |  |
| - Amount: US $192,250 | 79 | 21 | NCB | NO | 1st Semester 2007 | Ex Ante | Awarded |
| - Court Management System Software - Amount : US$416,000 | 79 | 21 | DC | NO | - | Ex Ante | Awarded |
| - Conversion of Laws for CPC - Software and Hardware |  |  |  |  |  |  |  |
| - Amount US$200,000 | 79 | 21 | ICB | NO | 1st Semester 2009 | Ex Ante | In Process |
| - Offender Management System |  |  |  |  |  |  |  |
| - Amount: US$500,000 | 79 | 21 | ICB | NO | 1st Semester 2009 | Ex Ante | In Process |
| - Access to Justice |  |  |  |  |  |  |  |
| - ADR Office Equipment |  |  |  |  |  |  |  |
| - Amount: US$10,000 | 60 | 40 | NCB | NO | 1st Semester 2009 | Ex Post | Awarded |
| 3. CIVIL WORKS |  |  |  |  |  |  |  |
| - Young Offenders Institutions Designs - Amount: US $500,000 | 58 | 42 | LCP | NO | 2nd Semester 2007 | Ex Ante | In Process |
| 4. SECTOR MANAGEMENT - OAG Chambers Designs - Amount: US $1,620,000 | 58 | 42 | LCP | NO | 1st Semester 2009 | Ex Ante | In Process |
| - Agricultural Equipment |  |  |  |  |  |  |  |
| - Amount US$40,000 | 79 | 21 | NCB | NO | 1st Semester 2008 | Ex Post | Awarded |
| - Agricultural Equipment |  |  |  |  |  |  |  |
| - Amount US$400,000 | 79 | 21 | NCB | NO | 1st Semester 2008 | Ex Ante | Pending |
| - Relocation of Farm |  |  |  |  |  |  |  |
| - Amount: US $ 300,000 | 58 | 42 | NCB | NO | 2nd Semester 2008 | Ex Ante | Pending |

Notes: 	ICB: International Competitive Bidding	NCB: National Competitive Bidding	LIB: Limited International Bidding	LCP: Local Call for Proposals

DC: Direct Contracting		ILS: International/Local  Shopping	FA: Force Account			ICP: International Call for Proposals

Terminology to be used: 	Pending/In Process/Awarded/Cancelled

Terminology to be used: 	Pending/In Process/Awarded/Cancelled

Notes: 	ICB: International Competitive Bidding	NCB: National Competitive Bidding	LIB: Limited International Bidding	LCP: Local Call for Proposals

DC: Direct Contracting		ILS: International/Local  Shopping	FA: Force Account			ICP: International Call for Proposals

2 Terminology to be used: 	Pending/In Process/Awarded/Cancelled

Notes: 	ICB: International Competitive Bidding	NCB: National Competitive Bidding	LIB: Limited International Bidding	LCP: Local Call for Proposals

DC: Direct Contracting		ILS: International/Local  Shopping	FA: Force Account			ICP: International Call for Proposals

1 Notes: 	ICB: International Competitive Bidding	NCB: National Competitive Bidding	LIB: Limited International Bidding	LCP: Local Call for Proposals

DC: Direct Contracting		ILS: International/Local  Shopping	FA: Force Account 			ICP: International Call for Proposals

2 Terminology to be used: 	Pending/In Progress/Awarded/Cancelled