## Sheet1
Project: _________ADMINISTRATION OF JUSTICE PROGRAMME_______________________________
Project Number _______ and Loan Contract Number 1332 OC-BA
Period comprised in this Procurement Plan: From January 2011 to June 2011
Ref. No. 1 | Description of and category of procurement contract | Estimated cost in (US$ thousand) | Procure-ment method 2 | Review (ex-ante or ex-post) | Source of financing and percentage |  | Prequali-fication 3 (Yes/No) | Estimated Dates |  | Status 4 (pending, in process, awarded, cancelled) | Comments
[5 empty] | IDB % | Local / Other % |  | Publication of specific procurement notice | Completion of contract
1 | CONSULTING SERVICES
Technical Assistance
| Baseline Study | 10 | QCNI | Ex Ante | 79 | 21 | No | NA | 2 Q 2004 | Awarded
| Opinion Survey | 10 | QCNI | Ex Ante | 67 | 33 | No | 3 Q 2003 | 3 Q 2007 | Awarded
| Project Officer | 44 | QCNI | Ex Ante | 67 | 33 | No | NA | 4 Q 2010 | Awarded
| Procurement Specialist | 50 | DC | Ex Ante | 67 | 33 | No | NA | 4 Q 2010 | Awarded
| Opinion Survey Consultant | 25 | DC | Ex Ante | 67 | 33 | No | NA | 2 Q 2011 | In Process
| Project Completion Report | 40 | QCNI | Ex Ante | 67 | 33 | No | NA | 4 Q 2011 | In Process
Sector Management
| Short Term Court Reporter | 36 | QCNI | Ex Ante | 79 | 21 | No | NA | 3 Q 2007 | Awarded
| Court Reporting and PM Consulting Services | 50 | DC | Ex Ante | 79 | 21 | No | NA | 2 Q 2011 | Cancelled
| Court Reporting Consulting Services | 200 | QCNI | Ex Ante | 79 | 21 | No | 2 Q 2010 | 2 Q 2011 | Cancelled
| Sector Wide Information System (IJIS) | 1700 | ICB | Ex Post | 79 | 21 | No | 2 Q 2010 | 2 Q 2011 | In Process
| Sector Wide Information System Specs | 40 | QCNI | Ex Ante | 79 | 21 | No | NA | 3 Q 2010 | Awarded
| CMIS Coordinator | 50 | QCNI | Ex Ante | 79 | 21 | No |  |  | Awarded
| Information Tech Coordintor | 18 | QCNI | Ex Ante | 79 | 21 | No | NA | 4 Q 2009 | Awarded
| Civil Society Coordination Consultant | 50 | CQS | Ex Post | 79 | 21 | No | NA | 3 Q 2010 | Awarded
Access to Justice
| Case Management Coordinator + Trainer | 70 | QCBS | Ex Ante | 79 | 21 | No | NA | 2 Q 2011 | In Process
| 2 Judicial Assistants | 60 | QCNI | Ex Ante | 79 | 21 | No | 1 Q 2008 | 4 Q 2009 | Awarded
| Alternative Dispute Resolution (ADR) | 750 | QCBS | Ex Ante | 60 | 40 | Yes | 1Q 2007 | 1 Q 2010 | Awarded
| Legal Aid Study | 40 | QCII | Ex-Ante | 67 | 33 | No | 2 Q 2003 | 2 Q 2005 | Awarded
Youth and Rehabilitation
Institutional Strengthening
| Management Reorganization - Probation Department | 335000 | QCBS | Ex Ante | 77 | 23 | Yes | 4 Q 2009 | 3 Q 2011 | Awarded
| Cognitive Behavioral Training | 250000 | QCNI | Ex Ante | 77 | 23 | No | NA | 3 Q 2010 | Awarded
Rehabilitative Capacity
| Inmate Rehabilitation - Staff | 350000 | QCBS | Ex Ante | 70 | 30 | No | 1 Q 2010 | 2 Q 2011 | Awarded
| Literacy Testing | 50 | QCNI | Ex Ante | 70 | 30 | No | 1 Q 2008 | 2 Q 2009 | Awarded
| EIA/SIA for Relocation of Farm | 90000 | QBS | Ex Ante | 70 | 30 | No | 2 Q 2010 | NA | Awarded
| Young Offenders Institution Eng | 300 | QCBS | Ex Ante | 70 | 30 | No | 2 Q 2010 | 1 Q 2011 | In Process
| Quantity Surveyor OAG | 50 | QCNI | Ex-Post | 70 | 30 | No | NA | 3 Q 2010 | Awarded
| Project Manager OAG | 50 | QCNI | Ex-Post | 70 | 30 | No | NA | 3 Q 2010 | Awarded
1 If there are a number of similar individual contracts to be executed in different places or at different times, these can be grouped together under a single heading, with an explanation in the comments column, indicating the average individual amount and the period during which the contracts would be executed. For example: an education project that includes school construction might include an item labeled “School Construction” for an estimated cost of US$20 million and an explanation under the Comments column such as this: “This item encompasses some 200 contracts for school construction averaging US$100,000 each, to be awarded individually by the participating municipal governments over a three-year period between January 2006 and December 2008.”
2 Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; Consulting Firms: QCBS: Quality- and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection; Individual Consultants: QCNI: Selection based on comparison of qualifications of national individual consultants; QCII: Selection based on comparison of qualifications of international individual consultants.
3 Applicable only to Goods and Works in case the new Policies apply. In the case of previous Policies, it is applicable to Goods, Works and Consulting Services.
4 Column “Status” will be used for retroactive procurement and when updating the procurement plan.
Project: _________ADMINISTRATION OF JUSTICE PROGRAMME_______________________________
Project Number _______ and Loan Contract Number 1332 OC-BA
Period comprised in this Procurement Plan: From June 2009 to June 2010
Ref. No. 1 | Description of and category of procurement contract | Estimated cost in (US$ thousand) | Procure-ment method 2 | Review (ex-ante or ex-post) | Source of financing and percentage |  | Prequali-fication 3 (Yes/No) | Estimated Dates |  | Status 4 (pending, in process, awarded, cancelled) | Comments
[5 empty] | IDB % | Local / Other % |  | Publication of specific procurement notice | Completion of contract
2 | GOODS
Sector Management
| Court Reporting Equipment | 150 | ICB | Ex-Post | 79 | 21 | No |  |  | Cancelled
| Court Management System Hardware | 193 | NCB | Ex-Ante | 79 | 21 | No | 2 Q 2007 | 4 Q 2007 | Awarded
| Court Mangt System Hardware 2 | 30 | NCB | Ex-Post | 79 | 21 | No | NA | 2 Q 2010 | Awarded
| Court Management System software | 416 | DC | Ex-Ante | 79 | 21 | No | NA | 4 Q 2009 | Awarded
| Conversion of Laws for CPC - Software and Hardware | 2500 | ICB | Ex-Post | 79 | 21 | No | 4Q 2009 | 2 Q 2012 | In Process
| ADR Office Equipment | 10 | NCB | Ex-Post | 60 | 40 | No | 1 Q 2009 | 1 Q 2009 | Awarded
| Agricultural Equipment 1 | 40 | NCB | Ex-Post | 79 | 21 | No | 2 Q 2008 | 1 Q 2009 | Awarded
| Agricultural Equipment 2 | 400 | NCB | Ex-Post | 79 | 21 | No | 1 Q 2010 | 4 Q 2010 | Awarded
| Law Books for Courts | 350 | ICB | Ex-Post | 79 | 21 | No | 4 Q 2009 | 1 Q 2011 | Awarded
| Books for SG and OAG | 798 | LIB | Ex-Ante | 79 | 21 | No | 4 Q 2010 | 2 Q 2011 | In Process
| Telephone Network - OAG Chambers | 200 | NCB | Ex-Ante | 79 | 21 | No | 4 Q 2010 | 2 Q 2011 | In Process
| Access System - OAG Chambers | 50 | NCB | Ex-Post | 79 | 21 | No | NA | 2 Q 2011 | In Process
| Network for OAG | 50 | NCB | Ex-Ante | 79 | 21 | No | 1 Q 2011 | 2 Q 2011 | In Process
3 | WORKS
| Relocation of Farm | 300 | NCB | Ex Ante | 58 | 42 | No | 3 Q 2011 | 2 Q 2012 | Cancelled
| OAG Chambers | 1500 | NCB | Ex Ante | 58 | 42 | No | 3 Q 2010 | 4 Q 2010 | Awarded
| Young Offenders Inst | 2000 | NCB | Ex Ante | 58 | 42 | Yes | 1 Q 2011 | 2 Q 2013 | Cancelled
1 If there are a number of similar individual contracts to be executed in different places or at different times, these can be grouped together under a single heading, with an explanation in the comments column, indicating the average individual amount and the period during which the contracts would be executed. For example: an education project that includes school construction might include an item labeled “School Construction” for an estimated cost of US$20 million and an explanation under the Comments column such as this: “This item encompasses some 200 contracts for school construction averaging US$100,000 each, to be awarded individually by the participating municipal governments over a three-year period between January 2006 and December 2008.”
2 Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; Consulting Firms: QCBS: Quality- and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection; Individual Consultants: QCNI: Selection based on comparison of qualifications of national individual consultants; QCII: Selection based on comparison of qualifications of international individual consultants.
3 Applicable only to Goods and Works in case the new Policies apply. In the case of previous Policies, it is applicable to Goods, Works and Consulting Services.
4 Column “Status” will be used for retroactive procurement and when updating the procurement plan.