## SM2015 Grant
Project: Improving the Efficiency of th Public Health Expenditure
Technical Cooperation No.: ATN/OC-16194-BL
Period Comprised in this Procurement Plan: From September 2017 to September 2019
WBS No. | Ref. No. | Description of and Category of Procurement Contract | Estimated Cost in (US$ ) | Procurement Method | Review (Ex ante/Ex-Post) | Source of Financing and Percentage |  | Prequalification (Yes/No) | Estimated Dates |  |  |  | Status (pending, in process awarded, cancelled) | Comments
[6 empty] | % IDB | % local/other |  | Publication of Specific Procurement Notice | Bids/RFP Submission Date | Contract Signing | Completion of contract
GOODS
| BZ/IPHE/G/003 | Truck for Central Medical Stores (Cab and Chassis) | 30000 | PC | Ex-ante | 100% | 0% | No | 2018-01-01 |  |  | 2018-12-01 | In process | 2nd Tender Process Launched
| BZ/IPHE/G/004 | Refrigerated Cargo Box for CMS | 15000 | PC | Ex-ante | 100% | 0% | No | 2018-01-01 |  |  | 2018-12-01 | In process | 2nd Tender Process Launched
CONSULTING SERVICES
1.1 and 1.2 | BZ/IPHE/CS/001 | Combined Consultancy to review and update the current women health norms and protocols and to strengthen the Maternal Death Surveillance & Response (MDSR) | 30000 | SSS | Ex-ante | 100% | 0% | No | 2018-09-01 |  |  | 2019-09-01 | In process | TOR with IDB for non-objection
1.3 | BZ/IPHE/CS/002 | Consultancy to develop alternative financial mechanisms for the implementation of a new health service delivery model | 25000 | SSS | Ex-ante | 100% | 0% | No | 2018-10-01 |  |  | 2019-04-01 | Pending | Consultancy firm of Oxford to be direct contracted.TOR pending finalization
| BZ/IPHE/CS/003 | Consultancy to strengthen the public health supply chain management | 50000 | CQS | Ex-ante | 100% | 0% | No | 2018-10-01 |  |  | 2019-09-01 | Pending | TOR pending finalization
1.5
1.4.1 | BZ/IPHE/CS/005 | Quality Improvement Project Manager | 64655 | SSS | Ex-ante | 100% | 0% | No | 2017-09-01 |  |  | 2019-02-28 | Awarded
1.4.1 | BZ/IPHE/CS/006 | Quality Improvement Officer | 15345 | NICQ | Ex-ante | 100% | 0% | No | 2018-01-01 |  |  | 2018-11-21 | Awarded | Contract Awarded to Dr. Michael Mendez
3.1 | BZ/IPHE/CS/007 | Executive Assistant - Procurement | 20000 | SSS | N/A | 0% | 100% | No | 2017-09-01 |  |  | 2019-09-01 | Awarded
3.1 | BZ/IPHE/CS/008 | Executive Assistant - Administration | 20000 | SSS | N/A | 0% | 100% | No | 2017-09-01 |  |  | 2019-09-01 | Awarded
3.2 | BZ/IPHE/CS/09 | Financial Audit | 10000 | LCS | Ex-ante | 100% | 0% | No | 2019-04-01 |  |  | 2019-09-01 | Pending
| BZ/IPHE/CS/10 | Technical Support to Improve Dashboard | 10000 | SSS | Ex-ante | 100% | 0% | No | 2018-09-01 |  |  |  | Pending | Consultancy firm of Tech Salud to be direct contracted. TOR currently being finalized
| TOTAL |  | 290000
ICB -International Competitive Bidding
DC - Direct Contracting
LIB - Limited International Bidding
NCB -National Competitive Bidding
PC -Price Comparison
SSS - Single Source Selection
LCS - Least Cost Selection
NICQ - National Individual Consultant selection based on Qualification
IICQ: International Individual Consultant Selection Based on Qualifications
| Prepared by: | Jamillah Bulwer, Procurement Manager, Project Management Unit, Ministry of Health
| Date: | September 27, 2018