## Procurement pla V2.0
ATN/ME-14422-RG
Proyecto: Sistema Biobolsa
Plan de Adquisiciones 01/Agosto/2014 | Description | Cotrato | Approximate cost | Procurement method | Revision | Source of funding |  |  |  | Comments
[5 empty] | (ex-ante / ex-post) | BID |  | Executing agency
1. Consolidation of Regional Growth Strategy
1.1. Conduct detailed market studies
1.1.1 Geographic and Market Segment Expansion
1.1.1.1 Market analysis and technical oversight of new markets | Marketing consultants and researchers with specialization in key markets | Contrato I (Feher) | 12500 | SD |  | 12500 | 100% | 0 | 0%
1.1.1.2 Technical oversight of tools for new market segments | Technical design, engineering, and development firm | Contrato II (SUEMA) | 26000 | SD | ex-post | 26000 | 100% | 0 | 0%
1.2. Develop a marketing and promotional plan
1.2.1 Public-facing webpage and online sales functionality
1.2.1.1 Website with Social Media and Promotion Package | Top-in-class website design with social media integration (design firm) | Contrato III (agencia X) | 14500 | SD | ex-post | 14500 | 100% | 0 | 0%
1.2.1.2 Content generation (photos, videos) | Independent contractors for photo, video and graphic content development | Contrato IV (Camaroni) | 12000 | CD | ex-post | 12000 | 100% | 0 | 0%
1.3. Expand the technical capacity to service new markets
1.3.1 Legal Structure for Franchise and Distribution
1.3.1.1 Legal Structure and Oversight | Legal business council | Contrato I (Feher) | 5500 | CD |  | 5500 | 100% | 0 | 0%
1.3.1.2 Specific contract drafts and execution of legal agreements | Legal business council and contract services | Contrato V (despacho X) | 2200 | CD | ex-post | 2200 | 100% | 0 | 0%
1.3.1.2 All patent and copyright registration in order for expansion | Legal business council and patent services | Contrato V (despacho X) | 8000 | CD | ex-post | 8000 | 100% | 0 | 0%
1.3.2 Education, promotion, installaton and training
1.3.2.1 Community visits; Daily expenses | 2 sales staff x 2 days | Contrato VI (BMC inhouse) | 6600 | CD |  | 6600 | 100% | 0 | 0%
1.3.2.2 Educational and promotional materials | Purchase of display stands, flyers, samples, sound system etc | Contrato VII (proveedor X) | 7500 | CD |  | 7500 | 100% | 0 | 0%
1.3.2.3 Daily expenses | Expenses x 2 sales staff x 2 days | Contrato VI (BMC inhouse) | 3600 | CD | ex-post | 3600 | 100% | 0 | 0%
1.3.4 Financial Strategy and Oversight
1.3.4.1 Fiancial Consultant For Expansion and Growth | Long term consultant X 1 person X 18 months | Contrato VIII (Contratación Esther) | 41538.4615 | CCIN | ex-post | 26538.4615 | 63.89% | 15000 | 36.11%
1.3.4.2 Microfinance oversight for loan program | Short term consultant X 6 months | Contrato IX (Consultor X) | 18000 | CCIN | ex-post | 13000 | 72.22% | 5000 | 27.78%
1.4. Develop a franchising package and target retailers
1.4.1 Conceptual package for BMC distribution and growth | Growth and business consulting firm(s) to develop franchise packages | Contrato I (Feher) | 12000 | SD | ex-post | 12000 | 100% | 0 | 0%
1.4.2 Graphics elements to show capacity and growth plan | Graphic design firm | Contrato III (agencia X) | 2700 | SD | ex-post | 2700 | 100% | 0 | 0%
2. Strengthening of company´s data management and M&E capacity
2.1. Online Data Management Platform for Distribution
2.1.1 Design and graphic elements | Graphic design services | Contrato X | 1500 | SD | ex-post | 1500 | 100% | 0 | 0%
2.1.2 Programming and technical elements | Computer programming and product development firm | Contrato X | 12000 | SD | ex-post | 12000 | 100% | 0 | 0%
2.1.3 Integration of smartphone functionality | Computer Programming and mobil product development firm | Contrato X | 3500 | SD | ex-post | 3500 | 100% | 0 | 0%
2.2. Monitoring and Impact Database and Reporting Tool
2.2.1 Interagration of current impact monitoring software | Content specialist X 2 months | Contrato X | 4000 | CD | ex-post | 4000 | 100% | 0 | 0%
2.2.2 Design and Programming | Computer programming and product development firm | Contrato X | 11000 | SD | ex-post | 11000 | 100% | 0 | 0%
2.2.3 Smartphone compatible monitoring capabilities | Computer Programming and mobil product development firm | Contrato X | 3500 | SD | ex-post | 3500 | 100% | 0 | 0%
2.2.4 Cloud based interface for graphic elements and logs | Computer programming and cloud-based hosting services | Contrato X | 5000 | SD | ex-post | 5000 | 100% | 0 | 0%
2.3. Field Testing of Data and Survey Tools |  |  | 40500
3. Redesign of the Sistema Biobolsa production process
3.1 Process review of the production and distribution facilities
3.1.1 Identification of needed process improvements | Engineering and process development firm | Contrato XI (Proquipa) | 2300 | CD | ex-post | 2300 | 100% | 0 | 0%
3.1.2 Identiciation of material, infrastructure and tool needs | Content specialist in geomembrane speciality production and equipment | Contrato XII (SEICSA) | 3700 | CD | ex-post | 3700 | 100% | 0 | 0%
3.2 Redesign process efficiency and quality control
3.2.1 Design of process flow and quality control | Engineering and process development firm | Contrato XI (Proquipa) | 7000 | SD | ex-post | 7000 | 100% | 0 | 0%
3.2.2 Design of infrastucture improvments | Engineering and process development firm / Content specialist | Contrato XI (Proquipa) | 6500 | SD | ex-post | 6500 | 100% | 0 | 0%
3.2.3 Design and spec. of new fabrication tools | Content and equipment specialist for geomembrane production and equipment | Contrato XII (ALI PolyWeld) | 18500 | SD | ex-post | 18500 | 100% | 0 | 0%
3.3 Implementation of new infrastructure and tools
3.3.1 Acquisition of new infrasture and tools | Purchase of tools, equipment and infrastructure per new fabrication designs | Contrato XIII (proveedor Y) | 18000 | CP | ex-post | 0 | 0% | 18000 | 100%
3.3.2 Implementation of new fab and QC processes | Engineering oversight, quality control and measurment of new system | Contrato XIV | 12000 | CP | ex-post | 0 | 0% | 12000 | 100%
4. Administration
4.1 Project coordinator | Salary x 1 coordinator x 1 month |  | 18000 | CD | ex-post | 0 | 0% | 18000 | 100%
4.2 Daily expenses | Expenses x 1 coordinator x 10 days per month |  | 10800 | CD | ex-post | 0 | 0% | 10800 | 100%
Goods and work: ICB: International competitive bidding; LIL: Limited International Bidding; NCB: National Competitive Bidding; CP: Compare Prices; CD: Direct Contracting; AD: Direct Administration; PSA: Procurement through specialized agencies; AC: Agencies Procurement; AI: Inspection Agencies; CPIF: Procurement in Loans to Financial Intermediaries; BOO / BOT / BOOT: Build-Own-Operate / Build-Operate-Transfer / Build-Own- Operate-Transfer; CBD: Performance-based procurement; CPGB: Procurement under Loans Guaranteed by the Bank; PSC: Community Participation in Procurement
Conultancy firms: QCBS: Quality and Cost; QBS: Quality-Based Selection; FBS: Selection under a Fixed Budget; LCS: Selecting Least-Cost; CQS: Selection based on the consultants' qualifications; SD: Direct Selection
Individual consultants: CCIN: Selection based on Consultant Qualifications National Individual; CCII: Selection based on comparison of qualifications of international individual consultants
24900
8000
29880
37880
43940.8