## Sheet1
Project: Strengthening of the Energy Sector in The Bahamas
Project Number BH-T1012 Contract Number: ATC/OC-11436-BH
March 2012 to June 2013
Ref. No. 1 | Description of and category of procurement contract | Estimated cost in (US$ thousand) | Procure-ment method 2 | Review (ex-ante or ex-post) | Source of financing and percentage |  | Prequali-fication 3 (Yes/No) | Estimated Dates |  | Status 4 (pending, in process, awarded, cancelled) | Comments
[5 empty] | IDB % | Local / Other % |  | Publication of specific procurement notice | Completion of contract
1 | GOODS
Good 1
Brief description
Good 2
Brief description
2 | WORKS
Work 1
Brief description
Work 2
Brief description
3 | Non-consulting services
Service 1
Brief description
Service 2
Brief description
4 | CONSULTING SERVICES
| Consulting Services 1: Strengthening the Energy Sector in The Bahamas | US$680,000 | QCBS | ex-ante | 80% | 20% | No | 2009-07-01 | 2010-09-01 | awarded | completed
Brief description:
(i) financial and operational review of BEC; (ii) expansion plans include RE, and WE; (iii) regulatory review of the sector.
| Consulting Services 2: Consultancy for Energy Sector in The Bahamas also financed under ATN/MC-11467-BH | US$190,000 | QCBS | ex-ante | 100% |  | No | 2012-02-01 | 2013-06-01 | In process | Consulting firm selected and to be contracted
Brief description:
(i) Implementation of 2 pilot projects; (ii) Review and update investment plan to improve Electrical Corporations financial and operational sustainability, commercial potential for RE and EE &; (iii) Impact Evaluation of present EE and RE pilot projects in the country
| Consulting Services 3: Audit | US$5,000 | LCS | ex-ante | 100% |  | No | No | 2013-06-01 | Awarded
Brief description:
An audit of Financial Statements for the entire Project will be conducted by an audit firm recognized by the Bank during the last disbursement period of the Project and submitted to the Bank
1 If there are a number of similar individual contracts to be executed in different places or at different times, these can be grouped together under a single heading, with an explanation in the comments column, indicating the average individual amount and the period during which the contracts would be executed. For example: an education project that includes school construction might include an item labeled “School Construction” for an estimated cost of US$20 million and an explanation under the Comments column such as this: “This item encompasses some 200 contracts for school construction averaging US$100,000 each, to be awarded individually by the participating municipal governments over a three-year period between January 2006 and December 2008.”
2 Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; Consulting Firms: QCBS: Quality- and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection; Individual Consultants: QCNI: Selection based on comparison of qualifications of national individual consultants; QCII: Selection based on comparison of qualifications of international individual consultants.
3 Applicable only to Goods and Works in case the new Policies apply. In the case of previous Policies, it is applicable to Goods, Works and Consulting Services.
4 Column “Status” will be used for retroactive procurement and when updating the procurement plan.