## PEP and POA
|  |  | 2014 | [6 empty] | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018
|  |  | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Product
COMPONENT 1: Culture Change for Peaceful Co-existence and Community Governance. |  | Total Costs for Five years in US$
Sub-component 1111: Training courses provided to community members on parenting and healthy gender norms in families. |  | 587500
Implement Parenting Education training courses (including all costs - instructors; preparation of curriculum; workshops expenses)
Implement Positive Gender roles Programme (includes themes on gang culture, Women Empowerment outreach and Men with a Message Programmes events)
Sub-Component 1112: Counselling / psycho-social support provided to victims/witnesses of violence (including gender-based or domestic violence) |  | 3060000
Case management & Counselling Sessions - Individual
Case Management & Counselling Sessions- group or school
Social workers and psychologists
Sub-Component 1113: Violence interruption services provided (e.g. gang interruption) |  | 4500000
Provide Violence Interruption Services (includes messages on changing gang culture; Gang interruption and reintegration activities; Life Skills training; and training of facilitators)
Sub-Component 1114: Violence prevention and conflict resolution education and training provided in schools |  | 412500
Conflict resolution training sessions in schools (including on changing social norms tied to gangs)
Training from instructors and facilitators
Sub-Component 1115: Social marketing for awareness and attitude change to promote ‘culture of lawfulness’ (e.g. to address violent gender norms, anti-snitch culture) |  | 579000
Social Marketing: Media Campaigns (particularly on gang culture and social norm transformation)
Social Marketing: Participatory workshops to develop messages on changing gang culture & social norms
Software and Hardware to support to social marketing unit | bar: 2014 Jun to 2014 Sept
Contract Social Marketing & Media design experts
Sub-Component 1116: Community events to improve citizen-police relations conducted |  | 40000
Community events to promote citizen police relations (including on changing social norms related to gangs)
Sub-Component 1117: Crisis intervention activities conducted (including but not limited to violence and gang interruption) |  | 240000
Rapid response interventions in unexpected crisis situations (e.g. by PMI)
Sub-Component 1121: Training and technical assistance provided to community leaders and residents to establish or improve community governance capacity (e.g. community development, operations) |  | 600000
Development of Community Profiles for 30 communities
Implementation of CDC operational capacity training
Sub-component 1122: Community infrastructure (situational crime prevention project and multi-purpose centres) built or renovated |  | 1650000
Expansion and repairs of community centres (5 in total; 1 per year)
Implement Situational Crime Prevention Projects (small infrastructure) (includes Personnel to manage and assist with infrastructure projects)
Sub-componet 1123:Community safety plans (including safety audits for vulnerable groups) developed, with implementa-tion/advocacy campaign. |  | 165000
Preparation of new Community Safety Plans
Design and implementation of campaigns organized by CACs
Sub-component 1124: Peace-building through cultural and sporting activities |  | 180000
Cultural and sporting events with peacebuilding and gang culture/social norm transformation messages delivered through Goals 4 Life Programme | bar: 2014 Jun to 2017 Dec
Cultural and sporting events with peace messages (including on changing gang-related social norms)
Sub-component 1125:Coordination at the local level among MDAs and with CDCs/CBOs |  | 100000
Events to faciliate coordination
Service Delivery (staff - includes regional Coordinators, Community Action Officers and Asst. CAOs) |  | 3820750
Component 2 - Labour Market Attachment and Employability
Sub-component 1211: Technical assistance delivered on case management system for job training / placement. |  | 90000
Case-management system training for service providers (includes trainers) | bar: 2014 Jun to 2016 Dec
Sub-component 1212: Vocational training provided to targeted beneficiaries |  | 1400000
Vocational skills training (includes pre-test and selection of trainees)
Sub-component 1213: Support for access to tertiary education and secondary education provided to selected beneficiaries |  | 1625000
Provide scholarships for secondary education to selected beneficiaries
Provide scholarships for tertiary education to selected beneficiaries
Sub-component 1214:Remedial education provided in or outside communities, with integrated and life-skills training. |  | 6150000
Implementation of Remedial/Pre-vocational education sessions
Contracting of Private and public sector outreach experts
Sub-Component 1221: Job-seeking, placement, and training services provided to target beneficiaries |  | 900000
Job Preparation Expo Sessions
Job preparation training services
Sub-Component 1222: On-the-job or work orientation apprenticeship/internships provided for youth, with emphasis on life skills and high-demand occupations. |  | 3473000
On-the-job training for Jamaican Defense Force (male and female)
On-the-job training through Internships Program (male and female)
On the job Training for Police Cadet (male and female)
Implementation of Summer Diversion/Empoyment Program (male and female)
Sub-Component 1223: Business development services provided for community residents in entrepreneurship, with emphasis on high-demand sectors |  | 100000
Development and training on Business Grants
Service Delivery (staff includes regional Coordinators, Community Action Officers and Asst. CAOs) |  | 2091750
Component 3 - Community Justice Services
Subtotal 1311-1312-1321-1322 - Service 1 Victim Support Unit |  | 2848000
Victim Service Unit service point (location) for 4 communities | bar: 2014 Jun to 2017 Dec
Emergency assistance for victim clients (eg. shelter, transportation, lawyer, etc)
National tool for assessing needs of children vulnerable to violence or abduction. | bar: 2014 Jun to 2014 Dec
Interventions with children experiencing trauma in schools
Children In Court Programme
Public education materials
Stipend for volunteers
Technical assistance on victim services (include, for example, methodology and curriculum design and guides, workshop design, etc)
Subtotal - 1311-1312-1321-1322 - Service 2 Legal Aid Council |  | 2544000
Legal aid attorney consultations
Legal aid attorney representation for clients
Duty Counsel (people served)
Training of Police officers on Legal Aid issues & police responsibilities
Legal Aid fairs
Legal Aid Information Guide | bar: 2014 Jun to 2017 Dec
Mobile Justice unit expansion | bar: 2014 Jun to 2017 Dec
Subtotal - 1311-1312-1321-1322 - Service 3 Justices of the Peace |  | 894000
Purchase and printing of material for JP guidebook/manual (10,000 copies) | bar: 2014 Jun to 2015 Dec
Design and development of JP Directory (20,000 copies) | bar: 2014 Jun to 2015 Dec
Implementation of basic training for JPs | bar: 2015 Jan to 2018 Jun
Implementation of advanced training for JPs | bar: 2015 Jan to 2018 Jun
Parish consultations + JP recruitment | bar: 2014 Jun to 2017 Dec
JP Services provided to official justice entities (Court, police station, etc). | bar: 2015 Jan to 2018 Jun
Subtotal - 1311-1312-1321-1322 - Service 4 Dispute Resolution Foundation |  | 2430000
Training through School Suspension Intervention
Training through Young Men's Work Programme
Training for police and court officials on mediation processes
Renovations for 3 mediation service points (1 in Trench Town; 1 in Spanish town; 1 in Western Dispute) | bar: 2014 Jun to 2016 Dec
New Mediation cases in target communities
Subtotal - 1331-5 - Restorative Justice |  | 1707000
Renovations for 3 RJ service points (1 for Kingston; 1 for St. Andrew; 1 for TBD). | bar: 2014 Jun to 2016 Dec
Training for RJ officers and staff | bar: 2014 Jun to 2017 Dec
Purchase of and printing of material for sensitisation sessions (1000 individuals)
Implementation of New RJ services in target communities
Subtotal - 1311-6 - Child Diversion |  | 1605000
Implementation of Child diversion resocialisation/parish diversion committee activities
Training of court professionals and child diversion processes
Psychosocial support for Child Diversion participants
Renovations for 4 CD centres (1 in Kingston; 1 in St Andrew; 1 in St. Catherine; 1 in St. James). | bar: 2014 Jun to 2017 Dec
Sub-Component 1313: Technical assistance provided to the Social Justice Consortium (unit within MoJ) to support the manage-ment and delivery of community jus-tice services and promote human rights compliance by officials. |  | 243778
Signing of contract and initiation of Human Rights compliance consultant
Design and Implementation of Human Rights Institute workshops
Sub-Component 1323: Public education workshops and media campaign conducted to promote a rights-based culture and awareness of justice services in target communities |  | 528000
Research and printing of material for multimedia campaign
Town hall meetings/community fora | bar: 2014 Jun to 2017 Dec
Design and implementation of Multimedia campaigns (1 per year)
Research and focus groups for campaign development | bar: 2014 Jun to 2015 Dec
Media sensitisation session | bar: 2015 Jan to 2017 Dec
Transition Plan |  | 350000
Implementation of workshops for Stakeholders consultation
Signing of contract and initiation of Consultancy to assess institutional capacity | bar: 2015 Jan to 2015 Dec
Signing of contract and initiation of consultancy to develop training programmes for MDAs | bar: 2016 Jan to 2016 Dec
Capacity Building training and materials for non-MDA stakeholders | bar: 2015 Jan to 2018 Jun
MOJ Transition Plan insitutional capacity-building | bar: 2015 Jan to 2018 Jun
Programe Administration: MNS and MOJ |  | 3610000
General Administrative Services (Stationery & Office supplies, utilities, rent, general administration)
Personnel (Program Manager, Finance & Accounts, Administrative, and Documentation)
Audit
MNS and MOJ M&E |  | 3190000
PEU Client management database Software purchased; staff trained; system implemented | bar: 2014 Jun to 2014 Dec
PEU hardware purchases, software upgrades
JCO software, hardware, tech support
Contracting of 4 new staff to aid with secondary data collection by the Jamaica Crime Observatory (JCO)
Consultancy: 2 new M&E staff to design and develop M&E system
One M&E consultant to help with monitoring implementation | bar: 2014 Jun to 2015 Dec
Feasibility study conducted by M&E consultant to determine additional indicators to be collected and programs to be evaluated | bar: 2014 Jun to 2014 Dec
Elaborate Progress Monitoring Reports (1 per year)
Elaborate Project Progress Reports (1 per year)
Training in experimental evaluations of selected interventions
Design and conduct CSJP Community Survey data collection, analysis, and report publication. | bar: 2014 Jun to 2014 Dec; 2016 Jan to 2016 Dec; 2018 Jan to 2018 Jun
Women’s health survey (to assess prevalence of violence against women) | bar: 2015 Jan to 2015 Dec
Process Evaluation
Mid-term evaluation report | bar: 2014 Jun to 2014 Dec; 2016 Jan to 2016 Dec; 2018 Jan to 2018 Jun
Impact Evaluation on Parenting Program | bar: 2014 Jun to 2017 Dec
Impact Evaluation on Vocational Program | bar: 2014 Jun to 2017 Dec
Ex-post Economic Analysis | bar: 2018 Jan to 2018 Jun
Final evaluation | bar: 2016 Jan to 2016 Dec; 2018 Jan to 2018 Jun
Dissemination of knowledge and lessons | bar: 2016 Jan to 2018 Jun
Technical Advisory Team -- Consultancy - Team (International) |  | 1100000
Contingency |  | 533478
Program Total |  | 533347756
Execution

## Detalle Plan de Adquisiciones (hidden)
Programa Salud.uy
PLAN DE ADQUISICIONES
[5 empty] | OBRAS | [13 empty] | Ex-Post
[5 empty] | Unidad Ejecutora: | Actividad: | Descripción adicional: | Método de Selección/Adquisición (Seleccionar una de las opciones): | Cantidad de Lotes : | Número de Proceso: | Monto Estimado |  |  | Componente Asociado : | Método de Revisión (Seleccionar una de las opciones): | Fechas |  | Comentarios | Ex-Ante
[11 empty] | Monto Estimado, en u$s : | Monto Estimado % BID: | Monto Estimado % Contraparte: |  |  | Aviso Especial de Adquisiciones | Firma del Contrato |  | Previsto
Proceso en curso
Relicitación
[5 empty] | BIENES | [13 empty] | Proceso Cancelado
[5 empty] | Unidad Ejecutora: | Actividad: | Descripción adicional: | Método de Adquisición (Seleccionar una de las opciones): | Cantidad de Lotes : | Número de Proceso: | Monto Estimado |  |  | Componente Asociado : | Método de Revisión (Seleccionar una de las opciones): | Fechas |  | Comentarios | Declaración de Licitación Desierta
[11 empty] | Monto Estimado, en u$s : | Monto Estimado % BID: | Monto Estimado % Contraparte: |  |  | Aviso Especial de Adquisiciones | Firma del Contrato |  | Rechazo de Ofertas
| 0 | 0 | 0 | 0 | AGESIC | Licencias |  | Licitación Pública Nacional |  |  | #REF! | #REF! | #REF! |  | Ex-Post |  |  |  | Contrato En Ejecución
| 0 | 0 | 0 | 0 | AGESIC | Hardware Final |  | Licitación Pública Nacional |  |  | #REF! | #REF! | #REF! |  | Ex-Post |  |  |  | Contrato Terminado
| 0 | 0 | 0 | 0 | AGESIC | Hardware Central |  | Licitación Pública Nacional |  |  | #REF! | #REF! | #REF! |  | Ex-Post
| 0 | 0 | 0 | 0 | AGESIC | Desarrollo Solución |  | Licitación Pública Nacional |  |  | #REF! | #REF! | #REF! |  | Ex-Post
| 0 | 0 | 0 | 0 | AGESIC | Implantación/Despliegue Prot. |  | Licitación Pública Nacional |  |  | #REF! | #REF! | #REF! |  | Ex-Post |  |  |  | Comparación de precios
| 0 | 0 | 0 | 0 | AGESIC | Desarrollo Prototipo |  | Licitación Pública Nacional |  |  | #REF! | #REF! | #REF! |  | Ex-Post |  |  |  | Licitación Pública Nacional
| 0 | 0 | 0 | 0 | AGESIC | Hardware Piloto |  | Licitación Pública Nacional |  |  | #REF! | #REF! | #REF! |  | Ex-Post |  |  |  | Contratación Directa
| 0 | 0 | 0 | 0 | AGESIC |  |  | Licitación Pública Nacional |  |  | #REF! |  |  |  | Ex-Post |  |  |  | Licitación Internacional Limitada
[11 empty] | #REF! | #REF! | #REF! | [5 empty] | Licitación Pública Internacional en 2 etapas
Licitación Pública Internacional por Lotes
SERVICIOS DE NO CONSULTORÍA
[5 empty] | Unidad Ejecutora: | Actividad: | Descripción adicional: | Método de Adquisición (Seleccionar una de las opciones): | Cantidad de Lotes : | Número de Proceso: | Monto Estimado |  |  | Componente Asociado : | Método de Revisión (Seleccionar una de las opciones): | Fechas |  | Comentarios
[11 empty] | Monto Estimado, en u$s : | Monto Estimado % BID: | Monto Estimado % Contraparte: |  |  | Documento de Licitación | Firma del Contrato
| 0 | 0 | 0 | 0 | AGESIC | Serv, de Mantenimiento/Sop |  | Licitación Pública Nacional |  |  | #REF! | #REF! | #REF! |  | Ex-Ante |  |  |  | Comparación de Calificaciones
| 0 | 0 | 0 | 0 | AGESIC | Servicio de Operación |  | Licitación Pública Nacional |  |  | #REF! | #REF! | #REF! |  | Ex-Ante |  |  |  | Contratación Directa
| 0 | 0 | 0 | 0 | AGESIC | Comunicación |  | Licitación Pública Nacional |  |  | #REF! | #REF! | #REF! |  | Ex-Ante |  |  |  | Selección basada en el menor costo
| 0 | 0 | 0 | 0 | AGESIC |  |  | Licitación Pública Nacional |  |  | #REF! | #REF! | #REF! |  | Ex-Ante
| 0 | 0 | 0 | 0 | [6 empty] | #REF!
Bienes
[5 empty] | CONSULTORÍAS INDIVIDUOS Y EMPRESAS | [14 empty] | Bienes
[5 empty] | Unidad Ejecutora: | Actividad: | Descripción adicional: | Método de Adquisición (Seleccionar una de las opciones): | Número de Proceso: | Monto Estimado |  |  | Cantidad Estimada de Consultores : | Componente Asociado : | Método de Revisión (Seleccionar una de las opciones): | Fechas |  | Comentarios | Suma global | Obras
[10 empty] | Monto Estimado, en u$s : | Monto Estimado % BID: | Monto Estimado % Contraparte: |  |  |  | No Objeción a los TdR de la Actividad | Firma Contrato |  | Suma global | Obras
| 0 | 0 | 0 | 0 | AGESIC | Consultoría Requerimientos |  | Comparación de Calificaciones |  | #REF! | #REF! | #REF! |  |  | Ex-Ante |  |  |  | Suma global + Gastos Reembolsables | Consultoría - Firmas
| 0 | 0 | 0 | 0 | AGESIC | Mesa de Ayuda |  | Comparación de Calificaciones |  | #REF! | #REF! | #REF! |  |  | Ex-Ante |  |  |  | Tiempo Trabajado
| 0 | 0 | 0 | 0 | AGESIC | Gestión del Proy.-RRHH |  | Comparación de Calificaciones |  | #REF! | #REF! | #REF! |  |  | Ex-Ante
| 0 | 0 | 0 | 0 | AGESIC | Consultoría Informes Radiológicos |  | Comparación de Calificaciones |  | #REF! | #REF! | #REF! |  |  | Ex-Ante
| 0 | 0 | 0 | 0 | AGESIC | Coordinadores |  | Comparación de Calificaciones |  | #REF! | #REF! | #REF! |  |  | Ex-Ante
| 0 | 0 | 0 | 0 | AGESIC | Estándares |  | Comparación de Calificaciones |  | #REF! | #REF! | #REF! |  |  | Ex-Ante
| 0 | 0 | 0 | 0 | AGESIC | Gestión Cambio |  | Comparación de Calificaciones |  | #REF! | #REF! | #REF! |  |  | Ex-Ante |  |  |  | Adquisición de Bienes
| 0 | 0 | 0 | 0 | AGESIC | Técnicos |  | Comparación de Calificaciones |  | #REF! | #REF! | #REF! |  |  | Ex-Ante |  |  |  | Adquisición de Bienes - Sector Salud
| 0 | 0 | 0 | 0 | AGESIC | Comunicación |  | Comparación de Calificaciones |  | #REF! | #REF! | #REF! |  |  | Ex-Ante
| 0 | 0 | 0 | 0 | AGESIC | Med.Radiol. |  | Comparación de Calificaciones |  | #REF! | #REF! | #REF! |  |  | Ex-Ante |  |  |  | Comparación de Precios para Bienes
| 0 | 0 | 0 | 0 | AGESIC | Tecnico Rad. |  | Comparación de Calificaciones |  | #REF! | #REF! | #REF! |  |  | Ex-Ante |  |  |  | Especificaciones Técnicas
| 0 | 0 | 0 | 0 | AGESIC | TRM |  | Comparación de Calificaciones |  | #REF! | #REF! | #REF! |  |  | Ex-Ante |  |  |  | Suministro e instalación de plantas y equipos
| 0 | 0 | 0 | 0 | AGESIC | Tec.RRHH S.uy |  | Comparación de Calificaciones |  | #REF! | #REF! | #REF! |  |  | Ex-Ante |  |  |  | Suministro e instalación de sist. de información
| 0 | 0 | 0 | 0 | AGESIC | Estudio TIC's Salud |  | Comparación de Calificaciones |  | #REF! | #REF! | #REF! |  |  | Ex-Ante |  |  |  | Suministro e instalación de sist. de información
| 0 | 0 | 0 | 0 | AGESIC |  |  | Comparación de Calificaciones | [6 empty] | Ex-Ante |  |  |  | 3CV
[10 empty] | #REF! | [9 empty] | Consultoría - Firmas
[5 empty] | CAPACITACIÓN | [14 empty] | Consultoría - Firmas
[5 empty] | Unidad Ejecutora: | Actividad: | Descripción adicional: | Método de Adquisición (Seleccionar una de las opciones): |  | Monto Estimado |  |  |  | Componente Asociado : | Método de Revisión (Seleccionar una de las opciones): | Fechas |  | Comentarios |  | Consultoría - Individuos
[9 empty] | Número de Proceso: | Monto Estimado, en u$s : | Monto Estimado % BID: | Monto Estimado % Contraparte: |  |  |  | Aviso de Expresiones de Interés | Firma del Contrato |  |  | Consultoría - Individuos
| 0 | 0 | 0 | 0 | AGESIC | Capacitación |  | Selección Basada en la Calidad |  | #REF! | #REF! | #REF! |  |  | Ex-Ante
| 0 | 0 | 0 | 0 | AGESIC | Difusión/Capacitación |  | Selección Basada en la Calidad |  | #REF! | #REF! | #REF! |  |  | Ex-Ante
| 0 | 0 | 0 | 0 |  |  |  | Selección Basada en la Calidad | [6 empty] | Ex-Ante
[10 empty] | #REF! | [9 empty] | Bienes
Bienes
#REF! | [19 empty] | Servicios de No Consultoría
Consultoría - Firmas