|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Title | Citizen Security and Justice Program III (CSJP III) | No. | IDB JA-L1043; D-000158 DFATD | Team Leader | GoJ + IDB + DFATD + DFID |
| Country/Region | Jamaica | Budget | $53.25M US (TBC) | Duration | 5 years |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **ULTIMATE OUTCOME** | 1000 Enhanced citizen security and justice in Jamaica in target communities. | | | | | | | | | |  | | |
| 🡹 | 🡹 | | | | | 🡹 | | | |  | | | |
| **INTERMEDIATE OUTCOMES** | **Component 1: Culture change for peaceful co-existence & Community Governance**  1100 Improved behaviors for non-violent conflict resolution in target communities | | | | **Component 2: Labour Market Attachment and Employability**  1200 Increased labor market attachment\* and employability among youth in target communities  *(\*a spectrum of attachment, from employment, to pre-employment / orientation / readiness, to zero attachment)* | | | **Component 3: Community Justice Services:**  1300 Increased access to effective community and alternative justice services in target communities. | | |  | **Management, Coordination, and Monitoring/Evaluation** | |
| 🡹 | 🡹 | | | 🡹 | | 🡹 | | 🡹 | |  | | |  |
| **IMMEDIATE OUTCOMES** | 1110 Improved knowledge and attitudes of individuals, families, and groups to resolve conflicts in target communities. | 1120 Increased capacity of community governance mechanisms to address safety issues in target communities. | | | 1210 Increased vocational and cognitive skills and other job-relevant (e.g. education) credentials of target community residents | | 1220 Increased access to on-the-job training and experience for target community residents. | 1310 Increased capacity of community and alternative justice services in target communities. | 1320 Increased access by residents of target communities to community and alternative justice services. | |  | Improved coordination among MDAs for delivery and sustainability. | Improved Monitoring and Evaluation plans, processes, and info/data systems. |
| 🡹 |  | | |  | | |  |  | |  | | |  |
| OUTPUTS | 1111) Gender-responsive training provided to community members. (*Parenting; Conflict resolution)*  1112) Gender-responsive counselling / psycho-social support provided.  1113) Gang interruption activities conducted *(PMI)*  1114) Gender-responsive violence prevention and conflict resolution training provided in schools.  1115) Campaigns for awareness, attitude, and behavior change to promote ‘culture of lawfulness’ conducted (e.g. on domestic violence, guns, gender).  1116) Activities conducted to improve citizen-police interactions.  1117) Crisis intervention conducted in situations of community violence. | | 1121) Training and technical assistance provided to community leaders/residents to improve community governance structures.  1122) Gender-responsive community infrastructure expanded or renovated (multi-purpose centers, lighting) for collective use.  1123) Community safety plans (including safety audits for vulnerable groups) developed and promoted for implementation.  1124) Peace-building promoted through inclusive cultural and sporting activities.  1125) Coordination and transition activities conducted at the local level among MDAs and with CDCs/CBOs. | | 1211) Technical assistance delivered to service providers on how to apply client-centred case management to targeted beneficiaries.  1212) Job-readiness and vocational training provided to targeted beneficiaries.  1213) Support for access to secondary and tertiary education provided to selected beneficiaries.  1214) Remedial education, including literacy and numeracy, provided in or outside communities, with integrated socio-emotional and life-skills training and gender-responsive design and delivery. | | 1221) Gender-responsive job-seeking, placement, and training services provided to target beneficiaries.  1222) On-the-job or work orientation apprenticeship/internships provided for youth, with gender-responsive design, emphasis on life skills, and focus on high-demand occupations (e.g. JDF, Police Cadets, summer employment, employment internships).  1223) Business development services (e.g. support for market studies, business plans, access to funding, and links to private sector) provided for community residents in entrepreneurship, with emphasis on high-demand sectors | 1311) Technical assistance and resources provided to community justice service entities:  - Victim Support Unit  - Legal Aid Council  - Justices of the Peace  - Dispute Resolution Foundation  - Restorative Justice  - Child Diversion  1312) Training provided to community volunteers, facilitators, and leaders involved in community justice service delivery:  (same list as 1311)  1313) Technical assistance provided to the Social Justice Consortium (a unit within MoJ) to support the management and delivery of community justice services. | 1321) Sensitization training and material provided to target community residents and justice system officials on community justice services.  1322) Community justice service points improved (including mobile units) that are accessible to target communities.  1323) Public education/outreach campaigns conducted to promote a rights-based culture and awareness of justice services in target communities. | |  | 1) Technical assistance strategic and budget planning for all MDAs involved in transition plan  2) Sensitization and training of staff in all MDAs involved in transition plan  3) Coordination activities to ensure links between national, parish, and community level MDAs and organizations  4) Promotion/branding of CSJP as a GoJ initiative | 1) Collection & disaggregation of Baseline data for indicators.  2) Technical assistance on implementing the M&E plan.  3) Info system upgrades, integration, and staff training provided for data collection, management, and reporting systems in PEU & MDAs.  3) Technical assistance for improving monitoring systems & reporting templates at all levels  4) Hiring & implementation of Program Evaluation team (outcomes, objectives, process, implementation).  5) Hiring & implementation of Technical Expert and Advisory Team (not evaluation)  6) Hiring & implementation of impact evaluation (experimental evaluation of select interventions)  7) Events and publications to disseminate knowledge |

*Please note:* ***Gender-responsive*** *is an approach that assesses the different needs and interests of women and men, girls and boys, as well as the different impact of initiatives on women and men, girls and boys, and develops programming that responds to these so that neither women nor men, girls or boys, are disadvantaged from the initiative and the gap in access and control can be reduced. Gender responsive approaches can also promote empowerment of women by recognizing the important role they play, creating awareness of the rights of women, and increasing women in decision-making at all levels. There is a best practice that involves men in addressing gender-based violence and a culture of violence.*