- Results Matrix

- The general objective is to enhance citizen security and justice in Jamaica in target communities. The specific objectives are to: (i) improve behaviors for non-violent conflict resolution in target communities; (ii) increase labor market attachment among youth; and (iii) increase access to effective community and alternative justice services.

| INDICATORS | UNIT OF MEASURE | BASELINE |  |  | Mid-Term |  | TARGET |  | MEANS of VERIFICATION | OBSERVATIONS |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Value |  | Year | Value | Year | Value | Year |  |  |  |  |  |
| EXPECTED IMPACT: Enhanced citizen security and justice in target communities. (ULTIMATE OUTCOME 1000) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Murders in CSJP target communities. | Annual rate per 100,000 residents | 50.5 | 2012 |  | 45.5 | 2016 | 40.4 | 2018 | Sources: - Jamaica Crime Observatory Integrated Crime and Violence Information System (JCO-ICVIS) - MNS - Population estimates compiled based on SDC numbers. Means: Analysis of data and construction of rates Frequency: Annual Responsibility: MNS | The Baseline is computed by dividing the number of reported homicides in CSJP target communities in 2012 (178) by the total population of the CSJP communities combined (352,690) and multiplying the result by 100,000. (50.46 is rounded to 50.5) The target is estimated based on the decline in the national murder rate from 2009 to 2012: from 62.76 to 40.14, or a 36% decline (using JCF murder incidents and STATIN mid-year population). However, this trend is levelling off (4.3% decline from 2011 to 2012), so the target for 2018 is estimated more modestly (20% of 50.5 is 10.1, which leads to a target rate of 40.4). The rate in CSJP communities will likely continue to be higher than the national rate, but the decline trend may be steeper. The population of CSJP communities is 352,690 (excluding 4 communities for which population data is not currently available). This is approx. 13% of the 2012 national population (STATIN end-year figure). |  |  |  |
| - Shootings in parishes with CSJP target communities. | Annual rate per 100,000 residents | 53 | 2012 |  | 46.3 | 2016 | 39.5 | 2018 | Sources: - Jamaica Constabulary Force Monthly & Annual Statistics Report - STATIN 2012 mid-year population Means: Analysis of data and construction of rates Frequency: Annual Responsibility: MNS | The Baseline is computed by dividing the number of reported shootings in parishes with CSJP target communities in 2012 (1,084) by the total population of the parishes (2,044,874), and multiplying the result by 100,000. 53.01 is rounded to 53. The target is estimated based on the decline in the national shooting rate from 2009 to 2012: 62.13 to 45.2, or a 27% decline (using JCF shooting incidents and STATIN mid-year population) However, this trend is levelling off (10% decline from 2011 to 2012), so the target for 2018 is estimated more modestly (20% of 53 is 10.6, which leads to a target rate of 42.6). The rate in CSJP communities will likely continue to be higher than the national rate, but the decline trend may be steeper. The CSJP community population (352,690) represents 17% of the total population of the 8 parishes (2,044,874). |  |  |  |
| - Perception of safety at night by residents in CSJP target communities. | % of respondents. | 74 | 2012 |  | 76.5 | 2016 | 79.1 | 2018 | Source: CSJP Community Survey (2012, 2014, 2016, 2018) Means: Analysis of data and construction of rates Frequency: Bi-annual Responsibility: MNS | This baseline data was calculated based on the proportion of respondents answering a) or b) to the following CSJP Community Survey question: “How safe do you feel walking alone in your community after dark? Do you feel…?” a) Very safe; b) Safe; c) Unsafe; d) Very unsafe; e) Don’t know; f) Refused. The target is estimated from JNCVS data because it covers more years than the CSJP Survey. In the JNCVS, there is a decline in the respondents who feel unsafe at night in their communities: 23.5% in 2009 and 20.9% in 2012. The target for the perception of safety is calculated by assuming that the remainder of JNCVS respondents in this question (76.5% in 2009 and 79.1% in 2012) feel safe or very safe. The trend here is calculated based on the JNCVS data: an increase of 3.4% of the 2009 figure over three years. The target for 2018 is calculated by increasing the 2012 baseline (74%) by 7% (twice the 3-year trend), which is 79.1%. |  |  |  |
| - Perception that the courts provide justice quickly and help crime victims. | % of respondents | 15.5 | 2012 |  | 19.375 | 2016 | 24.2 | 2018 | Source: Jamaica National Crime Victimization Survey (2012, 2015) Means: Analysis of data and construction of rates Frequency: Every three years Responsibility: MNS | This data was calculated based on the % of respondents who answered “a good job” to 2 questions (average % of the 2 questions): Q1: Are the courts providing justice quickly? Q2: Are the courts helping victims? The target is estimated based on the trend from 2009 (12.4% average (12.1% for Q1; 12.7% for Q2)) to 2012 (15.5% for each question): a 25% increase over three years; this trend is calculated for 2012 to 2016 and again for 2016 to 2018. (JNCVS 2012, p. 262). |  |  |  |
| OUTCOMES FOR COMPONENT 1: CULTURE CHANGE & COMMUNITY GOVERNANCE |  |  |  |  |  |  |  |  |  |  |  |  |  |
| RESULT 1.: Improved behaviors for non-violent conflict resolution in target communities (INTERMEDIATE OUTCOME 1100) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Target communities with gang interruption activities that achieved ceasefire agreements that were sustained for at least 6 months. | % of communities | 0 | 2012 |  | 58 | 2016 | 60 | 2018 | Sources: PEU Database; Activity pre/post survey (PMI project reports to PEU) Means: Analysis of data and construction of rates. Frequency: Annual Responsibility: MNS | The baseline is 0 because this intervention refers to new communities. The estimated target is based on PMI's project reports covering the period 2008-2012: 25 out of 44 communities in which PMI intervened (not all are CSJP communities), or 57%, achieved ceasefire agreements lasting at least six months and with independent verification. The PMI definition of a ceasefire agreement is “mutual understanding reached between groups involved in violent conflict to suspend shootings.” This may be formal (written) or informal; both types of agreements require minimum validation through a written statement by the head of the local police division. The target is estimated to be approximately the same, in new communities, i.e. 30 out of 50 CSJP communities (60%). |  |  |  |
| - Persons who reportedly avoided certain areas of their own community because of fear of crime (in CSJP target communities). | % of respondents | 22 | 2012 |  | 20 | 2016 | 18 | 2018 | Sources: CSJP Community Surveys (2012, 2014, 2016, 2018). Means: Analysis of data and construction of rates Frequency: Bi-annual Responsibility: MNS | The estimate is based on the question about personal safety tactics in the 2012 CSJP Community Survey (Question: “Are there areas within [name of community] that you avoid for fear of being victim of a crime?” Answer: Yes (List areas); No; Refused.) The target is to decrease the measure by 18% of the baseline by the end of the project. This is based on the difference between the 2009 and 2012 JNCVS respondents who report avoiding certain areas of their city or town due to fear of crime: 36% to 32.9%, or a 9% decrease over three years (18% over the project duration.) This indicator speaks to mobility of residents due to crime dynamics, not fear of crime per se. |  |  |  |
| - Witnesses to crime who talked to police about the last crime they witnessed in their community in the past year (in CSJP target communities). | % of respondents | 21 | 2012 |  | 24 | 2016 | 27 | 2018 | Sources: CSJP Community Surveys (2012, 2014, 2016, 2018). Means: Analysis of data and construction of rates Frequency: Bi-annual Responsibility: MNS | This indicator reflects a change in behaviour (talking to police) due to change in knowledge and attitudes about snitching (through campaigns challenging “anti-informer” views). The indicator is based on the CSJP Community Survey Question (2012): “Think about the last time you say any of the crimes mentioned in your community. Did you talk to the police about what you saw?” Answers: Yes, No, Refused. The target is to increase the measure by 30% of the baseline by the end of the project. According to the CSJP Survey, this indicator rose from 14% to 21% from 2011 to 2012 (50% increase). The target estimate is somewhat more conservative. |  |  |  |
| - Use of coercive parenting strategies by participants in target communities. | % of respondents | TBD | 2014 |  | TBD | 2016 | -10% | 2018 | Source: Activity pre/post surveys Means: Impact evaluation carried out on the parenting course intervention (see M&E Plan); Analysis of data Frequency: Annual Responsibility: MNS | The baseline is estimated based on the 2008-2009 Jamaica Reproductive Health Survey: 69% of parents reported hitting (with or without an object) or spanking their child. The target is estimated based on the effect size found in an evaluation of the Triple-P System (parenting): a 22% reduction in a validated scale measuring parental overreactivity in an RCT in Australia (Morawska, A. et al 2010. As limited data are available from a developing country using this intervention, we are setting a conservative target of a 10% decrease in coercive parenting. |  |  |  |
| - CDC Community Safety Plans in target communities that include findings from women’s safety audits and action plans to address the findings. | % of CDC safety plans | 0 | 2012 |  | 50 | 2016 | 100 | 2018 | Sources: PEU Database; Activity pre/post surveys; CDC reports. Means: Analysis of data and construction of rates Frequency: Bi-annual Responsibility: MNS | Out of the 50 CSJP communities, 9 have community safety plans, but none of these include analysis or recommendations from women’s safety audits, which address both physical and social risk factors. (Whitzman et al 2009; UN Habitat, 2008) The target is that all the CSJP communities have safety plans integrating this type of information. |  |  |  |
| OUTCOMES FOR COMPONENT 2: LABOUR MARKET ATTACHMENT* AND EMPLOYABILITY |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Result 2: Increased labour market attachment among youth of target communities. (INTERMEDIATE OUTCOME 1200) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Group 1 (most job-ready) participants who obtain a job through services / support. | % of total participants in this group | 10 | 2013 |  | 12.5 | 2016 | 15 | 2018 | Sources: PEU Database; Activity pre/post surveys Means: Review of data; Impact evaluation (see M&E Plan) Frequency: Semi-Annual Responsibility: PEU | Baseline is according to current PEU records (Estimated Group 1 - 120 out of 1200). PEU records from the previous phase show a 25% increase over 1 year from 2012 (16.4%, or 130 out of 802) to 2013 (20% or 178 out of 883). The target is to increase the measure by 50% of the baseline by the end of the project (10% of graduates to 15%), which is more conservative than the 1-year trend from PEU data. |  |  |  |
| - Group 1 and 2: beneficiaries receiving support who are in their final year and complete secondary or tertiary education. | % of total participants in this group | 90 | 2013 |  | 90 | 2016 | 90 | 2018 | Sources: PEU Database; Activity pre/post surveys Means: Review of quantitative data Frequency: Semi-Annual Responsibility: PEU | Baseline is according to current PEU records (Estimated Group 1 - 1370 out of 1523). The target is to maintain the graduation baseline throughout the project. There is no PEU trend data for this indicator. This is a conservative target, since the baseline is already quite high – higher in fact than the average secondary graduation rate in Jamaica (84.7% of students who entered grade 7 in 2008-09 graduated secondary school in 2012-13, according to the Min.Ed). (Graduation is not the same as the more rigorous standard of passing five or more CXC subjects (including English and math); 15% of students achieved this in 2011 (Min Ed).) |  |  |  |
| - Group 2 (intermediate job-readiness) for HEART-certified Level 1 & 2 participants who move to Level 3. | % of total participants in this group | 25 | 2013 |  | 37.5 | 2016 | 56 | 2018 | Sources: PEU Database; Activity pre/post surveys Means: Review of quantitative data Frequency: Semi-Annual Responsibility: PEU | Baseline is according to current PEU records (Estimated Group 2 - 176 out of 705) (includes HEART participants). The trend data from the PEU records shows a 58% increase over 2 years: 15.8% in 2011 (143/900) to 25% in 2013. Maintaining a more conservative trend (baseline increases by 50% for the first two years, repeated again for the second two years), the target is 56% completion. Level 1 produces a semi-skilled worker, Level 2 produces a skilled worker, and Level 3 produces technicians, supervisors and own-account workers (McArdle 2013). (Data is captured the year after a trainee completes the previous level; i.e. 2012 graduates who move to the next level in 2013 are listed in 2013 data). |  |  |  |
| - Group 3 (low job-readiness) pre-vocational participants who pass the eligibility test for HEART level 1. | % of total participants in this group | 45 | 2013 |  | 54 | 2016 | 64 | 2018 | Sources: PEU Database; Activity pre/post surveys Means: Review of quantitative data Frequency: Semi-Annual Responsibility: PEU | Baseline is according to current PEU records (Estimated Group 3 - 93 out of 206). The data from PEU records shows: 37.8% (84/222) in 2012 to 45% in 2013, or 20% of the baseline in one year. Maintaining a more conservative trend (20% increase in the first two years, then again in the second two years), the target is 64% completion. This test is approximately equivalent to grade 9 literacy and numeracy. |  |  |  |
| - New community enterprises that are still in operation at least one year after receiving support (e.g. training, grant). | % of new businesses | 0 | 2013 |  | 20 | 2016 | 40 | 2018 | Sources: PEU Database; Activity pre/post surveys Means: Review of quantitative data Frequency: Semi-Annual Responsibility: PEU | Baseline is estimated at 0 because there are currently no community enterprises supported through this type of program. The target is to increase the measure to 50% of new businesses by the end of the project. This is estimated based on similar programmes (financial- and non-financial support) funded by the IDB in Peru, with an emphasis on youth: 65% of youth beneficiaries’ new businesses were still in operation one year after the intervention. However, given the economic situation in Jamaica, the target estimate is lower (50%) (RTI 2012). |  |  |  |
| OUTCOMES FOR COMPONENT 3: COMMUNITY JUSTICE SERVICES |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Result 3: Increased access to effective community and alternative justice services in target communities (INTERMEDIATE OUTCOME 1300) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - New mediation cases settled in target communities. | % of new cases settled | 0 | 2013 |  | 30 | 2016 | 67 | 2018 | Sources: PEU Database; MoJ records; Activity pre/post surveys Means: Review of quantitative data Frequency: Annual Responsibility: PEU & MoJ | Baseline is estimated on the assumption that the settlement rate for mediation cases (new) in target communities will be similar to the current national average In 2012, the Dispute Resolution Foundation (which conducts mediation for MoJ) settled 938 out of 1434 cases in which mediation was conducted – a 65% rate. The aim is to achieve a 67% settlement rate in areas currently underserved by mediation services. The output target for number of new cases is 1250. |  |  |  |
| - Restorative justice cases in which an agreement is reached (in target communities). | % of cases | 0 | 2013 |  | 20 | 2016 | 50 | 2018 | Sources: PEU Database; MoJ records; Activity pre/post surveys Means: Review of quantitative data Frequency: Annual Responsibility: PEU & MoJ | Agreement refers to the signing of a formal "restorative justice agreement," as defined in the MoJ RJ Policy (2012), using the form in Appendix 11. This is signed, at minimum, by the offender (or parent/guardian), the victim (or parent/guardian or representative), the facilitator, and, where appropriate, a community representative. The baseline is zero as this is a new program (launched in 2012; 46 cases are underway but none are completed). The target is estimated based on RJ processes in South Africa: Two programmes reached agreements in 80% and 90% of cases, respectively. (Monaghan 2008) Since RJ is new in Jamaica, the target is more conservative (50% out of an output target of 500 new cases). |  |  |  |
| - Juveniles selected for the Child Diversion Program (in pilot locations) who complete the requirements. | % of juveniles | 0 | 2013 |  | 40 | 2016 | 75 | 2018 | Sources: PEU Database; DCS & MoJ records; Activity pre/post surveys Means: Review of quantitative data Frequency: Annual Responsibility: PEU & MoJ | ### Baseline is zero because Child Diversion is a new program beginning in 2014. It is expected that the program will serve 200 new participants by 2018 (see output target). The Child Diversion Programme will cover 4 pilot parishes (the KMA and surrounding area) and juveniles in conflict with the law for minor offences (see POD) will be eligible at the pre-charge, pre-prosecution, pre-sentence, and post-adjudication stage. The program consists of community service work and treatment programs (individualized) for 12 months, under the supervision of a Parish Diversion Committee, and MoJ and DCS. The target for completing requirements of CD is based on data from Jamaica (1995) that 91% of adults sentenced to community service orders completed requirements (UNICEF Juvenile Justice Portfolio, Case Studies). The 75% target is more conservative because this is a new program dealing with juveniles. |  |  |  |

| OUTPUTS |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| OUTPUT | UNIT of MEASURE | BASELINE (Year) | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Program End Target | Source of Information & Means of Verification |
| COMPONENT 1 (Approx $15,934,750) |  |  |  |  |  |  |  |  |  |
| Sub-component 1.1 |  |  |  |  |  |  |  |  |  |
| 1111) Training courses provided to community members on parenting. | # of parenting courses | 70 (2013) | 25 | 25 | 25 | 25 | 25 | 125 | Source: PEU Database Note: Under CSJP III, longer, more intensive, evidence-based courses will be delivered to a smaller group. Therefore the number of beneficiaries served per year will be less than in CSJP II. Estimate: 50 participants / course; 1 course / year, in 25 communities. |
| 1111) Training courses provided to community members on healthy gender norms. | # of Men with a Message & Women Empowerment events | 20 (2013) | 30 | 30 | 45 | 30 | 15 | 150 | Source: PEU Database |
| 1112) Counselling / psycho-social support provided to victims/witnesses of violence (including domestic violence). | # of sessions | 775 (2013) | 70 | 70 | 105 | 70 | 35 | 350 | Source: PEU Database Note: Includes 250 individual sessions and 100 group sessions (2 per community per year) plus treatment, tests, instruments, and 2 psychologist staff. |
| 1113) Violence interruption services provided (e.g. gang interruption). | # of communities in which violence interruption is offered for at least 6 months | 4 (2012) | 10 | 10 | 10 | 10 | 10 | 50 | Source: PEU Database. This does not include "unexpected" flare-up locations where rapid-response is needed - see 1117). Assuming 10 workshops per community per year. The intent is to increase the scope & resources for this activity, compared to CSJPII. This cost includes staff and organizational resources (e.g. PMI). “Violence interruption” refers to the PMI model: workshops with gang-involved youth (and other actors), off-site retreat and mediation sessions, interventions to prevent retaliatory shootings, trauma counselling, ceasefire agreements, etc. |
| 1114) Violence prevention and conflict resolution education and training provided in schools. | # of workshops | 40 (2012) | 50 | 50 | 70 | 50 | 30 | 250 | Source: PEU Database. Note: This is assuming 25 schools with 2 workshops each / year. Includes instructors. |
| 1115) Social marketing for awareness and attitude change to promote ‘culture of lawfulness’ (e.g. to address violent gender norms, anti-snitch culture). | # of campaigns developed & delivered | 2 (2012) | 1 | 1 | 1 | 1 | 1 | 5 | Source: PEU Database. Note: Includes 1 media campaign per year (total 5), 10 workshops per year (total 50), 4 software programs, and 3 staff. |
| 1116) Community events to improve citizen-police relations conducted. | # of events | 18 (2012) | 4 | 4 | 4 | 4 | 4 | 20 | Source: PEU Database |
| 1117) Crisis intervention activities conducted (including but not limited to violence and gang interruption). | # of interventions | 10 (2012) | 10 | 10 | 10 | 10 | 10 | 50 | Source: PEU Database. Note: The quantity of interventions may be scaled up or down depending on needs per situation (unpredictable). Crisis intervention activities vary according to the situation, but typically include: mediation and retaliation intervention (by PMI), victim support services (by MNS-VSU), community workshops (by appropriate CBO). |
| Satisfaction surveys conducted and monitored for each type of training or intervention. | # of interventions with satisfaction survey systems active | 0 | 8 | 8 | 8 | 8 | 8 | 40 | Source: PEU Database, based on service provider reports that survey systems are in place and responses are submitted. The number of interventions (8) in this sub-component refers to the general interventions in the RM; specific sub-activities may implement specific surveys. |
| Women’s Health Survey (incl a module on violence against women) designed and implemented. | # of surveys | 0 | n/a | 1 | n/a | n/a | See notes | 1 | Source: PEU Database. Note: the most recent Reproductive Health Survey was 2008-2009. The POD proposes that the GOJ will conduct another in 2018, using government funds. |
| Feasibility study designed & implemented by M&E consultant to determine add’l indicators to be collected & programs to be evaluated (Comp 1). | # of studies | 0 | 1 | n/a | n/a | n/a | n/a | 1 | Source: Final Report. For additional information see section 2.3.7. of M&E Plan (Required Link #3). |
| Information system constructed and implemented to disaggregate the statistical data for Comp 1 by age, sex, community, risk profile, and other factors | # of systems | 0 | 1 | n/a | n/a | n/a | n/a | 1 | Source: Final Report. For additional information see section 2.3.6. of M&E Plan (Required Link #3). |
| Sub-component 1.2 |  |  |  |  |  |  |  |  |  |
| 1121) Training and technical assistance provided to community leaders and residents to improve community governance capacity on needs assessment and strategic planning. | # of Community Profile trainings provided | 0 (2013) | 6 | 6 | 9 | 6 | 3 | 30 | Source: PEU Database. Note: 20 Profiles already exist (recent versions), so there are only 30 that to be developed or updated. |
| 1121) Training and technical assistance provided to community leaders and residents to improve community governance capacity on operations. | # of CDCs receiving operations training | 7 (2013) | 10 | 10 | 10 | 10 | 10 | 50 | Source: PEU Database. Note: The activity is training but the most concrete output is operational capacity as defined by benevolent society status. With 35 CDCs already at this status, 15 are remaining. Aim: 3 per year. (This output is derived from operational capacity training). |
| 1122) Community infrastructure (situational crime prevention project and multi-purpose centres) built or renovated. | # of small infrastructure (situational crime prevention) projects and multi-purpose centers | 6 (2013) | 3 | 3 | 4 | 3 | 2 | 15 | Source: PEU Database. Includes 10 small infrastructure projects, 5 multi-purpose centers, and 2 staff. Note: Situational crime prevention projects include lighting, fencing, etc. |
| 1123) Community safety plans developed with safety audits for vulnerable groups. | # of community safety plans developed that include women’s and children’s safety audits | 0 (2013) | 8 | 8 | 10 | 8 | 6 | 40 | Source: PEU Database. Note: There are currently 9 community safety plans, but none with women’s and children’s safety audits. |
| 1123) Advocacy campaigns developed and implemented for community safety plans. | # of advocacy campaigns by CDCs on community safety plan implementation | 0 (2013) | 4 | 4 | 4 | 4 | 4 | 20 | Source: PEU Database. Note: Campaigns could be aimed at residents, at local government, or at other key actors. |
| 1124) Peace-building through cultural and sporting activities. | # of cultural/ sporting events with peace messages held | 12 (2013) | 5 | 5 | 5 | 5 | 5 | 25 | Source: PEU Database. Note: Some of these events will be delivered through Goals 4 Life programmes. |
| 1125) Coordination at the local level among MDAs and with CDCs/CBOs. | # of events held to facilitate coordination | 10 (2013) | 10 | 15 | 10 | 10 | 5 | 50 | Source: PEU Database. |
| Satisfaction surveys conducted and monitored for each type of training or intervention. | # of interventions with satisfaction survey systems active | 0 | 7 | 7 | 7 | 7 | 7 | 35 | Source: PEU Database, based on service provider reports that survey systems are in place and responses are submitted. The number of interventions (7) in this sub-component refers to the general interventions in the RM; specific sub-activities may implement specific surveys. |
| COMPONENT 2 (Approx $15,829,750) |  |  |  |  |  |  |  |  |  |
| Sub-component 2.1 |  |  |  |  |  |  |  |  |  |
| 1211) Technical assistance delivered on case management system for job training / placement. | # of workshops | 0 (2013) | 12 | 8 | 0 | 0 | 0 | 20 | Source: PEU Database. Note: All staff should be trained on this system in the first year. |
| 1212) Vocational training provided to targeted beneficiaries. | # of workshops | n/a | 40 | 60 | 40 | 40 | 20 | 200 | Source: PEU Database. Note: This assumes 200 positions per year (ongoing and new; 100 male and 100 female). In year 2, there will be 300 positions (150 male, 150 female); this cohort will be used for the impact evaluation treatment group (stratified selection). Costs of curriculum, instructors, etc. are included in the cost per workshop. Baseline for 2012: 490 male & 300 female. |
| 1213) Support for access to tertiary education provided to male beneficiaries. | # of males attending tertiary school due to scholarships | 183 (2013) | 36 | 36 | 27 | 26 | 0 | 125 | Source: PEU Database. 2nd year cohort will be used for impact evaluation treatment group. |
| 1213) Support for access to tertiary education provided to female beneficiaries. | # of females attending tertiary school due to scholarships | 397 (2013) | 36 | 36 | 27 | 26 | 0 | 125 | Source: PEU Database. 2nd year cohort will be used for impact evaluation treatment group. |
| 1213) Support for access to secondary education provided to male beneficiaries. | # of male students attending secondary school due to scholarships | 245 (2013) | 101 | 101 | 87 | 86 | 0 | 375 | Source: PEU Database. Due to reduced resources for this activity compared to CSJP II, fewer students will benefit than in 2013. |
| 1213) Support for access to secondary education provided to female beneficiaries. | # of female students attending secondary school due to scholarships | 335 (2013) | 101 | 101 | 87 | 86 | 0 | 375 | Source: PEU Database. Due to reduced resources for this activity compared to CSJP II, fewer students will benefit than in 2013. |
| 1214) Remedial education provided in or outside communities, with integrated and life-skills training for male participants. | # of male participants | 222 (2013) | 150 | 150 | 150 | 150 | 150 | 750 | Source: PEU Database. Note: This includes curriculum delivery, workshop delivery, instructors, etc (through service providers). |
| 1214) Remedial education provided in or outside communities, with integrated and life-skills training for female participants. | # of female participants | 197 (2013) | 150 | 150 | 150 | 150 | 150 | 750 | Source: PEU Database. Note: This includes curriculum delivery, workshop delivery, instructors, etc (through service providers). |
| Satisfaction surveys conducted and monitored for each type of training or intervention. | # of interventions with satisfaction survey systems active | 0 | 8 | 8 | 8 | 8 | 8 | 40 | Source: PEU Database, based on service provider reports that survey systems are in place and responses are submitted. The number of interventions (8) in this sub-component refers to the general interventions in the RM; specific sub-activities may implement specific surveys. |
| Feasibility study designed & implemented by M&E consultant to determine add’l indicators to be collected & programs to be evaluated (Comp 2) | # of studies | 0 | 1 | n/a | n/a | n/a | n/a | 1 | Source: Final Report. For additional information see section 2.3.7. of M&E Plan (Required Link #3). |
| Information system constructed and implemented to disaggregate the statistical data for Comp 2 by age, sex, community, risk profile, and other factors | # of systems | 0 | 1 | n/a | n/a | n/a | n/a | 1 | Source: Final Report. For additional information see section 2.3.6. of M&E Plan (Required Link #3). |
| Sub-component 2.2 |  |  |  |  |  |  |  |  |  |
| 1221) Job-seeking, placement, and training services provided to target beneficiaries. | # of participants who received job-seeking/placement services | 200 (2013) | 100 | 100 | 150 | 100 | 50 | 500 | Source: PEU Database. Includes 10 job expos (approx. 2 per year). |
| 1222) On-the-job or work orientation apprenticeship/internships provided for male youth, with emphasis on life skills and high-demand occupations. | # of male participants placed in positions | 587 (2013) | 100 | 100 | 100 | 100 | 100 | 500 | Source: PEU Database. Note: Breakdown by Program for 2013: JDF: 440; Cadet: 45; Summer Employment: 90; Internship: 57. |
| 1222) On-the-job or work orientation apprenticeship/internships provided for female youth, with emphasis on life skills and high-demand occupations. | # of female participants placed in positions | 323 (2013) | 100 | 100 | 100 | 100 | 100 | 500 | Source: PEU Database. Note: Breakdown by Program for 2013: JDF: 23; Cadet: 45; Summer Employment: 181; Internships: 119. |
| 1223) Business development services provided for community residents in entrepreneurship; emphasis on high-demand sectors. | # of small business grants disbursed to community members | 0 (2013) | 4 | 4 | 6 | 4 | 2 | 20 | Source: PEU Database. Includes, for example, support for market studies, business plans, access to funding, and links to private sector. |
| Satisfaction surveys conducted and monitored for each type of training or intervention. | # of interventions with satisfaction survey systems active | 0 | 4 | 4 | 4 | 4 | 4 | 20 | Source: PEU Database, based on service provider reports that survey systems are in place and responses are submitted. The number of interventions (4) in this sub-component refers to the general interventions in the RM; specific sub-activities may implement specific surveys. |
| COMPONENT 3 (Approx. $12,799,778) |  |  |  |  |  |  |  |  |  |
| Sub-Component 3.1 |  |  |  |  |  |  |  |  |  |
| 1300) Victim Services expanded and serving new clients in target communities. | # of new clients in Victim Services | 0 (2013) | 572 | 572 | 572 | 572 | 572 | 2860 | PEU database, with MOJ data. This includes 100 children. Baseline is 0, ref. only to new clients, beyond existing service levels. |
| 1300) Dispute Resolution Foundation services expanded and serving new clients in target communities. | # of new clients in Dispute Resolution Foundation | 0 (2013) | 1020 | 1020 | 1020 | 1020 | 1020 | 5,100 | PEU database, with MOJ data. This includes 300 in the Young Men's Work program and 4,800 in the School Suspension Intervention program. Baseline is 0, ref. only to new clients, beyond existing service levels. |
| 1300) Dispute Resolution Foundation services expanded and conducting new mediation cases in target communities. | # of new mediation cases in target communities. | 0 (2013) | 250 | 250 | 250 | 250 | 250 | 1250 | PEU database, with MOJ data. Baseline is zero, referring only to new cases, beyond existing service levels. Target is estimated based on Dispute Resolution Foundation records and track record: for comparable resources, it can attend to approx 5 additional cases per community per year in vulnerable urban communities. This is 250 cases per year (5 x 50 communities) x 5 yrs. |
| 1300) Child Diversion pilot designed and operational in target communities. | # of new participants in Child Diversion | 0 (2013) | 40 | 40 | 40 | 40 | 40 | 200 | PEU database, with MOJ data. This covers only the CD pilot locations. Baseline is zero because this is a new program. |
| 1300) Restorative Justice services designed and operational in target communities. | # of new Restorative Justice cases in target communities | 46 (2013) | 80 | 120 | 140 | 90 | 70 | 500 | PEU database, with MOJ data. Baseline refers to the new cases opened with CSJP funds in 2013 (10 communities). Target is estimated based on MoJ records: for approx. double the resources, the # of cases double, about 5 cases per community per year, in 20 target communities. |
| 1311) Technical assistance and resources provided to Victim Services entities. | Victim Services Unit: # of new TA sessions | 0 (2013) | 3 | 3 | 3 | 8 | 8 | 25 | Source: MOJ Reports; PEU Database. Technical assistance products include, for example, methodology and curriculum design and guides, workshop design, etc. |
| 1311) Technical assistance and resources provided to Legal Aid Council. | Legal Aid Council: # of people trained | 0 (2013) | 60 | 60 | 60 | 60 | 60 | 300 | Source: MOJ Reports; PEU Database. |
| 1311) Technical assistance and resources provided to Justices of the Peace service entities. | Justices of the Peace: # of new JPs trained | 0 (2013) | 116 | 116 | 116 | 116 | 116 | 580 | Source: MOJ Reports; PEU Database. The target includes 500 basic training and 80 advanced training. |
| 1311) Technical assistance and resources provided to DRF for training police & justice officials. | DRF: # of police & court officials trained | 0 (2013) | 40 | 40 | 40 | 40 | 40 | 200 | Source: MOJ Reports; PEU Database. |
| 1311) Technical assistance and resources provided to Restorative Justice Programme. | RJ: # of officers & staff operating | 3 (2013) | 4 | 4 | 4 | 4 | 4 | 16 | Source: MOJ Reports; PEU Database. The target includes 10 officers and 5 staff. |
| 1311) Technical assistance and resources provided to Child Diversion Programme. | CD: # of court professionals trained | 0 (2013) | 40 | 40 | 40 | 40 | 40 | 200 | Source: MOJ Reports; PEU Database. |
| 1312) Training provided to volunteers & facilitators, and leaders in community justice services. | # of volunteers (including facilitators) trained | 120 (2013) | 50 | 50 | 50 | 50 | 50 | 250 | MOJ Reports; PEU Database. Breakdown: VSU: 500 volunteers (baseline 0); DRF: 360 facilitators (baseline 0); RJ: 250 facilitators (baseline 120); CD: 70 committee members (baseline 0) |
| 1313) Technical assistance provided to the Social Justice Consortium (within MoJ) to support delivery of services and human rights compliance. | # workshops given to government officials | 0 (2013) | 40 | 40 | 40 | 40 | 40 | 200 | MOJ Reports; PEU Database (amount includes Human Rights compliance consultant |
| Feasibility study designed & implemented by M&E consultant to determine add’l indicators to be collected & programs to be evaluated (Comp 3) | # of studies | 0 | 1 | n/a | n/a | n/a | n/a | 1 | Source: Final Report. For additional information see section 2.3.7. of M&E Plan (Required Link #3). |
| Information system constructed and implemented to disaggregate the statistical data for Comp 3 by age, sex, community, risk profile, and other factors | # of systems | 0 | 1 | n/a | n/a | n/a | n/a | 1 | Source: Final Report. For additional information see section 2.3.6. of M&E Plan (Required Link #3). |
| Sub-Component 3.2 |  |  |  |  |  |  |  |  |  |
| 1321) Sensitization training and material provided to target community residents and justice system officials on community justice services. | # of events | 0 | 5 | 5 | 5 | 5 | 5 | 25 | MOJ Annual Report; DRF Annual Reports and Case reports. Includes 1 Legal Aid fair per year and 4 sensitization workshops per year (100 people per workshop). |
| 1322) Service points expanded/renovated; mobile service units provided in target communities. | # of service points expanded / made mobile | 7 (2013) | 3 | 4 | 4 | 4 | 3 | 18 | MOJ Reports; PEU Database. RJ currently has 7 service points. The target is to have 3 expanded service points for mediation, 3 new service points for RJ, 4 expanded service points for child diversion, and 1 mobile unit for legal aid (18 operational per year of the project). |
| 1323) Outreach conducted (rights-based culture and awareness of services) in target communities. | - # of campaigns | 0 (2013) | 1 | 1 | 1 | 1 | 1 | 5 | MOJ Reports; PEU Database. Includes 2 workshops per year. |
| Satisfaction surveys conducted and monitored for each type of training or intervention. | #of interventions with satisfaction survey systems active | 0 | 16 | 16 | 16 | 16 | 16 | 80 | Source: PEU Database, based on service provider reports that survey systems are in place and responses are submitted. The number of interventions (16) in these 2 sub-components refers to the general interventions in the RM; specific sub-activities may implement specific surveys. |

| Total estimated costs of outputs | US$45,564,278 | REFERENCES Monaghan, Rachel (2008). Community-Based Justice in Northern Ireland and South Africa. International Criminal Justice Review, 18:1, 83-105. Morawska, A. et al. (2010). Evaluation of a Brief Parenting Discussion Group for Parents of Young Children. Journal of Develop’l & Behavioral Pediatrics 31(8). RTI Report: MIF Youth Employment Programs, submitted to IDB 2012. UN Habitat, 2008. Women’s Safety Audits: What Works and Where? UNICEF Juvenile Justice Portfolio. “The Handling of Children who Come into Conflict with the Law: Alternatives to Custody.” Penal Reform Int’l, Puerto Rico. C. Whitzman, M. Shaw, C. Andrew, and K. Travers, 2009. The effectiveness of women’s safety audits. Security Journal Vol. 22, 3, 205–218. |
| --- | --- | --- |
| Total estimated for Transition Plan, Monitoring & Evaluation, Programme Management, Technical Advisory Team and Contingencies | US$8,783,477 |  |
| Total for Administrative Fee (5% of grants) | US$1,755,145 |  |
| Total estimated cost of the Program | US$55,102,900 |  |

Definition: a spectrum of attachment, from employment, to pre-employment / orientation / readiness, to zero attachment

The three groups are defined based on both labor market and social indicators, taking into account international experience on which youth populations are placed faster. Group 1 characteristics include secondary school completion, possibly tertiary school completion, some job experience; Group 2 characteristics include some secondary education, no formal job experience; Group 3 characteristics include primary to 2 years of secondary education or less, anyone with prior juvenile record, no formal job experience. For the baseline data, the PEU has estimated which beneficiaries would fall into which group, approximately, based on the following classifications. Participants in On-the-job Training Program and Employment Internship Program (for indicator 2.1 and 2.2) are considered Group 1. Scholarship beneficiaries (secondary and tertiary) fall into Group 1 and 2 and are counted together.  Vocational training programs (HEART) participants are considered Group 2. Pre-vocational participants (remedial education) are considered Group 3.