Document of the Inter-American Development Bank

- Not For Public Use

Regional

Social Capital, Ethics and Development Initiative

(RG-T1033)

- Plan of Operations

This document was prepared by the project team consisting of: Liliana Basile (SEC/SEC), Project Team Leader; Lionel Nicol (EVP); Orlando Reos (RE1/SC1); Helge Semb (RE2/OD3); Anamaría Viveros Long (OVE); Leyda Fajardo (INT/RTC); Juan Carlos Pérez-Segnini (LEG/OPR); and, Ada Inés Piazze (SEC/SEC).  María Luz Fuentes was in charge of document production.

Content

I.	Executive Summary	1

II.	Background and Justification	2

A.	Background	2

B.	The ethics and development issue within the Bank’s strategy framework	4

C.	Coordination with other Official Development Finance Institutions	4

D.	Value added of the operation	4

III.	Program Description	5

A.	Objectives	5

B.	Components	5

IV.	Cost and financing	10

A.	Summary and cost table	10

B.	Description and composition of financing	11

C.	Sustainability	12

V.	Executing Agency and Mechanism	12

A.	Executing Agency	12

B.	Execution mechanism	12

C.	Program implementation readiness	13

D.	Execution period and disbursement schedule	13

E.	Procurement of goods and services	13

F.	Publications	13

VI.	Monitoring and Evaluation	13

A.	Technical and basic responsibility	13

B.	Progress and final reports and evaluations	13

VII.	Program Benefits and Risks	14

A.	Benefits	14

B.	Target Beneficiaries	14

C.	Risks	14

VIII.	Environmental and Social Review	15

Annexes

| I | Logical Framework |
| --- | --- |
| II | Budget |

appendices

|  | Proposed Resolution |
| --- | --- |

Basic socioeconomic data

For basic socioeconomic data, including public debt information, please refer to the following address:

http://www.iadb.org/RES/index.cfm?fuseaction=externallinks.countrydata

Information available in the files of INT/RTC

Preparation:

III Coordinator’s Terms of Reference

V Assistant’s Terms of Reference

Execution:

Abbreviations

| ADC | Andean Development Corporation |
| --- | --- |
| CESI | Committee on Environment and Social Impact |
| IND | Indigenous Peoples Unit |
| INT | Integrations and Regional Programs Department |
| LAC | Latin American and Caribbean Region |
| MIF | Multilateral Investment Fund |
| NGOs | Non Governmental Organizations |
| NOW | Norwegian Fund for Women in Development |
| RTC | Regional Technical Cooperation Division |
| SDS | Sustainable Development Department |
| SUM | Centre for Development and the Environment |
| UNV | United Nations Volunteers |
| WB | World Bank |
| WID | Women in Development Unit |

- Executive Summary

| Beneficiary: | Borrowing Member Countries of the IDB. |
| --- | --- |
| Executing Agency: | The IDB through the Office of the Secretary (SEC/SEC). |
| Target Beneficiaries: | The public sector and civil society in IDB borrowing member countries and IDB specialists. |
| Financing: | IDB (Special grant of 11 million Norwegian Crowns, from the Government of Norway via the Norwegian Fund for Women and Development): US$1,500,000 Local: US$ 0.0 Total: US$1,500,000 |
| Objectives: | The main objectives of this technical cooperation are to: (i) contribute to the mobilization of social capital in the region within areas such as transparency, volunteerism, social inclusion, discrimination and human rights; (ii) advance the integration of ethics and social capital into the operations of the Bank including programming dialogues and Bank projects; and (iii) strengthen university education in the region on social capital and ethics for development. |
| Execution Timetable: | Execution Period: 36 months Disbursement Period: 42 months |
| Special Contractual Conditions: | None. |
| Exceptions to Bank Policies and Procedures: | None. |
| Environmental and Social Review: | The TC Profile was reviewed by the CESI/TRG in its Meeting 48-04 of December 17, 2004. The Committee recommended incorporating the theme of cultural diversity in the social dimensions of globalization section. (See paragraph 3.5 item (iii)). |
| Coordination with other official development finance institutions: | The IDB through the Inter-American Initiative on Social Capital, Ethics and Development is implementing several projects in association with other international and multilateral institutions. Examples of joint programs include a distance course for training university professors in Latin America on how to teach ethics for development together with the Organization of American States; the execution of diverse projects to mobilize social capital in association with the Andean Corporation for Development; the edition and distribution of academic materials in cooperation with the World Bank, and developing diverse projects with the Pan American Health Organization. |

- Background and Justification

- A.	Background

  - There is a strong interest on the issue of ethics in the Latin America and Caribbean Region (LAC). In the continuous progress for the democratization process there is a collective demand to strengthen key elements for development in areas such as transparency, ethical codes in the public service, social corporate responsibility, volunteerism, the ethical formation of professionals in universities and citizen participation. There is a general interest in strengthening several dimensions of social capital in society. The idea of social capital integrates, among others, trust, associativeness and civic behavior.

  - In 2000, the President of the IDB, Mr. Enrique Iglesias, and the Prime Minister of Norway, Mr. Kjell Magne Bondevik, conceived the idea of an initiative focused on the mobilization of social capital and ethics for development in LAC. This initial idea was submitted to an advisory meeting where prominent personalities highlighted the potential positive impact of launching an agenda on ethics and social capital.

  - In March of 2002, the Board of Executive Directors of the IDB approved project TC0108001 (ATN/NO-7809-RG) to implement the Initiative on Social Capital and Ethics for Development (the Initiative) with financial resources from the Government of Norway. Foundational to the Bank’s Initiative is its contribution, through ethics for development and social capital, to the reduction of poverty and inequality in Latin America, a continent with enormous growth potential but in which 44% of the population and 58% of children live below the poverty line.

  - The results of the Bank’s Initiative have surpassed its original objectives and expectations. The countries of the continent have indicated, through various channels, their genuine interest in the Bank’s Initiative and have participated massively in its activities. Presidents, ministers, legislators, political leaders, business executives, religious leaders, university presidents, ONG’s leaders, and many other sectors of civil society have become involved in the Bank’s Initiative’s work. The Bank personnel have also shown interest in this new area of activity. The Bank Presidency has given continuous support to the work of the Initiative and so has the Secretariat of the Bank. Numerous Executive Directors, both Vice Presidents, the three Regional Operation Departments, and various divisions of the Bank have also participated in the Initiative’s activities.

  - The Bank’s Initiative has developed various streams of work: First, it places the agenda of ethics and social capital at the center of the debate on public policies in the region. Its meetings have received concrete responses of interest regarding the work and agenda of the Bank’s Initiative. Nearly 25,000 Latin American leaders and representatives of relevant social groups have participated in these meetings. Six heads of state have convened Initiative meetings, and Vice Presidents, Prime Ministers, and numerous other Ministers have participated in them. These meetings served as catalysts for various related projects and for strengthening networks of cooperation among these leaders.

  - Second, the Bank’s Initiative has achieved sustained activity in advancing the integration of ethics and social capital into the design of Bank technical cooperation and loan projects. The three Regional Operation Departments and the Learning Office have worked jointly with the Bank’s Initiative, and over 200 specialists have been trained to address these areas in Bank operations. As a consequence, a culture of ethics and development is advancing within the IDB. Furthermore, the Bank organized a Seminar in Oslo with the University of Oslo, and for the first time in its history dedicated an annual one-day seminar at headquarters to the issue of social capital, ethics and development. The seminar included the participation of prominent personalities, such as, Nobel Laureate Dr. Amartya Sen, Norway Prime Minister Kjell Magna Bondevik, IDB’s president Enrique Iglesias, Norway’s Ambassador in the U.S., Mr. Knut Vollebaek, PAHO’s Director Mirta Roses, and former President of Chile Patricio Aylwin, Judge Eva Jolly (Integrity award of Transparency International), IDB Canadian Director Charles Bassett and other ethics specialists.  The first Ethics and Development Day was held on January 15, 2004 and the second on January 11th, 2005.

  - Third, the Bank’s Initiative has developed strong working collaborations with universities throughout LAC to institutionally integrate education in the ethics of development and social capital into the training of economists, managers and other key professionals. The goal is to have a strong impact on the behavior of organizational leaders from the public and private sectors in LAC. The Initiative has also prepared projects to strengthen ethics education as part of basic education.

  - Fourth, the Bank’s Initiative has built an Internet space that has become a vast center for information, exchange and cooperation on the ethical dimensions of development. The website attracts over 30,000 users a week from over 35 countries. On January 31st, 2005 the website accumulated 1,634,614 visits. The website often leads IDB Internet pages. And according to the statistics of Google and Yahoo it is the top website visited in the world for this field and it was selected as one of the top websites on sustainable development by Brussels University

  - Fifth, various international organizations have requested the technical support of the Bank’s Initiative for establishing and developing activities linked to ethics and development. These organizations have participated in many of the Initiative’s activities and have sent their specialists to its various workshops to learn how to apply social capital and ethics in development projects. Among them are the World Bank (WB), the Andean Development Corporation (ADC), the Organization of American States (OAS), the United Nations Development Program (UNDP), United Nations Volunteers (UNV), and the Pan-American Health Organization (PAHO).

- B.	The ethics and development issue within the Bank’s strategy framework

  - The project described herein fits within and is designed to support the priorities of the Eighth Replenishment and the Bank’s strategies for the social sectors and reform of the State. The Eighth Replenishment report, and more recent documents pertaining to the institutional strategy underscore, explicitly or implicitly, the importance of ethics issues for development effectiveness, social equity, social inclusion, and modernization of the State, particularly for governance, institution strengthening and creation of public/private-sector strategic partnerships. This technical cooperation proposes to introduce an ethical dimension into all these strategic spheres.

- C.	Coordination with other Official Development Finance Institutions

  - The Bank through the Inter-American Initiative on Social Capital, Ethics and Development is implementing several projects in association with other international and multilateral institutions. Examples of joint programs include a distance-training course for university professors in Latin America on how to teach ethics for development together with the OAS; the execution of diverse projects to mobilize social capital in association with the ADC; the edition and distribution of academic materials in cooperation with the WB, and developing diverse projects with the PAHO.

- D.	Value added of the operation

  - Continued financing for the Initiative’s activities will allow it to build on the momentum and public awareness that was created during the first phase of the project. As stated above, the Bank’s Initiative is demand driven and it has responded to the existing public interest on social capital and ethics, while also capturing the attention of new constituencies. The IDB through the Initiative’s activities has cultivated an interest and awareness for the importance of social capital and ethics in the region’s development in practical and applicable terms. The new phase of the technical cooperation undertakes carefully selected new projects, which take into consideration the countries’ demands, the Bank’s strategies and the available resources. It is aimed at concrete ethical issues and further institutionalizing the presence of social capital and ethics in societies throughout Latin America –made possible through the foundation of a renewed awareness and concern for these issues from the Initiative’s first phase. Because of its many coordinating functions and through its wide recognition as a pioneering resource on these topics, the Bank’s Initiative is positioned to continue fostering synergistic efforts within the region, in the Bank, and with other international development institutions to promote social capital and ethics.  Its network focus and strength in convoking groups will continue to have multiplying effects throughout the region and its institutions. The Initiative is also going to assist the Bank operational Departments apply ethics and social capital in the design, implementation, monitoring and project evaluation.

- Program Description

- A.	Objectives

  - The main objectives of this technical cooperation are to: (i) contribute to the mobilization of social capital in the region within areas such as transparency, volunteerism, social inclusion, discrimination and human rights; (ii) advance the integration of ethics and social capital into the operations of the Bank including programming dialogues and Bank projects; and (iii) strengthen university education in the region on social capital and ethics for development.

- B.	Components

  - Incorporating New Dimensions (Transparency and Human and Cultural Rights) and Strengthening Volunteerism (US$387,000)

  - The activities in this component have been conceived to have an impact in the countries of the region. Raising awareness about the significance of incorporating ethics and social capital for the sustainable development of the region is a long-term task, which will be achieved over time. For that reason the Bank, through the Initiative, will continue to hold seminars to place social capital and ethics on the public agenda and to incorporate two new topical dimensions: transparency and human and cultural rights and strengthen volunteerism. Each of these topics has current relevance in the discourse on ethics and social capital in Latin America.

  - In addition, other activities, such as the research paper and workshops, will contribute to develop proposals for public policies, legislative norms and ethical codes.

    - Transparency

  - There is currently both a great interest and increasing public demand in Latin America to improve transparency in public institutions. The Government of Norway has been an international leader in fighting corruption as evidenced in its proposal for the UN Convention against Corruption.  Norway’s experience lead by Judge Eva Jolly can be very meaningful. Also among others, countries like Canada have an important experience on Public Service Ethics Codes. The following activities intend to strengthen transparency in the public sphere through the institutional channels of legislation, education and the media.

      - An international seminar on “Strengthening a Culture of Transparency” to be held in Guatemala for the Central American region.

      - Develop guidelines to structure and improve public ethics codes.  Guidelines will be used to strengthen the work of Public Ethics Commissions and other government-established organizations that work on this topic.

      - In association with the Latin American Parliament and the OAS, the Bank’s Initiative will organize an annual workshop for legislators of parliamentary commissions to discuss legislative measures that could be adopted in their respective countries to improve transparency.

      - The Initiative will organize a workshop with Ministries of Education in LAC on policies for teaching the value of transparency in primary schools.

      - In association with media representatives, the Initiative will organize an annual workshop with journalists to analyze how the media can contribute to advance a culture of transparency in the region. Furthermore, it will establish a special bibliographic service on the Internet for the workshop participants.

      - In association with the Multilateral Investment Fund (MIF), the Initiative will formulate operating guidelines to establish standards of accountability to improve the transparency and credibility of NGOs.

    - Human and Cultural Rights

  - The Bank, through the Initiative, will implement the following activities aimed at strengthening a culture of respect for human rights and gender values in the region.

      - In association with the SUM of Oslo University, the Initiative will develop a study entitled “Ethics, Poverty and Human Rights,” to produce concrete proposals for protecting human rights that can be used by legislatures and in education programs.

      - Prepare with the University of Oslo a research project on the economic and social vulnerability of excluded groups in the region – one of the most critical ethical and social issues.

      - Organize, with IDB’s Representation in Europe, a meeting of experts to produce concrete recommendations on how to support vulnerable groups and improve social cohesion in Latin America. The recommendations will consider the cultural diversity of excluded groups in the region.

      - In association with the OAS, the Initiative will organize, with representatives of social commissions of parliaments, a workshop in the area of Human Rights to consider the recommendations developed by the Oslo University in laws’ elaboration process.

    - Strengthening Volunteerism

  - In cooperation with the ADC, UNV, and the OAS, the Bank, through the Initiative, will develop activities aimed at strengthening volunteerism, a fundamental expression of social capital in the region. Among these will be:

      - Develop a proposal, to be submitted to legislatures, on how to improve the legal framework to support volunteer activities.

      - Support the institutionalized integration of volunteer experiences into the curricula of three universities of the region.

      - Strengthen social capital mobilization in underprivileged local communities by developing cooperation projects with universities and volunteer organizations.

      - Train 15 civil society leaders of the region on advanced volunteer experiences with a “training of trainers” approach.

      - Train 30 public officers and civil society leaders from Central America on how to strengthen volunteerism with a “training of trainers” approach.

  - Advancing the integration of ethics of development and social capital into Bank’s operations (US$249,000)

  - The incorporation of social capital and ethics for development can make strategic contributions to the Bank’s programming dialogues with each borrowing member country. To this end, the Bank’s Initiative will implement the following activities:

      - Together with the Regional Operation Departments and the Office of Learning, the Initiative will train specialists from the Country Divisions of the three Regional Operation Department on how to integrate the issues of ethics in IDB programming dialogue.

      - Participate in the programming exercises of three of the Bank’s borrowing member countries to promote the issues of ethics and social capital for development with the country’s authorities and to identify opportunities to integrate these components in the Bank’s lending operations. Incorporation of these issues in the preparation of the country dialogue paper and country strategy.

      - Assist Country Divisions in the design of appropriate methodologies for participation and dialogue with members of civil society. The methodologies will contribute to promote the transparency, inclusiveness of the Bank’s consultation process around Country Papers with civil society.

  - The IDB, through the Initiative, will develop a number of projects in association with other IDB Departments such as the Women in Development Unit (WID/SDS) and the Indigenous Peoples Unit (IND/SDS) of the Sustainable Development Department, the Department of Development Effectiveness and the MIF.

      - In association with WID/SDS and MIF, the Initiative will develop a program aimed at identifying and promoting the incorporation of policies and practices to overcome gender discrimination in the workplace.

      - In association with WID/SDS and the Ministries of Education of Argentina and Brazil, the Initiative will develop a project to teach gender values in primary schools.

      - In association with IND/SDS, WID/SDS and PAHO the Initiative will develop a project to support the reduction of maternal mortality in indigenous populations in three countries with large concentration of indigenous populations.

      - In cooperation with the University of Oslo, the Initiative will support the Department of Development Effectiveness develop a research project on strategies to integrate the dimensions of ethics and social capital to enhance the final results of development within countries.

      - In cooperation with the MIF, the Initiative will develop a project on ethics education for business leaders.

      - In association with the Office of Learning the Initiative will organize workshops to train 50 specialists, from Headquarters and the Representations, on the application of ethics for development and social capital in IDB´s technical cooperation and lending operations. Special emphasis will be placed on working with IDB Representations in Central America.

  - Strengthening ethics of development and social capital education in universities (US$219,000)

  - The Bank, through the Initiative, will contribute to the institutionalization of social capital and ethics in university training in key development professions through a special distance program on “training the trainers”. The specific activities under this component are:

      - Training 600 university professors at ninety-three renowned institutions to teach social capital and ethics of development and to establish permanent programs in social capital and ethics for development.  Special emphasis will be placed to train university professors in the Central American countries.

      - Editing publications based on recommended outputs to support the learning process.

      - Strengthening of the University Network on Ethics and Development aimed at institutionalizing and advancing the teaching of social capital and ethics for development through periodic electronic forums, a virtual portal, and other joint activities. Ninety-three universities from 19 countries participate in the Network.

      - The Initiative will prepare “instructional packets” for university professors to support them in providing programs in ethics for development, transparency, corporate ethics and social capital. The Initiative will produce a Continental Directory of the University Programs that focus and work on these areas.

  - Educating through the Internet (US$298,000)

  - The large response to the Bank’s Initiative website has resulted in the constitution of an extensive continental audience, which is very representative of the region and its organizations. During this second phase the Initiative will capitalize on the experience and transform the page into a highly interactive site.  The specific goal is to build knowledge on these topics in the region through the following activities, i) intraregional exchanges on critical topics, ii) electronic forums, iii) public consultations, iv) identify opportunities for cooperation and joint action, v) specialized portals, vi) virtual conferences, and in general, vii) take advantage of the most advanced internet technology to promote the agenda on social capital and ethics for development.

  - With the Bank’s help, the current technology will be remodeled to create the technological opportunities and capability required to deliver the above services. Furthermore, the Bank, through the Initiative plans to obtain the support of the Global Development Learning Network in the mentioned dimensions.

  - Additionally, the Bank’s Initiative will continue to support and develop the existing sites of its website, and integrate the proposed new dimensions of transparency, the ethical and social dimensions of globalization and human rights. These sites include:

      - Digital Library

      - Abstract Collection

      - Recommended Books

      - Relevant Links

      - Key Interviews

      - Video Conferences that Broaden Horizons

      - Innovations in Social Capital and Ethics

      - Events and Registration Forms

      - Weekly Bulletin, “Ethics and Development”

      - Directory of Volunteerism

  - The Initiative will continue to expand its Internet alliances with recognized organizations in order to maximize impact.

  - Training specialists from other international organizations (US$20,000)

  - Various international organizations have indicated their interest in training their experts on applying ethics and social capital in the projects they undertake. This can support the advancement of a culture in designing projects throughout the region. In response to the demand, the Bank through the Initiative will undertake training programs for the ADC, one of the principal sources of funding in the region, the OAS, and PAHO.

  - Coordination Unit (US$259,859)

  - A Coordinator, two IDB specialists, and an assistant will integrate this unit. The TC will cover the salary costs of the senior coordinator and the assistant.  The coordinator will be responsible for (i) advising Senior Management on how to achieve the three main objective of the technical cooperation in the region and the IDB, (ii) for supervising the execution of all components of the operation. The assistant will be responsible for providing administrative support to the Coordinator in all matters related to the execution of the technical cooperation.

- Cost and financing

- A.	Summary and cost table

  - The total cost of the project is estimated in the amount of 11 million Norwegian crowns (US$1,500,000) as shown in the following budget table:

Table of Cost and Financing

(In US$)

| Component | BID/FNO |
| --- | --- |
| 1. Incorporating New Dimensions: Transparency, Human and Cultural Rights, and Strengthening Volunteerism | 387,000 |
| 2. Advancing the integration of ethics of development and social capital into Bank’s operations | 249,000 |
| 3. Strengthening ethics of development and social capital education in universities | 219,000 |
| 4. Educating through the Internet | 298,000 |
| 5. Training Specialists from other International Organizations | 20,000 |
| 6. Coordination Unit | 259,859 |
| 7. Contingencies | 67,141 |
| TOTAL | 1,500,000 |

- B.	Description and composition of financing

  - The Bank will increase its contribution to expand and reinforce the support provided during the previous phase. The Bank will supply the Initiative with two staff members, both of whom will be part of the Coordination Unit referred to in paragraph 5.3. It will also provide offices in its headquarters. It will contribute to the costs associated with the organization of international meetings, workshops and seminars on transparency, globalization and human rights. It will finance publications for meetings, workshops with country divisions, and Bank Representations, activities with other international organizations and publications. The Bank will also finance traveling costs, computer equipment, communication, electricity, and general services.

  - The Bank will provide several inputs for the development and maintenance of the Initiative’s new web site. ITS will assist the migration to new technologies such as Microsoft.Net and provide software licensing, new servers, technical assistance and training. The Initiative’s new virtual space will include a system for carrying out electronic forums, surveys and document management. In collaboration with ITS, the Initiative will update and develop the current web site. Additionally, other IDB Departments will provide online content through an automated process. Finally, the Bank will provide assistance in graphic design, application development, back ups and others.

  - Other international organizations such as the ADC, the OAS, and the United Nations will provide financing to carry out the planned joint activities through strategic alliances with the Initiative. The Initiative also expects to receive support from the LAC Governments, the Government of Canada, the Government of Israel, universities and from other extra-regional countries to carry out specific agreed activities. The work plan is going to be implemented with joint financial participation of the Norwegian government, the IDB, LAC governments, universities and civil society organizations.

- C.	Sustainability

  - All available evidence clearly indicates that the Latin American governments´ demand for the activities provided by the Initiative will continue to increase. Furthermore, it is expected that during the execution period of this technical cooperation, the Bank, in response to the region’s demand, will continue to integrate these topics in its operations. Thus, both internally and externally, there will be strong basis to sustain the Initiative.  Additionally, the Bank is in the negotiating process of creating a Multi Donor Trust Fund to support social capital and ethics for development, and other countries, together with Norway, are expected to contribute to the Fund.  Canada has expressed its intention to join the Multi Donor Trust Fund.

- Executing Agency and Mechanism

- A.	Executing Agency

  - The Bank will implement this technical cooperation through the Coordination Unit of the Social Capital, Ethics and Development Initiative attached to the Secretariat of the Bank (SEC/SEC). The Coordination Unit will report periodically to SEC/SEC on its activities and receive direct instructions from the President of the Bank. The Coordination Unit will have active relationships of cooperation with other Bank Departments.

  - The Initiative will have a Board of External Advisers integrated by: Dr. Amartya Sen, Nobel laureate in Economics, Harvard University; Edgar Morin, Director Emeritus of the National Center for Scientific Research France, La Sorbonne, Paris; Patricio Aylwin, former President of Chile; Cardinal Oscar Andrés Rodríguez Maradiaga, Archbishop of Tegucigalpa, Honduras; Mirta Roses, Director of the Pan-American Health Organization; Judge Eva Joly, Special Advisor to the Government of Norway; Rebeca Grynspan, former Vice President of Costa Rica and Director of ECLAC Mexico; Rev. Gaspar LoBiondo, Director of the Woodstock Center at Georgetown University; Joan Prats i Catalá, Director of the International Institute on Governance of Catalonia; Rabbi Israel Singer, President of the Director Counsel of the World Jewish Congress; Sturla J. Stälsett, Associate Professor at the University of Oslo; Ruth Cardoso, President of Comunidade Solidária, Brazil; and, Myrna Cunningham, President of the University of the Autonomous Regions of the Nicaraguan Caribbean Coast.

- B.	Execution mechanism

  - The execution mechanism is composed of a Coordinating Unit, integrated by a Senior Coordinator, two IDB specialists, and an assistant. Furthermore, the Coordinating Unit will hire consultants who will provide technical and organizational assistance in the implementation of all activities.

- C.	Program implementation readiness

  - The Initiative’s activities are managed through annual Work-Plans. The one corresponding to 2005 is already developed and ready for implementation.

- D.	Execution period and disbursement schedule

  - The execution period is 36 months and the disbursement is 42 months from the approval date of the operation.

- E.	Procurement of goods and services

  - The contracting of all consulting services and the acquisition of goods and services will be carry out by SEC/SEC in accordance with the Bank’s policies and procedures.

- F.	Publications

  - Any publication to be produced with resources from the Bank’s Contribution will require the approval of the Bank’s Editorial Committee, in accordance with applicable policies and procedures as reflected in document AM-331

- Monitoring and Evaluation

- A.	Technical and basic responsibility

  - Technical responsibility will rest with SEC/SEC; basic responsibility and administration, including disbursements, will fall to the Regional Technical Cooperation Division of the Integrations and Development Programs Department (INT/RTC).

- B.	Progress and final reports and evaluations

  - The Coordination Unit will produce an annual report on the activities performed and their outcomes. The objectives and performance indicators established in the Logical Framework (Annex I) will be used as references to evaluate the execution process of this technical cooperation. The annual and final reports will include a two to three page long executive summary. As established in the Letter of Agreement with the Government of Norway, the project team will provide the donors with reports describing the achieved results as well as any other report or document resulting from the activities described in this operation and financed with the Norwegian Government’s contribution. Copies of the reports will also be forwarded to RE2/TEC.

- Program Benefits and Risks

- A.	Benefits

  - The project is expected to produce the following benefits for the countries in the region:

      - Contribute to the mobilization of social capital to support public policies that advance social development.

      - Support for the inclusion of the dimensions of social capital and ethics for development in IDB’s programming dialogue with countries and in IDB projects.

      - Contribute to the development of a culture of transparency.

      - Support for the strengthening of volunteer activity in the region.

      - Contribute to the institutionalization of teaching social capital and ethics for development at public and private universities in the region.

      - Catalyze alliances to promote these topics among representatives from government, civil society organizations and other international entities.

  - Assistance through systematic, large-scale dissemination over Internet so that governments, businesses, civil society organizations, universities and other key participants of development efforts have: a) access to the relevant advances being made in the region and internationally in social capital and ethics for development and relevant best practices; b) access to the products generated by the Initiative; and c) be able to use an efficient and quick medium for sharing information with other organizations in the region.

- B.	Target Beneficiaries

  - This operation will have both indirect and direct beneficiaries both in the Region and the Bank. For a quantification of direct beneficiaries refer to the Logical Framework in Annex I.

- C.	Risks

  - The following possibilities may signal risks in the implementation of the project:

      - Participants attending workshops and seminars may not meet the established prerequisites to be able to successfully apply the learned material to their countries’ development agenda.

      - Speakers in workshops and seminars may not have the knowledge, specialized technologies, experience and required expertise for the presentations.

      - Counterpart entities co-organizing the planned seminars and workshops may not have the required organizational skills to carry them.

      - Universities may select professors to the university training for “training the trainers” who do not meet the required criteria to adequately implement the course materials.

      - Professors may not have the required technology to complete the virtual training.

      - Ministers, legislators, journalist, may not have financial resources to cover travel expenditures to attend international workshops and/or seminars.

      - Country conditions may not be the most appropriate ones to implement the ethics codes and processes may take longer than anticipated.

- Environmental and Social Review

  - The TC profile was reviewed by the CESI/TRG in its Meeting 48-04 of December 17, 2004. The recommendation of the Committee was to incorporate the cultural diversity theme in component 1 (See paragraph 3.5 item (iii)).

  - The proposed project has no impact on the environment. It social impact will be delivered mainly from the benefits of improved transparency, and improvement of human rights.  It will also be felt by the mobilization of social capital through the construction of a culture of transparency, strengthening volunteerism and social inclusion, overcoming discrimination, and strengthening human rights.

- Certification

  - On November 23, 2004, a Letter of Agreement (the Agreement) was signed between the Bank and the Ministry of Foreign Affairs of Norway. The activities to be financed under this operation are fully covered under the aforesaid Agreement, whereby, subject to approval by the Norwegian Parliament, the Bank has received the sum of 3,000,000 Norwegian crowns. A second contribution of 4,000,000 Norwegian crowns will be disbursed no later than October 15, 2005 and a third and final contribution 4,000,000 Norwegian crowns will be disbursed no later than October 15, 2006, pursuant to the terms and conditions of this Agreement. The combined amount of the three disbursements will total 11,000,000 Norwegian crowns. The resources so committed will be channeled through the Norwegian Fund for Women in Development.

  - I hereby certify that the sum of $11,000,000 Norwegian crowns, to be converted to the United States dollar equivalent, has earmarked for this operation to be financed under the Norwegian Fund for Women and Development (the Fund) and in accordance with the above-mentioned Agreement. The sum will be available for disbursement, according to the schedule established in the aforesaid Agreement, to finance the activities described and budgeted for herein. The resources for which this certification is issued shall be committed and disbursed only in United States dollars by the Bank. The United States dollar will be the currency used for payment of remuneration and compensation to consultants, with the exception of local consultants working in their own countries, in which case such remuneration and compensation will be paid in the currency of that country. However, the resources of the Fund will not cover expenses exceeding the amount certified in Norwegian crowns for implementation of this plan of operations. Such expense overruns may be occasioned by exchange-rate differences arising from currency conversion, including conversion based on commitments specified in contracts denominated in a currency other than the currency of the Fund. The Fund will not assume any liability in respect of risks due to such differences or cost overruns.

- ________________________________		_____________________

- Arnoldo M. da Fonseca, Chief, RE2/TEC	 		Date

A budget with additional information is attached as Annex II.