Multilateral Investment Fund

Project Abstract

- Basic Project Data

| Project title: | Promoting Corporate Social Responsibility through Support for Local Productive Initiatives |  |
| --- | --- | --- |
| Project number: | BR-M1030 |  |
| Country: | Brazil |  |
| Beneficiaries: | Rural settlements and residents in the municipalities of Minaçu, Cavalcante and Colinas do Sul, Campinaçu, Niquelândia, Uruaçu, Barro Alto, Campinorte and Santa Rita do Novo Destino in Goias |  |
| Project team: | Daniel Shepherd (MIF), Team Leader; Ismael Gilio (COF/CBR); Antonio Gaspar (MIF); |  |
| Executing Agency: | Serviço Brasileiro de Apoio às Micro e Pequenas Empresas de Goiás (SEBRAE-GO) |  |
| Financing plan: | MIF – Facility III-A: Counterpart: Total: | US$ 1,000,000 (50%) US$ 1,000,000 (50%) US$ 2,000,000 |
| Tentative dates: | CRG – November 2005 Donors – December 2005 |  |
| MIF Classification: | SAGR / CSOR |  |

- Background and justification of the project

- Local situation and economic conditions in the area

  - The municipalities of Minaçu, Cavalcante and Colinas do Sul, Campinaçu, Niquelândia, Uruaçu, Barro Alto, Campinorte and Santa Rita do Novo Destino are located in the State of Goias and are generally characterized by low economic activities and development.  These areas are known to have limited growth of the population compared to the rest of the state of Goiás. In general,

  - Minaçu’s economy is supported by asbestos mining, energy generation and agricultural production, principally based on small farms along with a small commercial sector. In general its economy has been stagnated. Cavalcante and Colinas do Sul, have an economy based on agricultural production with relatively low economic activity, although it does maintain more direct access to main regional markets.

  - Despite the evident fragility of the analyzed economic sectors (agriculture and livestock), several associative activities exist in the region. In particular, 39 rural and urban producers and workers associations and two rural cooperatives are operating in the municipalities, which involves some 1500 people.  This demonstrates the opportunities for fomenting association among producers is possible in the region.

  - In 2000, the Companhia Energetica Meridional (CEM) began development of the Cana Brava hydroelectric power plant. Part of the investment was financed by a loan of the Private Sector Department (PRI) of the IDB (PRI provided an “A” loan of US$ 75).  The hydroelectric facility is located along the Tocantins River, approximately 50 km downstream from the Serra da Mesa reservoir, on the border between the municipalities of Minaçu and Cavalcante, in the State of Goiás. The Serra da Mesa hydroelectric facility operates in an area near Cana Brava.  As a result of the concerns regarding the impact of Cana Brava, PRI discussed the possibility of an initiative to provide additional support to the communities in the region for promoting productive initiatives, which would include the participation of different private and public actors such as the Ministerio de Minas e Energia (MME), CEM/Tractabel, SAMA Mineração de Amianto (owners of the asbestos mine) and CPFL/Furnas (owners of Serra da Mesa hydro) and with the geographic focus of Minaçu, Cavalcante, Colina do Sul, Campinaçu, Niquelândia, Uruaçu, Barro Alto, Campinorte and Santa Rita do Novo Destino.

- B. 	Problem

  - The most important economic activities in the target municipalities in Goias (i.e. agriculture and livestock) are not well developed and have limited value added within the productive chains.  The entire area is suffering economic stagnation due to the absence of a skilled and qualified workforce, lack of cooperation and interaction among local small producers and a dearth of available support services.  Many natural resources of the affected areas are not used (e.g. lake) or underused (e.g. land, new technologies, etc.) because of the lack of awareness among local producers.

- C. 	Proposed program

  - In this context, a program to provide support for local economic activities in the region could play an important role in the local economies stimulating the development of value added productive chain across a few different sectors. In addition, the proposed program could support the basic training and technical assistance needed for establishing the local skills needed for expanding economic opportunities.

  - As part of their corporate social responsibility (CSR) efforts, the large companies operating in the region CEM/Tractabel (owners of Cana Brava hydroelectric facility), SAMA Mineração de Amianto (owners of the asbestos mine) and CPFL/Furnas (owners of Serra da Mesa hydroelectric facility) are interested in providing support to local economic development in the region.  MIF is interested in partnering with the large companies in the region to facilitate their involvement, leverage resources and use this opportunity to demonstrate the importance of CSR efforts among companies.  This public private partnership would be a useful model for other parts of the country and in other areas in the region.

- Program objective and description

- A.	Objectives

3.1 	The general objective of this project is to develop and improve economic opportunities for local rural small-scale and community enterprises located in a specific region in Goias. The purpose is to strengthen and support the development of new businesses and expand existing small businesses with the financial support of the large companies operating in the Cana Brava and Serra Mesa region in Goias.

  - To achieve these objectives, the following four components are expected to be included: (i) Promotion and dissemination of the results; (ii) Development of materials and training; (iii) Technical assistance to smaller enterprises; and (iv) Development of productive value chains.

- B.	Components

  - Component 1: Promotion and dissemination of the results

  - The focus of this component is to inform potential beneficiaries as to the opportunities presented by this proposed program.  This component is also intended to disseminate the results of the activities of the entire program.  For this, the following activities are expected: (i) public seminars in the different municipalities; (ii) development and publication of informative materials; and (iii) final conference to disseminate the results of the program.

  - The seminars (one for each municipality) would include the participation of the participating companies, municipalities of the affected areas, local agriculture associations and cooperatives, private stakeholders and local communities. Informational materials will be developed and used to inform local stakeholders about the project and encourage an increased participatory approach to local productive initiatives.  The final conference is expected to take place in the last year of the program and would include the participation of stakeholders including the beneficiaries of the program and other donor participants.

  - As a result of this component, local private and public stakeholders, including local communities and other key actors of the affected areas would be informed and made more aware about the opportunities presented by the program as well as its results.

  - Component II:  Development of materials and training

  - The objective of this component is to develop the materials and undertake the necessary assessments in order to identify economic opportunities appropriate for the region.  The other important aspect of this component is to train local consultants in the area that would then be able to provide services to local private enterprises.  Part of this component is intended to help local stakeholders by providing important technical and market information need to develop or improve economic activities.

  - The objective of this component is to develop the materials and undertake the necessary assessments in order to identify economic opportunities appropriate for the region.  The other important aspect of this component is to train local consultants in the area that would then be able to provide services to local private enterprises.  Part of this component is intended to help local stakeholders by providing important technical and market information need to develop or improve economic activities.

  - This component has the aim to train local consultants to enable them to provide technical assistance to local private economic initiatives (micro-small enterprises, local communities, disadvantage groups, etc.) in order to develop or improve their economic activities, strengthen the present associations and cooperatives and develop new microenterprises.

  - The market assessments would also help define of the exact types of training and technical assistance needed to improve the economic activities in the area and link the present MSME associations and cooperatives to the agriculture productive chain, leading to increased value added.

  - The expected results of this component are: (i) a series of assessments to be used by local stakeholders in order to develop and/or improve local private enterprise efforts; and (ii) some 30 local experts trained so that they may be able to assist local stakeholders to improve and develop their economic activities.

  - Component III: Technical assistance to smaller enterprises

  - This component aims at assisting small-scale enterprises in order to improve their skills and competences and stimulate local economic development in the short term. The component would include direct assistance to small private enterprises and would be undertaken by contracting the local consultants trained during the Component II to provide technical assistance to local enterprises in the selected economic sectors.  The technical assistance could include the following activities: (i) administrative advice; (ii) technical advisory services related to the agriculture, livestock and aquaculture activities; (iii) design of business plans for developing the present activities and/or operating existing ones; and (iv) assistance for facilitating financial access to local credit institutions, etc.

  - Component IV: Development of productive value chains

  - This component is focused on stimulating the integral development of economic activities by supporting pilot projects in the affected areas. The program would provide a 50% matching grant fund for selected pilot projects in the affected areas.  Identification of the pilot projects: some local associations have already prepared detailed business plans for running economic activities that could be relevant for developing the value added in the productive chain of the selected economic sectors (e.g. dairy center, aquaculture, etc.). Local consultants, trained in Component II, could provide assistance to a handful of pilot projects in the affected areas and could assist local entrepreneurs with developing and improving their businesses in the short term. The selection criteria of the pilot projects could be as follows: (i) experience in the sector; (ii) economic and financial feasibility of the project; (iii) relevance of the project in terms of the value added in the productive chains of the selected economic activities; (iv) potential number of beneficiaries; and (iv) overall expected impacts.

  - The pilot projects could be structured as follows:

      - No more than 30% of the total pilot project could be allocated to finance basic equipment considered essential for the development of the business activities (all with counterpart resources). Considering the main needs showed by local stakeholders, such equipment could include, for example: (a) milk processing: special fridges for the conservation of the milk; machineries for the production of cheese, etc.; (b) agriculture equipment: minor equipment for production; fridges for the conservation of the products, etc.; and (c) fish processing: equipment for fish stocking and processing, netting, etc.

      - The remaining part of the matching grant fund (70%) could be used for providing training and technical assistance activities to the entrepreneurs.

- Cost, Financing and Execution Time

  - The total program cost is expected to be US$2,000,000, of which MIF would contribute US$1,000,000 in non-reimbursable funds through Facility III-A, and the remainder of US$1,000,000 would be expected from counterpart resources (the bulk of which is expected to come from the large companies). The program would be implemented in 48 months.

- Executing Agency

  - The proposed executing agency for this project is Serviço Brasileiro de Apoio às Micro e Pequenas Empresas de Goiás (SEBRAE-GO). SEBRAE-GO was established as a Department of the Federal Government of Goiás, but since 1991 it has evolved into an individual private institution with the purpose supporting micro, small and medium enterprise development and increase skills and competences of local public and private stakeholders in the state of Goias. SEBRAE-GO is well known by both local public and private entities.   Its organizational structure is composed of by a Council including the representatives of the enterprise sector (e.g. AGPE, Facieg, Faeg, FCDL, Fecomercio and Fieg), Federal Government (Banco do Brasil, CAIXA and Universitade Federal de Goiás), and National Government (Agência de Fomento de Goiás, Coniteg, Seplan).  SEBRAE-GO has a total of 98 employees and most of them with more than 10 years of experience. Its annual financial budget increased from US$10.7 million in 2002 to US$17.2 million in 2004.  Revenue is primarily derived from the INSS (Instituto Nacional de Seguridade Social) based on 0.6% of the salaries paid by the companies on behalf of its employees. In addition, other incomes are collected through special projects revenue.

  - For this proposed project, there would be a Consultative Council consisting of the large company donors and key public and private stakeholders in the target region of the project.

- Major Issues

  - The project team has identified the following issues that warrant further consideration and analysis: (i) ensure that the proposed executing agency has the institutional capacity to carry out the project; (ii) distinguish this project from the compensation efforts and requests from communities related to Cana Brava and Serra Mesa; (iii) assess and minimize any potential adverse reason from local advocacy groups; (iv) assess the possibilities and expected advantages of partnering SEBRAE-GO with SEBRAE National; and (v) role of other entities (e.g. large companies, government) in terms of the counterpart funding of this proposed project.