Document of the Inter-American Development Bank

- Not For Public Use

Regional

Strengthening Pro-Poor Integration in Latin America and the Caribbean

(RG-T1669)

- Plan of Operations

This document was prepared by Kea Wollrad (INT/INT), Team Leader; Paolo Giordano (INT/INT); Mauricio Mesquita Moreira (INT/INT); Christian Volpe (INT/INT); Juan Blyde (INT/INT); Julio Guzmán (INT/INT); Diego Buchara (LEG/SGO); and Virginia Franzini (LEG/SGO).

Content

I.	Executive Summary	1

II.	Background and Justification	2

A.	Problem Definition	2

B.	Relation with Bank Regional and Sector Strategies	3

C.	Relation with the Trust Fund	3

D.	Coordination with Other Official Development Institutions	3

III.	Description	3

A.	Purpose and Goal	3

B.	Components	4

C.	Expected Results	6

IV.	Budget	6

V.	Executing Agency and Mechanism	7

A.	Executing agency	7

B.	Executing mechanism	7

C.	Program implementation readiness	8

D.	Execution period and disbursement schedule	8

E.	Procurement	8

VI.	Monitoring and Evaluation	8

A.	Monitoring	8

B.	Technical and basic responsibility	8

C.	Evaluations	8

VII.	Benefits and Risks	8

A.	Benefits	8

B.	Risks	9

VIII.	Environmental and Social Aspects	9

IX.	Recommendation	9

X.	Approval	9

Annexes

| Annex I | Procurement Plan |
| --- | --- |

Basic socioeconomic data

For basic socioeconomic data, including public debt information, please refer to the following address:

http://www.iadb.org/RES/index.cfm?fuseaction=externallinks.countrydata

Information available in the files of INT

Preparation:

Project Profile

Annex II: Background information on project components and outline for consultancies

Research outlines for the three components

Abbreviations

| CAF | Corporación Andina de Fomento |
| --- | --- |
| DFID | Department for International Development of the United Kingdom |
| ECLAC | United Nation Economic Commission for Latin America and the Caribbean |
| ESR | Environmental and Social Review |
| IDB | Inter-American Development Bank |
| INT/INT | Integration and Trade Sector |
| KMG | Market and Governance Trust Fund for Poverty Reduction |
| LA | Latin America |
| LAC | Latin America and the Caribbean |
| LEG/SGO | Legal Department Sovereign Guaranteed Operations |
| MDG | Millennium Development Goals |
| OECD | Organization for European Cooperation and Development |
| vpc/gcm | Grants and Cofinancing Management Unit |

“Strengthening Pro-Poor Integration in Latin America and the Caribbean”

(RG-T1669)

- Executive Summary

| Beneficiaries: | IDB borrowing member countries. |  |  |  |
| --- | --- | --- | --- | --- |
| Team Leader/ Members: | Kea Wollrad (INT/INT) / Paolo Giordano (INT/INT); Mauricio Mesquita Moreira (INT/INT); Christian Volpe (INT/INT); Juan Blyde (INT/INT); Julio Guzmán (INT/INT); Diego Buchara (LEG/SGO); and Virginia Franzini (LEG/SGO). |  |  |  |
| Executive Agency: | Inter-American Development Bank. |  |  |  |
| Target Beneficiaries: | National and sub-national governments of the beneficiary countries, with special emphasis on the public sector agencies concerned with the topics of the TC. |  |  |  |
| Sources of Funding: | IDB (Market and Governance Trust Fund for Poverty Reduction - KMG): Total: |  | US$ US$ | 500,000 500,000 |
| Objectives: | The objective of the present project is to generate state-of-the-art knowledge and policy recommendations in three emerging topics of economic integration and its impact on poverty reduction: biofuels, labor migration and the relationship between trade and sub-national disparities. The results of the project are expected to support governments in Latin America and the Caribbean in devising policies that take advantage of new trade opportunities while at the same ensuring that global market integration does not negatively affect the most vulnerable part of the region’s population. |  |  |  |
| Execution Timetable | Execution Period: Disbursement Period: | 9 12 | months months |  |
| Special Contractual Conditions: | None. |  |  |  |
| Exceptions to Bank Policies and Procedures: | None. |  |  |  |
| Environmental and Social Review: | The ESR reviewed the profile of this operation and confirmed the environmental and social safeguard classification “C” for this project (ESR minutes 48-08, December 5, 20008). The ESR also made some recommendations regarding Component I that the team agreed to (see paragraph 8.3). |  |  |  |
| Coordination with other Official Development Finance Institutions: | The project’s research activities will be closely coordinated with all international, regional and national institutions that have carried out research in the areas of this TC (paragraph 2.7). |  |  |  |

- Background and Justification

- A.	Problem Definition

  - It has become a truism that economic integration creates winners and losers. On the negative side, trade can increase poverty through employment lost (or wages eroded) by competition. Other negative impacts include increases in social inequality and the informal sector. More positively, integration can help countries open or expand export markets, attract foreign investment, acquire and absorb production technology, and enhance competition and efficiency. Yet many countries that open trade and capital markets fail to take advantage of these opportunities.

  - Indeed, although cross-country experiences vary, on average the extent of trade reform has not matched proportional reductions in overall poverty in Latin America and the Caribbean. Moreover, gains from trade integration tend to be significantly less visible than costs, such as job losses in traditionally protected and labor-intensive sectors. This has placed policies in favor of greater trade liberalization under systematic political pressure, damaging the perception that trade integration can and should be a net welfare generator, particularly among the most vulnerable.

  - Even though internationally renowned scholars have taken an increased interest in analyzing the cause-effect linkages between trade and poverty, no consensus has emerged beyond a general agreement on the conceptual, methodological and empirical challenges that would allow researchers to reach country-specific conclusions and policy recommendations. In view of the urgent need to fully understand the social and economic impacts of trade integration and to support LAC countries to take advantage of global market integration, the IDB —led by the Integration and Trade Sector (INT)—pioneered a formal, open, academic dialogue and learning process both within and outside the Bank on the social and distributive impacts of trade integration in Latin America.

  - The present project will broaden and deepen the state-of-the-art knowledge the Bank has acquired in this area. It will finance research and dissemination activities on three innovative topics: (i) the effect of climate change and trade in biofuels on socio-economic development in LAC; (ii) the development impact of international labor migration in the region; and (iii) the interaction between trade regimes and development disparities at the sub-national level. The new data, knowledge and policy recommendations that the project will generate are expected to help advance the implementation of domestic polices that maximize the benefits and mitigate the potential costs associated with progressive trade integration in the region.

- B.	Relation with Bank Regional and Sector Strategies

  - The project is consistent with the Bank’s strategy on regional integration (GN-2245-1) and two IDB strategic areas: (i) expanding opportunities for the majority, which includes creating policies, strategies, and programs that, among others, expand housing opportunities, access to credit and financial services and basic infrastructure services; and (ii) implementing effective social policies that allow pro-poor growth and achievement of the Millennium Development Goals (MDGs).

- C.	Relation with the Trust Fund

  - The project relates directly to one of the key objectives of the Market and Governance Trust Fund for Poverty Reduction (KMG), i.e. the generation of innovative approaches and solutions that focus on the distributive impact of market opening and support the design of socially inclusive regional and domestic policies to complement the trade agenda.

- D.	Coordination with Other Official Development Institutions

  - Other international, regional and national institutions, like the World Bank, the Organization for European Cooperation and Development (OECD), the Andean Investment Corporation (Corporación Andina de Fomento - CAF) and the Economic Commission for Latin America and the Caribbean (ECLAC), have carried out research in the areas of this TC. Its activities will be coordinated with these and other institutions with expertise in these topics.

- Description

- A.	Purpose and Goal

  - The purpose of the project is to generate state-of-the-art knowledge and policy recommendations in three emerging topics of economic integration and its impact on poverty reduction: biofuels, labor migration and the relationship between trade and sub-national disparities. The results of the project are expected to support governments in Latin America and the Caribbean in devising policies that take advantage of new trade opportunities while at the same ensuring that global market integration does not negatively affect the most vulnerable part of the region’s population (goal).

- B.	Components

  - Trade in Biofuels - Measuring the “Subsidy” Component of Biofuel Policies

  - Measuring “producer subsidy equivalents” has a long and important history in agricultural economics. But biofuel policies are so complex and operate in such a different manner that a mere extension of long used methodologies to biofuel policies will not be adequate. Available empirical analysis suggests that, under certain market conditions, tax credits for ethanol consumption become a net cost to suppliers and represent a penalty on ethanol producers. There are other complex features of biofuel policies as well, such as the interplay between subsidies and binding mandates or the functioning of a subsidy when ethanol by-products have a market value that is not considered in the design of the subsidy.

  - Therefore, a comprehensive look is warranted at the subsidy component of biofuel policies and the implications not only for trade negotiations and trade disputes (and lobbying positions), but also to understand trade flows. This information can be used to provide economic and policy advice to support governments to improve the domestic and international performance of their policies. It also improves the capacity to monitor and evaluate biofuel policies, and measure the impact of reforms.

  - Under this component, the project will finance (i) consultancies to gather data and carry out a comparative analysis of biofuel policies and their effectiveness both in developed (USA, Canada) and Latin American countries (Brazil, Mexico); and (ii) a seminar with the participation of high-level policy makers to validate the results of the research and discuss the policy recommendations.

  - The Development Impact of International Migration in Latin America and the Caribbean

  - In a context of increasing trade integration, rising international migration flows could generate significant worldwide pro-poor effects. On one hand, cross-country labor reallocation produces greater efficiency. According to recent analysis, a one-time 3% increase in the stock of total international migrants results in global welfare gains equal to those associated with the elimination of all tariffs across the globe. On the other hand, the distributive effects of labor movements seem to be substantial. Since most of the migrant population are those who either have difficulties to find a job or belong to vulnerable social groups, income-generating activities across the border could be an effective tool for overall poverty reduction.

  - However, from the perspective of sending countries -most of them developing economies-, the net effect of international migration is not clear. “Brain drain”, or the exodus of the more skilled, can hamper economic growth perspectives because of both slower human capital accumulation and lower profitability of public investments. On the positive side, remittances play an increasingly important role as source of income, although its potential as an engine of sustainable growth remains controversial.

  - More recently, a growing literature on the topic has emphasized the potentially positive role of international migration for the development of emerging economies. These studies suggest that international migration may create a virtuous circle for development: in the short run, it generates remittances and increases the return of education; in the long run, it facilitates information flows, transmission of technology, and investment in expanding economic sectors. If empirical evidence supports that claim, public policy interventions may focus on “greasing” the wheel and shortening its diameter, by promoting temporary North-South migration programs, reducing transaction costs of exit and re-entry of migrants, decreasing financial costs of sending remittances, and fostering the full or partial integration of financial intermediaries to ease access to credit, among others.

  - The project will support the following research and dissemination activities: (i) a cross-country regression analysis on the effects of migration/brain drain on development; (ii) a study exploring the existing transmission channels between international migration and development; (iii) three case studies to apply and validate the methodologies developed under (i) and (ii); (iv) an analysis of temporary migration programs around the world, their effects on development, and their applicability to the LAC region; (v) a high-level technical workshop with the participation of policy-makers and representatives of the academia and specialized national and international agencies (e.g. International Organization for Migration); and (vi) a publication of the results of this component.

  - Trade, Transport Costs and Regional Disparities

  - Since the region opened up its economy in the late 80s and early 90s, little research capacity has been devoted to understand how the new trade regime interacts with prevailing regional disparities and what countries can do to ensure that the benefits of growth are spread evenly at the sub-national level. The lack of knowledge contrasts with the importance and urgency of this issue in Latin America. High levels of regional disparities seen in countries such as Brazil, Mexico and Bolivia, to name but a few, can threaten their national unity and political stability, as it has been proved by a number of past and contemporary events in the region and elsewhere.

  - Research to be carried out under this component will analyze the complex relationship between trade and development disparities among regions in one country, with special emphasis on the role of transport costs. Both theory and the evidence available so far in Latin America suggest that transport costs play a key role in the observed outcomes. Therefore, this component will focus, first, on documenting and quantifying the impact of those costs on the ability of Latin America’s lagged regions to trade with other regions of their countries and with the rest of the world. Second, on identifying the determinants of those costs and; finally, on making concrete policy recommendations on how to minimize them.

  - The research methodology will be to select a small sample of countries that combine both successful and not so successful regions in terms of their ability to leverage trade as a tool for convergence and development. The countries will be selected based primarily on the availability of reliable data on production, exports and domestic and international transport costs.

  - Under this component, the project will principally finance (i) consultancies to gather the data necessary for the research; (ii) the creation of a small group of external academic advisers; (iii) the preparation of background papers on specific aspects of the research methodology and/or the case studies; and (iv) technical workshop with the participation of trade experts from LA governments and the academia.

- C.	Expected Results

  - The project is expected to generate the following outputs and outcomes:

    - Studies assessing the economic costs of biofuel policies in selected LA and developed countries. The studies will result in valuable information for LA governments to improve the domestic and international performance of their biofuel policies.

    - Analytical and case studies to assess the effects of migration on development that will provide guidance for the design of public policy interventions aimed at enhancing the positive and mitigating the negative effects of North-South migration on the socio-economic development of Latin America and the Caribbean.

    - The development of a theoretical framework and empirical evidence to analyze the relationship between trade costs (especially transport costs) and development disparities among regions in selected Latin America countries. Again, the research will result in policy recommendations that are aimed at spurring the design of public policies to address the regional imbalances in development.

    - Workshops for each topic to validate and disseminate the results of the research carried out under this project.

- Budget

  - The total cost of the project and the Bank’s contribution will be US$500,000. The budget is shown below.

| The Bank’s contribution for this TC will be non-reimbursable and charged against the Market and Governance Trust Fund for Poverty Reduction (KMG). - Component | - Amount (US$) |
| --- | --- |
| - Component I: Trade in Biofuels | - 138,200 |
| - Comparative analysis of biofuel policies (5 countries) - Honoraria: 5 x $15,000 - Travel and per diem: 5 x $4,000 | - 95,000 - 75,000 - 20,000 |
| - Workshop participants (20) - Travel: 20 x $1,500 - Per diem: 20 x 3 days x $220 | - 43,200 - 30,000 - 13,200 |
| - Component II: International Labor Migration | - 137,200 |
| - Research assistant: 8 months x $5,000/month | - 40,000 |
| - Study on transmission channels | - 12,000 |
| - Case studies (3) | - 30,000 |
| - Study on temporary migration programs | - 12,000 |
| - Workshop participants (20) - Travel: 20 x $1,500 - Per diem: 20 x 3 days x $220 | - 43,200 - 30,000 - 13,200 |
| - Component III: Trade, Transport Costs and Regional Disparities | - 192,200 |
| - Group of external advisors (3): - Honoraria: 3 x $15,000 - Travel and per diem: 3 x $4,000 | - 57,000 - 45,000 - 12,000 |
| - Background papers: 4 x $14,00/paper | - 56,000 |
| - Creation of data bases or access to existing data bases | - 36,000 |
| - Workshop participants (20) - Travel: 20 x $1,500 - Per diem: 20 x 3 days x $220 | - 43,200 - 30,000 - 13,200 |
| - Publications | - 15,000 |
| - Contingencies | - 17,400 |
| - Total | - 500,000 |

- Executing Agency and Mechanism

- A.	Executing agency

  - The Bank through the Integration and Trade Sector (INT/INT) will be responsible for the execution of this project. In view of the prominent role that INT has played in advancing research and policy-relevant analysis on trade and poverty reduction in Latin America, the IDB is best suited to execute this TC, ensuring the continuity of its ground-breaking work and the quality of the products that will result from this project.

- B.	Executing mechanism

  - The Integration and Trade Sector (INT/INT) will have the responsibility for both the technical aspects of the project as well as the disbursement of its resources.

- C.	Program implementation readiness

  - The project is ready for execution after Plan of Operation’s approval in December 2008.

- D.	Execution period and disbursement schedule

  - The project will be executed over a period of 9 months with a disbursement period of 12 months.

- E.	Procurement

  - Procurement will be carried out according to the Bank’s policies and procedures set forth in documents GN-2349-7 (Policies for the Procurement of Works and Goods Financed by the IDB) and GN-2350-7 (Policies for the Selection and Procurement of Consulting Services Financed by the IDB).

- Monitoring and Evaluation

- A.	Monitoring

  - The Integration and Trade Sector (INT/INT) will monitor project implementation.

- B.	Technical and basic responsibility

  - The Integration and Trade Sector (INT/INT) will have the technical and basic responsibility of this operation.

- C.	Evaluations

  - In view of the activities financed by this operation (principally studies) and the fact that it will be executed by the Bank, an external evaluation is not deemed necessary.

- Benefits and Risks

- A.	Benefits

  - The results of the project will make an important contribution to the ongoing international dialogue on public policies that combine the insertion of LAC countries into global markets with socially-inclusive growth in the region. The project will not only provide new insights into trade in biofuels, international labor migration and the interaction between trade regimes and development disparities at the sub-national level; it will provide concrete policy recommendations and finance the organization of discussion fora to ensure that the recommendations reach policy makers in the region.

  - Moreover, the project will consolidate the Bank’s leadership position with respect to research on the relationship between trade and poverty reduction. Its findings will strengthen with Bank’s strategic priority on pro-poor integration through innovative and targeted public policies as well as public-private alliances. It is also expected to influence the discussion and agendas on socially-inclusive growth in other multilateral, international and bilateral development institutions.

- B.	Risks

  - In view of the fact that the Bank will execute this project, the team considers that there are no risks that could negatively affect the timely execution of the activities.

- Environmental and Social Aspects

  - The scope of this project is limited to the preparation of studies and the organization of workshops to disseminate the findings of the studies. While the research is certainly intended to provide input for economic and social policy-making in LAC countries, it cannot be directly linked to policy decisions that could have an environmental or social impact.

  - The ESR reviewed the profile of this operation and confirmed the environmental and social safeguard classification as “C” for this project. In accordance with the ESR minutes 48-08 (December 5, 20008), the ESR recommended and the team agreed to consider, in drafting the terms of reference of component I, how the research financed by the TC could be functional to: i) provide elements of judgment to assess the environmental implications of the bio-fuels policies analyzed; and ii) facilitate the dialogue between trade ministers and other public agencies concerned with the environmental aspects of bio-fuels policies.

- Recommendation

  - Kea Wollrad (INT/INT), designated team leader for the project of the reference, recommends the approval of this operation and the use of resources from the Market and Governance Trust Fund for Poverty Reduction (KMG) totaling up to US$500,000 in order to finance the corresponding project.

- Approval

____(Original signed)____						___(12/18/08)____

Antoni Estevadeordal						           Date

Manager, INT/INT

With the support of financing from U.K. Department for International Development (DFID) through the Trade and Poverty Trust Fund.

3.5% of Latin American GDP in year 2007.