## Sheet1
Project: TTL1036_Flood Alleviation and Drainage Programme
Project Number TT-L1036
Preliminary Procurement Plan
Ref. No. 1 | Description of and category of procurement contract | Estimated cost in (US$ thousand) | Procure-ment method 2 | Review (ex-ante or ex-post) | Source of financing and percentage |  | Prequali-fication 3 (Yes/No) | Estimated Dates |  | Status 4 (pending, in process, awarded, cancelled) | Comments
[5 empty] | IDB % | Local / Other % |  | Publication of specific procurement notice | Completion of contract
1 | GOODS
Component 1 - Drainage works for the critical flood areas in POS (USD 90 M)
| Component 2 - Institutional Strengthening of the Drainage Division | 5946000
| Servers and Computers | 3391000 | ICB | Ex-Ante
| Software | 575000 | ICB | Ex-Ante
| Flow measurement equipment | 1500000 | ICB | Ex-Ante
| Printers | 80000 | NCB | Ex-Ante
| Enterprise Resource Planning System | 400000 | ICB | Ex-Ante
Component 3 - Linear Park (USD 20 M)
2 | WORKS
| Component 1 - Drainage works for the critical flood areas in POS | 75689315
| Work Package 1 - Construction | 620155 | NCB | Ex-Ante
| Work Package 2 - Design Build | 17929302 | ICB | Ex-Ante
| Work Package 3 - Design Build | 10155783 | ICB | Ex-Ante
| Work Package 4 -Design Build | 4116577 | ICB | Ex-Ante
| Work Package 5 - Design Build | 18382735 | ICB | Ex-Ante
| Work Package 6 - Design Build | 14218096 | ICB | Ex-Ante
| Work Package 7 - Design Build | 2812403 | NCB | Ex-Ante
| Work Package 8 - Design Build | 7454264 | ICB | Ex-Ante
| Component 3 - Linear Park | 13838513
| Design Build - Linear Park | 13838513 | ICB | Ex-Ante
Component 3 - Linear Park (USD 20 M)
4 | CONSULTING SERVICES
| Component 1 - Drainage works for the critical flood areas in POS | 13339538
| Work Package 1 - Design Engineering | 10734884 | QCBS | Ex-Ante
| Work Package 1 - Construction -Supervision | 310078 | QCBS | Ex-Ante
| Work Package 2 - Design Build -Supervision | 496124 | QCBS | Ex-Ante
| Work Package 3 - Design Build -Supervision | 310078 | QCBS | Ex-Ante
| Work Package 4 -Design Build -Supervision | 155039 | QCBS | Ex-Ante
| Work Package 5 - Design Build -Supervision | 558140 | QCBS | Ex-Ante
| Work Package 6 - Design Build -Supervision | 434109 | QCBS | Ex-Ante
| Work Package 7 - Design Build -Supervision | 155039 | QCBS | Ex-Ante
| Work Package 8 - Design Build -Supervision | 186047 | QCBS | Ex-Ante
| Component 2 - Institutional Strengthening of the Drainage Division | 3950000
| Organizational Management Consultant | 600000 | QCBS | Ex-Ante
| Organizational Management - Legal Consultancy | 400000 | QCBS | Ex-Ante
| Asset Valuation | 200000 | CQS | Ex-Ante
| Strategic Planning - Strategic, Corporate and Operational Planning and Programming | 350000 | QCBS | Ex-Ante
| Personnel Management - Current Capacity Assessment, Recruitment | 200000 | QCBS | Ex-Ante
| Marketing and Institutional Branding | 100000 | CQS | Ex-Ante
| Business Processes Management - Process Engineering and Internal Procedures | 500000 | QCBS | Ex-Ante
| Technical Training - Operation and Maintenance (O&M), Management, Environmental | 1300000 | QCBS | Ex-Ante
| Corporate Governance and Oversight | 200000 | CQS | Ex-Ante
| Adoption, Training ans Steamlining | 100000 | CQS | Ex-Ante
| Component 3 - Linear Park | 7236477
| Supervsion - Linear Park | 661477 | QCBS | Ex-Ante
| Operation Manual | 20000 |  | Ex-Ante
| Project Administration | 3700000 |  | Ex-Ante
| External Audit | 300000 | QCBS | Ex-Ante
| Monitoring and Evaluation | 300000 |  | Ex-Ante
| Contigencies | 2255000 |  | Ex-Ante
Component 3 - Linear Park (USD 20 M)
TOTAL
1 If there are a number of similar individual contracts to be executed in different places or at different times, these can be grouped together under a single heading, with an explanation in the comments column, indicating the average individual amount and the period during which the contracts would be executed. For example: an education project that includes school construction might include an item labeled “School Construction” for an estimated cost of US$20 million and an explanation under the Comments column such as this: “This item encompasses some 200 contracts for school construction averaging US$100,000 each, to be awarded individually by the participating municipal governments over a three-year period between January 2006 and December 2008.”
2 Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; Consulting Firms: QCBS: Quality- and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection; Individual Consultants: QCNI: Selection based on comparison of qualifications of national individual consultants; QCII: Selection based on comparison of qualifications of international individual consultants.
3 Applicable only to Goods and Works in case the new Policies apply. In the case of previous Policies, it is applicable to Goods, Works and Consulting Services.
4 Column “Status” will be used for retroactive procurement and when updating the procurement plan.